## P3
| RES | None | RESOURCE | RESOURCEDESCRIPTION | OCT | NOV | DEC | JAN | FEB | MAR | APIL | MAY | JUNFY07 | JULFY07 | AUGFY07 | SEPFY07 | OCTFY08 | NOVFY08 | DECFY08 | JANFY08 | FEBFY08 | MARFY08 | APRFY08 | MAYFY08 | JUNFY08 | JULFY08 | AUGFY08 | SEPFY08 | OCTFY09 | NOVFY09 | DECFY09 | JANFY09 | FEBFY09 | MARFY09 | APRFY09 | MAYFY09 | JUNFY09 | JULFY09 | AUGFY09 | SEPFY09 | OCTFY10 | NOVFY10 | DECFY10 | JANFY10 | FEBFY10 | MARFY10 | APRFY10 | MAYFY10 | JUNFY10 | JULFY10 | AUGFY10 | SEPFY10 | OCTFY11 | NOVFY11 | DECFY11 | JANFY11 | FEBFY11 | MARFY11 | APRFY11 | MAYFY11 | JUNFY11 | JULFY11 | AUGFY11 | SEPFY11
35 - PPPL Travel | 35 | 35 - PPPL Travel | 35 | PPPL Travel | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 - stockroom | 37 | 37 - stockroom | 37 | stockroom | [7 empty] | JULFY09: 0; AUGFY09: 0; SEPFY09: 0; OCTFY10: 0; NOVFY10: 0; DECFY10: 0; JANFY10: 0; FEBFY10: 0; MARFY10: 0
41 - PPPL M&S | 41 | 41 - PPPL M&S | 41 | PPPL M&S | [7 empty] | -1 | 1 | 1 | 1 | 1 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 - | 43 | 43 - | 43 | [8 empty] | JULFY09: 0; AUGFY09: 0; SEPFY09: 0; OCTFY10: 0; NOVFY10: 0; DECFY10: 0; JANFY10: 0; FEBFY10: 0; MARFY10: 0
48 - | 48 | 48 - | 48 | 48 | [7 empty] | MAY: 1; AUGFY07: -1; MAYFY08: 0; JUNFY08: 1; JULFY08: 1; AUGFY08: 2; SEPFY08: 2; OCTFY09: 2; NOVFY09: 1; DECFY09: 0; JANFY09: 1; FEBFY09: 0; MARFY09: 1; APRFY09: 1; MAYFY09: 0; JUNFY09: 0; JULFY09: 0
54 - Allocations | 54 | 54 - Allocations | 54 | Allocations | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 - no G&A cost | 81 | 81 - no G&A cost | 81 | no G&A cost | [7 empty] | -2 |  | -1 |  | 1 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 1.3 | 1.2 | 1.3 | 1.1
B///CB - PPPL Project Clerical | B///CB | B///CB - PPPL Project Clerical | B///CB | PPPL Project Clerical | [7 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
EA//DM - Joe Rushinski Desinger | EA//DM | EA//DM - Joe Rushinski Desinger | EA//DM | Joe Rushinski Desinger | [7 empty] | JUNFY07: 1; JULFY07: 1; AUGFY07: 1; SEPFY07: 1; OCTFY08: 2; NOVFY08: 1; DECFY08: 1; JANFY08: 1; FEBFY08: 1; MARFY08: 0; OCTFY09: 0; NOVFY09: 0; DECFY09: 0
EA//EM - PPPL Analysis engineer | EA//EM | EA//EM - PPPL Analysis engineer | EA//EM | PPPL Analysis engineer | [7 empty] | 9 | 9 | 9 | 10 | 8 | 9 | 7 | 5 | 8 | 6 | 7 | 7 | 6 | 5 | 5 | 4 | 4 | 5 | 4 | 4 | 5 | 5 | 6 | 6 | 4 | 5 | 5 | 5 | 6 | 5 | 3 | 2 | 3 | 3 | 3 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 0
EA//SB - PPPL Designer | EA//SB | EA//SB - PPPL Designer | EA//SB | PPPL Designer | [7 empty] | 0 | 0 | 2 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
EC//EM - PPPL Comuter Engineer | EC//EM | EC//EM - PPPL Comuter Engineer | EC//EM | PPPL Comuter Engineer | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 2 | 3 | 3 | 2 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0
EC//TB - | EC//TB | EC//TB - | EC//TB | EC//TB | [7 empty] | SEPFY09: 0; OCTFY10: 0; NOVFY10: 0; DECFY10: 0; JANFY10: 0; FEBFY10: 0; MARFY10: 1; APRFY10: 1; MAYFY10: 1; JUNFY10: 1; JULFY10: 1; AUGFY10: 0
EE//AM - | EE//AM | EE//AM - | EE//AM | EE//AM | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EE//EM - PPPL Electrical engineer | EE//EM | EE//EM - PPPL Electrical engineer | EE//EM | PPPL Electrical engineer | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
EE//SM - PPPL Electrical Senior Tech | EE//SM | EE//SM - PPPL Electrical Senior Tech | EE//SM | PPPL Electrical Senior Tech | [7 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 2 | 3 | 2 | 2 | 2 | 3 | 2 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
EE//TB - PPPL Electrical Technician | EE//TB | EE//TB - PPPL Electrical Technician | EE//TB | PPPL Electrical Technician | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 3 | 2 | 2 | 1 | 1 | 1 | 1
EM//EM - PPPL FO&M Engineer | EM//EM | EM//EM - PPPL FO&M Engineer | EM//EM | PPPL FO&M Engineer | [7 empty] | 4 | 4 | 5 | 8 | 4 | 7 | 5 | 4 | 6 | 5 | 5 | 5 | 5 | 5 | 6 | 5 | 5 | 7 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 6 | 6 | 6 | 8 | 5 | 4 | 4 | 4 | 5 | 5 | 4 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
EM//SB - PPPL FO&M Senior Tech | EM//SB | EM//SB - PPPL FO&M Senior Tech | EM//SB | PPPL FO&M Senior Tech | [7 empty] | JANFY09: 0; FEBFY09: 0; MARFY09: 0; APRFY09: 0; SEPFY09: 0; OCTFY10: 0; NOVFY10: 0; DECFY10: 0; JANFY10: 0; FEBFY10: 0; MARFY10: 0; APRFY10: 0; MAYFY10: 0; JUNFY10: 0; OCTFY11: 1; NOVFY11: 1; DECFY11: 1; JANFY11: 1
EM//SM - PPPL FO&M Senior Tech | EM//SM | EM//SM - PPPL FO&M Senior Tech | EM//SM | PPPL FO&M Senior Tech | [7 empty] | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 4 | 4 | 4 | 3 | 3 | 4 | 4 | 3 | 3 | 3 | 6 | 3 | 3 | 3 | 2 | 5 | 5 | 4 | 4 | 4 | 5 | 4 | 5 | 5 | 4 | 0
EM//TB - PPPL FO&M Technician | EM//TB | EM//TB - PPPL FO&M Technician | EM//TB | PPPL FO&M Technician | [7 empty] | 17 | 13 | 22 | 20 | 20 | 19 | 15 | 11 | 22 | 18 | 18 | 16 | 16 | 13 | 15 | 16 | 14 | 16 | 20 | 25 | 27 | 26 | 27 | 22 | 23 | 23 | 22 | 17 | 18 | 19 | 9 | 8 | 13 | 12 | 23 | 26 | 20 | 14 | 11 | 12 | 9 | 14 | 13 | 10 | 2
EM2/TB - Field techs second shift | EM2/TB | EM2/TB - Field techs second shift | EM2/TB | Field techs second shift | [7 empty] | MAY: 7; JUNFY07: 5; JULFY07: 6; AUGFY07: 4; SEPFY07: 3; OCTFY08: 5; NOVFY08: 5; DECFY08: 3; JANFY08: 6; FEBFY08: 5; MARFY08: 4; APRFY08: 5; MAYFY08: 5; JUNFY08: 4; JULFY08: 2; AUGFY08: 0; MARFY10: 2; APRFY10: 2; MAYFY10: 2; JUNFY10: 2; JULFY10: 2; AUGFY10: 2; SEPFY10: 2; OCTFY11: 2; NOVFY11: 2; DECFY11: 2; JANFY11: 0
EMT/TB - PPPL Tech SHop | EMT/TB | EMT/TB - PPPL Tech SHop | EMT/TB | PPPL Tech SHop | [7 empty] | MAY: 1; JUNFY07: 0; JULFY07: 1; AUGFY07: 1; SEPFY07: 1; OCTFY08: 2; NOVFY08: 1; DECFY08: 1; JANFY08: 1; FEBFY08: 2; MARFY08: 2; APRFY08: 1; MAYFY08: 1; JUNFY08: 1; JULFY08: 1; AUGFY08: 0; SEPFY08: 0; OCTFY09: 1; NOVFY09: 0; OCTFY10: 0; JANFY10: 1; FEBFY10: 1; MARFY10: 2; APRFY10: 1
FC//AM - PPPL P&CO am | FC//AM | FC//AM - PPPL P&CO am | FC//AM | PPPL P&CO am | bar: MAY to JANFY11
FC//EM - PPPL P&CO em | FC//EM | FC//EM - PPPL P&CO em | FC//EM | PPPL P&CO em | [7 empty] | OCTFY09: 0; NOVFY09: 0; DECFY09: 0; JANFY09: 0; FEBFY09: 0; MARFY09: 0; APRFY09: 0; MAYFY09: 0; JUNFY09: 0; JULFY09: 0; AUGFY09: 0; SEPFY09: 0; OCTFY10: 0; NOVFY10: 0; DECFY10: 0; JANFY10: 0; FEBFY10: 0; MARFY10: 0; APRFY10: 0; MAYFY10: 0; JUNFY10: 0; JULFY10: 0; AUGFY10: 0; SEPFY10: 0; OCTFY11: 0; NOVFY11: 0; DECFY11: 0; JANFY11: 0
ORNL35 - ORNL Travel | ORNL35 | ORNL35 - ORNL Travel | ORNL35 | ORNL Travel | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ORNL41 - ORNL M&S | ORNL41 | ORNL41 - ORNL M&S | ORNL41 | ORNL M&S | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ORNL81 - ORNL cost | ORNL81 | ORNL81 - ORNL cost | ORNL81 | ORNL cost | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ORNLDM - ORNL Designer | ORNLDM | ORNLDM - ORNL Designer | ORNLDM | ORNL Designer | [7 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ORNLEM - ORNL Engineer | ORNLEM | ORNLEM - ORNL Engineer | ORNLEM | ORNL Engineer | [7 empty] | 7 | 10 | 11 | 8 | 5 | 8 | 4 | 3 | 5 | 4 | 3 | 3 | 3 | 4 | 3 | 3 | 3 | 4 | 3 | 2 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
R///RM2 - PPPL Scientist pdg2 | R///RM2 | R///RM2 - PPPL Scientist pdg2 | R///RM2 | PPPL Scientist pdg2 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
R///RM3 - PPPL Scientist pdg3 | R///RM3 | R///RM3 - PPPL Scientist pdg3 | R///RM3 | PPPL Scientist pdg3 | [7 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SH//TB - HP Techs | SH//TB | SH//TB - HP Techs | SH//TB | HP Techs | [7 empty] | MAY: 1; JUNFY07: 1; JULFY07: 1; AUGFY07: 1; SEPFY07: 1; OCTFY08: 1; NOVFY08: 1; DECFY08: 0; JANFY08: 1; FEBFY08: 1; MARFY08: 1; APRFY08: 1; MAYFY08: 1; JUNFY08: 1; JULFY08: 1; AUGFY08: 1; SEPFY08: 1; OCTFY09: 1; NOVFY09: 1; DECFY09: 1; JANFY09: 1; FEBFY09: 1; MARFY09: 1; APRFY09: 1; MAYFY09: 1; JUNFY09: 0
ZMET - metrology staff hours | ZMET | ZMET - metrology staff hours | ZMET | metrology staff hours | [7 empty] | AUGFY07: 2; SEPFY07: 2; OCTFY08: 2; NOVFY08: 3; DECFY08: 2; JANFY08: 2; FEBFY08: 4; MARFY08: 4; APRFY08: 3; MAYFY08: 4; JUNFY08: 3; JULFY08: 4; AUGFY08: 4; SEPFY08: 4; OCTFY09: 4; NOVFY09: 4; DECFY09: 3; JANFY09: 3; FEBFY09: 4; MARFY09: 3; APRFY09: 2; MAYFY09: 2; AUGFY09: 1; SEPFY09: 1; OCTFY10: 1
|  | None | RESOURCE | RESOURCEDESCRIPTION | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S
dsn | 1.0813 | 1.8562 | 1.5312 | PPPL Designers | 1.8938 | 1.2625 | 1.6062 | 1.4062 | 1.9688 | 2.325 | 1.5312 | 1.8562 | 1.5312 | 3 | 3 | 2 | 4 | 2 | 2.6667 | 3 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 3 | 2 | 1.3333 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 2 | 2 | 1.3333 | 1 | 2 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
EA Engr | 6.9313 | 8.425 | 8.2375 | PPPL Analyst Engrs | 5.0312 | 7.6 | 6.6375 | 4.8438 | 7.7562 | 7.625 | 6.9313 | 8.425 | 8.2375 | 9 | 10 | 8 | 9 | 7 | 6.6667 | 8 | 6 | 7 | 7 | 6 | 5 | 5 | 4 | 4 | 5 | 4 | 5.3333 | 5 | 5 | 6 | 6 | 4 | 5 | 5 | 5 | 6 | 5 | 3 | 2.6667 | 3 | 3 | 3 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 0 | 0
EC ENGR | 0.375 | 0 | 0 | PPPL Computing Engrs | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1.3333 | 2 | 2 | 3 | 3 | 2 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
EE ENGR' | 0.13125 | 0.15625 | 0.075 | PPPL FO&M Engrs | 1.5125 | 1.3813 | 2.8312 | 2.7 | 3.725 | 4.175 | 6.0375 | 6.0563 | 3.0375 | 5 | 8 | 4 | 7 | 5 | 5.3333 | 6 | 5 | 5 | 5 | 5 | 5 | 6 | 5 | 5 | 7 | 6 | 8 | 7 | 7 | 7 | 7 | 7 | 7 | 6 | 6 | 6 | 8 | 5 | 5.3333 | 4 | 4 | 5 | 5 | 4 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0
EM ENGR | 6.0375 | 6.0563 | 3.0375 | PPPL Electrical Engrs | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.3333 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 1.3333 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
tech | 11.9187 | 28.1562 | 22.8562 | PPPL Techs (SM/SB/TB) | 19.2812 | 27.4187 | 25.6625 | 20.925 | 33.1781 | 25.5312 | 32.0031 | 28.1562 | 23.8952 | 32 | 28 | 26 | 28 | 23 | 22.6667 | 31 | 27 | 26 | 24 | 24 | 20 | 19 | 17 | 15 | 18 | 23 | 30 | 32 | 32 | 32 | 28 | 30 | 31 | 28 | 23 | 24 | 29 | 16 | 14 | 22 | 20 | 38 | 38 | 29 | 23 | 19 | 21 | 17 | 24 | 21 | 17 | 3 | 0 | 0 | 0
|  |  |  | ORNL Engr/Designers | [7 empty] | 8 | 11 | 12 | 9 | 6 | 9 | 5 | 6.6667 | 7 | 6 | 6 | 5 | 5 | 6 | 5 | 5 | 5 | 6 | 4 | 3 | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
|  |  |  | ORNL Engrs | [7 empty] | 7 | 10 | 11 | 8 | 5 | 8 | 4 | 4 | 5 | 4 | 3 | 3 | 3 | 4 | 3 | 3 | 3 | 4 | 3 | 2.6667 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 1.3333 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
FY07 FY08 FY09 FY10 FY11