## RiskOpportunities may06
| Risk | Opportunity
PF Coil Procurement | 200 |  | Preliminary budgetary quotes being evaluated with Everson/Tesla
Coil Structure Procurement |  |  | Initial budgetary quotes being evaluated relative to design simplification.
Station 2 field period assembly | 744 |  | Preliminary assembly sequence and steps quantified. Fit-up trials to be pursued over the next few months to help better quantify cost and schedule impact.
Modular coil fabrication | 394 |  | Additional cost if current production cost continues through to completion.
System Engineering | 690 |  | FY08 manpower support of design integration and metrology need to be re-evaluated based on this year's Field Period Assembly experience.
Once-through bake out system | 314 |  | Adequacy of current approach in question.
| 2342 | 0
Working to quantify the schedule impact of the various design options and narrow our uncertainties. We will select the MC interface design in January and update our schedule estimates at that time. The number of stations and shifts will be established consistent with overall schedule constraints

## ETC deltas
ETC Updates
WBS
140 | 142 | Modular Coil Fabrication | 717 | ETC based on current costing trends
141 | 142 | Modular coil interface | 226 | Design of interface method. Include R&D and materials.
142 | 142 | Modular coil fabrication-hardware and assy dwgs | 121 | Completion of design plus hardware procurements
411 | 411 | Auxiliary AC power systems | -379 | Classified as infrastructure improvement. To be proposed in GPP directives.
441 | 441 | Control & protection-Interlocks and control | -74 | Based on more manual overrides. To be addressed in individual design review forums.
452 | 452 | Power systems-Diagnostic AC power support | -177 | Scope reduced keeping only minimum elect support for first plasma diagnostics
810 | 81 | Project Management | -170 | Re-estimate of required support amongst MIE, research preparations and QPS
820 | 82 | Project Engineering | 127 | Recognizes additional support for metrology and design integration.
900 | ALL | FY07 PPPL rate adjustment | -391 | re-alignment of G&A,Site,MHX, and burden rates based on final FY07 budget base.
0

## Contingency Analysis Summary
Contingency Analysis
|  | BCWR (ECP-53) | Budgeted Contingency (known Risks) |  | High Confidence Level Contingency Case (including known risks)
| WBS |  | $ | % | $ | %
12 | Vacuum Vessel | 360.7373 | 52.7211 | 14.61% | 180.3686 | 50%
13 | Conventional Coils | 2375.7078 | 240.926 | 10.14% | 1114.5539 | 46.91%
14 | Modular Coils | 6981.9133 | 667.3342 | 9.558% | 2576.4824 | 36.9%
15 | Coil Structures | 1234.6223 | 291.0779 | 23.58% | 1132.1225 | 91.7%
16 | Coil Services | 1143.74 | 167.1556 | 14.61% | 571.87 | 50%
17 | Cryostat & Base | 787.9663 | 141.523 | 17.96% | 1049.6763 | 133.2%
18 | Field Period Assembly | 3999.8988 | 1475.8024 | 36.9% | 4645.028 | 116.1%
19 | Stellarator Core Mgt. / Integration | 576.7641 | 33.7172 | 5.846% | 115.3528 | 20%
1 | Stellarator Core Systems | 17461.3499 | 3070.2575 | 17.58% | 11385.4545 | 65.2%
2 | Fueling & Vacuum | 138.2 | 12.1186 | 8.769% | 41.46 | 30%
3 | Diagnsotics | 196.799 | 18.9755 | 9.642% | 64.9188 | 32.99%
4 | Power Systems | 1830 | 142.7138 | 7.799% | 488.25 | 26.68%
5 | Central I&C / Data Aq. | 753.1 | 66.0386 | 8.769% | 225.93 | 30%
6 | Facility Systems | 576 | 141.1088 | 24.5% | 754.2 | 130.9%
7 | Test Cell Prep / Machine Assembly | 2875.0559 | 513.8833 | 17.87% | 1758.089 | 61.15%
8 | Project Mgt. & Integration | 3237.8103 | 1024.2887 | 31.64% | 2645.6629 | 81.71%
|  | 27068.3151 | 4989.3847 | 18.43% | 17363.9652 | 64.15%
|  |  | Cost YTD = | 60269 | Cost YTD = | 60269
|  |  | BCWR = | 27068.3151 | BCWR = | 27068.3151
|  |  | Available Contingency = | 4989.3847 | High Level Contingency = | 17363.9652
|  |  | DCMA = | 75 | DCMA = | 75
|  |  | TEC = | 92401.6998 | TEC = | 104776.2803
|  |  |  | 92400.6998 |  | 104776.2803

## Budget Summary may06
| EAC (ECP-53) | Cost Through 11/30/06 | ETC (from 12/1/06) |  | ETC Updates | ETC |  | EAC (ECP-53)
12 - Vacuum Vessel Systems | 9983.7373 | 9623 | 360.7373 |  | -6.7458 | 353.9915 |  | 9976.9915 |  | -6.7458
13 - Conventional Coils | 5332.7078 | 2957 | 2375.7078 |  | -42.6594 | 2333.0484 |  | 5290.0484 |  | -42.6594
14 - Modular Coils | 37117.9133 | 30136 | 6981.9133 |  | 878.6337 | 7860.5471 |  | 37996.5471 |  | -185.3663
15 - Structures | 1377.6223 | 143 | 1234.6223 |  | -16.2197 | 1218.4026 |  | 1361.4026 |  | -16.2197
16 - Coil Services | 1146.74 | 3 | 1143.74 |  | -4.5558 | 1139.1842 |  | 1142.1842 |  | -4.5558
17 - Cryostat and Base Suprt Struct | 1204.9663 | 417 | 787.9663 |  | -1.5772 | 786.3891 |  | 1203.3891 |  | -1.5772
18 - Field Period Assembly | 6697.8988 | 2698 | 3999.8988 |  | -94.369 | 3905.5298 |  | 6603.5298 |  | -71.369
19 - Stellarator Core Mgt & Integr | 2584.7641 | 2008 | 576.7641 |  | -5.5496 | 571.2146 |  | 2579.2146 |  | -5.5496
1 Stellarator Core Systems | 65446.3499 | 47985 | 17461.3499 |  | 706.9573 | 18168.3072 |  | 66153.3072
2 Heating, Fueling & Vac Sys | 486.2 | 348 | 138.2 |  |  | 138.2 |  | 486.2 |  | 0
3 Diagnostics | 1004.799 | 808 | 196.799 |  | -3.8072 | 192.9918 |  | 1000.9918 |  | -3.8072
4 Electrical Power Sys | 2544 | 714 | 1830 |  | -630 | 1200 |  | 1914 | -707.3653 | 0
5 Central I&C Sys | 786.1 | 33 | 753.1 |  |  | 753.1 |  | 786.1 |  | 0
6 Facility Sys | 600 | 24 | 576 |  |  | 576 |  | 600 |  | 0
7 Test Cell Prep & MachAssy | 3827.0559 | 952 | 2875.0559 |  | -0.91915 | 2874.1368 |  | 3826.1368 |  | -0.91915
8 Project Oversight & Support | 12642.8103 | 9405 | 3237.8103 |  | -72.639 | 3165.1714 |  | 12570.1714 |  | -53.639
subtotal | 87337.3151 | 60269 | 27068.3151 |  | -0.40799 | 27067.9071 |  | 87336.9071
Contingency | 4989 |  | 4989 | 18.43% | 0.40799 | 5229 |  | 4991
TEC = | 92326.3151 | 60269 | 32057.3151 |  |  | 32296.9071 |  | 92327.9071
DCMA | 75 | 75 | [5 empty] | 75
| 92401.3151 | 60344 | 32057.3151 |  |  |  |  | 92402.9071
[7 empty] | ETC | 27067.9071
|  |  | 92401.3151 |  |  |  | Contingency balance | 4991
18.44%
[6 empty] | BCWP | 36720
[6 empty] | ACWP | 38313
[6 empty] | CPI | 0.95842 |  |  | 70446.9071
[6 empty] | CV | 1593

## ETC Log
NCSX ETC Log
| Log # | Job | Title | Description | Respon. | Schedule | Cost + Increase/ -Decrease ($K) | FY07 | FY08 | Comments | Disposition /Action | ECP-53 | Documentaion | Total potential Risk | unavoidable cost risk | Opportunity
1 | 1 | 4501 | Power systems WBS 452 | Diagnostics AC power support | Raki | FY08 | -179 |  | -179 | Per M.Williams and Brent Stratton on 10/12/06. The scope was reduced – only keeping MINIMUM ELECTRICAL SUPPORT/LOAD NEEDS FOR WBS3(Diagnostics) for First Plasma: | ECP-53 | -179 | ECP53 database updated.
3 | 2 | 4401 | Control and Protection WBS 441 | Interlocks & control | Raki | FY08 | -70 |  | -70 | Reviewed the scope of work based on more manual overrides. However the conceived approach to new design will have to be reviewed and approved in design forums – from protection point of view. | ECP-53 | -70 | ECP53 database updated.
4 | 2 | [8 empty] | The scope was reduced as follows: |  |  | ECP53 database updated.
5 | 2 | [8 empty] | MINIMUM PLC changes for First Plasma: |  |  | ECP53 database updated.
6 | 2 | [8 empty] | a) No new PLCs will be procured |  |  | ECP53 database updated.
7 | 2 | [8 empty] | b) No redundant PLC will be procured/installed |  |  | ECP53 database updated.
8 | 2 | [8 empty] | However, Will retain funding needed for a) design of the minimum interlock systems, b) Installing interlock system, c) Complete documentation of the PLC system, d) programming , e) cabling as required and f) pre-commissioning tests |  |  | ECP53 database updated.
10 | 3 | 4101 | AC Power | Auxiliary AC Power Systems WBS 411 tasks 411-1-100,3-2, 3-4, 3-6, 3-8 | Raki | FY08 | -102.338 |  | -102.338 | Not MIE Cost per Accounting/Winkler. Transfer to GPP. | ECP-53 | -102.338 | ECP53 database updated.
12 | 4 | 4101 | AC Power | Experimental AC Power systems WBS 412 | Raki | FY08 | 0 |  | 0 | Not GPP Cost per Accounting/Winkler. Keep in the MIE project. | ECP-53 | 0 | ECP53 database updated.
11 | 5 | WBS 4 and 7 | AC Power | AC power upgrades at C-site in support of experimental projects-NCSX | Raki | completed scope | -412 | -412 |  | GPP determination being performed by accounting. Winkler/Hawyrluk to render decision on transferring to GPP. | ECP-53 | -412 | ECP53 database updated. | ?
18 | 7 | 1416 | Modular coil hardware design and procurement |  | Williamson | FY07 | 22 | 22 |  | TO BE DOCUMENTED IN A RESOURCE LOADED PLAN BY WILLIAMSON BY 1/24. | ECP-53 | 22 | preliminary
18 | 7 | 1408 | Mod Coil remaining supplies and procurements. |  | Williamson | FY07 | 104 | 104 |  | assy dwgs, add'l hardware and misc supplies in support of winding. | ECP-53 | 104 | ECP53 database updated.
20 | 8 | 1810 | Field Period assy station 2 |  | Viola | FY07/08 |  |  |  | TO BE DOCUMENTED IN A RESOURCE LOADED PLAN BY VIOLA BY 1/24. | Risk |  | preliminary | 0 | 250
|  | 1802 | Metrology support of field period assy
|  | 1805 | FP Assy fixture | [6 empty] | Fabrication of stage 2 fixtures not required. Use MTM fixtures. |  | -66 | ECP53 database updated.
22 | 9 | 1421 | Mod coil interface design |  | Williamson | FY07 | 215 | 68 | 147 | Raftopolous | ECP-53 | 215 | ECP53 database updated.
27 | 10 | 1352 | PF coil procurement |  | Kalish | FY07/08 | 200 |  | 200 |  | Risk |  |  | 200
| 11 | 1552 | Coil Structure procurement |  | Dahlgren | DY07/08 | 500 |  | 1066 |  | Risk |  |  | 500
| 14 | all | PPPL rates for FY07 |  | Winkler | FY07 | -391 | -391 |  |  |  | -391
| 15 | 1804 | metrology hardware | reclassfied as indriect engr burden | dudek | FY07 | -23.4 | -11.5 | -11.5 |  | ECP-53 | -23.4 | ECP53 database updated.
| 16 | 1451 & 1459 | Coil winding | full funding hold back plus cost variance increment plug | chrzanowski | FY07/08 | 716 | 537 | 179 |  | Risk | 716 | ECP53 database updated.
|  | WBS 81 | Proj Mgt | Neilson Strykowsky |  |  | -205 | -98 | -107 |  | ECP-53 & Risk | -205 | ECP53 database updated.
| 17 | WBS 82 | System Engineering | raftopolous,brooks,brown,simmons, | reiersen | FY07/08 | 636 | 73 | 563 | others charge their jobs with no budget increment. | ECP-53 & Risk | 636 | ECP53 database updated. | 563 | 690
|  | 8206 | FY07 rebaseling support | Blanchard 80, Raki 120 ,Sichta 160 ,Perry 80,Gentile 120 |  |  | 87 |  |  |  |  | 87 | ECP53 database updated.
| 19 | WBS 6 | Once through bakeout 150 C |  | dudek | FY08 |  |  |  |  | Risk |  |  | 0 | 50
30 | [6 empty] | 1097.262 | -108.5 | 1685.162 | 2584.262 |  | 331.262 |  | 1263 | 990 | 0
31
32
33
34
35

## Accomplishments
| Technical (could it be build) | Schedule (could it be done on time) | Cost (Is budget sufficient)
Vacuum Vessel Fabrication (Vendor)
MC Winding Design & hardware fab
Modular Coil Winding Forms (Vendor)
Modular Coil Winding Fabr (PPPL)
TF Coil Fabrication (Vendor)
Field Period Assy
Field Period assy station 2
Field Period assy station 3
Field Period assy station 4
Field Period assy station 5
Final Machine Assay
PF Coil Fabrication
Coil Structure Fabrication
Cryostat Fabrication

## CopntingencyB
WBS | JOB | [6 empty] | Prior FY | FY2007 |  |  |  |  | FY2008 | [5 empty] | FY2009 | [5 empty] | A | B | C | D | E | F | G | H | I | J
[26 empty] | A: BCWR; D: A+B+C; F: E x D; G: F x(4989-C)/sumF; H: G + C | [7 empty] | A+B | C | A+B+C | G | G / (A+B+C) | F | F / (A+B+C)
| Baseline Contingency Analysis |  |  |  | Budget (BCWS) | Cost Through 11/30/06 |  |  | BCWR (from 12/1/06) | ETC Increment | Total ETC | In-Budget Cont. % | In-Budget Contingency/Risk | BCWR | ETC Increment | Total ETC | In-Budget Cont. % | In-Budget Contingency/Risk | Add'l Contingency | BCWR | ETC Increment | Total ETC | In-Budget Cont. % | In-Budget Contingency/Risk | Add'l Contingency | BCWR (from 12/1/06) | ECP53 Increment | Unavoidable Risks | Total ETC | Risk Assessment % | Gross Contingency $ | Available Contingency | Total Budgeted contingency |  |  | In-Budget Contingency | Add'l Contingency | Known Risks |  |  |  | Baseline Contingency Analysis
|  |  | bcwp thru 11/30/06 |  | BUDGET |  | BCWR 12/1/067 | Cost | 11920.8151 |  |  | 11.27% | 1391.7229 | 12856.6 |  |  | 35.32% | 3454.8658 | 2705 | 2291.1 |  |  | 6.614% | 142.796 | 3900.0225 | [17 empty] | BCWR (ECP-53) | Unavoidable Risks | ETC=BCWR + Known Risks | Available Contingency |  | Total Budgeted Contingency | bar: H to I
dcma | dcma |  |  |  | 75 | 75 |  | 75 |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  | F: 0; G: 0; H: 0 | 0 | 0 |  |  |  |  | WBS |  |  |  | $ | % | $ | %
12 | Job: 1201 - Vacuum Vessel Prelim Dsn-**CLOSED** | 1201 | 424.42 | 1201 | 424.42 | 424 | 0 |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0 |  |  |  | 12 | Vacuum Vessel | 360.7373 | 0 | 360.7373 | 52.7211 | 14.61% | 52.7211 | 14.61%
12 | Job: 1202 - Vacuum Vessel R&D | 1202 | 1770.1819 | 1202 | 1769.81 | 1771 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0 |  |  |  | 13 | Conventional Coils | 2375.7078 | 0 | 2375.7078 | 240.926 | 10.14% | 240.926 | 10.14%
12 | Job: 1203 - Vacuum Vessel Final Dsn-**CLOSED** | 1203 | 1217.8391 | 1203 | 1217.81 | 1220 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0 |  |  |  | 14 | Modular Coils | 6981.9133 | 0 | 6981.9133 | 667.3342 | 9.558% | 667.3342 | 9.558%
12 | Job: 1204-VV Sys Procurements (non VVSA)-DUDEK | 1204 | 323.8427 | 1204 | 685.08 | 378 | 117.2373 |  | 116.7373 |  | 116.7373 | 15% | 17.5106 | 244 |  | 244 | 15% | 36.6 |  |  |  | 0 | 0% | 0 | 0.0225 | 360.7373 | 0 |  | 360.7373 | 50% | 180.3686 | 52.7211 | 52.7211 | 14.61% |  | 54.1106 | 0.0225 |  |  |  | 15 | Coil Structures | 1234.6223 | 0 | 1234.6223 | 291.0779 | 23.58% | 291.0779 | 23.58%
12 | Job: 1206 - VV Field Weld Joint R&D-**CLOSED** | 1206 | 15.6394 | 1206 | 15.64 | 16 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0 |  |  |  | 16 | Coil Services | 1143.74 | 0 | 1143.74 | 167.1556 | 14.61% | 167.1556 | 14.61%
12 | Job: 1250 - Vacuum Vessel Fabrication--**CLOSED** | 1250 | 5808.603 | 1250 | 5809 | 5815 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0 |  |  |  | 17 | Cryostat & Base | 787.9663 | 0 | 787.9663 | 141.523 | 17.96% | 141.523 | 17.96%
13 | Job: 1301 - TF Design-KALISH**CLOSED** | 1301 | 970.6526 | 1301 | 970.57 | 970 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0 |  |  |  | 18 | Field Period Assembly | 3999.8988 | 250 | 4249.8988 | 1225.8024 | 30.65% | 1475.8024 | 36.9%
13 | Job: 1302 - PF Design -KALISH | 1302 | -7.774 | 1302 | 131.97 | 19 | 139.744 |  | 139.744 |  | 139.744 | 25% | 34.936 |  |  | 0 |  | 0 |  |  |  | 0 | 0% | 0 |  | 139.744 | 0 |  | 139.744 | 50% | 69.872 | 20.4233 | 20.4233 | 14.61% |  | 34.936 | 0 |  |  |  | 19 | Stellarator Core Mgt. / Integration | 576.7641 | 0 | 576.7641 | 33.7172 | 5.846% | 33.7172 | 5.846%
13 | Job: 1303 -Central Solenoid Support Dsn-DAHLGREN | 1303 | 116.8828 | 1303 | 106.35 | 138 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0 |  |  |  | 1 | Stellarator Core Systems | 17461.3499 | 250 | 17711.3499 | 2820.2575 | 16.15% | 3070.2575 | 17.58%
13 | Job: 1350 TF Coil Fab Prep-CHRZANOWSKI**CLOSED** | 1350 | 547.015 | 1350 | 547.01 | 536 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0 |  |  |  | 2 | Fueling & Vacuum | 138.2 | 0 | 138.2 | 12.1186 | 8.769% | 12.1186 | 8.769%
13 | Job: 1351 - TF Coil Fabr Supplies-KALISH | 1351 | 463.4553 | 1351 | 470 | 453 | 6.5447 |  | 6.5447 |  | 6.5447 | 15% | 0.98171 |  |  | 0 |  | 0 |  |  |  | 0 | 0% | 0 |  | 6.5447 | 0 |  | 6.5447 | 20% | 1.3089 | 0.3826 | 0.3826 | 5.846% |  | 0.98171 | 0 |  |  |  | 3 | Diagnsotics | 196.799 | 0 | 196.799 | 18.9755 | 9.642% | 18.9755 | 9.642%
13 | Job: 1352 - PF Coil Procurement-KALISH | 1352 | 0 | 1352 | 787.95 | 0 | 226.95 |  | 226.25 |  | 226.25 | 10% | 22.625 | 561 |  | 561 | 31.9% | 178.959 | 50 |  |  | 0 | 0% | 0 | 100 | 787.25 | 0 |  | 787.25 | 60% | 472.35 | 138.0663 | 138.0663 | 17.54% |  | 201.584 | 150 | 200 |  |  | 4 | Power Systems | 1830 | 0 | 1830 | 142.7138 | 7.799% | 142.7138 | 7.799%
13 | Job: 1353 - CS Structure Procurement-DAHLGREN | 1353 | 0 | 1353 | 122.61 | 0 | 32.61 |  | 32.51 |  | 32.51 | 10% | 3.251 | 90 |  | 90 | 25% | 22.5 |  |  |  | 0 | 0% | 0 |  | 122.51 | 0 |  | 122.51 | 50% | 61.255 | 17.9046 | 17.9046 | 14.61% |  | 25.751 | 0 |  |  |  | 5 | Central I&C / Data Aq. | 753.1 | 0 | 753.1 | 66.0386 | 8.769% | 66.0386 | 8.769%
13 | Job: 1354 - Trim Coil Design &Procurement-KALISH | 1354 | 0 | 1354 | 106.07 | 0 |  |  |  |  | 0 |  | 0 | 106 |  | 106 | 25% | 26.5 |  |  |  | 0 | 0% | 0 | 200 | 106 | 0 |  | 106 | 75% | 79.5 | 23.2376 | 23.2376 | 21.92% |  | 26.5 | 200 |  |  |  | 6 | Facility Systems | 576 | 50 | 626 | 91.1088 | 15.82% | 141.1088 | 24.5%
13 | Job: 1355 - WBS 13 I&C Proc & | 1355 | 0 | 1355 | 93.42 | 0 |  |  |  |  | 0 |  | 0 | 93 |  | 93 | 25% | 23.25 |  |  |  | 0 | 0% | 0 |  | 93 | 0 |  | 93 | 30% | 27.9 | 8.1551 | 8.1551 | 8.769% |  | 23.25 | 0 |  |  |  | 7 | Test Cell Prep / Machine Assembly | 2875.0559 | 0 | 2875.0559 | 513.8833 | 17.87% | 513.8833 | 17.87%
13 | Job: 1361 - TF Fabrication-KALISH | 1361 | 923.411 | 1361 | 2044.97 | 841 | 874.559 |  | 873.659 |  | 873.659 | 10% | 87.3659 | 247 |  | 247 | 10% | 24.7 |  |  |  | 0 | 0% | 0 | 50 | 1120.659 | 0 |  | 1120.659 | 10% | 112.0659 | 32.7565 | 32.7565 | 2.923% |  | 112.0659 | 50 |  |  |  | 8 | Project Mgt. & Integration | 3237.8103 | 690 | 3927.8103 | 334.2887 | 10.32% | 1024.2887 | 31.64%
14 | Job: 1401 - Mod Coil Prel.Dsn**CLOSED** | 1401 | 304.04 | 1401 | 304.05 | 304 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0 | [5 empty] | 27068.3151 | 990 | 28058.3151 | 3999.3847 | 14.78% | 4989.3847 | 18.43%
14 | Job: 1402 - Mod.Coil Analyses**CLOSED** | 1402 | 239.14 | 1402 | 239.12 | 239 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0
14 | Job: 1403 - Modular Coil Final Design-WILLIAMSON | 1403 | 3310.5695 | 1403 | 3310.02 | 3310 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0 | [10 empty] | Cost YTD = | 60269
14 | Job: 1404-MCWF R&D & 1st Prod Casting**CLOSED** | 1404 | 2543.5181 | 1404 | 2544 | 2554 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0 | [10 empty] | BCWR = | 27068.3151
14 | Job: 1405-Mod Coil Winding R&D Prep-**CLOSED** | 1405 | 168.07 | 1405 | 168.07 | 168 | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0 | [10 empty] | Available Contingency = | 4989.3847 | 18.43%
14 | Job: 1406 - Mod. Coil Winding | 1406 | 2263.5684 | 1406 | 2262.96 | 2263 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0 | [10 empty] | DCMA = | 75
14 | Job: 1407 -Mod Coil Winding Facility-**CLOSED** | 1407 | 2571.3731 | 1407 | 2570.78 | 2570 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0 | [10 empty] | TEC = | 92401.6998
14 | Job: 1408-Mod Coil Winding Supplies-CHRZANOWSKI | 1408 | 1724.92 | 1408 | 1952.63 | 1957 | 223.71 |  | 223.51 |  | 223.51 | 15% | 33.5265 | 4 |  | 4 | 15% | 0.6 |  |  |  | 0 | 0% | 0 |  | 227.51 | 0 |  | 227.51 | 25% | 56.8775 | 16.6251 | 16.6251 | 7.307% |  | 34.1265 | 0
14 | Job: 1409 - Coil Test Stand-GETTELFINGER*CLOSED* | 1409 | 825.9413 | 1409 | 825.96 | 833 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0
14 | Job: 1410 MC Twisted Racetrack Fabr-**CLOSED** | 1410 | 1049.9713 | 1410 | 1049.9 | 1050 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0
14 | Job: 1411-MCWF Fabrication S005242-HEITZENROEDER | 1411 | 8669.4236 | 1411 | 9844.47 | 8720 | 1175.0464 |  | 1175.0464 |  | 1175.0464 | 5% | 58.7523 |  |  | 0 |  | 0 |  |  |  | 0 | 0% | 0 |  | 1175.0464 | 0 |  | 1175.0464 | 10% | 117.5046 | 34.3462 | 34.3462 | 2.923% |  | 58.7523 | 0
14 | Job: 1412 - Complete Winding Facilities-*CLOSED* | 1412 | 540.9969 | 1412 | 541.02 | 541 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0
14 | Job: 1413 -MCWF Fracture Analysis-**CLOSED** | 1413 | 27.8194 | 1413 | 27.84 | 28 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0
14 | Job: 1414 Coil Testing-Gettelfinger**CLOSED** | 1414 | 674.8333 | 1414 | 674.68 | 639 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0
14 | Job: 1415 Dim Cntrl Testing-RAFTOPOLOUS*CLOSED** | 1415 | 23.85 | 1415 | 23.83 | 24 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0
14 | Job: 1416-Mod Coil Type A&B Final Dsn-WILLIAMSON | 1416 | 579.5028 | 1416 | 685.89 | 642 | 106.3872 |  | 106.3872 | 121 | 227.3872 | 25% | 56.8468 |  |  | 0 |  | 0 |  |  |  | 0 | 0% | 0 |  | 106.3872 | 121 |  | 227.3872 | 25% | 56.8468 | 16.6161 | 16.6161 | 7.307% |  | 56.8468 | 0
14 | Job: 1419-Winding Fac. Mods-CHRZANOWSKI*CLOSED* | 1419 | 55.21 | 1419 | 55.21 | 46 | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0
14 | Job: 1421-Mod Coil Interface Design-WILLIAMSON | 1421 | 118.1756 | 1421 | 379.91 | 120 | 261.7344 |  | 261.7344 | 226 | 487.7344 | 20% | 97.5469 |  |  | 0 |  | 0 |  |  |  | 0 | 0% | 0 |  | 261.7344 | 226 |  | 487.7344 | 50% | 243.8672 | 71.2815 | 71.2815 | 14.61% |  | 97.5469 | 0
14 | Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 1431 | 0 | 1431 | 698.9 |  | 698.9 |  | 698.9 |  | 698.9 | 20% | 139.78 |  |  | 0 |  | 0 |  |  |  | 0 | 0% | 0 |  | 698.9 | 0 |  | 698.9 | 100% | 698.9 | 204.286 | 204.286 | 29.23% |  | 139.78 | 0
14 | Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 1451 | 2896.7274 | 1451 | 5994 | 4045 | 2637.2726 |  | 2633.9626 | 619 | 3252.9626 | 5% | 162.6481 | 460 | 98 | 558 | 36% | 200.88 | 250 |  |  | 0 | 0% | 0 |  | 3093.9626 | 717 | 0 | 3810.9626 | 20% | 762.1925 | 222.7862 | 222.7862 | 5.846% |  | 363.5281 | 250 | 394
| Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | 1459 | 77.7722 | 1459 | 422.86 | 45 | 302.0878 |  | 301.3878 |  | 301.3878 | 5% | 15.0694 | 43 |  | 43 | 36% | 15.48 |  |  |  | 0 | 0% | 0 |  | 344.3878 | 0 |  | 344.3878 | 100% | 344.3878 | 100.6634 | 100.6634 | 29.23% |  | 30.5494 | 0
14 | Job: 1460 3rd Winding Fixture-CHRZANOWSKI | 1460 | 53.0651 | 1460 | 63.05 | 37 | 9.9849 |  | 9.9849 |  | 9.9849 | 25% | 2.4962 |  |  | 0 |  | 0 |  |  |  | 0 | 0% | 0 |  | 9.9849 | 0 |  | 9.9849 | 25% | 2.4962 | 0.72964 | 0.72964 | 7.307% |  | 2.4962 | 0
15 | Job: 1501 - Coil Structures Design- DAHLGREN | 1501 | 124.7677 | 1501 | 217.92 | 143 | 93.1523 |  | 93.1523 |  | 93.1523 | 20% | 18.6305 |  |  | 0 |  | 0 |  |  |  | 0 | 0% | 0 |  | 93.1523 | 0 |  | 93.1523 | 150% | 139.7285 | 40.8421 | 40.8421 | 43.84% |  | 18.6305 | 0
15 | Job: 1550 - Coil Structures Procurement -DAHLGREN | 1550 | 0 | 1550 | 1132.27 |  | 465.27 |  | 474.47 |  | 474.47 | 5% | 23.7235 | 667 |  | 667 | 30% | 200.1 | 540 |  |  |  | 0% | 0 | 0 | 1141.47 | 0 | 0 | 1141.47 | 75% | 856.1025 | 250.2358 | 250.2358 | 21.92% |  | 223.8235 | 540 | 0
16 | Job: 1601 - Coil Services Design-WILLIAMSON | 1601 | 2.79 | 1601 | 1148.33 | 3 | 172.54 |  | 170.74 |  | 170.74 | 10% | 17.074 | 956 |  | 956 | 20% | 191.2 | 50 | 17 |  | 17 | 0% | 0 | 0 | 1143.74 | 0 |  | 1143.74 | 50% | 571.87 | 167.1556 | 167.1556 | 14.61% |  | 208.274 | 50
17 | Job: 1701-Cryost&Base Sprt Strct Dsn-GETTLEFINGER | 1701 | 425.3337 | 1701 | 605.72 | 417 | 56.3863 |  | 56.3863 |  | 56.3863 | 0% | 0 | 124 |  | 124 | 25% | 31 | 50 |  |  | 0 | 0% | 0 |  | 180.3863 | 0 |  | 180.3863 | 100% | 180.3863 | 52.7263 | 52.7263 | 29.23% |  | 31 | 50
17 | Job: 1751 - Cryostat Procurement | 1751 | 0 | 1751 | 377.29 | [5 empty] | 0 |  | 0 | 322 |  | 322 | 25% | 80.5 |  | 55 |  | 55 | 0% | 0 | 50 | 377 | 0 |  | 377 | 50% | 188.5 | 55.0979 | 55.0979 | 14.61% |  | 80.5 | 50
17 | Job: 1752 - Base Support Structure Procurement | 1752 | 0 | 1752 | 231.08 |  | 3.08 |  | 2.58 |  | 2.58 | 0% | 0 | 228 |  | 228 | 25% | 57 | 50 |  |  | 0 | 0% | 0 | 0 | 230.58 | 0 |  | 230.58 | 50% | 115.29 | 33.6989 | 33.6989 | 14.61% |  | 57 | 50
18 | Job: 1801-Field Period Assly -CHRZANOWSKI (ORNL) | 1801 | 64.69 | 1801 | 64.72 | 64 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0
18 | Job: 1802 - FP Assy Oversight&Support-VIOLA | 1802 | 785.9469 | 1802 | 1614.34 | 754 | 554.3931 |  | 552.2931 |  | 552.2931 | 0% | 0 | 274 |  | 274 | 25% | 68.5 | 50 |  |  | 0 | 0% | 0 |  | 826.2931 | 0 |  | 826.2931 | 40% | 330.5172 | 96.609 | 96.609 | 11.69% |  | 68.5 | 50
18 | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803 | 871.5155 | 1803 | 1170.14 | 1007 | 298.6245 |  | 298.6245 |  | 298.6245 | 20% | 59.7249 |  |  | 0 |  | 0 |  |  |  | 0 | 0% | 0 |  | 298.6245 | 0 |  | 298.6245 | 50% | 149.3122 | 43.6434 | 43.6434 | 14.61% |  | 59.7249 | 0
18 | Job: 1804-Metrology Hardware-RAFTOPOULOS | 1804 | 551.5359 | 1804 | 587.41 | 559 | 12.6741 |  | 12.6741 |  | 12.6741 | 0% | 0 | 11.7 | -11.7 | 0 | 0% | 0 |  | 11.5 | -11.5 | 0 | 0% | 0 | 0 | 35.8741 | -23.2 |  | 12.6741 | 0% | 0 | 0 | 0 | 0% |  | 0 | 0
18 | Job: 1805 -FP Assy H/W&Fixture | 1805 | 1.7489 | 1805 | 315.2 | 7 | 303.4511 |  | 303.0511 |  | 303.0511 | 20% | 60.6102 | 10 |  | 10 | 20% | 2 |  |  |  | 0 | 0% | 0 |  | 313.0511 | 0 |  | 313.0511 | 75% | 234.7883 | 68.6278 | 68.6278 | 21.92% |  | 62.6102 | 0
18 | Job: 1806 - FP Assembly specs & dwgs | 1806 | 32.4512 | 1806 | 210.18 | 4 | 177.7288 |  | 177.7288 |  | 177.7288 | 20% | 35.5458 |  |  | 0 |  | 0 |  |  |  | 0 | 0% | 0 |  | 177.7288 | 0 |  | 177.7288 | 40% | 71.0915 | 20.7798 | 20.7798 | 11.69% |  | 35.5458 | 0
18 | Job: 1810 - Field Period Assembly-VIOLA | 1810 | 235.4228 | 1810 | 2618 | 304 | 984.8772 |  | 973.8272 |  | 973.8272 | 25% | 243.4568 | 1397.7 |  | 1397.7 | 43.4% | 606.6018 | 550 |  |  | 0 | 0% | 0 | 700 | 2371.5272 | 0 | 250 | 2621.5272 | 130% | 3407.9854 | 996.1423 | 1246.1423 | 47.53% |  | 850.0586 | 1250 | 744
19 | Job: 1901 - Stellarator Core Mngtt&Integr-NELSON | 1901 | 2042.4259 | 1901 | 2621 | 2008 | 174.0741 |  | 172.2641 |  | 172.2641 | 5% | 8.6132 | 251.5 |  | 251.5 | 5% | 12.575 |  | 153 |  | 153 | 0% | 0 | 200 | 576.7641 | 0 |  | 576.7641 | 20% | 115.3528 | 33.7172 | 33.7172 | 5.846% |  | 21.1882 | 200
2 | Job: 2001-VPS Gas& Cond Sys Oversight-BLANCHARD | 2001 | 62.8972 | 2001 | 62.89 | 63 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0
2 | Job: 2101 - Fueling Systems | 2101 | 0 | 2101 | 61.21 | [5 empty] | 0 |  | 0 | 61.2 |  | 61.2 | 10% | 6.12 |  |  |  | 0 | 0% | 0 |  | 61.2 | 0 |  | 61.2 | 30% | 18.36 | 5.3666 | 5.3666 | 8.769% |  | 6.12 | 0
2 | Job: 2201 - Vacuum Pumping Systems | 2201 | 0 | 2201 | 77.22 | [5 empty] | 0 |  | 0 | 77 |  | 77 | 10% | 7.7 |  |  |  | 0 | 0% | 0 | 50 | 77 | 0 |  | 77 | 30% | 23.1 | 6.752 | 6.752 | 8.769% |  | 7.7 | 50
2 | Job: 2501 - Neutral Beam Refurbishment-STEVENSON | 2501 | 285.0177 | 2501 | 285.01 | 285 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0
3 | Job: 3101 Magnetic Diagnostics | 3101 | 387.7871 | 3101 | 521.71 | 481 | 112.2229 |  | 112.2229 |  | 112.2229 | 15% | 16.8334 | 21.6 |  | 21.6 | 15% | 3.24 | 0 | 0.1 |  | 0.1 | 0% | 0 |  | 133.9229 | 0 |  | 133.9229 | 25% | 33.4807 | 9.7863 | 9.7863 | 7.307% |  | 20.0734 | 0
3 | Job: 3601 - Edge and Divertor | 3601 | 0 | 3601 | 9.47 | [5 empty] | 0 |  | 0 | 9 |  | 9 | 10% | 0.9 |  |  |  | 0 | 0% | 0 | 25 | 9 | 0 |  | 9 | 50% | 4.5 | 1.3153 | 1.3153 | 14.61% |  | 0.9 | 25
3 | Job: 3801 - Electron Beam Mapping | 3801 | 0 | 3801 | 29.63 | [5 empty] | 0 |  | 0 | 29 |  | 29 | 30% | 8.7 |  |  |  | 0 | 0% | 0 | 100 | 29 | 0 |  | 29 | 50% | 14.5 | 4.2383 | 4.2383 | 14.61% |  | 8.7 | 100
3 | Job: 3901 - Diagnostics sys Integration-JOHNSON | 3901 | 350.3839 | 3901 | 375.26 | 327 | 24.8761 |  | 24.8761 |  | 24.8761 | 5% | 1.2438 |  |  | 0 |  | 0 |  |  |  | 0 | 0% | 0 | 50 | 24.8761 | 0 |  | 24.8761 | 50% | 12.438 | 3.6356 | 3.6356 | 14.61% |  | 1.2438 | 50
4 | Job: 4101 - AC Power-RAMAKRISHNAN | 4101 | 108.7335 | 4101 | 363.99 | 107 |  |  |  | -229 | -229 |  | 0 | 256 | -150 | 106 | 10% | 10.6 |  |  |  | 0 | 0% | 0 | 25 | 256 | -379 |  | -123 | 0% | 0 | 0 | 0 | 0% |  | 10.6 | 25
4 | Job: 4301 - DC Systems-RAMAKRISHNAN | 4301 | 382.5035 | 4301 | 729.11 | 370 |  |  |  |  | 0 |  | 0 | 347 |  | 347 | 10% | 34.7 |  |  |  | 0 | 0% | 0 | 50 | 347 | 0 |  | 347 | 25% | 86.75 | 25.3567 | 25.3567 | 7.307% |  | 34.7 | 50
4 | Job: 4401 - Control & Protection-RAMAKRISHNAN | 4401 | 82.727 | 4401 | 1012.6 | 81 |  |  |  |  | 0 |  | 0 | 756 | -74 | 682 | 10% | 68.2 |  | 173 |  | 173 | 0% | 0 | 150 | 929 | -74 |  | 855 | 25% | 213.75 | 62.4784 | 62.4784 | 7.307% |  | 68.2 | 150
4 | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 4501 | 148.2372 | 4501 | 1076.03 | 155 |  |  |  |  | 0 |  | 0 | 928 | -177 | 751 | 10% | 75.1 |  |  |  | 0 | 0% | 0 | 150 | 928 | -177 |  | 751 | 25% | 187.75 | 54.8787 | 54.8787 | 7.307% |  | 75.1 | 150
4 | Job: 4601 - FCPC Bldg Mods-RAMAKRISHNAN | 4601 | 1.3 | 4601 | 1.28 | 1.3 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0
5 | Job: 5101 - TCP/IP Infrastructure Systems | 5101 | 0 | 5101 | 150.84 | [5 empty] | 0 |  | 0 | 150 |  | 150 | 10% | 15 | 0 |  |  | 0 | 0% | 0 | 40 | 150 | 0 |  | 150 | 30% | 45 | 13.1533 | 13.1533 | 8.769% |  | 15 | 40
5 | Job: 5201 - I&C Systems | 5201 | 0 | 5201 | 138.77 | [5 empty] | 0 |  | 0 | 122 |  | 122 | 10% | 12.2 | 0 | 15 |  | 15 | 0% | 0 | 30 | 137 | 0 |  | 137 | 30% | 41.1 | 12.0134 | 12.0134 | 8.769% |  | 12.2 | 30
5 | Job: 5301 - Data Acquisition | 5301 | 0 | 5301 | 150.09 | [5 empty] | 0 |  | 0 | 150.1 |  | 150.1 | 10% | 15.01 | 0 |  |  | 0 | 0% | 0 | 50 | 150.1 | 0 |  | 150.1 | 30% | 45.03 | 13.1621 | 13.1621 | 8.769% |  | 15.01 | 50
5 | Job: 5401 - Facility Timing & | 5401 | 0 | 5401 | 82.15 | [5 empty] | 0 |  | 0 | 82 |  | 82 | 10% | 8.2 | 0 |  |  | 0 | 0% | 0 | 50 | 82 | 0 |  | 82 | 30% | 24.6 | 7.1905 | 7.1905 | 8.769% |  | 8.2 | 50
5 | Job: 5501 - Real Time Control System | 5501 | 0 | 5501 | 94 | [5 empty] | 0 |  | 0 | 85 |  | 85 | 10% | 8.5 | 0 | 8 |  | 8 | 0% | 0 | 20 | 93 | 0 |  | 93 | 30% | 27.9 | 8.1551 | 8.1551 | 8.769% |  | 8.5 | 20
5 | Job: 5601 - Central Safety Interlock Systems | 5601 | 0 | 5601 | 129.35 | [5 empty] | 0 |  | 0 | 129 |  | 129 | 10% | 12.9 | 0 |  |  | 0 | 0% | 0 | 50 | 129 | 0 |  | 129 | 30% | 38.7 | 11.3119 | 11.3119 | 8.769% |  | 12.9 | 50
5 | Job: 5801 -Central I&C Integr | 5801 | 45.6343 | 5801 | 58.2 | 33 |  |  |  |  | 0 |  | 0 | 12 |  | 12 | 10% | 1.2 |  |  |  | 0 | 0% | 0 | 50 | 12 | 0 |  | 12 | 30% | 3.6 | 1.0523 | 1.0523 | 8.769% |  | 1.2 | 50
6 | Job: 6101 - Water Systems | 6101 | 0 | 6101 | 13.81 | [5 empty] | 0 |  | 0 | 13 |  | 13 | 10% | 1.3 |  |  |  | 0 | 0% | 0 | 50 | 13 | 0 |  | 13 | 40% | 5.2 | 1.5199 | 1.5199 | 11.69% |  | 1.3 | 50
6 | Job: 6163 - Facility Systems Support FY04 | 6163 | 15 | 6163 | 15 | 15 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0
6 | Job: 6201 - Cryogenic Systems | 6201 | 0 | 6201 | 456.14 | [5 empty] | 0 |  | 0 | 456 |  | 456 | 10% | 45.6 |  |  |  | 0 | 0% | 0 | 25 | 456 | 0 |  | 456 | 50% | 228 | 66.6436 | 66.6436 | 14.61% |  | 45.6 | 25
6 | Job: 6301 - Utility Systems | 6301 | 0 | 6301 | 106.9 | [5 empty] | 0 |  | 0 | 107 |  | 107 | 250% | 267.5 | 0 |  |  | 0 | 0% | 0 | 25 | 107 | 0 | 50 | 157 | 50% | 78.5 | 22.9453 | 72.9453 | 46.46% |  | 267.5 | 25 | 314
6 | Job: 6501 - Facility Systems Integration-DUDEK | 6501 | 9.38 | 6501 | 9.38 | 9 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0
7 | Job: 7101 - Shield Wall Modif | 7101 | 32.64 | 7101 | 32.64 | 33 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0
7 | Job: 7301 - Platform Design & | 7301 | 76.0564 | 7301 | 113.89 | 76 |  |  |  |  | 0 |  | 0 | 39.3 |  | 39.3 | 20% | 7.86 |  |  |  | 0 | 0% | 0 | 50 | 39.3 | 0 |  | 39.3 | 50% | 19.65 | 5.7436 | 5.7436 | 14.61% |  | 7.86 | 50
7 | Job: 7401 - TC Prep & Mach Assy Planning-PERRY | 7401 | 833.6841 | 7401 | 1552 | 844 | 32.7159 |  | 31.9559 |  | 31.9559 | 5% | 1.5978 | 424.6 |  | 424.6 | 25% | 106.15 |  | 261 |  | 261 | 11.69% | 30.5236 | 100 | 717.5559 | 0 |  | 717.5559 | 25% | 179.389 | 52.4348 | 52.4348 | 7.307% |  | 138.2714 | 100
7 | Job: 7501 - Construction Support Crew | 7501 | 0 | 7501 | 589 | [5 empty] | 0 |  | 0 | 284.2 |  | 284.2 | 35% | 99.47 | 50 | 304 |  | 304 | 11.69% | 35.5524 | 100 | 588.2 | 0 |  | 588.2 | 25% | 147.05 | 42.9822 | 42.9822 | 7.307% |  | 135.0224 | 150
7 | Job: 7503 - Machine Assembly | 7503 | 0 | 7503 | 1306 | [5 empty] | 0 |  | 0 | 790 |  | 790 | 35% | 276.5 | 200 | 504 |  | 504 | 13.7% | 69.048 | 800 | 1294 | 0 |  | 1294 | 100% | 1294 | 378.2317 | 378.2317 | 29.23% |  | 345.548 | 1000
7 | Job: 7601 - Tooling Design & Fabrication | 7601 | 0 | 7601 | 237.65 | [5 empty] | 0 |  | 0 | 180 |  | 180 | 35% | 63 | 50 | 56 |  | 56 | 13.7% | 7.672 | 50 | 236 | 0 |  | 236 | 50% | 118 | 34.491 | 34.491 | 14.61% |  | 70.672 | 100
8 | Job: 8101 - Project Management & Control-NEILSON | 8101 | 2663.5332 | 8101 | 3836 | 2639 | 534.9668 |  | 532.5368 | -70 | 462.5368 | 5% | 23.1268 | 553 | -101 | 452 | 10% | 45.2 |  | 84.5 |  | 84.5 | 0% | 0 | 50 | 1170.0368 | -171 |  | 999.0368 | 10% | 99.9037 | 29.2015 | 29.2015 | 2.923% |  | 68.3268 | 50
8 | Job: 8102 - NCSX MIE Management ORNL-LYON | 8102 | 443.0212 | 8102 | 532.35 | 466 | 53.3288 |  | 52.6288 |  | 52.6288 | 5% | 2.6314 | 36 |  | 36 | 10% | 3.6 |  |  |  | 0 | 0% | 0 | 0 | 88.6288 | 0 |  | 88.6288 | 10% | 8.8629 | 2.5906 | 2.5906 | 2.923% |  | 6.2314 | 0
8 | Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | 8202 | 2366.498 | 8202 | 3091 | 2382 | 417.502 |  | 414.592 | 151 | 565.592 | 20% | 113.1184 | 246 |  | 246 | 155% | 381.3 | 415 | 61 |  | 61 | 0% | 0 | 50 | 721.592 | 151 |  | 872.592 | 20% | 174.5184 | 51.0111 | 51.0111 | 5.846% |  | 494.4184 | 465
8 | Job: 8203 - Design Integration-BROWN | 8203 | 883.5802 | 8203 | 1037 | 889 | 153.4198 |  | 152.6298 |  | 152.6298 | 10% | 15.263 |  |  | 0 |  | 0 | 200 |  |  | 0 | 0% | 0 | 50 | 152.6298 | 0 | 690 | 842.6298 | 40% | 337.0519 | 98.5191 | 788.5191 | 93.58% |  | 15.263 | 250 | 690
8 | Job: 8204 - Systems Analysis-BROOKS | 8204 | 1012.0586 | 8204 | 1216.11 | 1061 | 204.0514 |  | 204.0514 |  | 204.0514 | 10% | 20.4051 |  |  | 0 |  | 0 | 200 |  |  | 0 | 0% | 0 | 50 | 204.0514 | 0 |  | 204.0514 | 40% | 81.6206 | 23.8574 | 23.8574 | 11.69% |  | 20.4051 | 250
8 | Job: 8205 - Dimensional Control Coordination | 8205 | 243.966 | 8205 | 301 | 242 | 26.034 |  | 25.584 |  | 25.584 | 10% | 2.5584 | 31 |  | 31 | 20% | 6.2 |  |  |  | 0 | 0% | 0 | 50 | 56.584 | 0 |  | 56.584 | 40% | 22.6336 | 6.6157 | 6.6157 | 11.69% |  | 8.7584 | 50
8 | Job: 8401 - Project Physcis-ZARNSTORFF | 8401 | 324.6062 | 8401 | 324.61 | 324 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0
8 | Job: 8402 - Project Physics MIE ORNL-LYON | 8402 | 146.466 | 8402 | 146.44 | 146 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | F: 0; G: 0; H: 0 | 0 | 0
8 | Job: 8501 - Integrated Systems Testing | 8501 | 0 | 8501 | 814 | [5 empty] | 0 |  | 0 | 224 |  | 224 | 30% | 67.2 |  | 588 |  | 588 | 0% | 0 | 250 | 812 | 0 |  | 812 | 50% | 406 | 118.6724 | 118.6724 | 14.61% |  | 67.2 | 250
8 | Job: 8998 - Allocations | 8998 | 1260.2126 | 8998 | 1704 | 1257 | 276.0874 |  | 275.5874 | -391 | -115.4126 | 5% | -5.7706 | 167.7 |  | 167.7 | 10% | 16.77 |  |  |  | 0 | 0% | 0 | 10 | 443.2874 | -391 |  | 52.2874 | 25% | 13.0719 | 3.8209 | 3.8209 | 7.307% |  | 10.9994 | 10
Contingency | FY06 CV plus future Contingency |  |  |  | 6627 |  |  |  | 1828 |  |  |  |  | 3075 | [5 empty] | 132 | [5 empty] | F: 0; G: 0; H: 0 | 0
[5 empty] | 92401.16 | 60347.3 | [19 empty] | D: 28058.3151; G: 3999.3847; H: 4989.3847; I: 0.17782 | [6 empty] | 185796.1598
[5 empty] | 93394.9998 |  | 11944.2251 |  | 11920.8151 | 427 | 12347.8151 | 11.27% | 1391.7229 | 12856.6 | -415.7 | 12440.9 | 35.32% | 3454.8658 | 2705 | 2291.1 | -11.5 | 2279.6 | 6.614% | 142.796 | 3900.0225 | A: 27068.5151; B: -0.2; C: 990; E: 48.76%; F: 13682.6286 | 4989.3847 | 6605.0225 | 2342 | 44883.7223
[9 empty] | 11920.8151 |  |  |  | 1818.7229 |  |  |  |  | 3039.1658 | [5 empty] | 131.296 |  | A: 27068.5151; G: 3999.3847 | 4989.1847
[9 empty] | 13748.8151 | [15 empty] | Free balance contingency = | A: 4989.3847; B: 18.43% |  |  |  | 92401.8998
[10 empty] | spent oct + nov = | 2889 | [13 empty] | Free balance plus add'l contingency = | A: 11594.4072; B: 42.83%; E: TEC=; F: 102084.9437 |  |  |  | 99006.9223
[10 empty] | spent 06+ bcwr +cont = | 16628.538 |  |  |  |  | 15895.7658 | [9 empty] | E: TEC=; F: 92421.6998
[10 empty] | funding = | 16771 |  |  |  |  | 15900 | [9 empty] | A: 4989
[10 empty] | over/under = | 142.462 |  |  |  |  | 4.2342 | [9 empty] | A: 0.38474
| 5410.9133 | [7 empty] | FY2007 |  |  |  |  | FY2008 | [5 empty] | FY2009 | [5 empty] | A: TOTAL
| 5410.9133 | [7 empty] | BCWS | ETC Increment | Total ETC | In-Budget Cont. % | In-Budget Contingency | BCWS | ETC Increment | Total ETC | In-Budget Cont. % | In-Budget Contingency | Add'l Contingency | BCWS | ETC Increment | Total ETC | In-Budget Cont. % | In-Budget Contingency | Add'l Contingency | A: BCWS; B: ETC Increment; D: Total ETC; E: In-Budget Cont. % | In-Budget Contingency | Add'l Contingency
12 | Vacuum Vessel | [7 empty] | 116.7373 | 0 | 116.7373 | 15% | 17.5106 | 244 | 0 | 244 | 15% | 36.6 | 0 | 0 | 0 | 0 |  | 0 | 0.0225 | A: 360.7373; B: 0; D: 360.7373; E: 15% | 54.1106 | 0.0225 | 0 | 12
13 | Conventional Coils | [7 empty] | 1278.7078 | 0 | 1278.7078 | 11.66% | 149.1596 | 1097 | 0 | 1097 | 25.15% | 275.909 | 50 | 0 | 0 | 0 |  | 0 | 350 | A: 2375.7078; B: 0; D: 2375.7078; E: 17.89% | 425.0686 | 400 | 200 | 13
14 | Modular Coils | [7 empty] | 5410.9133 | 966 | 6376.9133 | 10.47% | 566.6663 | 507 | 98 | 605 | 42.79% | 216.96 | 250 | 0 | 0 | 0 |  | 0 | 0 | A: 5917.9133; B: 1064; D: 6981.9133; E: 11.22% | 783.6263 | 250 | 394 | 14
15 | Coil Structures | [7 empty] | 567.6223 | 0 | 567.6223 | 7.462% | 42.354 | 667 | 0 | 667 | 30% | 200.1 | 540 | 0 | 0 | 0 |  | 0 | 0 | A: 1234.6223; B: 0; D: 1234.6223; E: 19.64% | 242.454 | 540 | 0 | 15
16 | Coil Services | [7 empty] | 170.74 | 0 | 170.74 | 10% | 17.074 | 956 | 0 | 956 | 20% | 191.2 | 50 | 17 | 0 | 17 | 0% | 0 | 0 | A: 1143.74; B: 0; D: 1143.74; E: 18.21% | 208.274 | 50 | 0 | 16
17 | Cryostat & Base | [7 empty] | 58.9663 | 0 | 58.9663 | 0% | 0 | 674 | 0 | 674 | 25% | 168.5 | 100 | 55 | 0 | 55 | 0% | 0 | 50 | A: 787.9663; B: 0; D: 787.9663; E: 21.38% | 168.5 | 150 | 0 | 17
18 | Field Period Assembly | [7 empty] | 2318.1988 | 0 | 2318.1988 | 17.23% | 399.3377 | 1693.4 | -11.7 | 1681.7 | 39.98% | 677.1018 | 600 | 11.5 | -11.5 | 0 | 0% | 0 | 700 | A: 4023.0988; B: -23.2; D: 3999.8988; E: 26.91% | 1076.4395 | 1300 | 744 | 18
19 | Stellarator Core Mgt. / Integration | [7 empty] | 172.2641 | 0 | 172.2641 | 5% | 8.6132 | 251.5 | 0 | 251.5 | 5% | 12.575 | 0 | 153 | 0 | 153 | 0% | 0 | 200 | A: 576.7641; B: 0; D: 576.7641; E: 3.674% | 21.1882 | 200 | 0 | 19
2 | Fueling & Vacuum | [7 empty] | 0 | 0 | 0 |  | 0 | 138.2 | 0 | 138.2 | 10% | 13.82 | 0 | 0 | 0 | 0 |  | 0 | 50 | A: 138.2; B: 0; D: 138.2; E: 10% | 13.82 | 50 | 0 | 2
3 | Diagnsotics | [7 empty] | 137.099 | 0 | 137.099 | 13.19% | 18.0772 | 59.6 | 0 | 59.6 | 21.54% | 12.84 | 0 | 0.1 | 0 | 0.1 | 0% | 0 | 175 | A: 196.799; B: 0; D: 196.799; E: 15.71% | 30.9172 | 175 | 0 | 3
4 | Power Systems | [7 empty] | 0 | -229 | -229 |  | 0 | 2287 | -401 | 1886 | 8.247% | 188.6 | 0 | 173 | 0 | 173 | 0% | 0 | 375 | A: 2460; B: -630; D: 1830; E: 10.31% | 188.6 | 375 | 0 | 4
5 | Central I&C / Data Aq. | [7 empty] | 0 | 0 | 0 |  | 0 | 730.1 | 0 | 730.1 | 10% | 73.01 | 0 | 23 | 0 | 23 | 0% | 0 | 290 | A: 753.1; B: 0; D: 753.1; E: 9.695% | 73.01 | 290 | 0 | 5
6 | Facility Systems | [7 empty] | 0 | 0 | 0 |  | 0 | 576 | 0 | 576 | 54.58% | 314.4 | 0 | 0 | 0 | 0 |  | 0 | 100 | A: 576; B: 0; D: 576; E: 54.58% | 314.4 | 100 | 314 | 6
7 | Test Cell Prep / Machine Assembly | [7 empty] | 31.9559 | 0 | 31.9559 | 5% | 1.5978 | 1718.1 | 0 | 1718.1 | 32.19% | 552.98 | 300 | 1125 | 0 | 1125 | 12.69% | 142.796 | 1100 | A: 2875.0559; B: 0; D: 2875.0559; E: 24.26% | 697.3738 | 1400 | 0 | 7
8 | Project Mgt. & Integration | [7 empty] | 1657.6103 | -310 | 1347.6103 | 10.34% | 171.3326 | 1257.7 | -101 | 1156.7 | 41.37% | 520.27 | 815 | 733.5 | 0 | 733.5 | 0% | 0 | 510 | A: 3648.8103; B: -411; D: 3237.8103; E: 21.36% | 691.6026 | 1325 | 690 | 8
[9 empty] | 11920.8151 | 427 | 12347.8151 | 11.67% | 1391.7229 | 12856.6 | -415.7 | 12440.9 | 26.87% | 3454.8658 | 2705 | 2291.1 | -11.5 | 2279.6 | 6.233% | 142.796 | 3900.0225 | A: 27068.5151; B: -0.2; D: 27068.3151; E: 18.43% | 4989.3847 | 6605.0225 | 2342 | 41004.7223
| Contingency | [7 empty] | 1828 |  |  |  |  | 3075 | [5 empty] | 132 | [5 empty] | A: 5035
| Total | [7 empty] | 13748.8151 |  |  |  | 1391.7229 | 15931.6 |  |  |  | 3454.8658 | 2705 | 2423.1 |  |  |  | 142.796 | 3900.0225 | A: 32103.5151
13748.8151
| BCWS + Cont | [11 empty] | 13739.538 |  |  |  |  | 15895.7658 | [5 empty] | 2422.396 | [11 empty] | 32057.6998
| BA & c/o | [11 empty] | 16771 |  |  |  |  | 15900 | [5 empty] | 2269 | [11 empty] | 34940
High Confidence Contingency less Known Risks
12 | Vacuum Vessel | [7 empty] | 253.2 | -6.7458
13 | Conventional Coils | [7 empty] | 1601.2 | -42.6594 | [39 empty] | 14.61%
14 | Modular Coils | [7 empty] | 6920.1 | -184.3663 | [39 empty] | 10.14%
15 | Coil Structures | [7 empty] | 608.8 | -16.2197 | [39 empty] | 9.558%
16 | Coil Services | [7 empty] | 171 | -4.5558 | [39 empty] | 23.58%
17 | Cryostat & Base | [7 empty] | 59.2 | -1.5772 | [39 empty] | 14.61%
18 | Field Period Assembly | [7 empty] | 2678.8 | -71.369 | [39 empty] | 17.96%
19 | Stellarator Core Mgt. / Integration | [7 empty] | 208.3 | -5.5496 | [39 empty] | 30.65%
2 | Fueling & Vacuum | [7 empty] | 0 | 0 | [39 empty] | 5.846%
3 | Diagnsotics | [7 empty] | 142.9 | -3.8072 | [39 empty] | 16.15%
4 | Power Systems | [7 empty] | 0 | 0 | [39 empty] | 8.769%
5 | Central I&C / Data Aq. | [7 empty] | 0 | 0 | [39 empty] | 9.642%
6 | Facility Systems | [7 empty] | 0 | 0 | [39 empty] | 7.799%
7 | Test Cell Prep / Machine Assembly | [7 empty] | 34.5 | -0.91915 | [39 empty] | 8.769%
8 | Project Mgt. & Integration | [7 empty] | 1998.3 | -53.239 | [39 empty] | 15.82%
[10 empty] | -391.008 | [39 empty] | 17.87%
10.32%
14.78%
60269
[9 empty] | FY2007 |  |  |  |  | FY2008 | [5 empty] | FY2009 | [5 empty] | A: TOTAL
[9 empty] | BCWR (from 12/1/06) | ETC Increment | Total ETC | In-Budget Cont. % | In-Budget Contingency/Risk | BCWR | ETC Increment | Total ETC | In-Budget Cont. % | In-Budget Contingency/Risk | Add'l Contingency | BCWR | ETC Increment | Total ETC | In-Budget Cont. % | In-Budget Contingency/Risk | Add'l Contingency | A: BCWR (from 12/1/06); B: ETC Increment; D: Total ETC; E: In-Budget Cont. % | In-Budget Contingency | Add'l Contingency | Total Contingency | Total Conting. % | Known Risks |  |  |  | #REF! |  |  | 27068.3151 | #REF! | 990 | #REF! | #REF! | #REF!
Activities (Job or WBS numbers)
High Risk | [8 empty] | 5042.6468 | 619 | 5661.6468 | 9.174% | 519.4051 | 3918.5 | 86.3 | 4004.8 | 36.13% | 1447.0418 | 1150 | 1136.5 | -11.5 | 1125 | 12.69% | 142.796 | 1800 | A: 10097.6468; B: 693.8; D: 10791.4468; E: 19.55% | 2109.2429 | 2950 | 5059.2429 | 46.88% | 1138
| Mod. Coil Winding Ops (1408, 1451, 1459, 1460) | [7 empty] | 3168.8453 | 619 | 3787.8453 | 5.643% | 213.7403 | 507 | 98 | 605 | 35.86% | 216.96 | 250 | 0 | 0 | 0 |  | 0 | 0 | A: 3675.8453; B: 717; D: 4392.8453; E: 9.805% | 430.7003 | 250 | 680.7003 | 15.5% | 394
| Field Period Assy Ops. (1810, 1802, 1805, 1804) | [7 empty] | 1841.8455 | 0 | 1841.8455 | 16.51% | 304.067 | 1693.4 | -11.7 | 1681.7 | 40.26% | 677.1018 | 600 | 11.5 | -11.5 | 0 |  | 0 | 700 | A: 3546.7455; B: -23.2; D: 3523.5455; E: 27.85% | 981.1688 | 1300 | 2281.1688 | 64.74% | 744 | [9 empty] | #REF!
| Machine Assy. (7) | [7 empty] | 31.9559 | 0 | 31.9559 | 5% | 1.5978 | 1718.1 | 0 | 1718.1 | 32.19% | 552.98 | 300 | 1125 | 0 | 1125 | 12.69% | 142.796 | 1100 | A: 2875.0559; B: 0; D: 2875.0559; E: 24.26% | 697.3738 | 1400 | 2097.3738 | 72.95% | 0
Medium Risk | [8 empty] | 3825.0662 | 498 | 4323.0662 | 15.9% | 687.153 | 4143.5 | 0 | 4143.5 | 31.73% | 1314.884 | 1555 | 874 | 0 | 874 | 0% | 0 | 1000.0225 | A: 8842.5662; B: 498; D: 9340.5662; E: 21.43% | 2002.037 | 2555.0225 | 4557.0595 | 48.79% | 890
| VV System Procurements (1204) | [7 empty] | 116.7373 | 0 | 116.7373 | 15% | 17.5106 | 244 | 0 | 244 | 15% | 36.6 | 0 | 0 | 0 | 0 |  | 0 | 0.0225 | A: 360.7373; B: 0; D: 360.7373; E: 15% | 54.1106 | 0.0225 | 54.1331 | 15.01% | 0
| PF & Trim Coils (1302, 1303, 1352, 1354, 1353, 1355) | [7 empty] | 398.504 | 0 | 398.504 | 15.26% | 60.812 | 850 | 0 | 850 | 29.55% | 251.209 | 50 | 0 | 0 | 0 |  | 0 | 300 | A: 1248.504; B: 0; D: 1248.504; E: 24.99% | 312.021 | 350 | 662.021 | 53.03% | 200
| Mod. Coil Design & Hdwe. (1416, 1421, 1431) | [7 empty] | 1067.0216 | 347 | 1414.0216 | 20.8% | 294.1737 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | A: 1067.0216; B: 347; D: 1414.0216; E: 20.8% | 294.1737 | 0 | 294.1737 | 20.8% | 0
| Field Period Assy. Design (1803, 1806) | [7 empty] | 476.3533 | 0 | 476.3533 | 20% | 95.2707 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | A: 476.3533; B: 0; D: 476.3533; E: 20% | 95.2707 | 0 | 95.2707 | 20% | 0
| Coil Structures (15) | [7 empty] | 567.6223 | 0 | 567.6223 | 7.462% | 42.354 | 667 | 0 | 667 | 30% | 200.1 | 540 | 0 | 0 | 0 |  | 0 | 0 | A: 1234.6223; B: 0; D: 1234.6223; E: 19.64% | 242.454 | 540 | 782.454 | 63.38% | 0
| Coil Services (16) | [7 empty] | 170.74 | 0 | 170.74 | 10% | 17.074 | 956 | 0 | 956 | 20% | 191.2 | 50 | 17 | 0 | 17 | 0% | 0 | 0 | A: 1143.74; B: 0; D: 1143.74; E: 18.21% | 208.274 | 50 | 258.274 | 22.58% | 0
| Cryostat & Base (17) | [7 empty] | 58.9663 | 0 | 58.9663 | 0% | 0 | 674 | 0 | 674 | 25% | 168.5 | 100 | 55 | 0 | 55 | 0% | 0 | 50 | A: 787.9663; B: 0; D: 787.9663; E: 21.38% | 168.5 | 150 | 318.5 | 40.42% | 0
| Stellarator Core Design Integration | [7 empty] | 172.2641 | 0 | 172.2641 | 5% | 8.6132 | 251.5 | 0 | 251.5 | 5% | 12.575 | 0 | 153 | 0 | 153 | 0% | 0 | 200 | A: 576.7641; B: 0; D: 576.7641; E: 3.674% | 21.1882 | 200 | 221.1882 | 38.35% | 0
| System Engineering (82) | [7 empty] | 796.8573 | 151 | 947.8573 | 15.97% | 151.3449 | 277 | 0 | 277 | 139.9% | 387.5 | 815 | 61 | 0 | 61 | 0% | 0 | 200 | A: 1134.8573; B: 151; D: 1285.8573; E: 41.91% | 538.8449 | 1015 | 1553.8449 | 120.8% | 690
| Startup (85) | [7 empty] | 0 | 0 | 0 |  | 0 | 224 | 0 | 224 | 30% | 67.2 | 0 | 588 | 0 | 588 | 0% | 0 | 250 | A: 812; B: 0; D: 812; E: 8.276% | 67.2 | 250 | 317.2 | 39.06% | 0
Low Risk | [8 empty] | 3053.1022 | -690 | 2363.1022 | 7.836% | 185.1648 | 4794.6 | -502 | 4292.6 | 16.14% | 692.94 | 0 | 280.6 | 0 | 280.6 | 0% | 0 | 1100 | A: 8128.3022; B: -1192; D: 6936.3022; E: 12.66% | 878.1048 | 1100 | 1978.1048 | 28.52% | 314
| TF Fabrication (1351, 1361) | [7 empty] | 880.2038 | 0 | 880.2038 | 10.04% | 88.3476 | 247 | 0 | 247 | 10% | 24.7 | 0 | 0 | 0 | 0 |  | 0 | 50 | A: 1127.2038; B: 0; D: 1127.2038; E: 10.03% | 113.0476 | 50 | 163.0476 | 14.46% | 0
| MCWF Fabrication (1411) | [7 empty] | 1175.0464 | 0 | 1175.0464 | 5% | 58.7523 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | A: 1175.0464; B: 0; D: 1175.0464; E: 5% | 58.7523 | 0 | 58.7523 | 5% | 0
| Fueling & Vacuum (2) | [7 empty] | 0 | 0 | 0 |  | 0 | 138.2 | 0 | 138.2 | 10% | 13.82 | 0 | 0 | 0 | 0 |  | 0 | 50 | A: 138.2; B: 0; D: 138.2; E: 10% | 13.82 | 50 | 63.82 | 46.18% | 0
| Diagnostics (3) | [7 empty] | 137.099 | 0 | 137.099 | 13.19% | 18.0772 | 59.6 | 0 | 59.6 | 21.54% | 12.84 | 0 | 0.1 | 0 | 0.1 | 0% | 0 | 175 | A: 196.799; B: 0; D: 196.799; E: 15.71% | 30.9172 | 175 | 205.9172 | 104.6% | 0
| Power Systems (4) | [7 empty] | 0 | -229 | -229 | 0% | 0 | 2287 | -401 | 1886 | 10% | 188.6 | 0 | 173 | 0 | 173 | 0% | 0 | 375 | A: 2460; B: -630; D: 1830; E: 10.31% | 188.6 | 375 | 563.6 | 30.8% | 0
| Central I&C / Data Aq. (5) | [7 empty] | 0 | 0 | 0 |  | 0 | 730.1 | 0 | 730.1 | 10% | 73.01 | 0 | 23 | 0 | 23 | 0% | 0 | 290 | A: 753.1; B: 0; D: 753.1; E: 9.695% | 73.01 | 290 | 363.01 | 48.2% | 0
| Facility Systems (6) | [7 empty] | 0 | 0 | 0 |  | 0 | 576 | 0 | 576 | 54.58% | 314.4 | 0 | 0 | 0 | 0 |  | 0 | 100 | A: 576; B: 0; D: 576; E: 54.58% | 314.4 | 100 | 414.4 | 71.94% | 314
| Management (81) | [7 empty] | 860.7531 | -461 | 399.7531 | 5% | 19.9877 | 756.7 | -101 | 655.7 | 10% | 65.57 | 0 | 84.5 | 0 | 84.5 | 0% | 0 | 60 | A: 1701.9531; B: -562; D: 1139.9531; E: 7.505% | 85.5577 | 60 | 145.5577 | 12.77% | 0
Total Work | [8 empty] | 11920.8151 | 427 | 12347.8151 | 11.27% | 1391.7229 | 12856.6 | -415.7 | 12440.9 | 27.77% | 3454.8658 | 2705 | 2291.1 | -11.5 | 2279.6 | 6.264% | 142.796 | 3900.0225 | A: 27068.5151; B: -0.2; D: 27068.3151; E: 18.43% | 4989.3847 | 6605.0225 | 11594.4072 | 42.83% | 2342
Contingency | [8 empty] | 1828 |  | 0 |  |  | 3075 |  | 0 |  | 0 |  | 132 |  | 0 |  | 0
[9 empty] | FY2007 |  |  |  |  | FY2008 | [5 empty] | FY2009 | [5 empty] | A: TOTAL
[9 empty] | BCWR (from 12/1/06) | ETC Increment | Total ETC | In-Budget Cont. % | In-Budget Contingency/Risk | BCWR | ETC Increment | Total ETC | In-Budget Cont. % | In-Budget Contingency/Risk | Add'l Contingency | BCWR | ETC Increment | Total ETC | In-Budget Cont. % | In-Budget Contingency/Risk | Add'l Contingency | A: BCWR (from 12/1/06); B: ETC Increment; D: Total ETC; E: In-Budget Cont. % | In-Budget Contingency | Add'l Contingency | Total Contingency | Total Conting. % | Known Risks
Activities (Job or WBS numbers)
High Risk | [8 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | A: 0; B: 0; D: 0; E: 0% | 0 | 0 | 0 | 0% | 0
| Mod. Coil Winding Ops (1408, 1451, 1459, 1460) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | A: 0; B: 0; D: 0; E: 0% | 0 | 0 | 0 | 0% | 0
| Field Period Assy Ops. (1810, 1802, 1805, 1804) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | A: 0; B: 0; D: 0; E: 0% | 0 | 0 | 0 | 0% | 0
| Machine Assy. (7) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | A: 0; B: 0; D: 0; E: 0% | 0 | 0 | 0 | 0% | 0
Medium Risk | [8 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | A: 0; B: 0; D: 0; E: 0% | 0 | 0 | 0 | 0% | 0
| VV System Procurements (1204) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | A: 0; B: 0; D: 0; E: 0% | 0 | 0 | 0 | 0% | 0
| PF & Trim Coils (1302, 1303, 1352, 1354, 1353, 1355) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | A: 0; B: 0; D: 0; E: 0% | 0 | 0 | 0 | 0% | 0
| Mod. Coil Design & Hdwe. (1416, 1421, 1431) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | A: 0; B: 0; D: 0; E: 0% | 0 | 0 | 0 | 0% | 0
| Field Period Assy. Design (1803, 1806) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | A: 0; B: 0; D: 0; E: 0% | 0 | 0 | 0 | 0% | 0
| Coil Structures (15) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | A: 0; B: 0; D: 0; E: 0% | 0 | 0 | 0 | 0% | 0
| Coil Services (16) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | A: 0; B: 0; D: 0; E: 0% | 0 | 0 | 0 | 0% | 0
| Cryostat & Base (17) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | A: 0; B: 0; D: 0; E: 0% | 0 | 0 | 0 | 0% | 0
| Stellarator Core Design Integration | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | A: 0; B: 0; D: 0; E: 0% | 0 | 0 | 0 | 0% | 0
| System Engineering (82) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | A: 0; B: 0; D: 0; E: 0% | 0 | 0 | 0 | 0% | 0
| Startup (85) | [7 empty] | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | A: 0; B: 0; D: 0; E: 0% | 0 | 0 | 0 | 0% | 0
Low Risk | [8 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | A: 0; B: 0; D: 0; E: 0% | 0 | 0 | 0 | 0% | 0
| TF Fabrication (1351, 1361) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | A: 0; B: 0; D: 0; E: 0% | 0 | 0 | 0 | 0% | 0
| MCWF Fabrication (1411) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | A: 0; B: 0; D: 0; E: 0% | 0 | 0 | 0 | 0% | 0
| Fueling & Vacuum (2) | [7 empty] | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | A: 0; B: 0; D: 0; E: 0% | 0 | 0 | 0 | 0% | 0
| Diagnostics (3) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | A: 0; B: 0; D: 0; E: 0% | 0 | 0 | 0 | 0% | 0
| Power Systems (4) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | A: 0; B: 0; D: 0; E: 0% | 0 | 0 | 0 | 0% | 0
| Central I&C / Data Aq. (5) | [7 empty] | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | A: 0; B: 0; D: 0; E: 0% | 0 | 0 | 0 | 0% | 0
| Facility Systems (6) | [7 empty] | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | A: 0; B: 0; D: 0; E: 0% | 0 | 0 | 0 | 0% | 0
| Management (81) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | A: 0; B: 0; D: 0; E: 0% | 0 | 0 | 0 | 0% | 0
Total Work | [8 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | A: 0; B: 0; D: 0; E: 0% | 0 | 0 | 0 | 0% | 0

## ContingencyH
[8 empty] | Prior FY | FY2007 |  |  |  |  | FY2008 | [5 empty] | FY2009 | [5 empty] | A | B | C | D | E | F | G |  |  | H | I | J
[26 empty] | BCWR |  |  | A+B+C |  | E x D | F + C | G/(A+B) |  | F + C | [9 empty] | A+B | C | A+B+C | F | F/(A+B+C) | F + C | (F+C) / (A+B)
WBS | JOB | [7 empty] | BCWR (from 12/1/06) | ETC Increment | Total ETC | In-Budget Cont. % | In-Budget Contingency/Risk | BCWR | ETC Increment | Total ETC | In-Budget Cont. % | In-Budget Contingency/Risk | Add'l Contingency | BCWR | ETC Increment | Total ETC | In-Budget Cont. % | In-Budget Contingency/Risk | Add'l Contingency | BCWR (from 12/1/06) | ECP53 Increment | Unavoidaable Risk | Total ETC | Risk Assessment % | Growth Risk $ | Total contingency | Contingency % | In-Budget Contingency | Total free balance contingency |  |  | In-Budget Contingency | Add'l Contingency | Known Risks |  |  |  | High Level Contingency Analysis
High Level Contingency Analysis |  |  | bcwp thru 11/30/06 |  | Base Cost | Cost Through 11/30/06 | BCWR 12/1/067 | Cost | 11920.8151 |  |  | 11.27% | 1391.7229 | 12856.6 |  |  | 35.32% | 3454.8658 | 2705 | 2291.1 |  |  | 6.614% | 142.796 | 3900.0225 | [19 empty] | BCWR (ECP-53) | Known Risks | ETC= BCWR + Known Risks | Aditional Contingency |  | Total High Level Contingency
dcma | dcma |  |  |  | 75 | 75 |  | 75 |  |  | 0 |  |  |  |  | 0 | [5 empty] | 0 | [8 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  |  |  | WBS |  |  |  | $ | % | $ | %
12 | Job: 1201 - Vacuum Vessel Prelim Dsn-**CLOSED** | 1201 | 424.42 | 1201 | 424.42 | 424 | 0 |  | 0 |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 12 | Vacuum Vessel | 360.7373 | 0 | 360.7373 | 180.3686 | 50% | 180.3686 | 50%
12 | Job: 1202 - Vacuum Vessel R&D | 1202 | 1770.1819 | 1202 | 1769.81 | 1771 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 13 | Conventional Coils | 2375.7078 | 0 | 2375.7078 | 1114.5539 | 46.91% | 1114.5539 | 46.91%
12 | Job: 1203 - Vacuum Vessel Final Dsn-**CLOSED** | 1203 | 1217.8391 | 1203 | 1217.81 | 1220 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 14 | Modular Coils | 6981.9133 | 0 | 6981.9133 | 2576.4824 | 36.9% | 2576.4824 | 36.9%
12 | Job: 1204-VV Sys Procurements (non VVSA)-DUDEK | 1204 | 323.8427 | 1204 | 685.08 | 378 | 117.2373 |  | 116.7373 |  | 116.7373 | 15% | 17.5106 | 244 |  | 244 | 15% | 36.6 |  |  |  | 0 | 0% | 0 | 0.0225 | 360.7373 | 0 |  | 360.7373 | 50% | 180.3686 | 180.3686 | 50% | 44.0555 | 44.0555 |  |  | 54.1106 | 0.0225 |  |  |  | 15 | Coil Structures | 1234.6223 | 0 | 1234.6223 | 1132.1225 | 91.7% | 1132.1225 | 91.7%
12 | Job: 1206 - VV Field Weld Joint R&D-**CLOSED** | 1206 | 15.6394 | 1206 | 15.64 | 16 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 16 | Coil Services | 1143.74 | 0 | 1143.74 | 571.87 | 50% | 571.87 | 50%
12 | Job: 1250 - Vacuum Vessel Fabrication--**CLOSED** | 1250 | 5808.603 | 1250 | 5809 | 5815 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 17 | Cryostat & Base | 787.9663 | 0 | 787.9663 | 1049.6763 | 133.2% | 1049.6763 | 133.2%
13 | Job: 1301 - TF Design-KALISH**CLOSED** | 1301 | 970.6526 | 1301 | 970.57 | 970 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 18 | Field Period Assembly | 3999.8988 | 250 | 4249.8988 | 4395.028 | 103.4% | 4645.028 | 116.1%
13 | Job: 1302 - PF Design -KALISH | 1302 | -7.774 | 1302 | 131.97 | 19 | 139.744 |  | 139.744 |  | 139.744 | 25% | 34.936 |  |  | 0 |  | 0 |  |  |  | 0 | 0% | 0 |  | 139.744 | 0 |  | 139.744 | 100% | 139.744 | 139.744 | 100% | 34.1329 | 34.1329 |  |  | 34.936 | 0 |  |  |  | 19 | Stellarator Core Mgt. / Integration | 576.7641 | 0 | 576.7641 | 115.3528 | 20% | 115.3528 | 20%
13 | Job: 1303 -Central Solenoid Support Dsn-DAHLGREN | 1303 | 116.8828 | 1303 | 106.35 | 138 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 1 | Stellarator Core Systems | 17461.3499 | 250 | 17711.3499 | 11135.4545 | 62.87% | 11385.4545 | 65.2%
13 | Job: 1350 TF Coil Fab Prep-CHRZANOWSKI**CLOSED** | 1350 | 547.015 | 1350 | 547.01 | 536 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 2 | Fueling & Vacuum | 138.2 | 0 | 138.2 | 41.46 | 30% | 41.46 | 30%
13 | Job: 1351 - TF Coil Fabr Supplies-KALISH | 1351 | 463.4553 | 1351 | 470 | 453 | 6.5447 |  | 6.5447 |  | 6.5447 | 15% | 0.98171 |  |  | 0 |  | 0 |  |  |  | 0 | 0% | 0 |  | 6.5447 | 0 |  | 6.5447 | 20% | 1.3089 | 1.3089 | 20% | 0.31971 | 0.31971 |  |  | 0.98171 | 0 |  |  |  | 3 | Diagnsotics | 196.799 | 0 | 196.799 | 64.9188 | 32.99% | 64.9188 | 32.99%
13 | Job: 1352 - PF Coil Procurement-KALISH | 1352 | 0 | 1352 | 787.95 | 0 | 226.95 |  | 226.25 |  | 226.25 | 10% | 22.625 | 561 |  | 561 | 31.9% | 178.959 | 50 |  |  | 0 | 0% | 0 | 100 | 787.25 | 0 | 0 | 787.25 | 88% | 692.78 | 692.78 | 88% | 169.2134 | 169.2134 |  |  | 201.584 | 150 | 200 |  |  | 4 | Power Systems | 1830 | 0 | 1830 | 488.25 | 26.68% | 488.25 | 26.68%
13 | Job: 1353 - CS Structure Procurement-DAHLGREN | 1353 | 0 | 1353 | 122.61 | 0 | 32.61 |  | 32.51 |  | 32.51 | 10% | 3.251 | 90 |  | 90 | 25% | 22.5 |  |  |  | 0 | 0% | 0 |  | 122.51 | 0 |  | 122.51 | 50% | 61.255 | 61.255 | 50% | 14.9617 | 14.9617 |  |  | 25.751 | 0 |  |  |  | 5 | Central I&C / Data Aq. | 753.1 | 0 | 753.1 | 225.93 | 30% | 225.93 | 30%
13 | Job: 1354 - Trim Coil Design &Procurement-KALISH | 1354 | 0 | 1354 | 106.07 | 0 |  |  |  |  | 0 |  | 0 | 106 |  | 106 | 25% | 26.5 |  |  |  | 0 | 0% | 0 | 200 | 106 | 0 |  | 106 | 75% | 79.5 | 79.5 | 75% | 19.4181 | 19.4181 |  |  | 26.5 | 200 |  |  |  | 6 | Facility Systems | 576 | 50 | 626 | 704.2 | 112.5% | 754.2 | 130.9%
13 | Job: 1355 - WBS 13 I&C Proc & | 1355 | 0 | 1355 | 93.42 | 0 |  |  |  |  | 0 |  | 0 | 93 |  | 93 | 25% | 23.25 |  |  |  | 0 | 0% | 0 |  | 93 | 0 |  | 93 | 30% | 27.9 | 27.9 | 30% | 6.8146 | 6.8146 |  |  | 23.25 | 0 |  |  |  | 7 | Test Cell Prep / Machine Assembly | 2875.0559 | 0 | 2875.0559 | 1758.089 | 61.15% | 1758.089 | 61.15%
13 | Job: 1361 - TF Fabrication-KALISH | 1361 | 923.411 | 1361 | 2044.97 | 841 | 874.559 |  | 873.659 |  | 873.659 | 10% | 87.3659 | 247 |  | 247 | 10% | 24.7 |  |  |  | 0 | 0% | 0 | 50 | 1120.659 | 0 |  | 1120.659 | 10% | 112.0659 | 112.0659 | 10% | 27.3724 | 27.3724 |  |  | 112.0659 | 50 |  |  |  | 8 | Project Mgt. & Integration | 3237.8103 | 690 | 3927.8103 | 1955.6629 | 49.79% | 2645.6629 | 81.71%
14 | Job: 1401 - Mod Coil Prel.Dsn**CLOSED** | 1401 | 304.04 | 1401 | 304.05 | 304 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | [5 empty] | 27068.3151 | 990 | 28058.3151 | 16373.9652 | 58.36% | 17363.9652 | 64.15%
14 | Job: 1402 - Mod.Coil Analyses**CLOSED** | 1402 | 239.14 | 1402 | 239.12 | 239 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0
14 | Job: 1403 - Modular Coil Final Design-WILLIAMSON | 1403 | 3310.5695 | 1403 | 3310.02 | 3310 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | [10 empty] | Cost YTD = | 60269
14 | Job: 1404-MCWF R&D & 1st Prod Casting**CLOSED** | 1404 | 2543.5181 | 1404 | 2544 | 2554 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | [10 empty] | BCWR = | 27068.3151
14 | Job: 1405-Mod Coil Winding R&D Prep-**CLOSED** | 1405 | 168.07 | 1405 | 168.07 | 168 | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | [10 empty] | High Level Contingency = | 17363.9652 | 64.15%
14 | Job: 1406 - Mod. Coil Winding | 1406 | 2263.5684 | 1406 | 2262.96 | 2263 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | [10 empty] | DCMA = | 75
14 | Job: 1407 -Mod Coil Winding Facility-**CLOSED** | 1407 | 2571.3731 | 1407 | 2570.78 | 2570 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | [10 empty] | TEC = | 104776.2803
14 | Job: 1408-Mod Coil Winding Supplies-CHRZANOWSKI | 1408 | 1724.92 | 1408 | 1952.63 | 1957 | 223.71 |  | 223.51 |  | 223.51 | 15% | 33.5265 | 4 |  | 4 | 15% | 0.6 |  |  |  | 0 | 0% | 0 |  | 227.51 | 0 |  | 227.51 | 25% | 56.8775 | 56.8775 | 25% | 13.8925 | 13.8925 |  |  | 34.1265 | 0
14 | Job: 1409 - Coil Test Stand-GETTELFINGER*CLOSED* | 1409 | 825.9413 | 1409 | 825.96 | 833 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0
14 | Job: 1410 MC Twisted Racetrack Fabr-**CLOSED** | 1410 | 1049.9713 | 1410 | 1049.9 | 1050 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0
14 | Job: 1411-MCWF Fabrication S005242-HEITZENROEDER | 1411 | 8669.4236 | 1411 | 9844.47 | 8720 | 1175.0464 |  | 1175.0464 |  | 1175.0464 | 5% | 58.7523 |  |  | 0 |  | 0 |  |  |  | 0 | 0% | 0 |  | 1175.0464 | 0 |  | 1175.0464 | 10% | 117.5046 | 117.5046 | 10% | 28.7008 | 28.7008 |  |  | 58.7523 | 0
14 | Job: 1412 - Complete Winding Facilities-*CLOSED* | 1412 | 540.9969 | 1412 | 541.02 | 541 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0
14 | Job: 1413 -MCWF Fracture Analysis-**CLOSED** | 1413 | 27.8194 | 1413 | 27.84 | 28 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0
14 | Job: 1414 Coil Testing-Gettelfinger**CLOSED** | 1414 | 674.8333 | 1414 | 674.68 | 639 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0
14 | Job: 1415 Dim Cntrl Testing-RAFTOPOLOUS*CLOSED** | 1415 | 23.85 | 1415 | 23.83 | 24 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0
14 | Job: 1416-Mod Coil Type A&B Final Dsn-WILLIAMSON | 1416 | 579.5028 | 1416 | 685.89 | 642 | 106.3872 |  | 106.3872 | 121 | 227.3872 | 25% | 56.8468 |  |  | 0 |  | 0 |  |  |  | 0 | 0% | 0 |  | 106.3872 | 121 |  | 227.3872 | 25% | 56.8468 | 56.8468 | 25% | 13.885 | 13.885 |  |  | 56.8468 | 0
14 | Job: 1419-Winding Fac. Mods-CHRZANOWSKI*CLOSED* | 1419 | 55.21 | 1419 | 55.21 | 46 | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0
14 | Job: 1421-Mod Coil Interface Design-WILLIAMSON | 1421 | 118.1756 | 1421 | 379.91 | 120 | 261.7344 |  | 261.7344 | 226 | 487.7344 | 20% | 97.5469 |  |  | 0 |  | 0 |  |  |  | 0 | 0% | 0 |  | 261.7344 | 226 |  | 487.7344 | 100% | 487.7344 | 487.7344 | 100% | 119.1304 | 119.1304 |  |  | 97.5469 | 0
14 | Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 1431 | 0 | 1431 | 698.9 |  | 698.9 |  | 698.9 |  | 698.9 | 20% | 139.78 |  |  | 0 |  | 0 |  |  |  | 0 | 0% | 0 |  | 698.9 | 0 |  | 698.9 | 100% | 698.9 | 698.9 | 100% | 170.7082 | 170.7082 |  |  | 139.78 | 0
14 | Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 1451 | 2896.7274 | 1451 | 5994 | 4045 | 2637.2726 |  | 2633.9626 | 619 | 3252.9626 | 5% | 162.6481 | 460 | 98 | 558 | 36% | 200.88 | 250 |  |  | 0 | 0% | 0 |  | 3093.9626 | 717 | 0 | 3810.9626 | 21.3% | 811.735 | 811.735 | 21.3% | 198.2685 | 198.2685 |  |  | 363.5281 | 250 | 394
| Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | 1459 | 77.7722 | 1459 | 422.86 | 45 | 302.0878 |  | 301.3878 |  | 301.3878 | 5% | 15.0694 | 43 |  | 43 | 36% | 15.48 |  |  |  | 0 | 0% | 0 |  | 344.3878 | 0 |  | 344.3878 | 100% | 344.3878 | 344.3878 | 100% | 84.1176 | 84.1176 |  |  | 30.5494 | 0
14 | Job: 1460 3rd Winding Fixture-CHRZANOWSKI | 1460 | 53.0651 | 1460 | 63.05 | 37 | 9.9849 |  | 9.9849 |  | 9.9849 | 25% | 2.4962 |  |  | 0 |  | 0 |  |  |  | 0 | 0% | 0 |  | 9.9849 | 0 |  | 9.9849 | 25% | 2.4962 | 2.4962 | 25% | 0.60971 | 0.60971 |  |  | 2.4962 | 0
15 | Job: 1501 - Coil Structures Design- DAHLGREN | 1501 | 124.7677 | 1501 | 217.92 | 143 | 93.1523 |  | 93.1523 |  | 93.1523 | 20% | 18.6305 |  |  | 0 |  | 0 |  |  |  | 0 | 0% | 0 |  | 93.1523 | 0 |  | 93.1523 | 150% | 139.7285 | 139.7285 | 150% | 34.129 | 34.129 |  |  | 18.6305 | 0
15 | Job: 1550 - Coil Structures Procurement -DAHLGREN | 1550 | 0 | 1550 | 1132.27 |  | 465.27 |  | 474.47 |  | 474.47 | 5% | 23.7235 | 667 |  | 667 | 30% | 200.1 | 540 |  |  |  | 0% | 0 | 0 | 1141.47 | 0 | 0 | 1141.47 | 86.94% | 992.394 | 992.394 | 86.94% | 242.3949 | 242.3949 |  |  | 223.8235 | 540 | 0
16 | Job: 1601 - Coil Services Design-WILLIAMSON | 1601 | 2.79 | 1601 | 1148.33 | 3 | 172.54 |  | 170.74 |  | 170.74 | 10% | 17.074 | 956 |  | 956 | 20% | 191.2 | 50 | 17 |  | 17 | 0% | 0 | 0 | 1143.74 | 0 |  | 1143.74 | 50% | 571.87 | 571.87 | 50% | 139.6808 | 139.6808 |  |  | 208.274 | 50
17 | Job: 1701-Cryost&Base Sprt Strct Dsn-GETTLEFINGER | 1701 | 425.3337 | 1701 | 605.72 | 417 | 56.3863 |  | 56.3863 |  | 56.3863 | 0% | 0 | 124 |  | 124 | 25% | 31 | 50 |  |  | 0 | 0% | 0 |  | 180.3863 | 0 |  | 180.3863 | 100% | 180.3863 | 180.3863 | 100% | 44.0598 | 44.0598 |  |  | 31 | 50
17 | Job: 1751 - Cryostat Procurement | 1751 | 0 | 1751 | 377.29 | [5 empty] | 0 |  | 0 | 322 |  | 322 | 25% | 80.5 |  | 55 |  | 55 | 0% | 0 | 50 | 377 | 0 |  | 377 | 200% | 754 | 754 | 200% | 184.1665 | 184.1665 |  |  | 80.5 | 50
17 | Job: 1752 - Base Support Structure Procurement | 1752 | 0 | 1752 | 231.08 |  | 3.08 |  | 2.58 |  | 2.58 | 0% | 0 | 228 |  | 228 | 25% | 57 | 50 |  |  | 0 | 0% | 0 | 0 | 230.58 | 0 |  | 230.58 | 50% | 115.29 | 115.29 | 50% | 28.1599 | 28.1599 |  |  | 57 | 50
18 | Job: 1801-Field Period Assly -CHRZANOWSKI (ORNL) | 1801 | 64.69 | 1801 | 64.72 | 64 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0
18 | Job: 1802 - FP Assy Oversight&Support-VIOLA | 1802 | 785.9469 | 1802 | 1614.34 | 754 | 554.3931 |  | 552.2931 |  | 552.2931 | 0% | 0 | 274 |  | 274 | 25% | 68.5 | 50 |  |  | 0 | 0% | 0 |  | 826.2931 | 0 |  | 826.2931 | 40% | 330.5172 | 330.5172 | 40% | 80.7297 | 80.7297 |  |  | 68.5 | 50
18 | Job: 1803- FP Assy Toolg/Constructability-BROWN | 1803 | 871.5155 | 1803 | 1170.14 | 1007 | 298.6245 |  | 298.6245 |  | 298.6245 | 20% | 59.7249 |  |  | 0 |  | 0 |  |  |  | 0 | 0% | 0 |  | 298.6245 | 0 |  | 298.6245 | 50% | 149.3122 | 149.3122 | 50% | 36.4699 | 36.4699 |  |  | 59.7249 | 0
18 | Job: 1804-Metrology Hardware-RAFTOPOULOS | 1804 | 551.5359 | 1804 | 587.41 | 559 | 12.6741 |  | 12.6741 |  | 12.6741 | 0% | 0 | 11.7 | -11.7 | 0 | 0% | 0 |  | 11.5 | -11.5 | 0 | 0% | 0 | 0 | 35.8741 | -23.2 |  | 12.6741 | 0% | 0 | 0 | 0% | 0 | 0 |  |  | 0 | 0
18 | Job: 1805 -FP Assy H/W&Fixture | 1805 | 1.7489 | 1805 | 315.2 | 7 | 303.4511 |  | 303.0511 |  | 303.0511 | 20% | 60.6102 | 10 |  | 10 | 20% | 2 |  |  |  | 0 | 0% | 0 |  | 313.0511 | 0 |  | 313.0511 | 75% | 234.7883 | 234.7883 | 75% | 57.3477 | 57.3477 |  |  | 62.6102 | 0
18 | Job: 1806 - FP Assembly specs & dwgs | 1806 | 32.4512 | 1806 | 210.18 | 4 | 177.7288 |  | 177.7288 |  | 177.7288 | 20% | 35.5458 |  |  | 0 |  | 0 |  |  |  | 0 | 0% | 0 |  | 177.7288 | 0 |  | 177.7288 | 40% | 71.0915 | 71.0915 | 40% | 17.3643 | 17.3643 |  |  | 35.5458 | 0
18 | Job: 1810 - Field Period Assembly-VIOLA | 1810 | 235.4228 | 1810 | 2618 | 304 | 984.8772 |  | 973.8272 |  | 973.8272 | 25% | 243.4568 | 1397.7 |  | 1397.7 | 43.4% | 606.6018 | 550 |  |  | 0 | 0% | 0 | 700 | 2371.5272 | 0 | 250 | 2621.5272 | 137.7% | 3609.3187 | 3859.3187 | 162.7% | 881.5857 | 1131.5857 |  |  | 850.0586 | 1250 | 744
19 | Job: 1901 - Stellarator Core Mngtt&Integr-NELSON | 1901 | 2042.4259 | 1901 | 2621 | 2008 | 174.0741 |  | 172.2641 |  | 172.2641 | 5% | 8.6132 | 251.5 |  | 251.5 | 5% | 12.575 |  | 153 |  | 153 | 0% | 0 | 200 | 576.7641 | 0 |  | 576.7641 | 20% | 115.3528 | 115.3528 | 20% | 28.1752 | 28.1752 |  |  | 21.1882 | 200
2 | Job: 2001-VPS Gas& Cond Sys Oversight-BLANCHARD | 2001 | 62.8972 | 2001 | 62.89 | 63 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0
2 | Job: 2101 - Fueling Systems | 2101 | 0 | 2101 | 61.21 | [5 empty] | 0 |  | 0 | 61.2 |  | 61.2 | 10% | 6.12 |  |  |  | 0 | 0% | 0 |  | 61.2 | 0 |  | 61.2 | 30% | 18.36 | 18.36 | 30% | 4.4845 | 4.4845 |  |  | 6.12 | 0
2 | Job: 2201 - Vacuum Pumping Systems | 2201 | 0 | 2201 | 77.22 | [5 empty] | 0 |  | 0 | 77 |  | 77 | 10% | 7.7 |  |  |  | 0 | 0% | 0 | 50 | 77 | 0 |  | 77 | 30% | 23.1 | 23.1 | 30% | 5.6422 | 5.6422 |  |  | 7.7 | 50
2 | Job: 2501 - Neutral Beam Refurbishment-STEVENSON | 2501 | 285.0177 | 2501 | 285.01 | 285 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0
3 | Job: 3101 Magnetic Diagnostics | 3101 | 387.7871 | 3101 | 521.71 | 481 | 112.2229 |  | 112.2229 |  | 112.2229 | 15% | 16.8334 | 21.6 |  | 21.6 | 15% | 3.24 | 0 | 0.1 |  | 0.1 | 0% | 0 |  | 133.9229 | 0 |  | 133.9229 | 25% | 33.4807 | 33.4807 | 25% | 8.1778 | 8.1778 |  |  | 20.0734 | 0
3 | Job: 3601 - Edge and Divertor | 3601 | 0 | 3601 | 9.47 | [5 empty] | 0 |  | 0 | 9 |  | 9 | 10% | 0.9 |  |  |  | 0 | 0% | 0 | 25 | 9 | 0 |  | 9 | 50% | 4.5 | 4.5 | 50% | 1.0991 | 1.0991 |  |  | 0.9 | 25
3 | Job: 3801 - Electron Beam Mapping | 3801 | 0 | 3801 | 29.63 | [5 empty] | 0 |  | 0 | 29 |  | 29 | 30% | 8.7 |  |  |  | 0 | 0% | 0 | 100 | 29 | 0 |  | 29 | 50% | 14.5 | 14.5 | 50% | 3.5417 | 3.5417 |  |  | 8.7 | 100
3 | Job: 3901 - Diagnostics sys Integration-JOHNSON | 3901 | 350.3839 | 3901 | 375.26 | 327 | 24.8761 |  | 24.8761 |  | 24.8761 | 5% | 1.2438 |  |  | 0 |  | 0 |  |  |  | 0 | 0% | 0 | 50 | 24.8761 | 0 |  | 24.8761 | 50% | 12.438 | 12.438 | 50% | 3.038 | 3.038 |  |  | 1.2438 | 50
4 | Job: 4101 - AC Power-RAMAKRISHNAN | 4101 | 108.7335 | 4101 | 363.99 | 107 |  |  |  | -229 | -229 |  | 0 | 256 | -150 | 106 | 10% | 10.6 |  |  |  | 0 | 0% | 0 | 25 | 256 | -379 |  | -123 | 0% | 0 | 0 | 0% | 0 | 0 |  |  | 10.6 | 25
4 | Job: 4301 - DC Systems-RAMAKRISHNAN | 4301 | 382.5035 | 4301 | 729.11 | 370 |  |  |  |  | 0 |  | 0 | 347 |  | 347 | 10% | 34.7 |  |  |  | 0 | 0% | 0 | 50 | 347 | 0 |  | 347 | 25% | 86.75 | 86.75 | 25% | 21.1889 | 21.1889 |  |  | 34.7 | 50
4 | Job: 4401 - Control & Protection-RAMAKRISHNAN | 4401 | 82.727 | 4401 | 1012.6 | 81 |  |  |  |  | 0 |  | 0 | 756 | -74 | 682 | 10% | 68.2 |  | 173 |  | 173 | 0% | 0 | 150 | 929 | -74 |  | 855 | 25% | 213.75 | 213.75 | 25% | 52.209 | 52.209 |  |  | 68.2 | 150
4 | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 4501 | 148.2372 | 4501 | 1076.03 | 155 |  |  |  |  | 0 |  | 0 | 928 | -177 | 751 | 10% | 75.1 |  |  |  | 0 | 0% | 0 | 150 | 928 | -177 |  | 751 | 25% | 187.75 | 187.75 | 25% | 45.8584 | 45.8584 |  |  | 75.1 | 150
4 | Job: 4601 - FCPC Bldg Mods-RAMAKRISHNAN | 4601 | 1.3 | 4601 | 1.28 | 1.3 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0
5 | Job: 5101 - TCP/IP Infrastructure Systems | 5101 | 0 | 5101 | 150.84 | [5 empty] | 0 |  | 0 | 150 |  | 150 | 10% | 15 | 0 |  |  | 0 | 0% | 0 | 40 | 150 | 0 |  | 150 | 30% | 45 | 45 | 30% | 10.9914 | 10.9914 |  |  | 15 | 40
5 | Job: 5201 - I&C Systems | 5201 | 0 | 5201 | 138.77 | [5 empty] | 0 |  | 0 | 122 |  | 122 | 10% | 12.2 | 0 | 15 |  | 15 | 0% | 0 | 30 | 137 | 0 |  | 137 | 30% | 41.1 | 41.1 | 30% | 10.0388 | 10.0388 |  |  | 12.2 | 30
5 | Job: 5301 - Data Acquisition | 5301 | 0 | 5301 | 150.09 | [5 empty] | 0 |  | 0 | 150.1 |  | 150.1 | 10% | 15.01 | 0 |  |  | 0 | 0% | 0 | 50 | 150.1 | 0 |  | 150.1 | 30% | 45.03 | 45.03 | 30% | 10.9987 | 10.9987 |  |  | 15.01 | 50
5 | Job: 5401 - Facility Timing & | 5401 | 0 | 5401 | 82.15 | [5 empty] | 0 |  | 0 | 82 |  | 82 | 10% | 8.2 | 0 |  |  | 0 | 0% | 0 | 50 | 82 | 0 |  | 82 | 30% | 24.6 | 24.6 | 30% | 6.0086 | 6.0086 |  |  | 8.2 | 50
5 | Job: 5501 - Real Time Control System | 5501 | 0 | 5501 | 94 | [5 empty] | 0 |  | 0 | 85 |  | 85 | 10% | 8.5 | 0 | 8 |  | 8 | 0% | 0 | 20 | 93 | 0 |  | 93 | 30% | 27.9 | 27.9 | 30% | 6.8146 | 6.8146 |  |  | 8.5 | 20
5 | Job: 5601 - Central Safety Interlock Systems | 5601 | 0 | 5601 | 129.35 | [5 empty] | 0 |  | 0 | 129 |  | 129 | 10% | 12.9 | 0 |  |  | 0 | 0% | 0 | 50 | 129 | 0 |  | 129 | 30% | 38.7 | 38.7 | 30% | 9.4526 | 9.4526 |  |  | 12.9 | 50
5 | Job: 5801 -Central I&C Integr | 5801 | 45.6343 | 5801 | 58.2 | 33 |  |  |  |  | 0 |  | 0 | 12 |  | 12 | 10% | 1.2 |  |  |  | 0 | 0% | 0 | 50 | 12 | 0 |  | 12 | 30% | 3.6 | 3.6 | 30% | 0.87931 | 0.87931 |  |  | 1.2 | 50
6 | Job: 6101 - Water Systems | 6101 | 0 | 6101 | 13.81 | [5 empty] | 0 |  | 0 | 13 |  | 13 | 10% | 1.3 |  |  |  | 0 | 0% | 0 | 50 | 13 | 0 |  | 13 | 40% | 5.2 | 5.2 | 40% | 1.2701 | 1.2701 |  |  | 1.3 | 50
6 | Job: 6163 - Facility Systems Support FY04 | 6163 | 15 | 6163 | 15 | 15 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0
6 | Job: 6201 - Cryogenic Systems | 6201 | 0 | 6201 | 456.14 | [5 empty] | 0 |  | 0 | 456 |  | 456 | 10% | 45.6 |  |  |  | 0 | 0% | 0 | 25 | 456 | 0 |  | 456 | 50% | 228 | 228 | 50% | 55.6896 | 55.6896 |  |  | 45.6 | 25
6 | Job: 6301 - Utility Systems | 6301 | 0 | 6301 | 106.9 | [5 empty] | 0 |  | 0 | 107 |  | 107 | 250% | 267.5 | 0 |  |  | 0 | 0% | 0 | 25 | 107 | 0 | 50 | 157 | 300% | 471 | 521 | 486.9% | 115.043 | 165.043 |  |  | 267.5 | 25 | 314
6 | Job: 6501 - Facility Systems Integration-DUDEK | 6501 | 9.38 | 6501 | 9.38 | 9 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0
7 | Job: 7101 - Shield Wall Modif | 7101 | 32.64 | 7101 | 32.64 | 33 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0
7 | Job: 7301 - Platform Design & | 7301 | 76.0564 | 7301 | 113.89 | 76 |  |  |  |  | 0 |  | 0 | 39.3 |  | 39.3 | 20% | 7.86 |  |  |  | 0 | 0% | 0 | 50 | 39.3 | 0 |  | 39.3 | 50% | 19.65 | 19.65 | 50% | 4.7996 | 4.7996 |  |  | 7.86 | 50
7 | Job: 7401 - TC Prep & Mach Assy Planning-PERRY | 7401 | 833.6841 | 7401 | 1552 | 844 | 32.7159 |  | 31.9559 |  | 31.9559 | 5% | 1.5978 | 424.6 |  | 424.6 | 25% | 106.15 |  | 261 |  | 261 | 11.69% | 30.5236 | 100 | 717.5559 | 0 |  | 717.5559 | 25% | 179.389 | 179.389 | 25% | 43.8162 | 43.8162 |  |  | 138.2714 | 100
7 | Job: 7501 - Construction Support Crew | 7501 | 0 | 7501 | 589 | [5 empty] | 0 |  | 0 | 284.2 |  | 284.2 | 35% | 99.47 | 50 | 304 |  | 304 | 11.69% | 35.5524 | 100 | 588.2 | 0 |  | 588.2 | 25% | 147.05 | 147.05 | 25% | 35.9174 | 35.9174 |  |  | 135.0224 | 150
7 | Job: 7503 - Machine Assembly | 7503 | 0 | 7503 | 1306 | [5 empty] | 0 |  | 0 | 790 |  | 790 | 35% | 276.5 | 200 | 504 |  | 504 | 13.7% | 69.048 | 800 | 1294 | 0 |  | 1294 | 100% | 1294 | 1294 | 100% | 316.063 | 316.063 |  |  | 345.548 | 1000
7 | Job: 7601 - Tooling Design & Fabrication | 7601 | 0 | 7601 | 237.65 | [5 empty] | 0 |  | 0 | 180 |  | 180 | 35% | 63 | 50 | 56 |  | 56 | 13.7% | 7.672 | 50 | 236 | 0 |  | 236 | 50% | 118 | 118 | 50% | 28.8218 | 28.8218 |  |  | 70.672 | 100
8 | Job: 8101 - Project Management & Control-NEILSON | 8101 | 2663.5332 | 8101 | 3836 | 2639 | 534.9668 |  | 532.5368 | -70 | 462.5368 | 5% | 23.1268 | 553 | -101 | 452 | 10% | 45.2 |  | 84.5 |  | 84.5 | 0% | 0 | 50 | 1170.0368 | -171 |  | 999.0368 | 10% | 99.9037 | 99.9037 | 10% | 24.4017 | 24.4017 |  |  | 68.3268 | 50
8 | Job: 8102 - NCSX MIE Management ORNL-LYON | 8102 | 443.0212 | 8102 | 532.35 | 466 | 53.3288 |  | 52.6288 |  | 52.6288 | 5% | 2.6314 | 36 |  | 36 | 10% | 3.6 |  |  |  | 0 | 0% | 0 | 0 | 88.6288 | 0 |  | 88.6288 | 10% | 8.8629 | 8.8629 | 10% | 2.1648 | 2.1648 |  |  | 6.2314 | 0
8 | Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | 8202 | 2366.498 | 8202 | 3091 | 2382 | 417.502 |  | 414.592 | 151 | 565.592 | 20% | 113.1184 | 246 |  | 246 | 155% | 381.3 | 415 | 61 |  | 61 | 0% | 0 | 50 | 721.592 | 151 |  | 872.592 | 20% | 174.5184 | 174.5184 | 20% | 42.6266 | 42.6266 |  |  | 494.4184 | 465
8 | Job: 8203 - Design Integration-BROWN | 8203 | 883.5802 | 8203 | 1037 | 889 | 153.4198 |  | 152.6298 |  | 152.6298 | 10% | 15.263 |  |  | 0 |  | 0 | 200 |  |  | 0 | 0% | 0 | 50 | 152.6298 | 0 | 690 | 842.6298 | 40% | 337.0519 | 1027.0519 | 672.9% | 82.3258 | 772.3258 |  |  | 15.263 | 250 | 690
8 | Job: 8204 - Systems Analysis-BROOKS | 8204 | 1012.0586 | 8204 | 1216.11 | 1061 | 204.0514 |  | 204.0514 |  | 204.0514 | 10% | 20.4051 |  |  | 0 |  | 0 | 200 |  |  | 0 | 0% | 0 | 50 | 204.0514 | 0 |  | 204.0514 | 40% | 81.6206 | 81.6206 | 40% | 19.936 | 19.936 |  |  | 20.4051 | 250
8 | Job: 8205 - Dimensional Control Coordination | 8205 | 243.966 | 8205 | 301 | 242 | 26.034 |  | 25.584 |  | 25.584 | 10% | 2.5584 | 31 |  | 31 | 20% | 6.2 |  |  |  | 0 | 0% | 0 | 50 | 56.584 | 0 |  | 56.584 | 40% | 22.6336 | 22.6336 | 40% | 5.5283 | 5.5283 |  |  | 8.7584 | 50
8 | Job: 8401 - Project Physcis-ZARNSTORFF | 8401 | 324.6062 | 8401 | 324.61 | 324 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0
8 | Job: 8402 - Project Physics MIE ORNL-LYON | 8402 | 146.466 | 8402 | 146.44 | 146 |  |  |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 | 0
8 | Job: 8501 - Integrated Systems Testing | 8501 | 0 | 8501 | 814 | [5 empty] | 0 |  | 0 | 224 |  | 224 | 30% | 67.2 |  | 588 |  | 588 | 0% | 0 | 250 | 812 | 0 |  | 812 | 150% | 1218 | 1218 | 150% | 297.4998 | 297.4998 |  |  | 67.2 | 250
8 | Job: 8998 - Allocations | 8998 | 1260.2126 | 8998 | 1704 | 1257 | 276.0874 |  | 275.5874 | -391 | -115.4126 | 5% | -5.7706 | 167.7 |  | 167.7 | 10% | 16.77 |  |  |  | 0 | 0% | 0 | 10 | 443.2874 | -391 |  | 52.2874 | 25% | 13.0719 | 13.0719 | 25% | 3.1928 | 3.1928 |  |  | 10.9994 | 10
Contingency | Contingency |  |  |  | 6627 |  |  |  | 1828 |  |  |  |  | 3075 | [5 empty] | 132 | [10 empty] | 0 | 0 |  | 0 | 0 |  |  | 0
[5 empty] | 92401.16 | 60347.3
[7 empty] | 11944.2251 |  | 11920.8151 | 427 | 12347.8151 | 11.27% | 1391.7229 | 12856.6 | -415.7 | 12440.9 | 35.32% | 3454.8658 | 2705 | 2291.1 | -11.5 | 2279.6 | 6.614% | 142.796 | 3900.0225 | 27068.5151 | -0.2 | 990 | 28058.3151 | 58.36% | 16373.9652 | 17363.9652 | 64.15% | 3999.3847 | 4989.3847 |  |  | 4989.3847 | 6605.0225 | 2342 | 44883.7223
[9 empty] | 11920.8151 |  |  |  | 1818.7229 |  |  |  |  | 3039.1658 | [5 empty] | 131.296 |  | 27068.5151 |  |  |  |  | 3999.3847 | [6 empty] | 4989.1847
[9 empty] | 13748.8151 | [15 empty] | Free balance contingency = | 4989.3847 | 18.43% | [13 empty] | 92401.8998
[10 empty] | spent oct + nov = | 2889 | [13 empty] | Free balance plus add'l contingency = | 11594.4072 | 42.83% |  |  | TEC= | 104776.2803 | [9 empty] | 99006.9223
[10 empty] | spent 06+ bcwr +cont = | 16628.538 |  |  |  |  | 15895.7658 | [13 empty] | TEC= | 92421.6998
[10 empty] | funding = | 16771 |  |  |  |  | 15900 | [9 empty] | 4989
[10 empty] | over/under = | 142.462 |  |  |  |  | 4.2342 | [9 empty] | 0.38474
| 5410.9133 | [7 empty] | FY2007 |  |  |  |  | FY2008 | [5 empty] | FY2009 | [5 empty] | TOTAL
| 5410.9133 | [7 empty] | BCWS | ETC Increment | Total ETC | In-Budget Cont. % | In-Budget Contingency | BCWS | ETC Increment | Total ETC | In-Budget Cont. % | In-Budget Contingency | Add'l Contingency | BCWS | ETC Increment | Total ETC | In-Budget Cont. % | In-Budget Contingency | Add'l Contingency | BCWS | ETC Increment |  | Total ETC | In-Budget Cont. % | [7 empty] | In-Budget Contingency | Add'l Contingency
12 | Vacuum Vessel | [7 empty] | 116.7373 | 0 | 116.7373 | 15% | 17.5106 | 244 | 0 | 244 | 15% | 36.6 | 0 | 0 | 0 | 0 |  | 0 | 0.0225 | 360.7373 | 0 |  | 360.7373 | 15% | [7 empty] | 54.1106 | 0.0225 | 0 | 12
13 | Conventional Coils | [7 empty] | 1278.7078 | 0 | 1278.7078 | 11.66% | 149.1596 | 1097 | 0 | 1097 | 25.15% | 275.909 | 50 | 0 | 0 | 0 |  | 0 | 350 | 2375.7078 | 0 |  | 2375.7078 | 17.89% | [7 empty] | 425.0686 | 400 | 200 | 13
14 | Modular Coils | [7 empty] | 5410.9133 | 966 | 6376.9133 | 10.47% | 566.6663 | 507 | 98 | 605 | 42.79% | 216.96 | 250 | 0 | 0 | 0 |  | 0 | 0 | 5917.9133 | 1064 |  | 6981.9133 | 11.22% | [7 empty] | 783.6263 | 250 | 394 | 14
15 | Coil Structures | [7 empty] | 567.6223 | 0 | 567.6223 | 7.462% | 42.354 | 667 | 0 | 667 | 30% | 200.1 | 540 | 0 | 0 | 0 |  | 0 | 0 | 1234.6223 | 0 |  | 1234.6223 | 19.64% | [7 empty] | 242.454 | 540 | 0 | 15
16 | Coil Services | [7 empty] | 170.74 | 0 | 170.74 | 10% | 17.074 | 956 | 0 | 956 | 20% | 191.2 | 50 | 17 | 0 | 17 | 0% | 0 | 0 | 1143.74 | 0 |  | 1143.74 | 18.21% | [7 empty] | 208.274 | 50 | 0 | 16
17 | Cryostat & Base | [7 empty] | 58.9663 | 0 | 58.9663 | 0% | 0 | 674 | 0 | 674 | 25% | 168.5 | 100 | 55 | 0 | 55 | 0% | 0 | 50 | 787.9663 | 0 |  | 787.9663 | 21.38% | [7 empty] | 168.5 | 150 | 0 | 17
18 | Field Period Assembly | [7 empty] | 2318.1988 | 0 | 2318.1988 | 17.23% | 399.3377 | 1693.4 | -11.7 | 1681.7 | 39.98% | 677.1018 | 600 | 11.5 | -11.5 | 0 | 0% | 0 | 700 | 4023.0988 | -23.2 |  | 3999.8988 | 26.91% | [7 empty] | 1076.4395 | 1300 | 744 | 18
19 | Stellarator Core Mgt. / Integration | [7 empty] | 172.2641 | 0 | 172.2641 | 5% | 8.6132 | 251.5 | 0 | 251.5 | 5% | 12.575 | 0 | 153 | 0 | 153 | 0% | 0 | 200 | 576.7641 | 0 |  | 576.7641 | 3.674% | [7 empty] | 21.1882 | 200 | 0 | 19
2 | Fueling & Vacuum | [7 empty] | 0 | 0 | 0 |  | 0 | 138.2 | 0 | 138.2 | 10% | 13.82 | 0 | 0 | 0 | 0 |  | 0 | 50 | 138.2 | 0 |  | 138.2 | 10% | [7 empty] | 13.82 | 50 | 0 | 2
3 | Diagnsotics | [7 empty] | 137.099 | 0 | 137.099 | 13.19% | 18.0772 | 59.6 | 0 | 59.6 | 21.54% | 12.84 | 0 | 0.1 | 0 | 0.1 | 0% | 0 | 175 | 196.799 | 0 |  | 196.799 | 15.71% | [7 empty] | 30.9172 | 175 | 0 | 3
4 | Power Systems | [7 empty] | 0 | -229 | -229 |  | 0 | 2287 | -401 | 1886 | 8.247% | 188.6 | 0 | 173 | 0 | 173 | 0% | 0 | 375 | 2460 | -630 |  | 1830 | 10.31% | [7 empty] | 188.6 | 375 | 0 | 4
5 | Central I&C / Data Aq. | [7 empty] | 0 | 0 | 0 |  | 0 | 730.1 | 0 | 730.1 | 10% | 73.01 | 0 | 23 | 0 | 23 | 0% | 0 | 290 | 753.1 | 0 |  | 753.1 | 9.695% | [7 empty] | 73.01 | 290 | 0 | 5
6 | Facility Systems | [7 empty] | 0 | 0 | 0 |  | 0 | 576 | 0 | 576 | 54.58% | 314.4 | 0 | 0 | 0 | 0 |  | 0 | 100 | 576 | 0 |  | 576 | 54.58% | [7 empty] | 314.4 | 100 | 314 | 6
7 | Test Cell Prep / Machine Assembly | [7 empty] | 31.9559 | 0 | 31.9559 | 5% | 1.5978 | 1718.1 | 0 | 1718.1 | 32.19% | 552.98 | 300 | 1125 | 0 | 1125 | 12.69% | 142.796 | 1100 | 2875.0559 | 0 |  | 2875.0559 | 24.26% | [7 empty] | 697.3738 | 1400 | 0 | 7
8 | Project Mgt. & Integration | [7 empty] | 1657.6103 | -310 | 1347.6103 | 10.34% | 171.3326 | 1257.7 | -101 | 1156.7 | 41.37% | 520.27 | 815 | 733.5 | 0 | 733.5 | 0% | 0 | 510 | 3648.8103 | -411 |  | 3237.8103 | 21.36% | [7 empty] | 691.6026 | 1325 | 690 | 8
[9 empty] | 11920.8151 | 427 | 12347.8151 | 11.67% | 1391.7229 | 12856.6 | -415.7 | 12440.9 | 26.87% | 3454.8658 | 2705 | 2291.1 | -11.5 | 2279.6 | 6.233% | 142.796 | 3900.0225 | 27068.5151 | -0.2 |  | 27068.3151 | 18.43% | [7 empty] | 4989.3847 | 6605.0225 | 2342 | 41004.7223
| Contingency | [7 empty] | 1828 |  |  |  |  | 3075 | [5 empty] | 132 | [5 empty] | 5035
| Total | [7 empty] | 13748.8151 |  |  |  | 1391.7229 | 15931.6 |  |  |  | 3454.8658 | 2705 | 2423.1 |  |  |  | 142.796 | 3900.0225 | 32103.5151
13748.8151
| BCWS + Cont | [11 empty] | 13739.538 |  |  |  |  | 15895.7658 | [5 empty] | 2422.396 | [13 empty] | 32057.6998
| BA & c/o | [11 empty] | 16771 |  |  |  |  | 15900 | [5 empty] | 2269 | [13 empty] | 34940
High Confidence Contingency less Known Risks
12 | Vacuum Vessel | [7 empty] | 253.2 | -6.7458
13 | Conventional Coils | [7 empty] | 1601.2 | -42.6594 | [40 empty] | #REF!
14 | Modular Coils | [7 empty] | 6920.1 | -184.3663 | [40 empty] | #REF!
15 | Coil Structures | [7 empty] | 608.8 | -16.2197 | [40 empty] | #REF!
16 | Coil Services | [7 empty] | 171 | -4.5558 | [40 empty] | #REF!
17 | Cryostat & Base | [7 empty] | 59.2 | -1.5772 | [40 empty] | #REF!
18 | Field Period Assembly | [7 empty] | 2678.8 | -71.369 | [40 empty] | #REF!
19 | Stellarator Core Mgt. / Integration | [7 empty] | 208.3 | -5.5496 | [40 empty] | #REF!
2 | Fueling & Vacuum | [7 empty] | 0 | 0 | [40 empty] | #REF!
3 | Diagnsotics | [7 empty] | 142.9 | -3.8072 | [40 empty] | #REF!
4 | Power Systems | [7 empty] | 0 | 0 | [40 empty] | #REF!
5 | Central I&C / Data Aq. | [7 empty] | 0 | 0 | [40 empty] | #REF!
6 | Facility Systems | [7 empty] | 0 | 0 | [40 empty] | #REF!
7 | Test Cell Prep / Machine Assembly | [7 empty] | 34.5 | -0.91915 | [40 empty] | #REF!
8 | Project Mgt. & Integration | [7 empty] | 1998.3 | -53.239 | [40 empty] | #REF!
[10 empty] | -391.008 | [40 empty] | #REF!
#REF!
#REF!
60269
[9 empty] | FY2007 |  |  |  |  | FY2008 | [5 empty] | FY2009 | [5 empty] | TOTAL
[9 empty] | BCWR (from 12/1/06) | ETC Increment | Total ETC | In-Budget Cont. % | In-Budget Contingency/Risk | BCWR | ETC Increment | Total ETC | In-Budget Cont. % | In-Budget Contingency/Risk | Add'l Contingency | BCWR | ETC Increment | Total ETC | In-Budget Cont. % | In-Budget Contingency/Risk | Add'l Contingency | BCWR (from 12/1/06) | ETC Increment |  | Total ETC | In-Budget Cont. % | [7 empty] | In-Budget Contingency | Add'l Contingency | Total Contingency | Total Conting. % | Known Risks |  |  |  |  | 27068.3151 | 990 | 3.657% | 4.0597 | #REF! | #REF! | #REF!
Activities (Job or WBS numbers)
High Risk | [8 empty] | 5042.6468 | 619 | 5661.6468 | 9.174% | 519.4051 | 3918.5 | 86.3 | 4004.8 | 36.13% | 1447.0418 | 1150 | 1136.5 | -11.5 | 1125 | 12.69% | 142.796 | 1800 | 10097.6468 | 693.8 |  | 10791.4468 | 19.55% | [7 empty] | 2109.2429 | 2950 | 5059.2429 | 46.88% | 1138 | [5 empty] | 60269
| Mod. Coil Winding Ops (1408, 1451, 1459, 1460) | [7 empty] | 3168.8453 | 619 | 3787.8453 | 5.643% | 213.7403 | 507 | 98 | 605 | 35.86% | 216.96 | 250 | 0 | 0 | 0 |  | 0 | 0 | 3675.8453 | 717 |  | 4392.8453 | 9.805% | [7 empty] | 430.7003 | 250 | 680.7003 | 15.5% | 394 | [5 empty] | 75
| Field Period Assy Ops. (1810, 1802, 1805, 1804) | [7 empty] | 1841.8455 | 0 | 1841.8455 | 16.51% | 304.067 | 1693.4 | -11.7 | 1681.7 | 40.26% | 677.1018 | 600 | 11.5 | -11.5 | 0 |  | 0 | 700 | 3546.7455 | -23.2 |  | 3523.5455 | 27.85% | [7 empty] | 981.1688 | 1300 | 2281.1688 | 64.74% | 744 | [5 empty] | 88402.3151 |  |  | #REF!
| Machine Assy. (7) | [7 empty] | 31.9559 | 0 | 31.9559 | 5% | 1.5978 | 1718.1 | 0 | 1718.1 | 32.19% | 552.98 | 300 | 1125 | 0 | 1125 | 12.69% | 142.796 | 1100 | 2875.0559 | 0 |  | 2875.0559 | 24.26% | [7 empty] | 697.3738 | 1400 | 2097.3738 | 72.95% | 0
Medium Risk | [8 empty] | 3825.0662 | 498 | 4323.0662 | 15.9% | 687.153 | 4143.5 | 0 | 4143.5 | 31.73% | 1314.884 | 1555 | 874 | 0 | 874 | 0% | 0 | 1000.0225 | 8842.5662 | 498 |  | 9340.5662 | 21.43% | [7 empty] | 2002.037 | 2555.0225 | 4557.0595 | 48.79% | 890
| VV System Procurements (1204) | [7 empty] | 116.7373 | 0 | 116.7373 | 15% | 17.5106 | 244 | 0 | 244 | 15% | 36.6 | 0 | 0 | 0 | 0 |  | 0 | 0.0225 | 360.7373 | 0 |  | 360.7373 | 15% | [7 empty] | 54.1106 | 0.0225 | 54.1331 | 15.01% | 0
| PF & Trim Coils (1302, 1303, 1352, 1354, 1353, 1355) | [7 empty] | 398.504 | 0 | 398.504 | 15.26% | 60.812 | 850 | 0 | 850 | 29.55% | 251.209 | 50 | 0 | 0 | 0 |  | 0 | 300 | 1248.504 | 0 |  | 1248.504 | 24.99% | [7 empty] | 312.021 | 350 | 662.021 | 53.03% | 200
| Mod. Coil Design & Hdwe. (1416, 1421, 1431) | [7 empty] | 1067.0216 | 347 | 1414.0216 | 20.8% | 294.1737 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1067.0216 | 347 |  | 1414.0216 | 20.8% | [7 empty] | 294.1737 | 0 | 294.1737 | 20.8% | 0
| Field Period Assy. Design (1803, 1806) | [7 empty] | 476.3533 | 0 | 476.3533 | 20% | 95.2707 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 476.3533 | 0 |  | 476.3533 | 20% | [7 empty] | 95.2707 | 0 | 95.2707 | 20% | 0
| Coil Structures (15) | [7 empty] | 567.6223 | 0 | 567.6223 | 7.462% | 42.354 | 667 | 0 | 667 | 30% | 200.1 | 540 | 0 | 0 | 0 |  | 0 | 0 | 1234.6223 | 0 |  | 1234.6223 | 19.64% | [7 empty] | 242.454 | 540 | 782.454 | 63.38% | 0
| Coil Services (16) | [7 empty] | 170.74 | 0 | 170.74 | 10% | 17.074 | 956 | 0 | 956 | 20% | 191.2 | 50 | 17 | 0 | 17 | 0% | 0 | 0 | 1143.74 | 0 |  | 1143.74 | 18.21% | [7 empty] | 208.274 | 50 | 258.274 | 22.58% | 0
| Cryostat & Base (17) | [7 empty] | 58.9663 | 0 | 58.9663 | 0% | 0 | 674 | 0 | 674 | 25% | 168.5 | 100 | 55 | 0 | 55 | 0% | 0 | 50 | 787.9663 | 0 |  | 787.9663 | 21.38% | [7 empty] | 168.5 | 150 | 318.5 | 40.42% | 0
| Stellarator Core Design Integration | [7 empty] | 172.2641 | 0 | 172.2641 | 5% | 8.6132 | 251.5 | 0 | 251.5 | 5% | 12.575 | 0 | 153 | 0 | 153 | 0% | 0 | 200 | 576.7641 | 0 |  | 576.7641 | 3.674% | [7 empty] | 21.1882 | 200 | 221.1882 | 38.35% | 0
| System Engineering (82) | [7 empty] | 796.8573 | 151 | 947.8573 | 15.97% | 151.3449 | 277 | 0 | 277 | 139.9% | 387.5 | 815 | 61 | 0 | 61 | 0% | 0 | 200 | 1134.8573 | 151 |  | 1285.8573 | 41.91% | [7 empty] | 538.8449 | 1015 | 1553.8449 | 120.8% | 690
| Startup (85) | [7 empty] | 0 | 0 | 0 |  | 0 | 224 | 0 | 224 | 30% | 67.2 | 0 | 588 | 0 | 588 | 0% | 0 | 250 | 812 | 0 |  | 812 | 8.276% | [7 empty] | 67.2 | 250 | 317.2 | 39.06% | 0
Low Risk | [8 empty] | 3053.1022 | -690 | 2363.1022 | 7.836% | 185.1648 | 4794.6 | -502 | 4292.6 | 16.14% | 692.94 | 0 | 280.6 | 0 | 280.6 | 0% | 0 | 1100 | 8128.3022 | -1192 |  | 6936.3022 | 12.66% | [7 empty] | 878.1048 | 1100 | 1978.1048 | 28.52% | 314
| TF Fabrication (1351, 1361) | [7 empty] | 880.2038 | 0 | 880.2038 | 10.04% | 88.3476 | 247 | 0 | 247 | 10% | 24.7 | 0 | 0 | 0 | 0 |  | 0 | 50 | 1127.2038 | 0 |  | 1127.2038 | 10.03% | [7 empty] | 113.0476 | 50 | 163.0476 | 14.46% | 0
| MCWF Fabrication (1411) | [7 empty] | 1175.0464 | 0 | 1175.0464 | 5% | 58.7523 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1175.0464 | 0 |  | 1175.0464 | 5% | [7 empty] | 58.7523 | 0 | 58.7523 | 5% | 0
| Fueling & Vacuum (2) | [7 empty] | 0 | 0 | 0 |  | 0 | 138.2 | 0 | 138.2 | 10% | 13.82 | 0 | 0 | 0 | 0 |  | 0 | 50 | 138.2 | 0 |  | 138.2 | 10% | [7 empty] | 13.82 | 50 | 63.82 | 46.18% | 0
| Diagnostics (3) | [7 empty] | 137.099 | 0 | 137.099 | 13.19% | 18.0772 | 59.6 | 0 | 59.6 | 21.54% | 12.84 | 0 | 0.1 | 0 | 0.1 | 0% | 0 | 175 | 196.799 | 0 |  | 196.799 | 15.71% | [7 empty] | 30.9172 | 175 | 205.9172 | 104.6% | 0
| Power Systems (4) | [7 empty] | 0 | -229 | -229 | 0% | 0 | 2287 | -401 | 1886 | 10% | 188.6 | 0 | 173 | 0 | 173 | 0% | 0 | 375 | 2460 | -630 |  | 1830 | 10.31% | [7 empty] | 188.6 | 375 | 563.6 | 30.8% | 0
| Central I&C / Data Aq. (5) | [7 empty] | 0 | 0 | 0 |  | 0 | 730.1 | 0 | 730.1 | 10% | 73.01 | 0 | 23 | 0 | 23 | 0% | 0 | 290 | 753.1 | 0 |  | 753.1 | 9.695% | [7 empty] | 73.01 | 290 | 363.01 | 48.2% | 0
| Facility Systems (6) | [7 empty] | 0 | 0 | 0 |  | 0 | 576 | 0 | 576 | 54.58% | 314.4 | 0 | 0 | 0 | 0 |  | 0 | 100 | 576 | 0 |  | 576 | 54.58% | [7 empty] | 314.4 | 100 | 414.4 | 71.94% | 314
| Management (81) | [7 empty] | 860.7531 | -461 | 399.7531 | 5% | 19.9877 | 756.7 | -101 | 655.7 | 10% | 65.57 | 0 | 84.5 | 0 | 84.5 | 0% | 0 | 60 | 1701.9531 | -562 |  | 1139.9531 | 7.505% | [7 empty] | 85.5577 | 60 | 145.5577 | 12.77% | 0
Total Work | [8 empty] | 11920.8151 | 427 | 12347.8151 | 11.27% | 1391.7229 | 12856.6 | -415.7 | 12440.9 | 27.77% | 3454.8658 | 2705 | 2291.1 | -11.5 | 2279.6 | 6.264% | 142.796 | 3900.0225 | 27068.5151 | -0.2 |  | 27068.3151 | 18.43% | [7 empty] | 4989.3847 | 6605.0225 | 11594.4072 | 42.83% | 2342
Contingency | [8 empty] | 1828 |  | 0 |  |  | 3075 |  | 0 |  | 0 |  | 132 |  | 0 |  | 0
[9 empty] | FY2007 |  |  |  |  | FY2008 | [5 empty] | FY2009 | [5 empty] | TOTAL
[9 empty] | BCWR (from 12/1/06) | ETC Increment | Total ETC | In-Budget Cont. % | In-Budget Contingency/Risk | BCWR | ETC Increment | Total ETC | In-Budget Cont. % | In-Budget Contingency/Risk | Add'l Contingency | BCWR | ETC Increment | Total ETC | In-Budget Cont. % | In-Budget Contingency/Risk | Add'l Contingency | BCWR (from 12/1/06) | ETC Increment |  | Total ETC | In-Budget Cont. % | [7 empty] | In-Budget Contingency | Add'l Contingency | Total Contingency | Total Conting. % | Known Risks
Activities (Job or WBS numbers)
High Risk | [8 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0% | [7 empty] | 0 | 0 | 0 | 0% | 0
| Mod. Coil Winding Ops (1408, 1451, 1459, 1460) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 |  | 0 | 0% | [7 empty] | 0 | 0 | 0 | 0% | 0
| Field Period Assy Ops. (1810, 1802, 1805, 1804) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 |  | 0 | 0% | [7 empty] | 0 | 0 | 0 | 0% | 0
| Machine Assy. (7) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0% | [7 empty] | 0 | 0 | 0 | 0% | 0
Medium Risk | [8 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0% | [7 empty] | 0 | 0 | 0 | 0% | 0
| VV System Procurements (1204) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 |  | 0 | 0% | [7 empty] | 0 | 0 | 0 | 0% | 0
| PF & Trim Coils (1302, 1303, 1352, 1354, 1353, 1355) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 |  | 0 | 0% | [7 empty] | 0 | 0 | 0 | 0% | 0
| Mod. Coil Design & Hdwe. (1416, 1421, 1431) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 |  | 0 | 0% | [7 empty] | 0 | 0 | 0 | 0% | 0
| Field Period Assy. Design (1803, 1806) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 |  | 0 | 0% | [7 empty] | 0 | 0 | 0 | 0% | 0
| Coil Structures (15) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 |  | 0 | 0% | [7 empty] | 0 | 0 | 0 | 0% | 0
| Coil Services (16) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0% | [7 empty] | 0 | 0 | 0 | 0% | 0
| Cryostat & Base (17) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0% | [7 empty] | 0 | 0 | 0 | 0% | 0
| Stellarator Core Design Integration | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0% | [7 empty] | 0 | 0 | 0 | 0% | 0
| System Engineering (82) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0% | [7 empty] | 0 | 0 | 0 | 0% | 0
| Startup (85) | [7 empty] | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0% | [7 empty] | 0 | 0 | 0 | 0% | 0
Low Risk | [8 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0% | [7 empty] | 0 | 0 | 0 | 0% | 0
| TF Fabrication (1351, 1361) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 |  | 0 | 0% | [7 empty] | 0 | 0 | 0 | 0% | 0
| MCWF Fabrication (1411) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 |  | 0 | 0% | [7 empty] | 0 | 0 | 0 | 0% | 0
| Fueling & Vacuum (2) | [7 empty] | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 |  | 0 | 0% | [7 empty] | 0 | 0 | 0 | 0% | 0
| Diagnostics (3) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0% | [7 empty] | 0 | 0 | 0 | 0% | 0
| Power Systems (4) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0% | [7 empty] | 0 | 0 | 0 | 0% | 0
| Central I&C / Data Aq. (5) | [7 empty] | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0% | [7 empty] | 0 | 0 | 0 | 0% | 0
| Facility Systems (6) | [7 empty] | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 |  | 0 | 0% | [7 empty] | 0 | 0 | 0 | 0% | 0
| Management (81) | [7 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0% | [7 empty] | 0 | 0 | 0 | 0% | 0
Total Work | [8 empty] | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0% | [7 empty] | 0 | 0 | 0 | 0% | 0

## Mpwr smry
WBS1 | ACT ID | O | O | O | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S
1 - 1 - Stellarator Core Systems | EA//EM | 4.7 | 4.7 | 4.7 | 4.7 | 4.3 | 5.2 | 6.4 | 6.3 | 6.6 | 3.4 | 3.4 | 2.5 | 2.6 | 2.8 | 2.3 | 2.9 | 3.2 | 1.8 | 2 | 1 | 0.9 | 0.9 | 0.6 | 0.6 | 0.3 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0
7 - 7 - Test Cell Preparation and Machine Assy | EA//EM | [22 empty] | 0.8 | 0.9 | 1.1 | 0.2 | 0.5 | 0.3
8 - 8 - Project Oversight and Support | EA//EM | 2.6 | 2.6 | 2.6 | 2.6 | 2.4 | 1.9 | 2.6 | 2.4 | 2.6 | 2.5 | 2.8 | 2.7 | 2.7 | 3 | 2.3 | 0.7 | 0.7 | 0.5 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.6 | 0.3 | 0.2 | 0.2 | 0.3 | 0.2 | 0.3 | 0.3 | 0.2
5 - 5 - Central I&C Systems | EC//EM | [15 empty] | 1.3 | 1.1 | 0.8 | 1 | 0.8 | 0.8 | 1 | 1.4 | 1.4 | 1.4 | 1.3 | 1.1 | 0.4
8 - 8 - Project Oversight and Support | EC//EM | [28 empty] | 0.1 | 0.2 | 0.2 | 0.2 | 0.1
5 - 5 - Central I&C Systems | EC//TB | [20 empty] | 0.2 | 0.5 | 0.8 | 0.8 | 0.9 | 0.8 | 0.8 | 0.4
8 - 8 - Project Oversight and Support | EE//AM | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
4 - 4 - Electrical Power Systems | EE//EM | [15 empty] | 5.3 | 3.9 | 1.7 | 2.5 | 1.6 | 1.6 | 1.8 | 2.6 | 2.3 | 2.3 | 1.9 | 1.3 | 0.4 | 0.3 | 0.2 | 0.2 | 0.1 | 0.1
8 - 8 - Project Oversight and Support | EE//EM | [28 empty] | 0.3 | 0.8 | 1 | 0.9 | 0.4
1 - 1 - Stellarator Core Systems | EE//SM | 2.4 | 2.4 | 2.4 | 2.4 | 1.1 | 0.6 | 1.5 | 1.3 | 0.9 | 1.4 | 1.1 | 0.1 | 0.8 | 0.7 | 0 | 0.6 |  |  | 1.1 | 0.4 | 0.2
4 - 4 - Electrical Power Systems | EE//SM | [15 empty] | 0.2 | 0.1 | 0.1 | 0.5 | 1.2 | 1.7 | 2 | 2.4 | 1.9 | 1.6 | 1.3 | 0.9 | 0.9 | 0.5 | 0.3 | 0.3 | 0.2 | 0.1
7 - 7 - Test Cell Preparation and Machine Assy | EE//SM | [9 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0
4 - 4 - Electrical Power Systems | EE//TB | [15 empty] | 0.6 | 0.4 | 0.3 | 0.7 | 2 | 3.9 | 4.5 | 4 | 3 | 2 | 2 | 1.2 | 0.5 | 0.3 | 0.2 | 0.2 | 0.2 | 0.1
5 - 5 - Central I&C Systems | EE//TB | [18 empty] | 0.4 | 0.6 | 0.6 | 0.6 | 0.6 | 0.5
8 - 8 - Project Oversight and Support | EE//TB | [28 empty] | 0.1 | 0.4 | 0.5 | 0.5 | 0.2
1 - 1 - Stellarator Core Systems | EM//EM | 0.9 | 0.9 | 0.9 | 0.9 | 2 | 1.8 | 0.9 | 0.8 | 0.9 | 0.8 | 1.5 | 1.5 | 0.9 | 0.9 | 0.8 | 1 | 1.5 | 1.2 | 1.7 | 1 | 0.9 | 1.1 | 1.1 | 1.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
2 - 2 - Plasma Heating Fueling & Vac Systems | EM//EM | [16 empty] | 1 | 0.3 | 0.4 | 0.1 | 0 | 0
3 - 3 - Diagnostics | EM//EM | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.1 | 0.3 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 - 6 - Facility Systems | EM//EM | [15 empty] | 1.3 | 1 | 0.6 | 0.2 | 0.3 | 0.4 | 0.3 | 0.3 | 0.1
7 - 7 - Test Cell Preparation and Machine Assy | EM//EM | [9 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.1 | 0.8 | 0.8 | 1.5 | 0.9 | 1
8 - 8 - Project Oversight and Support | EM//EM | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.3 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.3 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.6 | 1 | 0.8 | 0.3
1 - 1 - Stellarator Core Systems | EM//SM | 0.7 | 0.7 | 0.7 | 0.7 | 0.6 | 0.7 | 0.7 | 0.6 | 0.8 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.6 | 1.2 | 0.9 | 0.2 | 0.2 | 0.3 | 0.3 | 0.2 | 0.1 | 0.1 | 0 | 0 | 0 | 0
2 - 2 - Plasma Heating Fueling & Vac Systems | EM//SM | [16 empty] | 0.7 | 0.1 | 0.3 | 0.1 | 0.2 | 0.2
3 - 3 - Diagnostics | EM//SM | 0.2 | 0.2 | 0.2 | 0.2 | [9 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0.1 | 0.1 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0
6 - 6 - Facility Systems | EM//SM | [19 empty] | 0 | 0.1 | 0.1 | 0.1
7 - 7 - Test Cell Preparation and Machine Assy | EM//SM | [9 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0.1 | 1 | 0.9 | 0.9 | 1 | 3.4 | 3.9 | 4.2 | 3.2 | 3.8 | 5.7 | 2.7 | 2.6 | 2.4 | 0.9 | 1
8 - 8 - Project Oversight and Support | EM//SM | [22 empty] | 0.2 | 1.1 | 1.1 | 1.1 | 1.1 | 1.2 | 1.4 | 2.2 | 1.8 | 1.6 | 0.6
1 - 1 - Stellarator Core Systems | EM//TB | 25.5 | 25.5 | 25.5 | 25.5 | 21.4 | 18.6 | 26.9 | 23.4 | 30.8 | 23.8 | 26.2 | 26.9 | 21.4 | 32.1 | 26 | 24.4 | 22.1 | 14.2 | 17.7 | 17.9 | 9.6 | 12.8 | 9.3 | 9.9 | 3.8 | 3.3 | 3.3 | 1.3
2 - 2 - Plasma Heating Fueling & Vac Systems | EM//TB | [19 empty] | 0.4 | 0.6 | 0.2
3 - 3 - Diagnostics | EM//TB | 2.3 | 2.3 | 2.3 | 2.3 | 0.1 | 0 | 0.7 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 - 5 - Central I&C Systems | EM//TB | [21 empty] | 0.5 | 1 | 1 | 1.1 | 1 | 0.6
6 - 6 - Facility Systems | EM//TB | [18 empty] | 1.6 | 2.1 | 2.6 | 2.5 | 2.4 | 0.7
7 - 7 - Test Cell Preparation and Machine Assy | EM//TB | [9 empty] | 0.1 | 0.1 | 0.1 |  |  |  | 0.1 | 0.1 | 1.3 | 0.7 | 0.1 | 0.1 | 0.1 | 8.8 | 10.3 | 11.8 | 9.5 | 14.5 | 17.3 | 6.2 | 5.9 | 7.4 | 4.3 | 1.7
8 - 8 - Project Oversight and Support | EM//TB | [28 empty] | 0.1 | 0.2 | 0.2 | 0.2 | 0.1
1 - 1 - Stellarator Core Systems | ORNLEM | 4.6 | 4.6 | 4.6 | 4.6 | 8.3 | 4.7 | 5.7 | 3.7 | 5.3 | 3.4 | 3.1 | 2.9 | 2.9 | 3.2 | 2.5 | 3.2 | 2.9 | 1.9 | 2.2 | 2 | 1.7 | 1.8 | 1.7 | 1.7 | 1.2 | 1 | 0.8 | 0.9 | 0.6 | 0.6 | 0.7 | 0.7 | 0.7 | 0.3
8 - 8 - Project Oversight and Support | ORNLEM | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.2 | 0.2 | 0.2 | 0.1
|  | O | O | O | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S
| Techs (incl baseline Contingency) | 31.7 | 31.7 | 31.7 | 31.7 | 24 | 22.5 | 33.4 | 28.7 | 36.2 | 29.7 | 32 | 31.5 | 26.6 | 37.6 | 30.1 | 34.8 | 31 | 18.8 | 27.9 | 29.5 | 24.4 | 28.8 | 36.6 | 36.7 | 30.1 | 25.7 | 29.6 | 27.6 | 11.5 | 12 | 13.1 | 8.2 | 3.8 | 0 | 0
| Engrs (incl baseline contingency) | 13.7 | 13.7 | 13.7 | 13.7 | 17.8 | 14.1 | 16.5 | 14 | 16 | 10.7 | 11.3 | 10.1 | 9.6 | 10.4 | 8.3 | 17.8 | 17.1 | 10.2 | 13.6 | 10.4 | 9.8 | 10.5 | 12.2 | 12.7 | 11.2 | 9.4 | 8.4 | 4.8 | 3.7 | 4.6 | 5.1 | 3.8 | 2.9 | 0.6 | 0.2
| Add'l contingency Techs | 31.7 | 31.7 | 31.7 | 31.7 | 24 | 22.5 | 33.4 | 28.7 | 36.2 | 29.7 | 32 | 31.5 | 26.6 | 37.6 | 30.1 | 34.8 | 35 | 23.8 | 33.9 | 35.5 | 30.4 | 34.8 | 42.6 | 43.7 | 38.1 | 38.7 | 44.6 | 47.6 | 40.5 | 44 | 47.1 | 40.2 | 31.8 | 28 | 25 | 23 | 15
C - Contingency | EM//EM | O: 1.8; N: 1.6; D: 1.2; J: 1.8; F: 1.7; M: 1.7; A: 1.8; M: 1.7; J: 1.7; J: 1.8; A: 1.7; S: 1.7
C - Contingency | EM//TB | 0.6 | 0.6 | 0.6 | 0.6 | 0.8 | 2.6 | 3.6 | 3.3 | 3.6 | 3.4 | 3.6 | 3.4 | 3.4 | 3.7 | 3.1 | 7.4 | 6.4 | 2.4 | 3.5 | 3.4 | 3.4 | 3.5 | 3.4 | 3.4 | 3.5 | 3.4 | 3.4 | 0.3 | 0.2 | 0.2 | 0.3 | 0.3
| add'l contingency techs | O: 0; N: 4; D: 5; J: 6; F: 6; M: 6; A: 6; M: 6; J: 7; J: 8; A: 13; S: 15; O: 20; N: 29; D: 32; J: 34; F: 32; M: 28; A: 28; M: 25; J: 23; J: 15
0
[17 empty] | 12.1 | 12.1 | 12.1 | 12.1 | 12.1 | 12.1 | 12.1 | 12.1 | 12.1 | 12.1 | 12.1 | 12.1 | 12.1 | 12.1 | 12.1 | 12.1 | 12.1 | 12.1 | 12.1 | 12.1 | 12.1 | 12.1
[17 empty] | 0 | 48.4 | 60.5 | 72.6 | 72.6 | 72.6 | 72.6 | 72.6 | 84.7 | 96.8 | 157.3 | 181.5 | 242 | 350.9 | 387.2 | 411.4 | 387.2 | 338.8 | 338.8 | 302.5 | 278.3 | 181.5
[28 empty] | 992.2 | 3218.6
[28 empty] | 0.9 | 3.3

## Milestones may06
NCSX MILESTONES
|  |  | CD-2 | CD-2
|  |  | Baseline |  | Baseline | float | Forecast | Actual | master schedule | Milestone float |  |  | ECP-53 Baseline | Forecast | early finish | float (milestone date - EF)
[11 empty] | Level II | Begin Field Period Assembly | 2007-07-01 | 2007-05-01
[11 empty] | Level II | Last MCWF Delivered | 2007-09-01 | 2007-06-01
M-0120 |  | CD-4 | 2008-05-30 | 14.2333 | 2009-07-31 | 1900-01-05 18:24 | 2009-01-09 |  | 2009-02-27 | 5.1333 | Level II | PF Coils Awarded | 2008-03-30 | 2008-12-29 | 2008-08-01 | 5 | 5
1201-500 | Level II | Vacuum Vessel & Modular Coil Prel Dsn Rvw | 2003-10-07 | 0 | 2003-10-07 |  |  | 2003-10-07 |  |  | Level II | All TF Coils Delivered | 2008-08-15 | 2008-08-15 | 2007-12-17 | 6 | 5
1403-08 |  | Performance Baseline Review | 2003-11-18 | 0 | 2003-11-18 |  |  | 2003-11-18 |  |  | Level II | Last Field Period Assembled | 2008-11-15 | 2010-04-23 | 2009-09-25 | 7 | 7
1203-341 |  | Conduct VVSA FDR | 2004-07-19 | 0 | 2004-07-19 |  |  | 2004-05-19 |  |  | Level II | Begin Vac Vsl Pumpdown | 2009-02-11 | 2010-12-11 | 2010-04-15 | 8 | 8
1403-51 |  | Mod Coil Winding Form Final Design Review | 2004-07-19 | 0 | 2004-07-19 |  |  | 2004-05-19 |  |  | Level II | Begin Cryostat Installation | 2009-04-07 | 2011-04-08 | 2010-07-27 | 8.5 | 8.5
1408-143.1 |  | Award MC Conductor Contract |  |  | 2004-12-19 |  |  | 2004-10-15 |  |  | Level II | Operational Readiness | 2009-06-01 | 2011-05-14 | 2010-08-17 | 9 | 9
121-6-9 |  | Award VV Production Vendor | 2004-12-01 | -2 | 2004-10-15 |  |  | 2004-09-15 |  |  | Level II | Begin Start-up Testing | 2009-06-16 | 2011-05-22 | 2010-08-25 | 9 | 9
C-081 |  | Award MCWF Mfg Contract | 2004-11-01 | -1 | 2004-10-01 |  |  | 2004-09-15 |  |  | Level I | CD-4 | 2009-07-31 | 2011-09-26 | 2010-11-30 | 10 | 10
C-121.1 |  | First MCWF Delivered | 2005-03-01 | 4 | 2005-07-15 | 1284.9333 |  | 2005-09-30
131-035 |  | Begin TF Coil fabrication activities | 2005-04-01 | 3 | 2005-09-30 | 1287.5 |  | 2005-06-30
P1-021.1 |  | Complete First Mod Coil Fabrication | 2005-08-31 | 6 | 2006-03-29 | 2006-04-15 |  | 2006-03-01 | 2006-03-29 | 0
121-038.1 |  | Vacuum Vessel Sectors Delivered | 2006-02-01 | 0 | 2006-09-15 | 1299.1667 |  | 2006-09-01 | 2006-03-21 | 1299.1667
C-501B1 |  | Last MCWF Delivered | 2006-08-01 | 4 | 2007-09-01 | 3.1333 | 2007-05-30 |  | 2007-02-28 | 3.1333
141-036 |  | PF Coils Awarded | 2006-06-01 | 7 | 2008-03-30 | 7.5667 | 2007-08-16 |  | 2007-10-27 | 7.5667
S3P1-101 |  | Begin Assembly of First Field Period | 2006-09-01 | 6 | 2007-07-01 | -0.33333 | 2007-07-11 |  | 2007-01-12 | -0.33333
1351-195x |  | All TF Coils Delivered | 2007-01-01 | 4 | 2008-08-15 | 10.9667 | 2007-09-21 |  | 2007-11-19 | 10.9667
S4P3-115 |  | Last Field Period Assembled | 2007-06-01 | 3 | 2008-11-15 | 4.1333 | 2008-07-14 |  | 2008-06-12 | 4.1333
7503-250 |  | Begin Vac Vsl Pumpdown | 2007-09-01 | 2 | 2009-02-11 | 4.2667 | 2008-10-06 |  | 2008-09-11 | 4.2667
7503-330 |  | Begin Cryostat Installation | 2007-11-01 | 2 | 2009-04-07 | 4.8 | 2008-11-14 |  | 2008-11-07 | 4.8
730.1250 |  | Operational Readiness | 2007-11-01 | 4 | 2009-06-01 | 3.8667 | 2009-02-05 |  | 2008-12-28 | 3.8667
920.004 |  | Begin Start-up Testing | 2008-03-31 | 0 | 2009-06-16 | 4.3667 | 2009-02-05 |  | 2008-12-01 | 4.3667
0
1404-109.J | Joule | FY04 JOULE #1-Authorize Prototype Fab | 2003-12-20 | 0.33333 | 2003-12-30 |  |  | 2003-10-20
1406-040 |  | FY04 JOULE #2-Begin winding on 3D surface | 2004-03-01 | 1 | 2004-03-31 |  |  | 2004-01-30
1404-110.J |  | FY04 JOULE #3-Prototype Casting Ready for Machining | 2004-06-01 | 0.96667 | 2004-06-30 |  |  | 2004-05-26
C-081.1 |  | FY04 JOULE #4 - CD-3 Readiness | 2004-09-01 | 0.96667 | 2004-09-30 |  |  | 2004-09-15
1408-143.1 |  | FY05 JOULE #1- VVSA, MCWF and MC Copper Conductor Awarded |  | 1278.3667 | 2004-12-30 | 2.5333 |  | 2004-10-15
1406-017.3 |  | FY05 JOULE #2- Cmplt Assy of twisted racetrack |  | 1281.4 | 2005-03-31 | 1281.4 |  | 2005-03-30
1403-20 |  | FY05 JOULE #3- Mod Coil Winding Type C FDR |  | 1284.4333 | 2005-06-30 | 1284.4333 |  | 2005-06-30
P1-011J |  | FY05 JOULE #4- Complete Winding First MC |  | 1287.5 | 2005-09-30 | 2005-10-31 |  | 2005-12-01 | 2005-12-15 | -2.5333
mcwf-311 |  | FY06 JOULE Complete Fabr. of one VVSA and two Mod Coils |  |  | 2006-09-30 |  | 2006-05-01 |  | 2006-03-22 | 6.4
P2-041joul |  | FY07 JOULE Complete Winding of 1/2 of Modular Coils |  |  | 2007-09-30 |  | 2006-12-01 |  | 2006-11-06 | 10.9333
NCSX Milestone Status
Formulas:
float = (+[Baseline]-[Forecast])/30
Forecast = +[early finish]+([float (milestone date - EF)]*30)
Forecast = +[ECP-53 Baseline]
Actual = +[Baseline]

## EIO IMPACT
Modular Coil Winding Form Delivery Schedule
[5 empty] | Project Forecast |  |  |  |  | Baseline |  |  |  | Critical path need date
[7 empty] | 2006 | [11 empty] | 2007
2005-01-01 | 2005-02-01 | MWF# | 2005-09-01 | 2005-10-01 | 2005-11-01 | 2005-12-01 | 2006-01-01 | 2006-02-01 | 2006-03-01 | 2006-04-01 | 2006-05-01 | 2006-06-01 | 2006-07-01 | 2006-08-01 | 2006-09-01 | 2006-10-01 | 2006-11-01 | 2006-12-01 | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | Sep | Oct
C1
C2
C3
C4
C5
A1
A2
A3
B1
A4
B2
B3
B4
B5
B6
A5
A6
C6
|  | 2005 |  |  |  |  | 2006 | [11 empty] | 2007
2005-01-01 | 2005-02-01 | 2005-03-01 | 2005-09-01 | 2005-10-01 | 2005-11-01 | 2005-12-01 | 2006-01-01 | 2006-02-01 | 2006-03-01 | 2006-04-01 | 2006-05-01 | 2006-06-01 | 2006-07-01 | 2006-08-01 | 2006-09-01 | 2006-10-01 | 2006-11-01 | 2006-12-01 | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | Sep | Oct | Nov
E
E
E
E
E
E
E
E
E
E

## Summary Schedule may06
NCSX Critical Path Summary Schedule
FY02 |  |  |  |  | FY03 | [11 empty] | FY04 | [11 empty] | FY05 | [11 empty] | FY06 | [12 empty] | FY07 | [11 empty] | FY08 | [11 empty] | FY09 | [11 empty] | FY10 | [11 empty] | FY11 | [11 empty] | FY12
[54 empty] | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J
CDR
|  | CD-1 | [13 empty] | MC/VV PDR | [5 empty] | CD-2
[19 empty] | EIR | [9 empty] | CD-3 Start of Fab
[23 empty] | Modular Coil FDR | [94 empty] | ♦
VACUUM VESSEL
Title I & II Design
Vessel Award
[27 empty] | Vessel Fab | [15 empty] | 1 |  | 2 | 3
MODULAR COILS
Title I & II MCWF
Twisted Racetrack Fabrication
[18 empty] | Title II MC Winding | [11 empty] | Type C |  |  |  | Type C | [8 empty] | Type A |  |  |  | Type B | bar: FY07 O to FY07 M
Modular Coil Interface Design and procurement | bar: FY07 O to FY08 O
Winding Component Fabrication | bar: FY07 O to FY07 M
MCWF Manufacturing Development
Fabricate Prototype Type "C"
Award Winding Form Contract
Fab Winding Forms | bar: FY07 O to FY07 J
Modular Coil WIndingWind | bar: FY07 O to FY08 A
FIELD PERIOD ASSEMBLY
Stage 1: Attach Cooling,Diag, Insulation | bar: FY07 O to FY08 M
Stage 2: Pre-Assemble Mod Coils
Stage 3: MC Installation
Stage 5: Assemble 1st Period
Stage 5: Assemble 2nd Period
Stage 5: Assemble 3rd Period
[60 empty] | MACHINE ASSEMBLY | [19 empty] | Install Supports and Lower PF Coils
Install,align, connect Field Period Assemblies
[5 empty] | Legend: | [48 empty] | FY10 D: Pump Down
[5 empty] | Completed Task | [48 empty] | FY10 D: Connect to Ancilliary Systems
[5 empty] | Critical Paths | [48 empty] | FY10 J: Install Cryostat & PTP
[5 empty] | Off critical path | [48 empty] | FY11 N: Startup Testing and E-Beam Mapping
[11 empty] | Current Baseline | [42 empty] | FY12 N: CD-4
FY02 |  |  |  |  | FY03 | [11 empty] | FY04 | [11 empty] | FY05 | [11 empty] | FY06 | [12 empty] | FY07 O: FY07; FY08 O: FY08; FY09 O: FY09; FY10 O: FY10; FY11 O: FY11; FY12 O: FY12
M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S |  | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J
M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A |  | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J
1
Total Float 11 mo.

## BA BO Profile
Total
| Original BA | 7.9 | 15.83 | 15.84 | 22.14 | 19.42 | 5.2 |  | 86.33
| New BA | 7.9 | 15.83 | 17.5 | 15.9 | 15.9 | 15.9 | 5.199 | 94.129
| PMB | 6.062 | 13.658 | 18.238 | 15.425 | 13.289 | 12.748 | 2.466 | 81.886
| Contingency |  |  | 0.8 | 3 | 2.6 | 3.1 | 2.742 | 12.242
| BA cum old | 7.9 | 23.73 | 39.57 | 61.71 | 81.13 | 86.33 | 86.33
| BA cum new | 7.9 | 23.73 | 41.23 | 57.13 | 73.03 | 88.93 | 94.129
| PMB cum | 6.062 | 19.72 | 37.958 | 53.383 | 66.672 | 79.42 | 81.886
FY03
%
24.8%
|  |  |  | FY03 | FY04 | FY05 | FY06 | FY07 | FY08 | FY09 | Total
| 22.01% |  | BA | 7.897 | 15.921 | 17.5 | 17 | 15.9 | 15.9 | 2.3 | 92.418
|  |  | EAC | 5.9419 | 14.2393 | 18.162 | 19.2 | 15.2 | 12.4 | 2.25 | 87.3932
| 5% |  | Contingency |  |  |  |  | 1.4 | 3.5 | 0.132 | 5.032
| 10% |  | BO (EAC + Cont) | 5.9419 | 14.2393 | 18.162 | 19.2 | 16.6 | 15.9 | 2.382 | 92.4252
|  |  | High Confidence Contingency increment | [6 empty] | 12.4 | 12.4
| 33.49% | [5 empty] | 57.5432
| 19.58% |  | Cum BA | 7.897 | 23.818 | 41.318 | 58.318 | 74.218 | 90.118 | 92.418
| 11.24% |  | Cum PMB | 5.9419 | 20.1812 | 38.3432 | 57.5432 | 72.7432 | 85.1432 | 87.3932
22.01%
|  |  | Cum BO | 5.9419 | 20.1812 | 38.3432 | 57.5432 | 74.1432 | 90.0432 | 92.4252
[5 empty] | 23.8 | 41.3 | 58.3 | 74.2 | 90.1 | 92.4
|  |  | pmb puts and takes |  |  | -0.415 | -1.047 | -0.712 | 0.151 | 0.121
|  |  | contingency puts and takes |  | 0 | 0.415 | 1.047 | 0.712 | -0.151 | -0.121
|  |  |  | wbs1 | -0.24 | -0.12 | -0.12
|  |  |  | wbs13 | -0.6 | -0.2 | -0.2 | -0.2
|  |  |  | wbs 141 | -0.64 |  | -0.32 | -0.32
|  |  |  | wbs142 | -0.095 | -0.095
|  |  |  | wbs142 | -0.097 |  | -0.097
|  |  |  | wbs18 | -0.3 |  | -0.15 | -0.15
|  |  |  | wbs82 | -0.32 |  | -0.16 | -0.16
|  |  |  | red | 0.48 |  |  | 0.118 | 0.151 | 0.121
0.09
[13 empty] | CD-2 | Directed rebaseline |  |  | EAC
[12 empty] | BCWR | 61.95 | 4.9 | 66.85
[12 empty] | Cont | 15.9 | 1.2 | 17.1 | 29.5
[13 empty] | 25.67% | 24.49% | 25.58% | 44.13%
[12 empty] | TEC | 86.3 |  | 92.4 | 12.4 | 104.8
$23.8
$74.2
$58.3
$41.3
$92.4
$90.1
$5.9
$72.7
$57.5
$38.3
$20.2
$87.4
$85.1
$104.8

## Financial History
NCSX MIE FINANCIAL SUMMARY
|  | FY03 | FY04 |  | FY05 | [5 empty] | FY05 | MIE BA |  |  |  | FY06 | FY06 | FY06 | FY06 | FY07 | FY08 | FY09 | TOTAL TEC
BA |  |  |  | FY03/04 carryover | Initial Fin Plan | DOE increment | Jan Fin Plan | May Fin Plan | July Fin Plan | Subtotal FY05 BA | Budget (incl c/o) | Thru FY05 | FY05 Carryover |  |  | Initial Fin Plan | Increment | 1% holdback | Net Budget
| ORNL | 1320000 | 2809000 | 135304 | 1500000 |  | 300000 | 300000 | 200000 | 2300000 | 2435304 | 6429000 | 274463 |  |  | 1500000 | 191000 | -16910 | 1948553 | 1000000 | 650000 | 59000 | #NAME?
| PPPL | 6577000 | 13037000 | 3426421 | 14300000 | 1700000 | -300000 | -300000 | -200000 | 15200000 | 18626421 | 34814000 | 2655650 |  |  | 14400000 | 1100000 | -155000 | 18000650 | 14900000 | 15250000 | 2033000 | 82497000
| DCMA |  | 75000 | 75000 | 0 | DCMA contract between DOE-PSO and Chicago. Managed by DOE-PSO. |  |  |  |  | 75000 | 75000 | [10 empty] | 75000
| TOTAL | 7897000 | 15921000 | 3636725 | 15800000 | [5 empty] | 21136725 | 41318000 | 2930113 |  |  | 15900000 | 1291000 | -171910 | 19949203 | 15900000 | 15900000 | 2092000 | #NAME?
MIE COST
Cost |  | FY03 | FY04 | [7 empty] | FY05 | Thru FY05
| ORNL | 1146273 | 2847423 | [7 empty] | 2160841 | 6154537
| PPPL | 4795653 | 11028219 | [7 empty] | 16409478 | 32233350
| d-site power sys |  | 438707 | D-Site pwr systems reclassified as non MIE & transferred to non MIE acount. DOE provided add'l BA in recognition of this being an upgrade. | [6 empty] | -438707 | 0
| dcma credit |  | -75000 | PPPL cost accounting credit applied. Reciprical cost applied to QA organization recovered as indirect cost for DCMA services. | [7 empty] | -75000
| subtotal PPPL | 4795653 | 11391926 | [7 empty] | 15970771 | 32158350
| DCMA |  | 75000 | [8 empty] | 75000
| TOTAL | 5941926 | 14239349 | [7 empty] | 18131612 | 38387887
| BA |  | FY06 |  |  |  | FY06 | MIE BA |  | FY07 |  | FY07 | FY08 | FY09 | TOTAL TEC
|  | FY05 Carryover | Initial Fin Plan | Increment | 1% holdback | Jun Fin Plan | Net Budget | CUM Through FY06 | FY06 Carryover | Initial fin plan | Nov Fin Plan req | Net Budget
| ORNL | 274463 | 1500000 | 191000 | -16910 | 175000 | 2123553 | 8278090 | 347291 | 995000 | 277000 | 1619291 | 650000 | 100000 | 10300090
| PPPL | 2655650 | 14400000 | 1100000 | -155000 | -175000 | 17825650 | 49984000 | 529096 | 14900000 | -277000 | 15152096 | 15250000 | 2168910 | 82025910
| DCMA | [6 empty] | 75000 | [6 empty] | 75000
|  | 2930113 | 15900000 | 1291000 | -171910 | 0 | 19949203 | 58337090 | 876387 | 15895000 | 0 | 16771387 | 15900000 | 2268910 | 92401000
[12 empty] | 74232090 | 90132090 | 92401000
| Cost |  |  |  |  | MIE COST | FY06 | MIE COST
[6 empty] | Thru FY05 | Cost | Thru FY06
[5 empty] | ORNL | 6154537 | 1776262 | 7930799
[5 empty] | PPPL | 32233350 | 17296554 | 49529904
[5 empty] | d-site power sys | 0 |  | 0
[5 empty] | dcma credit | -75000 |  | -75000
[5 empty] | subtotal PPPL | 32158350 |  | 49454904
[5 empty] | DCMA | 75000 |  | 75000
[5 empty] | TOTAL | 38343463 | 19072816 | 57460703 | (includes DCMA)
[6 empty] | 38312887 |  | 57385703 | pmb (excludes DCMA)