## Sheet1
Proposed NCSX Milestones
Months
| Milestone | Level | Approved | Scheduled | Proposed Baseline | Float | task id
1 | MC Interface FDR (excl C-C) | 2 |  | 2007-09-04 | 2007-11-03 | 2 | 1421-3136
2 | Deliver TF Coils for FPA #1 assy (4) | 2 | 2008-08-30 | 2007-09-28 | 2007-12-27 | 3 | 1361c-104m
3 | Shims required for 1st MCHP Assy. (Sta. 2) available | 2 |  | 2007-10-31 | 2008-01-29 | 3 | s21-5.04
4 | PF Coil PDR | 2 |  | 2007-12-10 | 2008-03-09 | 3 | 1302-225
5 | FDR Base Support Structure | 2 |  | 2008-02-04 | 2008-05-04 | 3 | 1702-525
6 | Complete 1st MCHP Assy. (Sta. 2) | 2 |  | 2008-05-09 | 2008-09-06 | 4 | s21-11.06
7 | Award PF Coils Contract | 2 | 2008-03-30 | 2008-05-27 | 2008-09-24 | 4 | 141-036
8 | Award Coil Support Structure | 2 |  | 2008-06-16 | 2008-10-14 | 4 | 162-036.9
9 | Complete VPI of 18th Mod. Coil | 2 |  | 2008-06-17 | 2008-10-15 | 4 | p3-171v
10 | Complete Modular Coil Fabrication | 2 |  | 2008-09-11 | 2009-02-08 | 5 | PLCT-C6
11 | Station 6 Assy Specifrication& Drawings Complete | 2 |  | 2008-10-02 | 2009-03-01 | 5 | 1803-601,1803-605
12 | Complete 1st MC-VV Assy. (Sta. 3) | 2 |  | 2008-11-29 | 2009-04-28 | 5 | s31-10.02
13 | Power Systems PDR | 2 |  | 2008-12-18 | 2009-06-16 | 6 | 451-2-3
14 | Complete Base Support Structure Assembly | 2 |  | 2009-01-12 | 2009-07-11 | 6 | 7501-10.4
15 | Complete 2nd MC-VV Assy. (Sta. 3) | 2 |  | 2009-03-11 | 2009-09-07 | 6 | s32-10.02
16 | Complete 1st Field Period Assy. (Sta. 5) | 2 |  | 2009-05-29 | 2009-11-25 | 6 | s51-14.03
17 | Complete 3rd MC-VV Assy. (Sta. 3) | 2 |  | 2009-06-08 | 2009-12-05 | 6 | s33-10.02
18 | Complete Fab. TF/MCWF Coil Structures Hardware | 2 |  | 2009-07-01 | 2009-12-28 | 6 | 162-037
19 | Power Systems C-Site Cabling FDR | 2 |  | 2009-07-28 | 2010-02-23 | 7 | 451-6-2
20 | Complete 2nd Field Period Assy. (Sta. 5) | 2 |  | 2009-10-05 | 2010-05-03 | 7 | s52-14.03
21 | Install 3rd Field Period on Assy. Sleds (Sta. 6) | 2 |  | 2009-12-15 | 2010-07-13 | 7 | 7503-150
22 | Move FPA's & Spacers together & check fitup | 2 |  | 2010-02-16 | 2010-10-14 | 8 | 7503-412
23 | E-Beam Mapping Apparatus Assembled and Ready for Installation | 2 |  | 2010-04-14 | 2010-12-10 | 8 | 380-135
24 | Complete Cryo Systems Pre-Ops Tests | 2 |  | 2010-07-01 | 2011-02-26 | 8 | 623-261
25 | Pump Down of Vacuum Vessel | 2 | 2009-02-28 | 2010-06-28 | 2011-03-25 | 9 | 7503-250
26 | Complete Central Safety & Interlock System Pre-Ops Tests | 2 |  | 2010-08-12 | 2011-05-09 | 9 | r56-70
27 | Begin Cryostat Installation | 2 | 2009-04-30 | 2010-10-07 | 2011-07-04 | 9 | 7503-330
28 | Complete Power System Pre-Ops Tests | 2 |  | 2010-10-25 | 2011-08-21 | 10 | 7503-458
29 | Complete Operational Readiness Assessment | 2 | 2009-06-30 | 2010-10-21 | 2011-09-16 | 11 | 730.1250
30 | Begin Start-Up Testing | 2 | 2009-06-30 | 2010-11-11 | 2011-10-07 | 11 | 8501-305
31 | Cooldown of machine | 2 |  | 2011-01-03 | 2011-11-29 | 11 | 730.8200
32 | Complete CD-4 Milestone (First Plasma and Completion of MIE Project) | 1 | 2009-07-30 | 2011-01-31 | 2011-12-27 | 11 | 8501-110
Not Included:
New | Complete 2nd MCHP Assy. (Sta. 2) | 2 |  | 2008-05-22 | 2008-10-19 | 5 | s22-11.06
10 | Complete 4th MCHP Assy. (Sta. 2) | 2 |  | 2008-09-19 | 2009-02-16 | 5 | s24-a4b4c4
New | Coil Support Structure Components Delivered | 2 |  | 2008-11-04 | 2009-06-02 | 7 | 162-051, -053, -057
13 | Update Final Assembly Plan | 2 |  | 2008-12-08 | 2009-06-06 | 6 | 714.025
19 | Install 1st Field Period on Assy. Sleds (Sta. 6) | 2 |  | 2009-07-24 | 2010-02-19 | 7 | 7503-080
22 | Cryostat Materials Delivered | 2 |  | 2010-01-13 | 2010-08-11 | 7 | 1751-151
|  |  |  | Ron | Hutch
|  |  | FY08 | 8 | 7
|  |  | FY09 | 7 | 7
|  |  | FY10 | 9 | 7
|  |  | FY11 | 5 | 7
|  |  | FY12 | 4 | 4
|  |  |  | 33 | 32
39356
| Milestone | Proposed Baseline
| Shims required for 1st MCHP Assy. (Sta. 2) available | 2008-02-28
| Complete TF Coils | 2008-05-16
| Complete VPI of 18th Mod. Coil | 2008-08-21
| Complete 1st MCHP Assy. (Sta. 2) | 2008-08-22
| Award PF Coils Contract | 2008-09-24 | 5
| Complete 4th MCHP Assy. (Sta. 2) | 2009-02-16
| Complete 1st MC-VV Assy. (Sta. 3) | 2009-02-27
| Lower PF Coils 4, 5, 6 Delivered | 2009-08-05
| Complete Base Support Structure Assembly | 2009-08-08
| Complete 2nd MC-VV Assy. (Sta. 3) | 2009-09-20 | 5
| Complete 3rd MC-VV Assy. (Sta. 3) | 2009-12-16
| Complete Fab. Coil Structures Hardware | 2009-12-28
| Complete 1st Field Period Assy. (Sta. 5) | 2010-01-21
| Install 1st Field Period on Assy. Sleds (Sta. 6) | 2010-02-19
| Complete 2nd Field Period Assy. (Sta. 5) | 2010-05-19
| Install 3rd Field Period on Assy. Sleds (Sta. 6) | 2010-08-06
| Cryostat Materials Delivered | 2010-08-11
| Complete DC Power Cable Installation | 2010-08-16 | 8
| Complete Cryo Systems Pre-Ops Tests | 2011-02-26
| Pump Down of Vacuum Vessel | 2011-03-16
| Complete Central Safety & Interlock System Pre-Ops Tests | 2011-04-09
| Complete Power System Pre-Ops Tests | 2011-08-09
| Begin Cryostat Installation | 2011-08-23 | 5
| Complete Operational Readiness Assessment | 2011-10-08
| Begin Start-Up Testing | 2011-10-29
| Cooldown of machine | 2011-12-17
| Complete CD-4 Milestone (First Plasma and Completion of MIE Project) | 2012-01-14 | 4
27
Formulas:
Proposed Baseline = +[Scheduled]+([Float]*30)