## Sheet1
NCSX Monthly Progress Assessment
Description: |  |  |  | RLM: | Initials | Period:
Stellarator CoreDesign and Procurement |  |  |  | Phil Heitzenroeder |  | 2007-07-30
Scope (jobs): |  |  |  | Job Manager | Initials
Conventional Coils WBS 13 |  |  |  | Mike Kalish
Coil Services WBS 16 |  |  |  | Paul Goranson
Cryostat Job 1701/1751 |  |  |  | Geoff Gettelfinger
Assy tooling & constructability Job 1803 |  |  |  | Tom Brown
Dimensional Control Job 8205 |  |  |  | Bob Ellis
Modular Coils Jobs 1416/1421/1429/1431 |  |  |  | Dave Williamson
Coil Structures & Base Support Structure WBS 15 |  |  |  | Fred Dahlgren
Assembly Specs & Dwgs Job 1806 |  |  |  | Mike Cole
Systems Analysis Job 8204 |  |  |  | Art Brooks
Systems Engineering & Support Job 8202 |  |  |  | Wayne Reiersen
Highlights and Progress:
Issues (not currently impacting technical, cost, or schedule but being watched):
Problems and work around plans :
Schedule
Milestones (6 month look ahead) | Job | Job Mgr | Baseline plan | Current Forecast | DOE Commitment | Level |  |  |  |  | Activity ID | Activity description | Early start | Early finish | Milestones | Job Number | Job Manager
Dimensional control plans for station 2 | 8205 | BE | 2007-08-31 |  |  | 3 |  |  |  |  | METFY07R1 | Dimensional control plans for station 2 | 01JUN07* | 2007-08-31 | 3 | 8205 | BE
Station 2 Assembly Specification | 1806 | MC | 2007-09-11 |  |  | 3 |  |  |  |  | 1803-201 | Station 2 Assembly Specification | 11JUN07* | 2007-09-11 | 3 | 1806 | MC
Station 2 Assembly Drawings | 1806 | MC | 2007-09-11 |  |  | 3 |  |  |  |  | 1803-205 | Station 2 Assembly Drawings | 11JUN07* | 2007-09-11 | 3 | 1806 | MC
FDR outboard shims | 1421 | DW | 2007-07-18 |  |  | 3 |  |  |  |  | INTRF-046 | FDR outboard shims |  | 2007-07-18 | 3 | 1421 | DW
PDR | 1501 | FD | 2007-07-20 |  |  | 3 |  |  |  |  | 1501-525P | PDR | 20JUL07* | 2007-07-20 | 3 | 1501 | FD
Check and promote top-level models/drawings | 1416 | DW | 2007-11-21 |  |  | 3 |  |  |  |  | 1416-506 | Check and promote top-level models/drawings | 2007-08-01 | 2007-11-21 | 3 | 1416 | DW
Conduct BC,AB,AA,Interface FDR incl job 1416 | 1421 | DW | 2007-09-04 |  | 2007-11-30 | 2 |  |  |  |  | 1421-3136 | Conduct BC,AB,AA,Interface FDR incl job 1416 |  | 2007-09-04 | 2 | 1421 | DW | 2007-11-30
FDR AB/BC/AA inboard shims | 1421 | DW | 2007-09-04 |  |  | 3 |  |  |  |  | INTRF-055 | FDR AB/BC/AA inboard shims |  | 2007-09-04 | 3 | 1421 | DW
Dimensional control plans for station 3 | 8205 | BE | 2007-10-15 |  |  | 3 |  |  |  |  | METDCP-3 | Dimensional control plans for station 3 | 2007-09-04 | 2007-10-15 | 3 | 8205 | BE
FDR Coil Structures | 1501 | FD | 2007-09-21 |  |  | 3 |  |  |  |  | 1501-541 | FDR Coil Structures | 2007-09-21 | 2007-09-21 | 3 | 1501 | FD
** DELIVER TF COILS FOR FPA #1 ASSY ** | 1361 | MK | 2007-09-28 |  | 2007-12-30 | 2 |  |  |  |  | 1361C-104M | ** DELIVER TF COILS FOR FPA #1 ASSY ** |  | 2007-09-28 | 2 | 1361 | MK | 2007-12-30
Prepare EM and structural analysis of leads | 1416 | DW | 2007-11-06 |  |  | 3 |  |  |  |  | 1416-601 | Prepare EM and structural analysis of leads | 01OCT07* | 2007-11-06 | 3 | 1416 | DW
Dimensional control plans for station 5 | 8205 | BE | 2008-02-15 |  |  | 3 |  |  |  |  | METDCP-5 | Dimensional control plans for station 5 | 2007-10-16 | 2008-02-15 | 3 | 8205 | BE
Fab, Test & Deliver Coil #6 | 1361 | MK | 2007-11-23 |  |  | 3 |  |  |  |  | 1361C-106 | Fab, Test & Deliver Coil #6 | 23NOV07* | 2007-11-23 | 3 | 1361 | MK
Conduct PDR | 1702 | FD | 2007-11-26 |  |  | 3 |  |  |  |  | 1702-515 | Conduct PDR | 2007-11-26 | 2007-11-26 | 3 | 1702 | FD
PF Coil PDR | 1302 | MK | 2007-12-11 |  | 2008-03-30 | 2 |  |  |  |  | 1302-225M | PF Coil PDR |  | 2007-12-11 | 2 | 1302 | MK | 2007-03-30
Prepare Type-ABC closeout FDR | 1416 | DW | 2008-01-14 |  |  | 3 |  |  |  |  | 1416-605 | Prepare Type-ABC closeout FDR | 2007-12-14 | 2008-01-14 | 3 | 1416 | DW
FDR C-C Shims | 1421 | DW | 2008-01-07 |  |  | 3 |  |  |  |  | 1421-3144 | FDR C-C Shims |  | 2008-01-07 | 3 | 1421 | DW
Base Support Structure FDR | 1702 | FD | 2008-02-04 |  | 2008-05-31 | 2 |  |  |  |  | 1702-525M | Base Support Structure FDR |  | 2008-02-04 | 2 | 1702 | FD | 2007-05-30
Cost and schedule Performance
Indices
[5 empty] | From May 1,2007 | Current Month
BCWS =
BCWP =
ACWP =
CV =
SV =
CPI =
SPI =
BAC =
EAC =
Projected cost variance =
EAC Variance Explanation
Analysis
Cost Variance (Cause, Impact, and Corrective Action) (>5% and >$50k) |  |  |  | Schedule Variance (Cause, Impact, and Corrective Action) (>5% and >$50k)
Changes/Additions to the risk registry
Description |  |  | Likelihood of Occurrence | Cost and schedule impact
1803-6.6 0 0 0 | [5 empty] | Stage 3 support FDR |  | * | 2007-07-13 | 3 |  |  | 2007-07-13
3101-326 0 0 0 | [5 empty] | FDR - ROWGOSKI COIL |  |  | 2007-09-06 | 3
S21-11.07 0 0 0 | [5 empty] | Shims required for 1st 3 pack MC assy |  |  | 2007-10-31 | 2
S22-11.06 2 2 0 | [5 empty] | Station 5 FDR |  |  | 2007-11-21 | 3 |  |  | 2008-02-01
P3-171V 11 11 0 | [5 empty] | Final Scan |  |  | 2008-02-06 | 3 |  |  | 2008-05-12
PLCT-C6 14 14 0 | [5 empty] | Move A1-B1-C1 to holding area. |  |  | 2008-05-09 | 2
S21-5.04X 0 0 0 | [5 empty] | Station 6 FDR |  |  | 2008-06-04 | 3
1803-3.4 1 1 0
R1810-1329 4 4 0
1803-5.6 0 0 0
S31-10.02 1 1 0
S32-10.02 1 1 0 | [5 empty] | VPI (Station 5) B6 | 2008-06-03 |  | 2008-06-17 | 2
S33-10.02 1 1 0 | [5 empty] | Remove from stand Move A2-B2-C2 to holding area | 2008-06-18 |  | 2008-06-19 | 3
[6 empty] | Insul,measure,TC,SG other punch list-C6 | 2008-08-22 |  | 2008-09-11 | 2
[6 empty] | Transfer Period 1 to Station 5 in NCSX TC | 2008-10-29 |  | 2008-10-29 | 2
[6 empty] | Transfer Period 2 to Station 5 in NCSX TC | 2009-03-11 |  | 2009-03-11 | 2
[6 empty] | Transfer Period 3 to Station 5 in NCSX TC | 2009-06-08 |  | 2009-06-08 | 2

## Sheet2
| M | J | J | A | S | O | N | D | J | F | M | A
BCWS (planned) | 1000 | 1100 | 1150 | 1250 | 1400 | 1500 | 1600 | 1675 | 1750 | 1800 | 1825 | 1845
ACWP (Actual) | 950 | 1100 | 1200 | 1250 | 1375 | 1500 | 1600 | 1650 | 1675
BCWP (Earned) | 1000 | 1075 | 1125 | 1225 | 1350 | 1490 | 1550 | 1600 | 1650

## Sheet3
Activity ID | Activity description | Milestones | Job Number | Job Manager | Target 1 early start | Target 1 early finish | Early start | Early finish
METFY07R1 | Dimensional control plans for station 2 | 3 | 8205 | BE | 01JUN07* | 2007-08-31 | 01JUN07A | 2007-08-31
1803-205 | Station 2 Assembly Drawings | 3 | 1806 | MC | 11JUN07* | 2007-09-11 | 11JUN07A | 2007-09-11
INTRF-045 | FDR prep outboard shims | 3 | 1421 | DW | 2007-07-05 | 2007-07-18 | 25JUN07A | 29JUN07A
1803-201 | Station 2 Assembly Specification | 3 | 1806 | MC | 11JUN07* | 2007-09-11 | 02JUL07* | 2007-09-11
1501-525P | PDR | 3 | 1501 | FD | 20JUL07* | 2007-07-20 | 23JUL07* | 2007-07-23
1416-506 | Check and promote top-level models/drawings | 3 | 1416 | DW | 2007-08-01 | 2007-11-21 | 2007-08-01 | 2007-11-21
1421-3136 | Conduct BC,AB,AA,Interface FDR incl job 1416 | 2 | 1421 | DW |  | 2007-09-04 |  | 2007-09-04
INTRF-055 | FDR AB/BC/AA inboard shims | 3 | 1421 | DW |  | 2007-09-04 |  | 04SEP07*
METDCP-3 | Dimensional control plans for station 3 | 3 | 8205 | BE | 2007-09-04 | 2007-10-15 | 2007-09-04 | 2007-10-15
1501-541 | FDR Coil Structures | 3 | 1501 | FD | 2007-09-21 | 2007-09-21 | 2007-09-24 | 2007-09-24
1361C-104M | ** DELIVER TF COILS FOR FPA #1 ASSY ** | 2 | 1361 | MK |  | 2007-09-28 |  | 2007-09-28
1416-601 | Prepare EM and structural analysis of leads | 3 | 1416 | DW | 01OCT07* | 2007-11-06 | 01OCT07* | 2007-11-06
METDCP-5 | Dimensional control plans for station 5 | 3 | 8205 | BE | 2007-10-16 | 2008-02-15 | 2007-10-16 | 2008-02-15
1361C-106 | Fab, Test & Deliver Coil #6 | 3 | 1361 | MK | 23NOV07* | 2007-11-23 | 23NOV07* | 2007-11-23
1702-515 | Conduct PDR | 3 | 1702 | FD | 2007-11-26 | 2007-11-26 | 2007-11-26 | 2007-11-26
1302-225M | PF Coil PDR | 2 | 1302 | MK |  | 2007-12-11 |  | 2007-12-11
1416-605 | Prepare Type-ABC closeout FDR | 3 | 1416 | DW | 2007-12-14 | 2008-01-14 | 2007-12-14 | 2008-01-14
1421-3144 | FDR C-C Shims | 3 | 1421 | DW |  | 2008-01-07 |  | 2008-01-07