## Sheet1
NCSX Monthly Progress Assessment
Description: |  | RLM: | Initials | Period:
Stellarator Core On-Site Fabrication & Assembly |  | L.Dudek |  | 2007-06-01
Scope (jobs): |  | Job Manager | Initials
1451/1459/1408 Modular Coil Fabrication |  | J.Chzanowski
1802/1810 Field Period Assembly |  | M.Viola
1803 Assembly Tooling design and procurement |  | T.Brown
1204/1431 VVSA and MC interface Hardware Procurement |  | L.Dudek
Highlights and Progress:
Issues (not currently impacting technical, cost, or schedule but being watched):
Problems and work around plans :
Schedule
Milestones (6 month look ahead) | Baseline plan | Current Forecast | DOE Commitment | Level
Stage 3 support FDR | 2007-07-13 |  |  | 3
FDR - ROWGOSKI COIL | 2007-09-06 |  |  | 3
Shims required for 1st 3 pack MC assy | 2007-10-31 |  | 2008-01-31 | 2
Station 5 FDR | 2007-11-21 |  |  | 3
Station 1 FPA #1 complete (Final Scan) | 2008-02-06 |  |  | 3
Complete 1st MCHP Assy (Move A1-B1-C1 to holding area. ) | 2008-05-09 |  | 2008-09-30 | 2
Station 6 FDR | 2008-06-04 |  |  | 3
Cost and schedule Performance
Indices
|  |  | From May 1,2007 | Current Month
BCWS =
BCWP =
ACWP =
CV =
SV =
CPI =
SPI =
BAC =
EAC =
Projected cost variance =
EAC Variance Explanation
Analysis
Cost Variance (Cause, Impact, and Corrective Action) (>5% and >$50k) |  | Schedule Variance (Cause, Impact, and Corrective Action) (>5% and >$50k)
Changes/Additions to the risk registry
Description | Likelihood of Occurrence | Cost and schedule impact
1803-6.6 0 0 0 |  |  |  | Stage 3 support FDR |  | * | 2007-07-13 | 3 | 2007-07-13
3101-326 0 0 0 |  |  |  | FDR - ROWGOSKI COIL |  |  | 2007-09-06 | 3
S21-11.07 0 0 0 |  |  |  | Shims required for 1st 3 pack MC assy |  |  | 2007-10-31 | 2
S22-11.06 2 2 0 |  |  |  | Station 5 FDR |  |  | 2007-11-21 | 3 | 2008-02-01
P3-171V 11 11 0 |  |  |  | Final Scan |  |  | 2008-02-06 | 3 | 2008-05-12
PLCT-C6 14 14 0 |  |  |  | Move A1-B1-C1 to holding area. |  |  | 2008-05-09 | 2
S21-5.04X 0 0 0 |  |  |  | Station 6 FDR |  |  | 2008-06-04 | 3
1803-3.4 1 1 0
R1810-1329 4 4 0
1803-5.6 0 0 0
S31-10.02 1 1 0
S32-10.02 1 1 0 |  |  |  | VPI (Station 5) B6 | 2008-06-03 |  | 2008-06-17 | 2
S33-10.02 1 1 0 |  |  |  | Remove from stand Move A2-B2-C2 to holding area | 2008-06-18 |  | 2008-06-19 | 3
|  |  |  | Insul,measure,TC,SG other punch list-C6 | 2008-08-22 |  | 2008-09-11 | 2
|  |  |  | Transfer Period 1 to Station 5 in NCSX TC | 2008-10-29 |  | 2008-10-29 | 2
|  |  |  | Transfer Period 2 to Station 5 in NCSX TC | 2009-03-11 |  | 2009-03-11 | 2
|  |  |  | Transfer Period 3 to Station 5 in NCSX TC | 2009-06-08 |  | 2009-06-08 | 2

## Sheet2
| M | J | J | A | S | O | N | D | J | F | M | A
BCWS (planned) | 1000 | 1100 | 1150 | 1250 | 1400 | 1500 | 1600 | 1675 | 1750 | 1800 | 1825 | 1845
ACWP (Actual) | 950 | 1100 | 1200 | 1250 | 1375 | 1500 | 1600 | 1650 | 1675
BCWP (Earned) | 1000 | 1075 | 1125 | 1225 | 1350 | 1490 | 1550 | 1600 | 1650