## Sheet1
| FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | FY2009 | FY2010 | FY2011
BCWS = | 5942.19 | 14314.35 | 18131.61 | 19072.81 | 15837.72 | 14483 | 15068 | 12581 | 2602
Contingency | FY2007: 144; FY2008: 2205; FY2009: 3492; FY2010: 4450; FY2011: 3440
EAC | 5942.19 | 14314.35 | 18131.61 | 19072.81 | 15981.72 | 16688 | 18560 | 17031 | 6042
Funding (BA) | FY2007: 16771; FY2008: 15900; FY2009: 18560
|  |  |  | Planned Finish = | 2011-01-31
|  |  |  | CD-4= | 2011-12-31
|  |  |  | Schedule Contingency = | 10.9832

## P3
| NCSX Proposed Cost Estimate | [12 empty] | NCSX Proposed Cost Estimate | [10 empty] | NCSX Proposed Cost Estimate
|  | TOTAL | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | FY2009 | FY2010 | FY2011 |  |  |  | TOTAL | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | FY2009 | FY2010 | FY2011 |  | TOTAL | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | FY2009 | FY2010 | FY2011
1204 | Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 408 |  |  |  |  | 47 | 162 | 1 | 198 |  |  |  | Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 415 |  |  |  |  | 47 | 90 |  | 278 |  | Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | -7 | 0 | 0 | 0 | 0 | 0 | 72 | 1 | -80 | 0
1250 | Job: 1250 - Vacuum Vessel Fabrication**CLOSED** | -252 |  |  |  |  | -252 | [6 empty] | Job: 1250 - Vacuum Vessel Fabrication**CLOSED** | -162 |  |  |  |  | -162 |  |  |  |  | Job: 1250 - Vacuum Vessel Fabrication**CLOSED** | -90 | 0 | 0 | 0 | 0 | -90 | 0 | 0 | 0 | 0
1302 | Job: 1302 - PF Design -KALISH | 257 |  |  |  |  | 44 | 213 | [5 empty] | Job: 1302 - PF Design -KALISH | 254 |  |  |  |  | 43 | 211 |  |  |  | Job: 1302 - PF Design -KALISH | 3 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0
1352 | Job: 1352 - PF Coil Procurement-KALISH | 1630 | [5 empty] | 968 | 634 | 28 |  |  |  | Job: 1352 - PF Coil Procurement-KALISH | 1596 | [5 empty] | 926 | 642 | 28 |  | Job: 1352 - PF Coil Procurement-KALISH | 34 | 0 | 0 | 0 | 0 | 0 | 42 | -8 | 0 | 0
1353 | Job: 1353 - CS Structure Procurement-DAHLGREN | 337 | [6 empty] | 78 | 259 |  |  |  | Job: 1353 - CS Structure Procurement-DAHLGREN | 337 | [6 empty] | 78 | 259 |  | Job: 1353 - CS Structure Procurement-DAHLGREN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1354 | Job: 1354 - Trim Coil Design &Procurement-KALISH | 162 | [6 empty] | 162 |  |  |  |  | Job: 1354 - Trim Coil Design &Procurement-KALISH | 123 | [6 empty] | 45 | 78 |  | Job: 1354 - Trim Coil Design &Procurement-KALISH | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | -78 | 0
1355 | Job: 1355 - WBS 13 I&C Proc and Coil Assy-KALISH | 73 | [5 empty] | 32 | 39 | 2 |  |  |  | Job: 1355 - WBS 13 I&C Proc and Coil Assy-KALISH | 72 | [5 empty] | 41 | 29 | 2 |  | Job: 1355 - WBS 13 I&C Proc and Coil Assy-KALISH | 1 | 0 | 0 | 0 | 0 | 0 | -9 | 10 | 0 | 0
1361 | Job: 1361 - TF Fabrication-KALISH | 1003 |  |  |  |  | 228 | 775 | [5 empty] | Job: 1361 - TF Fabrication-KALISH | 954 |  |  |  |  | 227 | 727 |  |  |  | Job: 1361 - TF Fabrication-KALISH | 49 | 0 | 0 | 0 | 0 | 1 | 48 | 0 | 0 | 0
1404 | Job: 1404 - MCWF R&D 1st Prod | -36 |  |  |  |  | -36 | [6 empty] | Job: 1404 - MCWF R&D 1st Prod | -36 |  |  |  |  | -36 |  |  |  |  | Job: 1404 - MCWF R&D 1st Prod | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1408 | Job: 1408 - MC Winding Supplies-CHRZANOWSKI | 350 |  |  |  |  | 178 | 172 | [5 empty] | Job: 1408 - MC Winding Supplies-CHRZANOWSKI | 310 |  |  |  |  | 188 | 122 |  |  |  | Job: 1408 - MC Winding Supplies-CHRZANOWSKI | 40 | 0 | 0 | 0 | 0 | -10 | 50 | 0 | 0 | 0
1411 | Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER | -80 |  |  |  |  | -80 | [6 empty] | Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER | 9 |  |  |  |  | 9 |  |  |  |  | Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER | -89 | 0 | 0 | 0 | 0 | -89 | 0 | 0 | 0 | 0
1416 | Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | 280 |  |  |  |  | 70 | 210 | [5 empty] | Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | 280 |  |  |  |  | 70 | 210 |  |  |  | Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1421 | Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 1208 |  |  |  |  | 996 | 212 | [5 empty] | Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 1370 |  |  |  |  | 1160 | 209 |  |  |  | Job: 1421 - Mod Coil Interface Design-WILLIAMSON | -162 | 0 | 0 | 0 | 0 | -164 | 3 | 0 | 0 | 0
| Job: 1429 - MC Interface R&D-GETTELFINGER | 118 |  |  |  |  | 118
1431 | Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 1039 |  |  |  |  | 362 | 660 |  | 17 |  |  |  | Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 1039 |  |  |  |  | 366 | 656 |  | 17 |  | Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 0 | 0 | 0 | 0 | 0 | -4 | 4 | 0 | 0 | 0
1451 | Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 2867 |  |  |  |  | 1054 | 1813 | [5 empty] | Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 2885 |  |  |  |  | 1159 | 1726 |  |  |  | Job: 1451 - Mod Coil Winding-CHRZANOWSKI | -18 | 0 | 0 | 0 | 0 | -105 | 87 | 0 | 0 | 0
1459 | Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | 501 |  |  |  |  | 90 | 411 | [5 empty] | Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | 486 |  |  |  |  | 119 | 367 |  |  |  | Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | 15 | 0 | 0 | 0 | 0 | -29 | 44 | 0 | 0 | 0
1501 | Job: 1501 - Coil Structures Design-DAHLGREN | 186 |  |  |  |  | 164 | 22 | [5 empty] | Job: 1501 - Coil Structures Design-DAHLGREN | 189 |  |  |  |  | 189 | 0 |  |  |  | Job: 1501 - Coil Structures Design-DAHLGREN | -3 | 0 | 0 | 0 | 0 | -25 | 22 | 0 | 0 | 0
1550 | Job: 1550 - Coil Struct. Procurement -DAHLGREN | 1076 | [5 empty] | 403 | 673 |  |  |  |  | Job: 1550 - Coil Struct. Procurement -DAHLGREN | 1076 | [5 empty] | 403 | 673 |  |  | Job: 1550 - Coil Struct. Procurement -DAHLGREN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1601 | Job: 1601 - Coil Services Design-GORANSON | 861 |  |  |  |  | 6 | 323 | 372 | 160 |  |  |  | Job: 1601 - Coil Services Design-GORANSON | 873 |  |  |  |  | 6 | 184 | 445 | 238 |  | Job: 1601 - Coil Services Design-GORANSON | -12 | 0 | 0 | 0 | 0 | 0 | 139 | -73 | -78 | 0
1701 | Job: 1701 - Cryostat Design-GETTLEFINGER | 207 | [6 empty] | 207 |  |  |  |  | Job: 1701 - Cryostat Design-GETTLEFINGER | 207 | [6 empty] | 207 |  |  | Job: 1701 - Cryostat Design-GETTLEFINGER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1702 | Job: 1702 - Base Support Struct Design-DAHLGREN | 163 | [5 empty] | 163 | [5 empty] | Job: 1702 - Base Support Struct Design-DAHLGREN | 163 | [5 empty] | 163 |  |  |  | Job: 1702 - Base Support Struct Design-DAHLGREN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1751 | Job: 1751 - Cryostat Procurement-GETTLEFINGER | 325 | [7 empty] | 325 |  |  |  | Job: 1751 - Cryostat Procurement-GETTLEFINGER | 325 | [7 empty] | 325 |  | Job: 1751 - Cryostat Procurement-GETTLEFINGER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1752 | Job: 1752 - Base Support Proc-DAHLGREN | 89 | [5 empty] | 61 | 28 |  |  |  |  | Job: 1752 - Base Support Proc-DAHLGREN | 89 | [5 empty] | 69 | 20 |  |  | Job: 1752 - Base Support Proc-DAHLGREN | 0 | 0 | 0 | 0 | 0 | 0 | -8 | 8 | 0 | 0
1802 | Job: 1802 - FP Assy Oversight&Support-VIOLA | 1989 |  |  |  |  | 253 | 790 | 858 | 88 |  |  |  | Job: 1802 - FP Assy Oversight&Support-VIOLA | 1998 |  |  |  |  | 257 | 787 | 832 | 121 |  | Job: 1802 - FP Assy Oversight&Support-VIOLA | -9 | 0 | 0 | 0 | 0 | -4 | 3 | 26 | -33 | 0
1803 | Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 522 |  |  |  |  | 131 | 316 | 75 |  |  |  |  | Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 524 |  |  |  |  | 143 | 305 | 75 |  |  | Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | -2 | 0 | 0 | 0 | 0 | -12 | 11 | 0 | 0 | 0
1806 | Job: 1806 - FP Assembly specs | 514 |  |  |  |  | 92 | 382 | 40 |  |  |  |  | Job: 1806 - FP Assembly specs | 515 |  |  |  |  | 92 | 382 | 40 |  |  | Job: 1806 - FP Assembly specs | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1810 | Job:1810-Field Period Assy -Station 1 2 3 VIOLA | 5745 |  |  |  |  | 1266 | 2353 | 1961 | 165 |  |  |  | Job:1810-Field Period Assy -Station 1 2 3 VIOLA | 5445 |  |  |  |  | 1181 | 2395 | 1640 | 229 |  | Job:1810-Field Period Assy -Station 1 2 3 VIOLA | 300 | 0 | 0 | 0 | 0 | 85 | -42 | 321 | -64 | 0
1815 | Job: 1815 - Field Period Assy | 1334 | [5 empty] | 223 | 1017 | 94 |  |  |  | Job: 1815 - Field Period Assy | 1317 | [5 empty] | 223 | 925 | 169 |  | Job: 1815 - Field Period Assy | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | -75 | 0
1901 | Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 1620 |  |  |  |  | 162 | 408 | 432 | 448 | 170 |  |  | Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 1743 |  |  |  |  | 165 | 425 | 453 | 468 | 232 | Job: 1901 - Stellarator Core Mngtt&Integr-COLE | -123 | 0 | 0 | 0 | 0 | -3 | -17 | -21 | -20 | -62
2101 | Job: 2101 - Fueling Systems-BLANCHARD | 69 | [6 empty] | 13 | 56 |  |  |  | Job: 2101 - Fueling Systems-BLANCHARD | 69 | [6 empty] | 16 | 53 |  | Job: 2101 - Fueling Systems-BLANCHARD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | 3 | 0
2201 | Job: 2201 - Vacuum Pumping Systems-BLANCHARD | 172 | [6 empty] | 70 | 102 |  |  |  | Job: 2201 - Vacuum Pumping Systems-BLANCHARD | 174 | [6 empty] | 124 | 50 |  | Job: 2201 - Vacuum Pumping Systems-BLANCHARD | -2 | 0 | 0 | 0 | 0 | 0 | 0 | -54 | 52 | 0
3101 | Job: 3101 - Magnetic Diagnostics-STRATTON | 291 |  |  |  |  | 184 | 107 | [5 empty] | Job: 3101 - Magnetic Diagnostics-STRATTON | 294 |  |  |  |  | 187 | 107 |  |  |  | Job: 3101 - Magnetic Diagnostics-STRATTON | -3 | 0 | 0 | 0 | 0 | -3 | 0 | 0 | 0 | 0
3601 | Job: 3601 - Edge Divertor Diagnostics-STRATTON | 31 | [7 empty] | 31 |  |  |  | Job: 3601 - Edge Divertor Diagnostics-STRATTON | 31 | [7 empty] | 31 |  | Job: 3601 - Edge Divertor Diagnostics-STRATTON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3801 | Job: 3801 - Electron Beam Mapping-STRATTON | 263 | [6 empty] | 101 | 162 |  |  |  | Job: 3801 - Electron Beam Mapping-STRATTON | 263 | [6 empty] | 103 | 160 |  | Job: 3801 - Electron Beam Mapping-STRATTON | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 2 | 0
3901 | Job: 3901 - Diagnostics sys Integration-STRATTON | 132 |  |  |  |  | 11 | 29 | 30 | 62 |  |  |  | Job: 3901 - Diagnostics sys Integration-STRATTON | 133 |  |  |  |  | 12 | 29 | 30 | 62 |  | Job: 3901 - Diagnostics sys Integration-STRATTON | -1 | 0 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0
4101 | Job: 4101 - AC Power-RAMAKRISHNAN | 55 |  |  |  |  | -104 |  | 57 | 102 |  |  |  | Job: 4101 - AC Power-RAMAKRISHNAN | 54 |  |  |  |  | -104 |  | 58 | 101 |  | Job: 4101 - AC Power-RAMAKRISHNAN | 1 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0
4301 | Job: 4301 - DC Systems-RAMAKRISHNAN | 603 | [5 empty] | 11 | 274 | 318 |  |  |  | Job: 4301 - DC Systems-RAMAKRISHNAN | 603 | [5 empty] | 11 | 274 | 318 |  | Job: 4301 - DC Systems-RAMAKRISHNAN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4401 | Job: 4401 - Control & Protection-RAMAKRISHNAN | 1084 | [6 empty] | 314 | 770 |  |  |  | Job: 4401 - Control & Protection-RAMAKRISHNAN | 1084 | [6 empty] | 326 | 758 |  | Job: 4401 - Control & Protection-RAMAKRISHNAN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -12 | 12 | 0
4501 | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 683 | [6 empty] | 356 | 274 | 53 |  |  | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 685 | [6 empty] | 356 | 230 | 99 | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | -46
5101 | Job: 5101 - Network and Fiber | 150 | [6 empty] | 7 | 143 |  |  |  | Job: 5101 - Network and Fiber | 151 | [6 empty] | 7 | 144 |  | Job: 5101 - Network and Fiber | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0
5201 | Job: 5201 - I&C Systems-SICHTA | 196 | [6 empty] | 81 | 115 |  |  |  | Job: 5201 - I&C Systems-SICHTA | 197 | [6 empty] | 82 | 115 |  | Job: 5201 - I&C Systems-SICHTA | -1 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | 0
5301 | Job: 5301 - Data Acquisition-SICHTA | 165 | [6 empty] | 51 | 114 |  |  |  | Job: 5301 - Data Acquisition-SICHTA | 164 | [6 empty] | 51 | 114 |  | Job: 5301 - Data Acquisition-SICHTA | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5401 | Job: 5401 - Facility Timing & | 205 | [6 empty] | 12 | 193 |  |  |  | Job: 5401 - Facility Timing & | 205 | [6 empty] | 12 | 194 |  | Job: 5401 - Facility Timing & | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0
5501 | Job: 5501 - Real Time Control | 129 | [6 empty] | 17 | 112 |  |  |  | Job: 5501 - Real Time Control | 129 | [6 empty] | 17 | 112 |  | Job: 5501 - Real Time Control | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5601 | Job: 5601 - Central Safety &Interlock Sys-SICHTA | 222 | [6 empty] | 12 | 210 |  |  |  | Job: 5601 - Central Safety &Interlock Sys-SICHTA | 223 | [6 empty] | 12 | 211 |  | Job: 5601 - Central Safety &Interlock Sys-SICHTA | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 0
5801 | Job: 5801 - Central I&C Integr& Oversight-SICHTA | 69 |  |  |  |  | 7 | 24 | 19 | 19 |  |  |  | Job: 5801 - Central I&C Integr& Oversight-SICHTA | 69 |  |  |  |  | 7 | 24 | 19 | 19 |  | Job: 5801 - Central I&C Integr& Oversight-SICHTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6101 | Job: 6101 - Water Systems-DUDEK | 46 | [6 empty] | 46 |  |  |  |  | Job: 6101 - Water Systems-DUDEK | 46 | [6 empty] | 46 |  |  | Job: 6101 - Water Systems-DUDEK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6201 | Job: 6201 - Cryogenic Syst-GETTELFINGER | 655 | [6 empty] | 271 | 384 |  |  |  | Job: 6201 - Cryogenic Syst-GETTELFINGER | 655 | [6 empty] | 271 | 384 |  | Job: 6201 - Cryogenic Syst-GETTELFINGER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6301 | Job: 6301 - Utility Systems-DUDEK | 105 | [6 empty] | 105 |  |  |  |  | Job: 6301 - Utility Systems-DUDEK | 105 | [6 empty] | 105 |  |  | Job: 6301 - Utility Systems-DUDEK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6401 | Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH | 573 | [6 empty] | 107 | 466 |  |  |  | Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH | 570 | [6 empty] | 245 | 325 |  | Job: 6401 - PFC/VV Htng/Cooling(bakeout)- KALISH | 3 | 0 | 0 | 0 | 0 | 0 | 0 | -138 | 141 | 0
7301 | Job: 7301 - Platform Design & | 204 |  |  |  |  | 2 | 5 | 197 |  |  |  |  | Job: 7301 - Platform Design & | 204 |  |  |  |  | 2 | 5 | 197 |  |  | Job: 7301 - Platform Design & | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7401 | Job: 7401 - TC Prep & Mach Assy Planning-PERRY | 1417 |  |  |  |  | -308 | 23 | 615 | 857 | 230 |  |  | Job: 7401 - TC Prep & Mach Assy Planning-PERRY | 1435 |  |  |  |  | -308 | 23 | 577 | 857 | 286 | Job: 7401 - TC Prep & Mach Assy Planning-PERRY | -18 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | -56
7501 | Job: 7501 - Construction Support Crew-PERRY | 1407 | [6 empty] | 336 | 806 | 265 |  |  | Job: 7501 - Construction Support Crew-PERRY | 1436 | [6 empty] | 311 | 799 | 326 | Job: 7501 - Construction Support Crew-PERRY | -29 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 7 | -61
7503 | Job: 7503 - Machine Assembly (station 6)-PERRY | 4511 | [6 empty] | 1668 | 2205 | 638 |  |  | Job: 7503 - Machine Assembly (station 6)-PERRY | 4518 | [6 empty] | 1579 | 2192 | 747 | Job: 7503 - Machine Assembly (station 6)-PERRY | -7 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 13 | -109
7601 | Job: 7601 - Tooling Design & Fabrication-PERRY | 412 | [6 empty] | 207 | 205 |  |  |  | Job: 7601 - Tooling Design & Fabrication-PERRY | 413 | [6 empty] | 192 | 221 |  | Job: 7601 - Tooling Design & Fabrication-PERRY | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | -16 | 0
8101 | Job: 8101 - Project Management & Control-NEILSON | 3843 |  |  |  |  | 278 | 1034 | 1158 | 1074 | 299 |  |  | Job: 8101 - Project Management & Control-NEILSON | 3486 |  |  |  |  | 283 | 895 | 1015 | 927 | 365 | Job: 8101 - Project Management & Control-NEILSON | 357 | 0 | 0 | 0 | 0 | -5 | 139 | 143 | 147 | -66
8102 | Job: 8102 - NCSX MIE Management ORNL-LYON | 499 |  |  |  |  | 60 | 159 | 159 | 102 | 19 |  |  | Job: 8102 - NCSX MIE Management ORNL-LYON | 504 |  |  |  |  | 60 | 159 | 159 | 102 | 24 | Job: 8102 - NCSX MIE Management ORNL-LYON | -5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5
8202 | Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | 2649 |  |  |  |  | 476 | 665 | 663 | 660 | 185 |  |  | Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | 2658 |  |  |  |  | 484 | 666 | 663 | 661 | 185 | Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | -9 | 0 | 0 | 0 | 0 | -8 | -1 | 0 | -1 | 0
8203 | Job: 8203 - Design Integration-BROWN | 1408 |  |  |  |  | 160 | 377 | 376 | 374 | 121 |  |  | Job: 8203 - Design Integration-BROWN | 1411 |  |  |  |  | 160 | 378 | 376 | 375 | 121 | Job: 8203 - Design Integration-BROWN | -3 | 0 | 0 | 0 | 0 | 0 | -1 | 0 | -1 | 0
8204 | Job: 8204 - Systems Analysis-BROOKS | 1154 |  |  |  |  | 181 | 295 | 293 | 292 | 93 |  |  | Job: 8204 - Systems Analysis-BROOKS | 1161 |  |  |  |  | 177 | 283 | 282 | 281 | 138 | Job: 8204 - Systems Analysis-BROOKS | -7 | 0 | 0 | 0 | 0 | 4 | 12 | 11 | 11 | -45
8205 | Job: 8205 - Dimensional Control Coordin-ELLIS | 598 |  |  |  |  | 102 | 266 | 162 | 56 | 12 |  |  | Job: 8205 - Dimensional Control Coordin-REIERSEN | 599 |  |  |  |  | 104 | 264 | 160 | 57 | 14 | Job: 8205 - Dimensional Control Coordin-REIERSEN | -1 | 0 | 0 | 0 | 0 | -2 | 2 | 2 | -1 | -2
8210 | Job: 8210 - FY07 Rebaseling tasks | 19 |  |  |  |  | 19 | [6 empty] | Job: 8210 - FY07 Rebaseling tasks | 19 |  |  |  |  | 19 |  |  |  |  | Job: 8210 - FY07 Rebaseling tasks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8215 | Job: 8215 Plant Design | 121 |  |  |  |  | 15 | 32 | 32 | 32 | 10 |  |  | Job: 8215 Plant Design | 121 |  |  |  |  | 15 | 32 | 32 | 32 | 10 | Job: 8215 Plant Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8501 | Job: 8501 - Integrated Systems Testing-GENTILE | 765 | [6 empty] | 276 | 70 | 419 |  |  | Job: 8501 - Integrated Systems Testing-GENTILE | 765 | [6 empty] | 276 | 70 | 419 | Job: 8501 - Integrated Systems Testing-GENTILE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8998 | Job: 8998 - Allocations-STRYKOWSKY | 1453 |  |  |  |  | 144 | 384 | 406 | 431 | 88 |  |  | Job: 8998 - Allocations-STRYKOWSKY | 1457 |  |  |  |  | 147 | 384 | 406 | 431 | 88 | Job: 8998 - Allocations-STRYKOWSKY | -4 | 0 | 0 | 0 | 0 | -3 | 0 | 0 | 0 | 0
| ETC (from May1st 2007)= | 50854 |  |  |  |  | 6120 | 14483 | 15068 | 12581 | 2602 |  |  | ETC (from May1st 2007)= | 50487 |  |  |  |  | 6468 | 13881 | 14483 | 12598 | 3054 | ETC (from May1st 2007)= | 367 | 0 | 0 | 0 | 0 | -348 | 602 | 585 | -17 | -452
| Contingency = | 14380 | 28.28% |  |  |  | 144 | 2205 | 3492 | 4450 | 4089 |  |  | Contingency = | 11765 | 23.3% |  |  |  | 390 | 2050 | 3720 | 3305 | 2300 | Contingency = | 2615 | 0.04974 | 0 | 0 | 0 | -246 | 155 | -228 | 1145 | 1789
[8 empty] | 15.22% | 23.17% | 35.37% | 157.1% | [8 empty] | 6.03% | 14.77% | 25.69% | 26.23% | 75.31% | [6 empty] | 0.060297 | 0.14768 | 0.25685 | 0.26234 | 0.75311
[6 empty] | Probabilistic range = | 0% | 11%-20% | 17%-24% | 34%-42% | 116%-161% | [8 empty] | Gruber range = | 9%-17% | 21% | 28% | [7 empty] | Gruber range = | 9%-17% | 0.21 | 0.28
| Actual Cost (through April 30th)= | 67178.41 | 5941.92 | 14314.35 | 18131.61 | 19072.81 | 9717.72 | [6 empty] | Actual Cost (through April 30th)= | 67306 | 5942 | 14314 | 18132 | 19073 | 9845 |  |  |  |  | Actual Cost (through April 30th)= | -127.59 | -0.08 | 0.35 | -0.39 | -0.19 | -127.28 | 0 | 0 | 0 | 0
| EAC = | 132412.41 | 5942.2028 | 14314.35 | 18131.61 | 19072.81 | 15981.72 | 16688 | 18560 | 17031 | 6691 | 132412.6928 | 132412.6928 | EAC = | 129558 | 5942.233 | 14314 | 18132 | 19073 | 16703 | 15931 | 18203 | 15903 | 5354 | EAC = | 2854.41 | -0.03026 | 0.35 | -0.39 | -0.19 | -721.28 | 757 | 357 | 1128 | 1337
0
| MIE Funding = | [5 empty] | 16771 | 15900 | 18560 | 17031 | 6691 |  | 74953 | Funding = | [5 empty] | 16771 | 15900 | 18200 | 18900 | 19500 | Funding = | [5 empty] | 16771 | 15900 | 18200 | 18900 | 19500
| Research Funding = | [5 empty] | 680 | 720 | 740 | 2269 | 12609
| TOTAL PROGRAM FUNDING = | [5 empty] | 17451 | 16620 | 19300 | 19300 | 19300
0
0
| PPPL | [11 empty] | 0 | PPPL | [10 empty] | PPPL
| Plan with all contingency = | 118382 | 4796 | 11467 | 15971 | 17297 | 13974 | 14829 | 17261 | 16308 | 6479 | 132412 | 118382 | Plan with all contingency = | 115398 | 4796 | 11467 | 15971 | 17297 | 14612 | 14220 | 16818 | 15148 | 5069 | Plan with all contingency = | 2984 | 0 | 0 | 0 | 0 | -638 | 609 | 443 | 1160 | 1410
| Funding*= | [5 empty] | 14902 | 14950 |  |  |  |  | 29852 | Funding= | [5 empty] | 15152 | 14950 |  |  |  | Funding= | [5 empty] | 15152 | 14950
| ORNL | [11 empty] | 0 | ORNL | [10 empty] | ORNL
| Plan= | 14030 | 1146 | 2847 | 2161 | 1776 | 2090 | 1776 | 1299 | 723 | 212 |  | 14030 | Plan= | 14159 | 1146 | 2847 | 2161 | 1776 | 2091 | 1712 | 1386 | 753 | 287 | Plan= | -129 | 0 | 0 | 0 | 0 | -1 | 64 | -87 | -30 | -75
| Funding*= | [5 empty] | 1869 | 950 |  |  |  |  | 2819 | Funding= | [5 empty] | 1619 | 950 |  |  |  | Funding= | [5 empty] | 1619 | 950
[7 empty] | 16064 | 16605 | 18560 | 17031 | 6691
[7 empty] | 82.28 | -83 | 0 | 0 | 0
|  | * = includes FY06 carryover plus Sept2007 fin plan change request | [10 empty] | 0
|  |  | Planned Finish = | 2011-01-31 | [8 empty] | 40574 |  |  | Planned Finish = | Feb 2011 | [9 empty] | Planned Finish = | Feb 2011
|  |  | CD-4= | 2011-12-31 | [8 empty] | 40908 |  |  | CD-4= | Jan 2012 | [9 empty] | CD-4= | Jan 2012
|  |  | Schedule Contingency = | 10.9832 | months | [10 empty] | Schedule Contingency = | 11 mos. | [9 empty] | Schedule Contingency = | 11 mos.
|  |  | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | FY2009 | FY2010 | FY2011
|  | BCWS = | 5942.2028 | 14314.35 | 18131.61 | 19072.81 | 15837.72 | 14483 | 15068 | 12581 | 2602
|  | Contingency | FY2007: 144; FY2008: 2205; FY2009: 3492; FY2010: 4450; FY2011: 4089
|  | EAC | 5942.2028 | 14314.35 | 18131.61 | 19072.81 | 15981.72 | 16688 | 18560 | 17031 | 6691
|  | Funding (BA) | FY2007: 16771; FY2008: 15900; FY2009: 18560
[6 empty] | Planned Finish = | 2011-01-31
[6 empty] | CD-4= | 2011-12-31
[6 empty] | Schedule Contingency = | 10.9832
| 12 | 156 | FY2004: 12; FY2005: 0
| 13 | 3462 | FY2004: 13; FY2005: 0
| 14 | 6247 | FY2004: 14; FY2005: 0
| 15 | 1262 | FY2004: 15; FY2005: 0
| 16 | 861 | FY2004: 16; FY2005: 0
| 17 | 784 | FY2004: 17; FY2005: 0
| 18 | 10104 | FY2004: 18; FY2005: 0
| 19 | 1620 | FY2004: 19; FY2005: 0
| 2 | 241 | FY2004: 2; FY2005: 0
| 3 | 717 | FY2004: 3; FY2005: 0
| 4 | 2425 | FY2004: 4; FY2005: 0
| 5 | 1136 | FY2004: 5; FY2005: 0
| 6 | 1379 | FY2004: 6; FY2005: 0
| 7 | 7951 | FY2004: 7; FY2005: 0
| 8 | 12509 | FY2004: 8; FY2005: 0
50854
| 12 | 156
| 13 | 3462
| 14 | 6247
| 15 | 1262
| 16 | 861
| 17 | 784
| 18 | 10104
| 19 | 1620 | FY2003: 24496
| 2 | 241
| 3 | 717
| 4 | 2425
| 5 | 1136
| 6 | 1379
| 7 | 7951
| 8 | 11056
| a | 1453
50854