## est sheet
NCSX VACUUM LINER COST ALGORITHM - 2/22/01
Includes estimates back from graphite manufacturer
All material costs are direct FY-99$. LAB & S/C labor fully loaded.
Units are in inches, dollars, and lbs
Ra | mean radius of torus |  |  | NA
N | number of periods |  |  | 3 |  | (Assy) | [6 empty] | Tile Average Sizes
ni | liner fabricated pieces per half-period |  |  | 4 |  | Ka | Pre-assy /dis-assy reqd or not(1,0) |  |  | 0
S | liner surface area |  |  | 63000 |  | Wi | lab labor cost/hr |  |  | 100 |  |  | St = |  |  | poloidal dimen of tile
| torus |  |  |  |  | Zi | inconel cost/lb |  |  | 7.75 |  |  | bt = |  |  | toroidal width of tile
t | liner (VV) thickness |  |  | 0.375 |  | Ai | cost of programming NC tapes(Ea) |  |  | 400 |  |  | At = | 500 |  | area of average tile
b | rib lateral thickness |  |  | 0.375 |  | La | purchased fab/labor cost/hr |  |  | 60 |  |  | Nt = | 42 |  | number of tiles per period
a | rib radial thickness |  |  | 1.25 |  | pi | p |  |  | 3.14
np | number of acess ports |  |  |  |  | We | welding time per inch |  |  | 0.072
pc | density of copper |  |  | 0.323 |  | Ci | graphite cost per lb |  |  | 11 |  |  | Engineering Dwg Tile Assy's
K(welded) | component used,1 |  |  | 1 |  | CCi | carbon carbon cost per lb |  |  | 746 |  |  | x = | 29 |  |  |  | 20.8989 | w/cm^2
| component not used,0 |  |  |  |  | Zh | hardware cost per lb(SS) |  |  | 10
Ki(PFCs) | component used,1 |  |  | 0 |  | Zc | copper cost per lb |  |  | 2
| component not used,0 |  |  |  |  | p | density of material(incon.) |  |  | 0.305
[6 empty] | MATERIAL |  | NC TAPE |  | MACHINING/FABRICATION |  |  | WELDING |  |  | ENGINEERING |  | TOTAL
[5 empty] | WEIGHT | TOTAL | SUBTOTAL |  | FAB TIME | FAB TIME | SUBTOTAL | [6 empty] | COST
|  |  | AREA | VOLUME | Ea | WT | MATL COST |  | Ea | TOTAL | FAB COST | TOTAL | COST | TESTING | Title 1 | Detail | Analysis
Description | WBS |  | in^2 | in^3 | lbs | lbs | $ | $ | hrs | hrs | $ | INCH | $ | $ | HOURS | HOURS | HOURS | $
• Modular coils | 121 | Liner Assy | [12 empty] | 500 |  | 100000 | 100500
• Inconel vacuum vessel |  | Vessel period mating flgs |  |  | 183 | 1098 | 8509.5 |  | 100 | 600 | 36000 |  |  |  |  | 240 |  | 44749.5
• LI-383 plasma |  | Mounting hardware | NA | NA | NA | 67.5 | 675 | 0 | NA | NA | 0 | NA | 0 | 0 |  | 0 |  | 675
• 3 periods |  | Vessel supports | NA | NA | NA | 450 | 3487.5 | 0 | NA | 621 | 37260 | NA | 0 | 0 |  | 500 |  | 41247.5
• Cryo enclosure |  | Thermal blankets | 89000 | 89000 | NA | 618.0556 | 12361.1111 | 0 | NA | 900 | 90000 | 0 | 0 | 0 |  | 666.6667 |  | 103027.7778
Welded Vessel Shell
|  | dies(4 reqd) | NA | NA | NA | NA | 0 | 2400 | 1000 | 4000 | 240000 | 0 | 0 | 10000 |  | 920 |  | 253320
|  | press blanks | 2625 | 984.375 | 300.2344 | 7205.625 | 55843.5938 | 0 | 440 | 10560 | 633600 | 0 | 0 | 0 |  |  |  | 689443.5938
|  | assy into periods | NA | NA | NA | NA | 0 | 0 | 80 | 1920 | 115200 | 0 | 0 | 0 |  |  |  | 115200
|  | fixturing | NA | NA | NA | Na | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 |  |  |  | 60000
1212060
Estimate Basis | 122 | Access Ports | NA | NA | 0 | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 800 |  | 800
• PFCs molded carbon, baked to 350 C, mounted on ring frames. 50% cverage initially |  | Port interface, flgs, bellows, tracing, etc. | NA | NA | Na | 4620.375 | 35807.9062 | 0 | 10 | 0 | 0 | 0 | 0 | 0 |  | 800 |  | 36607.9062
• Vessel maintained at 150 C.
• No separate limiters |  | Diagnostic ports | 60 | ea | NA | NA | 0 | 0 | 24 | 1440 | 86400 | 0 | 0 | 0 |  | 2000 |  | 88400
• No separate NB targets |  |  | 24 | ea |  |  | 0 |  | 32 | 768 | 46080 | [6 empty] | 46080
•Tracing welded onto vessel |  |  | 6 | ea |  |  | 0 |  | 40 | 240 | 14400 | [6 empty] | 14400
• Vessel pressed formed
• Vessel fabricated in three
subassemblies. | 171 | Vessel Coolant lines | 250 | (gpm) | 6.6667 | 300 | 2325 | 0 | 16 | 720 | 72000 | 0 | 0 | 0 |  | 200 |  | 74525
• Vessel formed in 4 pieces per | [6 empty] | 119009.6111 | 2400 |  |  | 218880 |  | 0 | 10000 | 500 | 6126.6667 | 100000
half-period(24 total pieces) | [15 empty] | sub | 106626.6667 |  | 106626.6667
• 90 "add-on" ports
•Three large access port covers | 151 | Limiters(toroidal fixed) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | 0 | 0
|  | Mounts | 0 | 0 | NA | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 |  | 0
|  | Limiters(poloid. Mov.) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 |  |  | 0 | 0 | 0
|  | Mounts | NA |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
[7 empty] | 0 |  |  |  | 0
| 131 | NB armor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | 0 | 0
|  | Brackets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0
| 111 | PFC
| Tiles | dies(21 reqd) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  | 0
|  | mold 100% of tiles | NA | NA | 0 | 0 | 0 | 0 | 0 | 0 | 2970000 | NA | 0 | 0 | 320 | 7080 | 1800 | 2979200
| Mounts | ribs(21 reqd) 7 styles | NA | 196.8 | 60.024 | 1260.504 | 9768.906 | 5000 | 331.3325 | 1987.9949 | 119279.6928 | 0 | 0 |  | 320 | 2240 |  | 136608.5988
|  | bracket plates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 560 |  | 560
| Thermal | heat/cool tracing headers | NA | Na | Na | NA | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  | 0
|  | heat shields(ss) | 126000 | 630 | NA | 0 | 0 | [8 empty] | 0 |  | 0
| Liner | liner mount studs | 336 | ea | Na | NA | 3360 | 2400 | 0 | 0 | 0 | NA | 40320 | 0 | 0 | 200 |  | 46280
| Install. | install 100% of tiles/100% of peripherals | [6 empty] | 80 | 2240 | 224000 | [6 empty] | 224000 | 3386648.5988
[7 empty] | 13128.906 | 7400 |  |  | 3313279.6928 |  | 40320 |  | 640 | 10080 | 1800
[16 empty] | sub | 12520
|  | Pre/Dis-Assy | NA | NA | NA | NA | 0 | 0 | NA | 0 | 0 | NA | 0 | 0 | 0 | 0 | 0 | 0
|  | Liner Assy | NA | NA | NA | NA | 30000 | 0 | 0 | 3000 | 300000 | 462 | 6652.8 | 33000 | 0 | 0 | 0 | 369652.8
|  | PFC R&D | NA | NA | NA | NA | 40000 | 0 | NA | 480 | 48000 | NA | 0 | 0 | 0 | 62000 | 0 | 150000
[6 empty] | 15620.0596 | 202138.5171 | 9800 |  | FAB | 5092219.6928 |  | 46972.8 | 43000 | 1140 | 78206.6667 | 101800 |  | 5575277.6766
[5 empty] | liner wt | [11 empty] | 181146.6667
COST SUMMARY |  | Notes | K$ | % Budget | [10 empty] | GRAND TOTAL |  |  | 5575277.6766
(no contingency)
Engineering | Design (title 1&2)excludes PFCs |  | -10062.6533 | -107.1695
| Analysis |  | 100 | 1.065 | -9962.6533
Vessel fab | Welded lvessel shell |  | 1084.8 | 11.5534
| Ports |  | 146.88 | 1.5643
| Support structure |  | 37.26 | 0.39683
| Blankets |  | 90 | 0.95852
| Coolant lines |  | 72 | 0.76682 | 1430.94
Material | Excluding R&D &PFCs |  | 149.0096 | 1.587
Testing | Leak,welding |  | 43 | 0.45796
PFC | Design PFCs |  | 10080 | 107.3542
| Analysis |  | 1800 | 19.1704
| Weld on mount studs |  | 40.32 | 0.42942
| Material |  | 13.1289 | 0.13983
| Fab PFCs and ribs(100%) |  | 3089.2797 | 32.9015
| Install PFCs and ribs (100%) |  | 2240 | 23.8565 | 17262.7286
NB | NB armor(includes design) |  | 0 | 0
Limiters | Limiters(includes design) |  | 0 | 0
Installation | Vessel Installation/assy |  | 306.6528 | 3.2659
NC tapes |  |  | 9.8 | 0.10437
R&D | R&D with Engr and matl |  | 150 | 1.5975
|  | Total | 9389.4777 | 100

## summary
Assumptions
PFCs are molded C-C tiles based on concept developed with BFGoodrich.
PFCs are attached to uncooled ribs stud-welded to interior of VV
PFCs are cooled by radiation to the cooled vacuum vessel. Hotter tiles also radiate to cooler tiles
100 % coverage of molded tiles, no separate limiters of NB armor
|  | $k |  | comment
| Design PFCs | 10080 | hours | 2 manyears + 120 hours per tile type+320 hrs per rib+5 weeks for stud layout
| Analysis | 1800 | hours | 1 man-year
| Weld on mount studs | 40.32 | $k | 2 hours per stud to locate and weld
| Material | 13.1289 | $k | studs and ribs only
| Fab PFCs and ribs(100%) | 3089.2797 | $k | material included in procurement
| Install PFCs and ribs (100%) | 2240 | hours
|  | year 1 |  | year 2 | year 3 | year 4
Design / analysis
Procure
Install
| NBI armor only | 30% | coverage
comment
| Design PFCs | 10080 | hours | 2 manyears + 120 hours per tile type+320 hrs per rib+5 weeks for stud layout (3600 engr 6500 dsn)
| Analysis | 1800 | hours | 1 man-year
| Weld on mount studs | 12.096 | $k | 2 hours per stud to locate and weld
| Material | 3.9387 | $k | studs and ribs only
| Fab PFCs and ribs(100%) | 926.7839 | $k | material included in procurement
| Install PFCs and ribs (100%) | 672 | hours