## Main
NCSX WBS 4 UPGRADE ESTIMATE (080206) | [12 empty] | M&S | [5 empty] | Design/ Procurement |  | Installation |  |  |  | Commissioning |  |  | Line Total | Contingency |  |  |  | Total Cost
[6 empty] | Start date | Finish date | Multiplier | Qnty | Units | Qnty | Units | Qnty | Units | Unit Cost | Cost | Spare Units | Spare Cost | EEEM | Dm | EEEM | EESM | EETB | SC | EEEM | EESM | EETB |  | Tech | Cost | Schedule | Total
[15 empty] | (k$/unit) | ($K) |  | ($K) | (md) | (md) | (md) | (md) | (md) | ($K) | (md) | (md) | (md) | ($K) | (%) | (%) | (%) | (%) | ($K)
41- AC Power | 410.776 | 484.7157
| 411 - Auxiliary AC Power | 335.528 | 395.923
|  |  | Test Cell AC Power Distribution |  |  |  |  | 1 |  |  |  |  | 3 | lot | 8 | 24 |  | 0 | 10 | 25 | 5 | 10 | 30 |  | 2 | 6 | 12 | 121.648 | 8 | 8 | 2 | 18 | 143.5446
|  |  | Ex-Test Cell AC Power Distribution |  | Reactivate/new installation |  |  | 1 |  |  |  |  | 3 | xfmr/ panel | 3 | 9 |  | 0 | 10 | 15 | 15 | 20 | 30 |  | 10 | 10 | 20 | 138 | 8 | 8 | 2 | 18 | 162.84
|  |  | Standby Power for Cryo systems |  | UPS Systems |  |  | 1
|  |  | Grounding |  | Misc. grounding |  |  | 1 |  |  |  |  | 1 | lot | 3 | 3 |  | 3 | 5 | 10 | 5 | 10 | 30 |  | 5 | 5 | 10 | 75.88 | 8 | 8 | 2 | 18 | 89.5384
| 412 - Experimental AC Power | 75.248 | 88.7926
|  |  | D-site Pulsed AC Power Distribution |  | Lockouts/protection/reactivate |  |  | 1 |  |  |  |  | 1 | lot | 5 | 5 |  | 0 | 5 | 5 | 2 | 8 | 10 |  | 3 | 3 | 5 | 46.344 | 8 | 8 | 2 | 18 | 54.6859
|  |  | D-site Pulsed AC Power Distribution |  | Lockouts/protection/reactivate |  |  | 1 |  |  |  |  | 1 | lot | 3 | 3 |  | 0 | 3 | 3 | 1 | 5 | 6 |  | 2 | 2 | 4 | 28.904 | 8 | 8 | 2 | 18 | 34.1067
42 - AC/DC Converters | 67.548 | 79.7066
| 421 - C-site AC/DC Converters | 0 | 0
0
| 422 - D-site AC/DC Converters | 67.548 | 79.7066 |  |  |  |  | 1 | [24 empty] | 0
|  |  | Coil Power Supplies | Transrex PS Maintenance | Reactivation |  |  | 1 |  |  |  |  | 10 | PSS | 0.5 | 5 |  | 0 | 0.5 | 1 | 0 | 0 | 0 |  | 15 | 15 | 35 | 67.548 | 8 | 8 | 2 | 18 | 79.7066
43 - DC Systems | 4342.864 | 5421.3485
| 431 - C-site DC Systems | 1055.688 | 1244.8392
|  |  | Coil DC Cabling from Disconnect/Link Box (PCTB) | Design & Supervision |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 15; Design/ Procurement Dm: 60; Installation EEEM: 15; Installation EESM: 15; Installation EETB: 15 | 121.68 | 8 | 8 | 2 | 18 | 143.5824
|  |  |  | Materials/ Installation | Reroute & Reconnect in OH Bldg |  |  | 1 | 26 | Cable | [8 empty] | Installation SC: 310 | 396.8 | 8 | 8 | 2 | 18 | 468.224
|  |  |  | Materials / Installation | Reroute & Reconnect in MG Basement |  |  | 1 | 26 | Cable | [8 empty] | Installation SC: 195 | 249.6 | 8 | 8 | 2 | 18 | 294.528
[5 empty] | Cable Tray |  |  | 1 |  |  |  |  | 50 | ft | 0.05 | 2.5 |  | 0 | Design/ Procurement EEEM: 2; Design/ Procurement Dm: 4 | 9.552 | 8 | 8 | 2 | 18 | 11.2714
[5 empty] | Install Tray |  |  | 1 |  |  |  |  | 50 | ft | 0.05 | 2.5 |  | 0 | [9 empty] | 3.2 | 8 | 8 | 2 | 18 | 3.776
|  |  | DC Cabling to Trim Coils | Design & Supervision |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 5; Design/ Procurement Dm: 10; Installation EEEM: 5; Installation EESM: 5; Installation EETB: 5 | 31.36 | 8 | 8 | 2 | 18 | 37.0048
|  |  |  | Materials & Installation | 250MCM 5kV Cable For Circuit |  |  | 1 | 1 | Ckt | 150 | ft/ckt | 150 | ft | 0.012 | 1.8 |  | 0 | Installation SC: 20 | 27.904 | 8 | 8 | 2 | 18 | 32.9267
[5 empty] | Install Cable |  |  | 1 | 1 | Ckt | 150 | ft/ckt | 150 | ft | 0.055 | 8.25 |  | 0 | [9 empty] | 10.56 | 8 | 8 | 2 | 18 | 12.4608
[5 empty] | Cable Tray |  |  | 1 |  |  |  |  | 100 | ft | 0.012 | 1.2 |  | 0 | Design/ Procurement EEEM: 2; Design/ Procurement Dm: 4 | 7.888 | 2 | 8 | 2 | 12 | 8.8346
[5 empty] | Install Tray |  |  | 1 |  |  |  |  | 100 | ft | 0.012 | 1.2 |  | 0 | Installation SC: 4 | 6.656 | 2 | 8 | 2 | 12 | 7.4547
|  |  | Repositioning Switches in Test Cell Basment | Design & Supervision |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 15; Design/ Procurement Dm: 40; Installation EEEM: 10; Installation EESM: 10; Installation EETB: 10 | 87.8 | 8 | 8 | 2 | 18 | 103.604
|  |  |  | Materials & Installation | Switches |  |  | 1 | 4 | Ckt | [5 empty] | 3 |  | 0 | 2 | 10 | 2 | 10 | 10 | 12 |  |  |  | 51.344 | 8 | 8 | 2 | 18 | 60.5859
|  |  |  | Materials & Installation | Switch controls/ cabling |  |  | 1 | 4 | Ckt | [5 empty] | 3 |  | 0 | 2 | 10 | 2 | 10 | 10 | 12 |  |  |  | 51.344 | 8 | 8 | 2 | 18 | 60.5859
| 432 - D-to-C-Site DC Systems | 2453.824 | 3188.9427
|  |  | DC Cabling | Design & Supervision |  |  |  | 1 | [7 empty] | 0 |  | 0 | 30 | 60 | 30 | 30 | 40 |  | 10 | 20 | 20 | 243.28 | 8 | 8 | 2 | 18 | 287.0704
[5 empty] | Structural Supports design |  |  | 1 |  |  |  |  | 1 | lot |  |  |  | 0 | Installation SC: 60 | 76.8 | 8 | 20 | 2 | 30 | 99.84
[5 empty] | Facilities efforts |  |  | 1 |  |  |  |  | 1 | lot |  | 2 |  | 0 | 3 | 5 | 6 | 4 | 5 | 5 | 2 | 2 | 2 | 39.472 | 8 | 20 | 2 | 30 | 51.3136
[5 empty] | Structural Supports |  |  | 1 |  |  |  |  | 1 | lot |  |  |  | 0 | Installation SC: 650; Commissioning EEEM: 2; Commissioning EESM: 2; Commissioning EETB: 2 | 838.192 | 8 | 30 | 2 | 40 | 1173.4688
[5 empty] | Install tray with Supports |  |  | 1 |  |  |  |  | 1 | lot |  |  |  | 0 | Installation SC: 260 | 332.8 | 8 | 30 | 2 | 40 | 465.92
|  |  |  | Materials & Installation | 1000MCM 5kV Cable |  |  | 1 | 7 | ckt | 620 | ft/ckt | 4340 | ft | 0.05 | 217 |  | 0 | Design/ Procurement EEEM: 5; Design/ Procurement Dm: 10 | 293.64 | 8 | 8 | 2 | 18 | 346.4952
[5 empty] | Install Cable Outdoors |  |  | 1 | 7 | ckt | 620 | ft/ckt | 4340 | ft |  | 10 |  | 0 | 5 | 20 | 10 | 30 | 40 | 120 | 10 | 8 | 16 | 296.888 | 8 | 12 | 2 | 22 | 362.2034
[5 empty] | Pull & Install trays& Cables indoors D-Site from Transmission line to NCSX SDS |  |  | 1 | 7 | ckt | 100 | ft/ckt | 700 | ft | 0.025 | 17.5 |  | 0 | Installation SC: 80 | 124.8 | 8 | 12 | 2 | 22 | 152.256
[5 empty] | Install traus & Cable indoors from Transmission to PCTB |  |  | 1 | 7 | ckt | 100 | ft/ckt | 700 | ft | 0.025 | 17.5 |  | 0 | Installation SC: 80 | 124.8 | 8 | 12 | 2 | 22 | 152.256
[5 empty] | Cable Tray |  |  | 1 |  |  |  |  | 600 | ft | 0.05 | 30 |  | 0 | Design/ Procurement EEEM: 2; Design/ Procurement Dm: 4 | 44.752 | 8 | 8 | 2 | 18 | 52.8074
[5 empty] | Install Tray |  |  | 1 |  |  |  |  | 600 | ft | 0.05 | 30 |  | 0 | [9 empty] | 38.4 | 8 | 8 | 2 | 18 | 45.312
| 433 - D-site DC Systems | 833.352 | 987.5666
|  |  | DC Cabling | Design & Supervision |  |  |  | 1 | [7 empty] | 0 |  | 0 | 15 | 50 | 15 | 15 | 15 |  | 10 | 10 | 20 | 150 | 8 | 8 | 2 | 18 | 177
|  |  |  | Materials & Installation | 1000MCM 5kV Cable For PSS |  |  | 1 | 7 | PSS | 100 | ft/PSS | 700 | ft | 0.025 | 17.5 |  | 0 | Design/ Procurement EEEM: 5 | 29.08 | 8 | 8 | 2 | 18 | 34.3144
[5 empty] | Install Cable indoors D-Site from NCSX SDS to NSTX SDS |  |  | 1 | 7 | ckt | 70 | ft/ckt | 490 | ft | 0.025 | 12.25 |  | 0 | Installation SC: 70 | 105.28 | 8 | 12 | 2 | 22 | 128.4416
[5 empty] | Cable Tray |  |  | 1 |  |  |  |  | 200 | ft | 0.05 | 10 |  | 0 | Design/ Procurement EEEM: 2; Design/ Procurement Dm: 4 | 19.152 | 8 | 8 | 2 | 18 | 22.5994
[5 empty] | Install Tray |  |  | 1 |  |  |  |  | 200 | ft | 0.05 | 10 |  | 0 | Design/ Procurement EEEM: 2; Design/ Procurement Dm: 4 | 19.152 | 8 | 8 | 2 | 18 | 22.5994
|  |  | NSTX TF Power Supply changes | Task of NSTX TF PS changes |  |  |  | 1 | [7 empty] | 5 |  | 0 | 6 | 12 | 2 | 5 | 30 | 60 | 1 | 1 | 2 | 133.88 | 8 | 8 | 2 | 18 | 157.9784
|  |  | NSTX OH PS changes | Task of NSTX OH PS changes |  |  |  | 1 | [7 empty] | 5 |  | 0 | 6 | 12 | 2 | 5 | 30 | 65 | 1 | 1 | 2 | 140.28 | 8 | 8 | 2 | 18 | 165.5304
|  |  | Isolating Switch | Design & Specification |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 5; Design/ Procurement Dm: 5 | 11.28 | 8 | 8 | 2 | 18 | 13.3104
|  |  |  | Procurement |  |  |  | 1 |  |  |  |  | 5 | switch | 19 | 95 |  | 0 | [9 empty] | 121.6 | 8 | 8 | 2 | 18 | 143.488
|  |  |  | Installation |  |  |  | 1 | [7 empty] | 2 |  | 0 |  |  | 5 | 10 | 10 | 50 | 3 | 5 | 5 | 103.648 | 8 | 8 | 2 | 18 | 122.3046
44 - Control & Protection Systems | 1842.935 | 2195.4057
| 441 - Electrical Interlocks | 611.0736 | 724.928
|  |  | C-site | Design Interlock System |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 15; Design/ Procurement Dm: 25; Installation EEEM: 8; Installation EESM: 15; Installation EETB: 40 | 96.528 | 12 | 8 | 2 | 22 | 117.7642
|  |  |  | Procure PLC | 1 + 1 spare |  |  | 1 |  |  |  |  | 1 | units | 10 | 10 | 1 | 10 | Design/ Procurement EEEM: 10; Design/ Procurement Dm: 20; Installation EEEM: 5; Installation EESM: 5; Installation EETB: 10 | 63.32 | 8 | 8 | 2 | 18 | 74.7176
|  |  |  | Procure I/O |  |  |  | 1 |  |  |  |  | 80 | channels | 0.012 | 0.96 |  | 0 | Design/ Procurement EEEM: 10; Design/ Procurement Dm: 10; Installation EEEM: 10; Installation EESM: 5; Installation EETB: 5 | 45.9488 | 8 | 8 | 2 | 18 | 54.2196
|  |  |  | Program PLC |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 10; Design/ Procurement Dm: 5; Installation EEEM: 5; Installation EESM: 5; Installation EETB: 10 | 36.72 | 8 | 8 | 2 | 18 | 43.3296
|  |  |  | Crate & PS |  |  |  | 1 |  |  |  |  | 1 | units | 1 | 1 |  | 0 | Design/ Procurement EEEM: 10; Installation EEEM: 5; Installation EESM: 5; Installation EETB: 10 | 33.4 | 8 | 8 | 2 | 18 | 39.412
|  |  |  | Install I/O & Cabling |  |  |  | 1 |  |  |  |  | 1 | units | 8 | 8 |  | 0 | Installation EESM: 5; Installation EETB: 50 | 48.56 | 8 | 8 | 2 | 18 | 57.3008
|  |  | D-to-C-site | Design Interconnection |  |  |  | 1 |  |  |  |  | 1 | lot | 5 | 5 |  | 0 | 10 | 15 | 5 | 5 | 20 |  | 5 | 5 | 10 | 77.64 | 8 | 8 | 2 | 18 | 91.6152
|  |  | D-site | Design Interlock System |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 10; Design/ Procurement Dm: 15; Installation EEEM: 5; Installation EESM: 10; Installation EETB: 30 | 64.56 | 8 | 8 | 2 | 18 | 76.1808
|  |  |  | Procure PLC |  |  |  | 1 |  |  |  |  | 1 | units | 10 | 10 |  | 0 | Design/ Procurement EEEM: 3; Design/ Procurement Dm: 8; Installation EEEM: 0; Installation EESM: 0; Installation EETB: 0 | 24.168 | 8 | 8 | 2 | 18 | 28.5182
|  |  |  | Procure I/O |  |  |  | 1 |  |  |  |  | 80 | channels | 0.012 | 0.96 |  | 0 | Design/ Procurement EEEM: 0; Design/ Procurement Dm: 0; Installation EEEM: 0; Installation EESM: 0; Installation EETB: 0 | 1.2288 | 8 | 8 | 2 | 18 | 1.45
|  |  |  | Program PLC |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 10; Design/ Procurement Dm: 5; Installation EEEM: 5; Installation EESM: 5; Installation EETB: 5 | 33.44 | 8 | 8 | 2 | 18 | 39.4592
|  |  |  | Crate & PS |  |  |  | 1 |  |  |  |  | 1 | units | 1 | 1 |  | 0 | Design/ Procurement EEEM: 10; Installation EEEM: 5; Installation EESM: 5; Installation EETB: 5 | 30.12 | 8 | 8 | 2 | 18 | 35.5416
|  |  |  | Install I/O & Cabling |  |  |  | 1 |  |  |  |  | 1 | units | 2 | 2 |  | 0 | Installation EESM: 5; Installation EETB: 15 | 17.92 | 8 | 8 | 2 | 18 | 21.1456
|  |  |  | Test Modified NSTX HCS |  |  |  | 1 | [7 empty] | 0 |  | 0 | Commissioning EEEM: 10; Commissioning EESM: 10; Commissioning EETB: 20 | 37.52 | 8 | 8 | 2 | 18 | 44.2736
| 442 - Kirk Key Interlocks | 101.168 | 119.3782
|  |  |  | Kirk Keys |  |  |  | 1 |  |  |  |  | 1 | lot | 10 | 10 |  | 0 | 15 | 15 | 3 | 5 | 35 |  | 5 | 5 | 15 | 101.168 | 8 | 8 | 2 | 18 | 119.3782
| 443 - Real Time Control | 40.08 | 47.2944
|  |  |  | Develop Control Algorithms |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 30 | 40.08 | 8 | 8 | 2 | 18 | 47.2944
| 444 - Instrumentation | 359.296 | 423.9693
|  |  | DC Current Transducers (DCCTs) |  |  |  |  | 1 |  |  |  |  | 2 | units | 30 | 60 | 1 | 30 | 5 | 10 | 4 | 8 | 35 |  | 3 | 3 | 15 | 146.976 | 8 | 8 | 2 | 18 | 173.4317
|  |  | Signal Conditioning & Associated Cabling |  |  |  |  | 1 |  |  |  |  | 1 | lot | 9 | 9 | 0 | 0 | 35 | 10 | 5 | 0 | 35 |  | 10 | 5 | 5 | 119.28 | 8 | 8 | 2 | 18 | 140.7504
|  |  | DC Potential Transducers (DCPTs) |  |  |  |  | 1 |  |  |  |  | 7 | units | 1 | 7 | 2 | 2 | 10 | 20 | 5 | 5 | 35 |  | 3 | 3 | 15 | 93.04 | 8 | 8 | 2 | 18 | 109.7872
| 445 - Coil Protection | 412.096 | 500.4218
|  |  | Overload Protection & Associated Cabling |  |  |  |  | 1 |  |  |  |  | 7 | units | 4 | 28 | 1 | 4 | 50 | 50 | 10 | 30 | 35 |  | 10 | 4 | 10 | 242.416 | 12 | 8 | 2 | 22 | 295.7475
|  |  | Overtemp Protection & Associated cabling |  |  |  |  | 1 |  |  |  |  | 7 | units | 1.5 | 10.5 | 1 | 1.5 | 10 | 20 | 5 | 20 | 30 |  | 5 | 4 | 10 | 111.296 | 12 | 8 | 2 | 22 | 135.7811
|  |  | Ground Fault Protection |  |  |  |  | 1 |  |  |  |  | 1 | units | 3 | 3 | 1 | 3 | 10 | 10 | 4 | 4 | 15 |  | 4 | 4 | 4 | 58.384 | 8 | 8 | 2 | 18 | 68.8931
| 446 - Ground Fault Monitor | 319.2214 | 379.4141
|  |  | Ground Fault Monitor | Design System |  |  |  | 1 | [7 empty] | 0.5 |  | 0 | Design/ Procurement EEEM: 30; Design/ Procurement Dm: 30 | 68.32 | 12 | 8 | 2 | 22 | 83.3504 |  | 22
|  |  |  | Buy & Fabricate cards |  |  |  | 1 |  |  |  |  | 1 | lot | 70 | 70 |  | 0 | Design/ Procurement EEEM: 2; Design/ Procurement Dm: 2; Installation EEEM: 5; Installation EESM: 10; Installation EETB: 20 | 124.952 | 8 | 8 | 2 | 18 | 147.4434 |  | 18
|  |  |  | Bench Test |  |  |  | 1 |  |  |  |  | 1 | units | 1 | 1 |  | 0 | Design/ Procurement EEEM: 2; Design/ Procurement Dm: 2; Installation EEEM: 5; Installation EESM: 4; Installation EETB: 20 | 30.008 | 8 | 8 | 2 | 18 | 35.4094 |  | 18
|  |  |  | Assemble in Rack |  |  |  | 1 |  |  |  |  | 4 | channels | 0.012 | 0.048 |  | 0 | Design/ Procurement EEEM: 2; Design/ Procurement Dm: 2; Installation EEEM: 5; Installation EESM: 5; Installation EETB: 20 | 29.8934 | 8 | 8 | 2 | 18 | 35.2743 |  | 18
|  |  |  | Program PLC |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 1; Installation EEEM: 5; Installation EESM: 5 | 13.536 | 8 | 8 | 2 | 18 | 15.9725 |  | 18
|  |  |  | Install Equipment & Cabling |  |  |  | 1 |  |  |  |  | 1 | units | 4 | 4 |  | 0 | 5 | 10 | 5 | 5 | 20 |  | 2 | 2 | 2 | 52.512 | 8 | 8 | 2 | 18 | 61.9642 |  | 18
45 - System Design and Integration | 1405.784 | 1729.4581
| 451 - System Design | 325.08 | 383.5944
|  |  | Design Drawings & Drawings changes , as-builts | New drawings & Misc. updates |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 80; Design/ Procurement Dm: 80 | 180.48 | 8 | 8 | 2 | 18 | 212.9664
|  |  | CDR Power system | All power systems |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 5; Design/ Procurement Dm: 5 | 11.28 | 8 | 8 | 2 | 18 | 13.3104
|  |  | PDR Power system | All power systems |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 5; Design/ Procurement Dm: 5 | 11.28 | 8 | 8 | 2 | 18 | 13.3104
|  |  | FDR D-Site | Transrex D-Site |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 5; Design/ Procurement Dm: 5 | 11.28 | 8 | 8 | 2 | 18 | 13.3104
|  |  | FDR C-Site | C-Site |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 5; Design/ Procurement Dm: 5 | 11.28 | 8 | 8 | 2 | 18 | 13.3104
|  |  | FDR Cabling | D site |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 5; Design/ Procurement Dm: 5 | 11.28 | 8 | 8 | 2 | 18 | 13.3104
|  |  | FDR Cabling | C site |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 5; Design/ Procurement Dm: 5 | 11.28 | 8 | 8 | 2 | 18 | 13.3104
|  |  | FDR DC transmission | D-site to C-site |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 5; Design/ Procurement Dm: 5 | 11.28 | 8 | 8 | 2 | 18 | 13.3104
|  |  | FDR AC auxiliaries & grounding | AC Auxiliaries power panels etc., grounding etc. |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 5; Design/ Procurement Dm: 5 | 11.28 | 8 | 8 | 2 | 18 | 13.3104
|  |  | Calculations | Calculations - documentation |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 40; Design/ Procurement Dm: 1 | 54.36 | 8 | 8 | 2 | 18 | 64.1448
| 452 - Electrical Systems Support | 774 | 975.24
|  |  | Diagnostics AC Power Distribution | Based on Input from Diagnostics WBS |  |  |  | 1 |  |  |  |  | 10 | racks | 5 | 50 |  | 0 | 10 | 80 | 10 | 10 | 80 | 40 | 5 | 10 | 50 | 329.56 | 16 | 8 | 2 | 26 | 415.2456
|  |  | Diagnostics sensor cabling | Based on Input from Diagnostics WBS |  |  |  | 1 |  |  |  |  | 100 | cables | 0.2 | 20 |  | 0 | 25 | 100 | 15 | 20 | 100 | 80 | 5 | 10 | 100 | 444.44 | 16 | 8 | 2 | 26 | 559.9944
| 46- FCPCBuilding Modifications | 108.912 | 137.2291
|  | 460-01 | Clear area in West wing from SPS cabinets to HVAC equipment (Elect) | Based on Input from Mech./construction |  |  |  | 1 |  |  |  |  | 1 | lot | 1 | 1 |  | 0 | Design/ Procurement EEEM: 8; Design/ Procurement Dm: 8; Installation EEEM: 2; Installation EESM: 2; Installation EETB: 12 | 32.08 | 16 | 8 | 2 | 26 | 40.4208
|  | 460-02 | Clear the small Vacuum prep lab | Based on Input from Mech./construction |  |  |  | 1 |  |  |  |  | 1 | lot | 0.5 | 0.5 |  | 0 | Installation EETB: 30 | 20.32 | 16 | 8 | 2 | 26 | 25.6032
|  | 460-03 | Mechanical Clearing | Based on Input from Mech./construction |  |  |  | 1 |  |  |  |  | 1 | lot | 2 | 2 |  | 0 | Design/ Procurement EEEM: 2; Design/ Procurement Dm: 2; Installation EEEM: 1; Installation EESM: 2; Installation EETB: 6 | 14.552 | 16 | 8 | 2 | 26 | 18.3355
|  | 460-04 | Floor & Wall Penetrations | Based on Input from Mech. (WBS-610) | 1 Wall penetration & 20 floor penetrations |  |  | 1 |  |  |  |  | 1 | lot | 5 | 5 |  | 0 | 1 | 2 | 4 | 5 | 25 | 4 |  |  |  | 41.96 | 16 | 8 | 2 | 26 | 52.8696
| 453 - System Testing | 197.792 | 233.3946 | [24 empty] | 0
|  |  | Preop Testing |  |  |  |  | 1 | [7 empty] | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 0
|  |  |  | Test Equipment |  |  |  | 1 |  |  |  |  | 1 | lot | 25 | 25 |  | 0 | [9 empty] | 32 | 8 | 8 | 2 | 18 | 37.76
|  |  | Procedures PTPs, ISTPs | New Procedures |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 20; Design/ Procurement Dm: 20 | 45.12 | 8 | 8 | 2 | 18 | 53.2416
|  |  |  | DC Circuit Hipots and Impedance Measurements |  |  |  | 1 | [7 empty] | 0 |  | 0 | Commissioning EEEM: 3; Commissioning EETB: 8 | 9.256 | 8 | 8 | 2 | 18 | 10.9221
|  |  |  | Electrical Interlock Testing |  |  |  | 1 | [7 empty] | 0 |  | 0 | Commissioning EEEM: 3; Commissioning EETB: 8 | 9.256 | 8 | 8 | 2 | 18 | 10.9221
|  |  |  | Kirk Key Interlock Testing |  |  |  | 1 | [7 empty] | 0 |  | 0 | Commissioning EEEM: 2; Commissioning EETB: 3 | 4.64 | 8 | 8 | 2 | 18 | 5.4752
|  |  |  | Instrumentation Test & Calibration |  |  |  | 1 | [7 empty] | 0 |  | 0 | Commissioning EEEM: 2; Commissioning EETB: 2 | 3.984 | 8 | 8 | 2 | 18 | 4.7011
|  |  |  | Real Time Control System Testing |  |  |  | 1 | [7 empty] | 0 |  | 0 | Commissioning EEEM: 3; Commissioning EETB: 3 | 5.976 | 8 | 8 | 2 | 18 | 7.0517
|  |  |  | Coil Protection System Testing |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 20; Commissioning EEEM: 3; Commissioning EETB: 3 | 32.696 | 8 | 8 | 2 | 18 | 38.5813
|  |  |  | Ground Fault Monitor Testing |  |  |  | 1 | [7 empty] | 0 |  | 0 | Commissioning EEEM: 2; Commissioning EETB: 2 | 3.984 | 8 | 8 | 2 | 18 | 4.7011
|  |  |  | Coil Power Supply Dummy Load Testing |  |  |  | 1 |  |  |  |  | 10 | PS |  | 0 |  | 0 | Design/ Procurement EEEM: 0; Commissioning EEEM: 20; Commissioning EESM: 10; Commissioning EETB: 20 | 50.88 | 8 | 8 | 2 | 18 | 60.0384
|  |  | TOTALS | [12 empty] | 898.668 |  | 53.5 | 713.5 | 1000 | 278 | 412 | 1079 | 2177 | 181 | 165 | 460 | 8069.907 |  |  |  |  | 9910.6346
IN MAN HOURS | [18 empty] | 5708 | 8000 | 2224 | 3296 | 8632 |  | 1448 | 1320 | 3680
RATES FY06 | [14 empty] | M&S --> | 898.668 | Spares--> | 53.5 | Installation EETB: SC -->; Installation SC: 2786.56
[28 empty] | ∑MD | Rate | $K | ∑FTE | Years | FTE/yr
EEEM | 1.336 | [14 empty] | 1150.295 |  |  | 1873.236 |  | 1534.08 |  |  | 2786.56 | 725.736 | cross check | EEEM | 1172.5 | 1.336 | 1566.46 | 5.3295 | 4 | 1.3324
EESM | 1.104 | [17 empty] | Commissioning EETB: EESM | 577 | 1.104 | 637.008 | 2.6227 | 2 | 1.3114
EETB | 0.656 | [17 empty] | Design/ Procurement EEEM: 8069.907; Commissioning EETB: EETB | 1539 | 0.656 | 1009.584 | 6.9955 | 2 | 3.4977
G&A (MHX) | 1.28 | [14 empty] | 8069.907 |  |  | Commissioning EETB: EADM | 1000 | 0.92 | 920 | 4.5455 | 3 | 1.5152
DM | 0.92 | [26 empty] | $K
#REF!
|  |  | k$ loaded without contingency | k$ loaded with contingency
4 | Power Systems |  | 8069.907 | 9910.6346 | [11 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | AC Power Systems |  | 410.776 | 484.7157 | 484.7157
| 411 | Auxiliary AC Power Systems | 335.528 | 395.923
| 412 | Experimental AC Power Systems | 75.248 | 88.7926
42 | AC/DC Converters |  | 67.548 | 79.7066 | 79.7066
| 422 | D-Site AC/DC Converters | 67.548 | 79.7066
43 | DC Systems |  | 4342.864 | 5421.3485 | 5421.3485
| 431 | C-Site DC Systems | 1055.688 | 1244.8392
| 432 | D-to-C Site DC Systems | 2453.824 | 3188.9427 | [29 empty] | 9.91
| 433 | D-Site DC Systems | 833.352 | 987.5666
44 | Control & Protection Systems |  | 1842.935 | 2195.4057 | 2195.4057 | [28 empty] | 10.857
| 441 | Electrical Interlocks | 611.0736 | 724.928
| 442 | Kirk Key Interlocks | 101.168 | 119.3782
| 443 | Real Time Control | 40.08 | 47.2944
| 444 | Instrumentation | 359.296 | 423.9693
| 445 | Coil Protection | 412.096 | 500.4218
| 446 | Ground fault Monitor | 319.2214 | 379.4141
45 | Electrical System Design and Integration |  | 1405.784 | 1729.4581 | 1592.229
| 451 | System Design | 325.08 | 383.5944
| 452 | Electrical Systems Support | 774 | 975.24
| 453 | Electrical Systems Support | 197.792 | 233.3946
46 | FCPCBuilding Modifications |  | 108.912 | 137.2291 | 137.2291
Given below are the division of cost of labor & sub-contract without contingency
| k$ | PPPL Labor | Subcontract
Procurement | 1150.295 | 0 | 0
Design | 1873.236 | 1873.236 | 0
Installation | 4320.64 | 1534.08 | 2786.56
Commissioning | 725.736 | 725.736 | 0
Total | 8069.907
Notes:
SCOPE AS OUTLINED IN GRD
1. 10 circuits - PF5U & PF5L also assumed to be fed separately from D-Site
2 Sub-contract estimates based on bids and a projected increase of costs
3. Ground Fault Monitor included
4. Cost in 06 Dollars
5. SCHEDULE WILL AFFECT COST
7. Analog coil protection included
Note on D8: This covers uninteruptible power for critical control and interlock systems and cryo system

## CDR - PDR COMPARISON
NCSX CD-2 Cost Baseline Update Reconciliation
WBS: 4 | Electrical Power Systems | 21
Manager: | Raki Ramakrishnan
|  | CDR Base |  |  |  |  | Revised Estimate |  |  |  |  | Delta's | [7 empty] | Delta's
|  | Estimate $ |  | Cont % | Cont $ | TOTAL $ | Estimate |  | Cont % | Cont $ | TOTAL $ |  | TOTAL $ |  | Cont | Cont % | NSTX w/Cntg |  | Comments
41- AC Power |  | 542 |  |  |  |  | 592.8956 | [5 empty] | 699.6168 |  | 288.8408 | 48.72% | 190
| 411 - Auxiliary AC Power |  | 499 | 17% | 84.83 | 583.83 |  | 335.528 | 18% | 60.395 | 395.923 | -187.907 |  | 570.8273 | 235.2993 | 70.13% |  | 169 | More work to ready C-site test cell and bring C-site infrastructure into operation, compared to D-site
| 412 - Experimental AC Power |  | 43 | 18% | 7.74 | 50.74 |  | 75.248 | 18% | 13.5446 | 88.7926 | 38.0526 |  | 128.7895 | 53.5415 | 71.15% |  | 21 | NSTX was underestimated
42 - AC/DC Converters |  | 14.5 |  |  |  |  | 26.1367 | [5 empty] | 30.8414 |  | -36.7066 | -140.4% | 41
| 421 - C-site AC/DC Converters |  | 0 | 0% | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0% |  |  | Not req'd for NSTX
| 422 - D-site AC/DC Converters |  | 14.5 | 18% | 2.61 | 17.11 |  | 67.548 |  | 12.1586 | 79.7066 | 62.5966 |  | 30.8414 | -36.7066 | -54.34% |  | 41 | Approx equal
43 - DC Systems |  | 2395.449 |  |  |  |  | 3119.7109 | [5 empty] | 3732.8589 |  | -610.0051 | -19.55% | 1154
| 431 - C-site DC Systems |  | 365.479 | 18% | 65.7862 | 431.2652 |  | 1055.688 | 17.92% | 189.1512 | 1244.8392 | 813.574 |  | 456.3852 | -599.3028 | -56.77% |  | 0 | Not req'd for NSTX
| 432 - D-to-C-Site DC Systems |  | 1311.1 | 21.3% | 279.2643 | 1590.3643 |  | 2453.824 | 29.96% | 735.1187 | 3188.9427 | 1598.5784 |  | 1916.3805 | -537.4435 | -21.9% |  | 0 | Not req'd for NSTX
| 433 - D-site DC Systems |  | 718.87 | 18% | 129.3966 | 848.2666 |  | 833.352 | 18.51% | 154.2146 | 987.5666 | 139.3 |  | 1360.0932 | 526.7412 | 63.21% |  | 1154 | NCSX has more work per circuit but fewer circuits
44 - Control & Protection Systems |  | 1623.937 |  |  |  |  | 1565.4259 | [5 empty] | 1860.1072 |  | 336.3936 | 21.49% | 727
| 441 - Electrical Interlocks |  | 584.74 | 18.6% | 108.7616 | 693.5016 |  | 611.0736 | 18.63% | 113.8544 | 724.928 | 31.4263 |  | 679.1534 | 68.0798 | 11.14% |  | 209 | NCSX system new, NSTX was modification of existing
| 442 - Kirk Key Interlocks |  | 96.4 | 18% | 17.352 | 113.752 |  | 101.168 | 18% | 18.2102 | 119.3782 | 5.6262 |  | 110.6858 | 9.5178 | 9.408% |  | 50 | NCSX requires interface between C-and D-sites
| 443 - Real Time Control |  | 39.63 | 18% | 7.1334 | 46.7634 |  | 40.08 | 18% | 7.2144 | 47.2944 | 0.531 |  | 44.0176 | 3.9376 | 9.824% |  | 260 | NCSX is covered in different WBS
| 444 - Instrumentation |  | 607.84 | 12% | 72.9408 | 680.7808 |  | 359.296 | 18% | 64.6733 | 423.9693 | -256.8115 |  | 672.4144 | 313.1184 | 87.15% |  | 128 | NCSX system new, NSTX was modification of existing
| 445 - Coil Protection |  | 236.8 | 21.3% | 50.4384 | 287.2384 |  | 412.096 | 21.43% | 88.3258 | 500.4218 | 213.1834 |  | 353.836 | -58.26 | -14.14% |  | 80 | NCSX system new, NSTX was modification of existing
| 446 - Ground Fault Monitor |  | 58.527 | 18% | 10.5349 | 69.0619 |  | 319.2214 |  | 0 | 379.4141 | 310.3522 |  | #REF! | #REF! | #REF! |  |  | Not costed in NSTX baseline
45 - System Design and Integration |  | 1011.025 |  |  |  |  | 998.2616 | [5 empty] | 1218.8036 |  | -78.0684 | -7.82% | 784
| 451 - System Design |  | 378.4 | 18% | 68.112 | 446.512 |  | 325.08 | 18% | 58.5144 | 383.5944 | -62.9176 |  | 456.3183 | 131.2383 | 40.37% |  | 784 | NCSX design plus test approx equal to NSTX
| 452 - Electrical Systems Support |  | 466.935 | 26% | 121.4031 | 588.3381 |  | 774 | 26% | 201.24 | 975.24 | 386.9019 |  | 574.0006 | -199.9994 | -25.84% |  | 0 | NSTX was covered in different WBS
| 453 - System Testing |  | 165.69 | 18% | 29.8242 | 195.5142 |  | 197.792 | 18% | 35.6026 | 233.3946 | 37.8804 |  | 188.4847 | -9.3073 | -4.706% |  | 0 | In system design on NSTX
46 - FCPC Building Modifications |  | 5586.911 | 1e-05 |  |  | 1e-06 | #REF! | 108.912 | 26% | 28.3171 | 137.2291 | 137.2291 | #REF! |  | #REF! | #REF! | 2896
|  |  | 5586.911 |  | 1056.1275 | 6643.0385 |  | 8069.907 |  | 1780.5349 | 9910.6346 | 3267.5961 | 7542.2279 | #REF! | #REF! | #REF! | 2896 | 2896
41- AC Power | 699.6168
42 - AC/DC Converters | 30.8414
43 - DC Systems | 3732.8589
44 - Control & Protection Systems | 1860.1072
45 - System Design and Integration | 1218.8036
Total w/ Contingency | 7542.2279

## .
|  | NCSX w/o Cntg |  | NCSX w/Cntg |  | Cont | Cont % | NSTX w/Cntg |  | Comments
41- AC Power |  | 410.776 |  | 484.7157 |  | 73.9397 | 18% | 190
| 411 - Auxiliary AC Power |  | 335.528 |  | 395.923 | 60.395 | 18% |  | 169 | More work to ready C-site test cell and bring C-site infrastructure into operation, compared to D-site
| 412 - Experimental AC Power |  | 75.248 |  | 88.7926 | 13.5446 | 18% |  | 21 | NSTX was underestimated
42 - AC/DC Converters |  | 67.548 |  | 79.7066 |  | 12.1586 | 18% | 41
| 421 - C-site AC/DC Converters |  | 0 |  | 0 | 0 | #DIV/0! |  |  | Not req'd for NSTX
| 422 - D-site AC/DC Converters |  | 67.548 |  | 79.7066 | 12.1586 | 18% |  | 41 | Approx equal
43 - DC Systems |  | 4342.864 |  | 5421.3485 |  | 1078.4845 | 24.83% | 1154
| 431 - C-site DC Systems |  | 1055.688 |  | 1244.8392 | 189.1512 | 17.92% |  | 0 | Not req'd for NSTX
| 432 - D-to-C-Site DC Systems |  | 2453.824 |  | 3188.9427 | 735.1187 | 29.96% |  | 0 | Not req'd for NSTX
| 433 - D-site DC Systems |  | 833.352 |  | 987.5666 | 154.2146 | 18.51% |  | 1154 | NCSX has more work per circuit but fewer circuits
44 - Control & Protection Systems |  | 1842.935 |  | 2195.4057 |  | 292.278 | 15.86% | 727
| 441 - Electrical Interlocks |  | 611.0736 |  | 724.928 | 113.8544 | 18.63% |  | 209 | NCSX system new, NSTX was modification of existing
| 442 - Kirk Key Interlocks |  | 101.168 |  | 119.3782 | 18.2102 | 18% |  | 50 | NCSX requires interface between C-and D-sites
| 443 - Real Time Control |  | 40.08 |  | 47.2944 | 7.2144 | 18% |  | 260 | NCSX is covered in different WBS
| 444 - Instrumentation |  | 359.296 |  | 423.9693 | 64.6733 | 18% |  | 128 | NCSX system new, NSTX was modification of existing
| 445 - Coil Protection |  | 412.096 |  | 500.4218 | 88.3258 | 21.43% |  | 80 | NCSX system new, NSTX was modification of existing
| #REF! |  | #REF! |  | #REF! | #REF! | #REF! |  |  | Not costed in NSTX baseline
45 - System Design and Integration |  | 1405.784 |  | 1729.4581 |  | 122.4341 | 8.709% | 784
| 451 - System Design |  | 325.08 |  | 383.5944 | 58.5144 | 18% |  | 784 | NCSX design plus test approx equal to NSTX
| 46- FCPCBuilding Modifications |  | 108.912 |  | 137.2291 | 28.3171 | 26% |  | 0 | NSTX was covered in different WBS
| 453 - System Testing |  | 197.792 |  | 233.3946 | 35.6026 | 18% |  | 0 | In system design on NSTX
|  | 8069.907 | #REF! | 9910.6346 | #REF! | #REF! | #REF! | 2896 | 2896
41- AC Power | 484.7157
42 - AC/DC Converters | 79.7066
43 - DC Systems | 5421.3485
44 - Control & Protection Systems | 2195.4057
45 - System Design and Integration | 1729.4581
Total w/ Contingency | 9910.6346