## Sheet1
Sum of TOTAL |  | Phase
cc | DESC | Commission | Design | Fab/Assemble/Install | Grand Total
Diagnostic Upgrades | 3102 - 3102 - In-vessel Magnetics | 23 | 86 | 36 | 145
| 3103 - 3103 - Magnetic Instrumentation | 111 | 926 | 376 | 1413
| 3104 - 3104 - Terminate ex-vessel magnetics sensors |  |  | 63 | 63
| 3320 - 3320 - UV Spectrometer | 14 | 36 | 59 | 109
| 3330 - 3330 - Bolometer Array | 29 | 49 | 154 | 232
| 3350 - 3350 - Filterscopes |  | 25 | 115 | 140
| 3410 - 3410 - Soft X-Ray Arrays | 24 |  | 193 | 217
| 3420 - 3420 - X-ray crystal spectroscopy | 48 |  | 715 | 763
| 3510 - 3510 - Thomson Scattering | 126 | 1517 | 578 | 2221
| 3520 - 3520 - DNB Installation and servies | 252 | 448 | 265 | 965
| 3530 - 3530 - MSE | 291 | 638 | 521 | 1450
| 3540 - 3540 - CHERS | 29 | 649 | 268 | 946
| 3550 - 3550 - ECE | 205 | 164 | 177 | 546
| 3562 - 3562 - Interferometer | 52 | 121 | 158 | 331
| 3570 - 3570 - Reflectometer | 122 | 191 | 659 | 972
| 3611 - 3611 - Filtered 2-D cameras |  |  | 161 | 161
| 3612 - 3612 - Filtered 1-D camera |  |  | 64 | 64
| 3640 - 3640 - IR Camera | 14 | 26 | 46 | 86
| 3660 - 3660 - PFC mounted Langmiur probe | 27 | 17 | 32 | 76
Machine Upgrades | 1100 - 1100 - NB Armor |  | 1578 | 1459 | 3037
| 1211 - 1211 - Port Extensions |  |  | 398 | 398
| 1212 - 1212 - NB Ports & Covers |  | 40 | 257 | 297
| 1330 - 1330 - Trim Coils |  |  | 119 | 119
| 2111 - 2111 - 3 Gas Injectors |  | 112 | 164 | 276
| 2202 - 2202 - 2 pumps on one duct |  | 215 | 354 | 569
| 2310 - 2310 - Glow Discharge Cleaning |  | 33 | 160 | 193
| 2505 - 2505 - Beamline #1 Installation |  | 513 | 770 | 1283
| 2506 - 2506 - Beamline #1 Commissioning | 448 |  |  | 448
| 2507 - 2507 - Beamline #2 Installation |  | 457 | 651 | 1108
| 2508 - 2508 - Beamline #2 Commissioning | 448 |  |  | 448
| 2591 - Job: 2591 - 3rd and 4th Beamline-STEVENSON | 954 | 923 | 3561 | 5438
| 2600 - 2600 - ECH System | 546 | 736 | 1007 | 2289
| 4110 - Auxliary AC Power Systems | 77 | 142 | 138 | 357
| 4120 - Experimantal AC Power Systems | 19 | 31 | 29 | 79
| 4220 - D-SIte AC/DC Converters | 60 | 9 |  | 69
| 4310 - C-Site DC Systems | 420 | 229 | 983 | 1632
| 4320 - D to C Site DC Systems | 96 | 629 | 2599 | 3324
| 4330 - D Site DC Systems | 59 | 367 | 775 | 1201
| 4410 - Electrical Interlocks | 59 | 311 | 281 | 651
| 4420 - Kirk Key Interlocks | 23 | 51 | 32 | 106
| 4430 - Real Time Control Systems |  | 42 |  | 42
| 4440 - Instrument Systems | 59 | 271 | 102 | 432
| 4450 - Coil Protection Systems | 57 | 251 | 140 | 448
| 4460 - Ground Fault Monitoring System | 7 | 217 | 119 | 343
| 4510 - Sys design and interfaces |  | 344 |  | 344
| 4520 - Electrical Systems support | 136 | 329 | 365 | 830
| 4530 - Systems Testing PTP's | 99 | 117 |  | 216
| 4600 - FCPC Bldg Mods |  | 40 | 72 | 112
| 5101 - Job: 5101 - TCP/IP Infrastructure Systems |  |  | 206 | 206
| 5201 - 5201 - I&C Systems |  |  | 318 | 318
| 5301 - 5301 - Data Acquisition |  |  | 132 | 132
| 5401 - Job: 5401 - Facility Timing & Synchronization |  |  | 244 | 244
| 5501 - 5501 - Real Time Control System |  |  | 502 | 502
| 5601 - Job: 5601 - Central Safety Interlock Systems |  |  | 222 | 222
| 5701 - Job: 5701 - Control Room Facility |  |  | 301 | 301
| 6120 - NB Cooling Water |  |  | 365 | 365
| 6130 - Vacuum Pumping Cooling Water |  |  | 97 | 97
| 6150 - Diag Cooling Water |  |  | 43 | 43
Grand Total |  | 4934 | 12880 | 21605 | 39419

## P3
RLM | Phase | cc | DESC | TOTAL | FY 2009 | FY 2010 | FY 2011 | FY 2012 | FY 2013 | FY 2014 | FY 2015
D - | Design | Machine Upgrades | 1100 - 1100 - NB Armor | 1578 | FY 2010: 831; FY 2011: 748
F - | Fab/Assemble/Install | Machine Upgrades | 1100 - 1100 - NB Armor | 1459 | FY 2010: 72; FY 2011: 943; FY 2012: 390; FY 2013: 54
F - | Fab/Assemble/Install | Machine Upgrades | 1211 - 1211 - Port Extensions | 398 | FY 2012: 398
D - | Design | Machine Upgrades | 1212 - 1212 - NB Ports & Covers | 40 | FY 2011: 40
F - | Fab/Assemble/Install | Machine Upgrades | 1212 - 1212 - NB Ports & Covers | 257 | FY 2011: 222; FY 2012: 35
F - | Fab/Assemble/Install | Machine Upgrades | 1330 - 1330 - Trim Coils | 119 | FY 2011: 25; FY 2012: 94
D - | Design | Machine Upgrades | 2111 - 2111 - 3 Gas Injectors | 112 | FY 2012: 112
F - | Fab/Assemble/Install | Machine Upgrades | 2111 - 2111 - 3 Gas Injectors | 164 | FY 2013: 164
D - | Design | Machine Upgrades | 2202 - 2202 - 2 pumps on one duct | 215 | FY 2012: 215
F - | Fab/Assemble/Install | Machine Upgrades | 2202 - 2202 - 2 pumps on one duct | 354 | FY 2013: 354
D - | Design | Machine Upgrades | 2310 - 2310 - Glow Discharge Cleaning | 33 | FY 2012: 33
F - | Fab/Assemble/Install | Machine Upgrades | 2310 - 2310 - Glow Discharge Cleaning | 160 | FY 2012: 56; FY 2013: 104
D - | Design | Machine Upgrades | 2505 - 2505 - Beamline #1 Installation | 513 | FY 2010: 82; FY 2011: 312; FY 2012: 119
F - | Fab/Assemble/Install | Machine Upgrades | 2505 - 2505 - Beamline #1 Installation | 770 | FY 2010: 89; FY 2011: 414; FY 2012: 267
S - | Commission | Machine Upgrades | 2506 - 2506 - Beamline #1 Commissioning | 448 | FY 2013: 448
D - | Design | Machine Upgrades | 2507 - 2507 - Beamline #2 Installation | 457 | FY 2011: 311; FY 2012: 123; FY 2013: 23
F - | Fab/Assemble/Install | Machine Upgrades | 2507 - 2507 - Beamline #2 Installation | 651 | FY 2011: 315; FY 2012: 283; FY 2013: 53
S - | Commission | Machine Upgrades | 2508 - 2508 - Beamline #2 Commissioning | 448 | FY 2013: 448
D - | Design | Machine Upgrades | 2591 - Job: 2591 - 3rd and 4th Beamline-STEVENSON | 923 | FY 2014: 923
F - | Fab/Assemble/Install | Machine Upgrades | 2591 - Job: 2591 - 3rd and 4th Beamline-STEVENSON | 3561 | FY 2013: 1952; FY 2014: 1609
S - | Commission | Machine Upgrades | 2591 - Job: 2591 - 3rd and 4th Beamline-STEVENSON | 954 | FY 2014: 13; FY 2015: 941
D - | Design | Machine Upgrades | 2600 - 2600 - ECH System | 736 | FY 2013: 531; FY 2014: 205
F - | Fab/Assemble/Install | Machine Upgrades | 2600 - 2600 - ECH System | 1007 | FY 2014: 918; FY 2015: 89
S - | Commission | Machine Upgrades | 2600 - 2600 - ECH System | 546 | FY 2015: 546
D - | Design | Diagnostic Upgrades | 3102 - 3102 - In-vessel Magnetics | 86 | FY 2011: 86
F - | Fab/Assemble/Install | Diagnostic Upgrades | 3102 - 3102 - In-vessel Magnetics | 36 | FY 2011: 30; FY 2012: 6
S - | Commission | Diagnostic Upgrades | 3102 - 3102 - In-vessel Magnetics | 23 | FY 2012: 23
F - | Design | Diagnostic Upgrades | 3103 - 3103 - Magnetic Instrumentation | 926 | FY 2011: 269; FY 2012: 657
D - | Fab/Assemble/Install | Diagnostic Upgrades | 3103 - 3103 - Magnetic Instrumentation | 376 | FY 2012: 113; FY 2013: 263
F - | Commission | Diagnostic Upgrades | 3103 - 3103 - Magnetic Instrumentation | 111 | FY 2013: 111
S - | Fab/Assemble/Install | Diagnostic Upgrades | 3104 - 3104 - Terminate ex-vessel magnetics sensors | 63 | FY 2013: 63
D - | Design | Diagnostic Upgrades | 3320 - 3320 - UV Spectrometer | 36 | FY 2012: 25; FY 2013: 10
F - | Fab/Assemble/Install | Diagnostic Upgrades | 3320 - 3320 - UV Spectrometer | 59 | FY 2013: 59
S - | Commission | Diagnostic Upgrades | 3320 - 3320 - UV Spectrometer | 14 | FY 2013: 14
D - | Design | Diagnostic Upgrades | 3330 - 3330 - Bolometer Array | 49 | FY 2012: 49
F - | Fab/Assemble/Install | Diagnostic Upgrades | 3330 - 3330 - Bolometer Array | 154 | FY 2012: 1; FY 2013: 49; FY 2015: 104
C - | Commission | Diagnostic Upgrades | 3330 - 3330 - Bolometer Array | 29 | FY 2013: 9; FY 2015: 20
F - | Design | Diagnostic Upgrades | 3350 - 3350 - Filterscopes | 25 | FY 2012: 25
S - | Fab/Assemble/Install | Diagnostic Upgrades | 3350 - 3350 - Filterscopes | 77 | FY 2012: 5; FY 2013: 72
F - | Fab/Assemble/Install | Diagnostic Upgrades | 3350 - 3350 - Filterscopes | 38 | FY 2013: 38
S - | Fab/Assemble/Install | Diagnostic Upgrades | 3410 - 3410 - Soft X-Ray Arrays | 193 | FY 2012: 2; FY 2013: 192
D - | Commission | Diagnostic Upgrades | 3410 - 3410 - Soft X-Ray Arrays | 24 | FY 2013: 24
F - | Fab/Assemble/Install | Diagnostic Upgrades | 3420 - 3420 - X-ray crystal spectroscopy | 715 | FY 2012: 31; FY 2013: 684
S - | Commission | Diagnostic Upgrades | 3420 - 3420 - X-ray crystal spectroscopy | 48 | FY 2013: 48
D - | Design | Diagnostic Upgrades | 3510 - 3510 - Thomson Scattering | 1517 | FY 2011: 630; FY 2012: 886
F - | Fab/Assemble/Install | Diagnostic Upgrades | 3510 - 3510 - Thomson Scattering | 578 | FY 2013: 578
S - | Commission | Diagnostic Upgrades | 3510 - 3510 - Thomson Scattering | 126 | FY 2013: 126
D - | Design | Diagnostic Upgrades | 3520 - 3520 - DNB Installation and servies | 448 | FY 2014: 448
F - | Fab/Assemble/Install | Diagnostic Upgrades | 3520 - 3520 - DNB Installation and servies | 265 | FY 2014: 132; FY 2015: 132
S - | Commission | Diagnostic Upgrades | 3520 - 3520 - DNB Installation and servies | 252 | FY 2015: 252
D - | Design | Diagnostic Upgrades | 3530 - 3530 - MSE | 638 | FY 2014: 638
F - | Fab/Assemble/Install | Diagnostic Upgrades | 3530 - 3530 - MSE | 521 | FY 2014: 386; FY 2015: 135
S - | Commission | Diagnostic Upgrades | 3530 - 3530 - MSE | 291 | FY 2015: 291
D - | Design | Diagnostic Upgrades | 3540 - 3540 - CHERS | 649 | FY 2014: 649
F - | Fab/Assemble/Install | Diagnostic Upgrades | 3540 - 3540 - CHERS | 268 | FY 2014: 187; FY 2015: 82
S - | Commission | Diagnostic Upgrades | 3540 - 3540 - CHERS | 29 | FY 2015: 29
D - | Design | Diagnostic Upgrades | 3550 - 3550 - ECE | 164 | FY 2014: 164
F - | Fab/Assemble/Install | Diagnostic Upgrades | 3550 - 3550 - ECE | 177 | FY 2014: 8; FY 2015: 168
S - | Commission | Diagnostic Upgrades | 3550 - 3550 - ECE | 205 | FY 2015: 205
D - | Design | Diagnostic Upgrades | 3562 - 3562 - Interferometer | 121 | FY 2013: 121
F - | Fab/Assemble/Install | Diagnostic Upgrades | 3562 - 3562 - Interferometer | 158 | FY 2013: 158
S - | Commission | Diagnostic Upgrades | 3562 - 3562 - Interferometer | 52 | FY 2013: 52
F - | Design | Diagnostic Upgrades | 3570 - 3570 - Reflectometer | 191 | FY 2012: 171; FY 2013: 21
F - | Fab/Assemble/Install | Diagnostic Upgrades | 3570 - 3570 - Reflectometer | 659 | FY 2013: 659
D - | Commission | Diagnostic Upgrades | 3570 - 3570 - Reflectometer | 122 | FY 2013: 122
F - | Fab/Assemble/Install | Diagnostic Upgrades | 3611 - 3611 - Filtered 2-D cameras | 161 | FY 2013: 161
S - | Fab/Assemble/Install | Diagnostic Upgrades | 3612 - 3612 - Filtered 1-D camera | 64 | FY 2013: 64
D - | Design | Diagnostic Upgrades | 3640 - 3640 - IR Camera | 26 | FY 2013: 26
F - | Fab/Assemble/Install | Diagnostic Upgrades | 3640 - 3640 - IR Camera | 46 | FY 2013: 46
S - | Commission | Diagnostic Upgrades | 3640 - 3640 - IR Camera | 14 | FY 2013: 14
F - | Design | Diagnostic Upgrades | 3660 - 3660 - PFC mounted Langmiur probe | 17 | FY 2013: 17
F - | Fab/Assemble/Install | Diagnostic Upgrades | 3660 - 3660 - PFC mounted Langmiur probe | 32 | FY 2013: 32
F - | Commission | Diagnostic Upgrades | 3660 - 3660 - PFC mounted Langmiur probe | 27 | FY 2013: 27
D - | Design | Machine Upgrades | 4110 - Auxliary AC Power Systems | 142 | FY 2012: 142
F - | Fab/Assemble/Install | Machine Upgrades | 4110 - Auxliary AC Power Systems | 138 | FY 2012: 116; FY 2013: 22
S - | Commission | Machine Upgrades | 4110 - Auxliary AC Power Systems | 77 | FY 2013: 77
D - | Design | Machine Upgrades | 4120 - Experimantal AC Power Systems | 31 | FY 2012: 31
F - | Fab/Assemble/Install | Machine Upgrades | 4120 - Experimantal AC Power Systems | 29 | FY 2012: 25; FY 2013: 5
S - | Commission | Machine Upgrades | 4120 - Experimantal AC Power Systems | 19 | FY 2013: 19
D - | Design | Machine Upgrades | 4220 - D-SIte AC/DC Converters | 9 | FY 2012: 9
F - | Commission | Machine Upgrades | 4220 - D-SIte AC/DC Converters | 60 | FY 2012: 60
S - | Design | Machine Upgrades | 4310 - C-Site DC Systems | 229 | FY 2012: 229
D - | Fab/Assemble/Install | Machine Upgrades | 4310 - C-Site DC Systems | 983 | FY 2012: 413; FY 2013: 570
F - | Commission | Machine Upgrades | 4310 - C-Site DC Systems | 420 | FY 2012: 176; FY 2013: 243
S - | Design | Machine Upgrades | 4320 - D to C Site DC Systems | 629 | FY 2011: 629
D - | Fab/Assemble/Install | Machine Upgrades | 4320 - D to C Site DC Systems | 2599 | FY 2011: 1827; FY 2012: 773
F - | Commission | Machine Upgrades | 4320 - D to C Site DC Systems | 96 | FY 2012: 96
S - | Design | Machine Upgrades | 4330 - D Site DC Systems | 367 | FY 2011: 367
F - | Fab/Assemble/Install | Machine Upgrades | 4330 - D Site DC Systems | 775 | FY 2011: 252; FY 2012: 523
D - | Commission | Machine Upgrades | 4330 - D Site DC Systems | 59 | FY 2012: 59
S - | Design | Machine Upgrades | 4410 - Electrical Interlocks | 311 | FY 2012: 311
D - | Fab/Assemble/Install | Machine Upgrades | 4410 - Electrical Interlocks | 281 | FY 2012: 281
F - | Commission | Machine Upgrades | 4410 - Electrical Interlocks | 59 | FY 2012: 12; FY 2013: 46
S - | Design | Machine Upgrades | 4420 - Kirk Key Interlocks | 51 | FY 2012: 51
D - | Fab/Assemble/Install | Machine Upgrades | 4420 - Kirk Key Interlocks | 32 | FY 2012: 32
F - | Commission | Machine Upgrades | 4420 - Kirk Key Interlocks | 23 | FY 2012: 5; FY 2013: 18
S - | Design | Machine Upgrades | 4430 - Real Time Control Systems | 42 | FY 2012: 42
D - | Design | Machine Upgrades | 4440 - Instrument Systems | 271 | FY 2012: 271
F - | Fab/Assemble/Install | Machine Upgrades | 4440 - Instrument Systems | 102 | FY 2012: 72; FY 2013: 29
S - | Commission | Machine Upgrades | 4440 - Instrument Systems | 59 | FY 2013: 59
D - | Design | Machine Upgrades | 4450 - Coil Protection Systems | 251 | FY 2012: 251
F - | Fab/Assemble/Install | Machine Upgrades | 4450 - Coil Protection Systems | 140 | FY 2012: 121; FY 2013: 19
D - | Commission | Machine Upgrades | 4450 - Coil Protection Systems | 57 | FY 2013: 57
F - | Design | Machine Upgrades | 4460 - Ground Fault Monitoring System | 217 | FY 2012: 217
S - | Fab/Assemble/Install | Machine Upgrades | 4460 - Ground Fault Monitoring System | 119 | FY 2012: 101; FY 2013: 18
D - | Commission | Machine Upgrades | 4460 - Ground Fault Monitoring System | 7 | FY 2013: 7
F - | Design | Machine Upgrades | 4510 - Sys design and interfaces | 344 | FY 2012: 267; FY 2013: 77
S - | Design | Machine Upgrades | 4520 - Electrical Systems support | 329 | FY 2012: 329
D - | Fab/Assemble/Install | Machine Upgrades | 4520 - Electrical Systems support | 365 | FY 2012: 316; FY 2013: 49
F - | Commission | Machine Upgrades | 4520 - Electrical Systems support | 136 | FY 2013: 136
S - | Design | Machine Upgrades | 4530 - Systems Testing PTP's | 117 | FY 2013: 117
F - | Commission | Machine Upgrades | 4530 - Systems Testing PTP's | 99 | FY 2013: 99
F - | Design | Machine Upgrades | 4600 - FCPC Bldg Mods | 40 | FY 2012: 40
F - | Fab/Assemble/Install | Machine Upgrades | 4600 - FCPC Bldg Mods | 72 | FY 2012: 72
F - | Fab/Assemble/Install | Machine Upgrades | 5101 - Job: 5101 - TCP/IP Infrastructure Systems | 206 | FY 2012: 147; FY 2013: 60
D - | Fab/Assemble/Install | Machine Upgrades | 5201 - 5201 - I&C Systems | 318 | FY 2012: 227; FY 2013: 92
F - | Fab/Assemble/Install | Machine Upgrades | 5301 - 5301 - Data Acquisition | 132 | FY 2013: 132
S - | Fab/Assemble/Install | Machine Upgrades | 5401 - Job: 5401 - Facility Timing & Synchronization | 244 | FY 2012: 174; FY 2013: 70
F - | Fab/Assemble/Install | Machine Upgrades | 5501 - 5501 - Real Time Control System | 502 | FY 2012: 276; FY 2013: 226
D - | Fab/Assemble/Install | Machine Upgrades | 5601 - Job: 5601 - Central Safety Interlock Systems | 222 | FY 2012: 158; FY 2013: 64
D - | Fab/Assemble/Install | Machine Upgrades | 5701 - Job: 5701 - Control Room Facility | 301 | FY 2013: 301
D - | Fab/Assemble/Install | Machine Upgrades | 6120 - NB Cooling Water | 365 | FY 2012: 158; FY 2013: 207
S - | Fab/Assemble/Install | Machine Upgrades | 6130 - Vacuum Pumping Cooling Water | 97 | FY 2013: 97
F - | Fab/Assemble/Install | Machine Upgrades | 6150 - Diag Cooling Water | 43 | FY 2013: 43