## PPPL
Fabricated Equipment
Total Project Cost as of 08-31-08
CC | WP | JOB | Description | FY03 | FY04 | FY05 | FY06 | FY07 | FY08 | adj | Total | Asset ID
9449 |  |  | NCSX MIE Offsite
| **** |  | Cost Center Non-Job
|  | *NUL | Management Reserve
| 8*** |  | NCSX Project oversight & support
|  | 8202 | Eng Mgt & Sys Eng support | [5 empty] | 13638.07 |  | 13638.07 | NCSX MIE
| Total Since Inception |  | 13638.07
| Total Costs Already Assigned |  | 0
| Costs Remaining in Job |  | 13638.07
| Total FY08 to 06/30/08 |  | 13638.07
9450 |  |  | NCSX FABRICATION
| **** |  | Cost Center Non-Job
|  | *NUL | Management Reserve |  | 14171.16 | 89516.18 | 90205.93 | 88186.57 | 76013.89 |  | 358093.73 | x not on Ron's spreadsheet
|  | CRCD | Credit Card Default |  |  | 250.95 | 0 | 0 | 2484 | -2484 | 250.95
| 1*** |  | NCSX Stellerator & Core | [7 empty] | 0
|  | *NUL | Management Reserve |  | 12.28 | [5 empty] | 12.28
|  | 1201 | Vacuum Vessel Design | 105366.11 | [6 empty] | 105366.11
|  | 1202 | Vacuum Vessel R&D | 758529.85 | 986728.72 | [5 empty] | 1745258.57
|  | 1203 | Vacuum Vessel Final Design |  | 163798.59 | 76952.85 | 45401.07 |  |  |  | 286152.51
|  | 1204 | VV Sys Procurements (non VVSA) |  |  | 459.33 | 232664.17 | 358926.33 | 170344.19 |  | 762394.02
|  | 1206 | VV Field Weld Joint R&D |  |  | 15954.66 |  |  |  |  | 15954.66
|  | 1250 | Vacuum Vessel Fabrication |  |  | 2890537.79 | 2695491.77 | -271774.59 |  |  | 5314254.97
|  | 1260 | NB transition ducts | [7 empty] | 0
|  | 1301 | TF Design | 91661.59 | 336472.36 | 513906.48 | 28248.95 |  |  |  | 970289.38
|  | 1302 | PF Coil Design |  |  |  | 19338.88 | 45395 | 64561.1 |  | 129294.98
|  | 1303 | NCSX Central Solenoid Support System |  |  |  | 132865.28 | 20486.98 |  |  | 153352.26
|  | 1350 | TF Coil Fabrication Preparation |  |  | 394072.38 | 141807.36 |  |  |  | 535879.74
|  | 1351 | TF Coil Materials |  |  | 179101.64 | 272915.96 | 30057.11 |  |  | 482074.71
|  | 1352 | PF Coil Fabrication | [5 empty] | 177479.35 |  | 177479.35
|  | 1354 | Trim Coil and I&C | [5 empty] | 223362.42 |  | 223362.42
|  | 1355 | Coil local I&C | [7 empty] | 0
|  | 1361 | TF Coil Fabrication |  |  |  | 612818.48 | 730186.5 | 662984.58 |  | 2005989.56
|  | 1401 | MOD Coil Design |  | 1322.66 | [5 empty] | 1322.66
|  | 1402 | MOD Coil Analyses | 154916.77 | 22134.02 | [5 empty] | 177050.79
|  | 1403 | WBS 14 Final Design |  | 393653.53 | 270684.25 | 40559.45 |  |  |  | 704897.23 | x not on Ron's spreadsheet
|  | 1404 | MCWF R&D and Prod Casting | 464052.52 | 1363743.11 | 411021.28 | -966.24 | -23822.2 |  |  | 2214028.47
|  | 1405 | MOD Coil Winding R&D Pre | 168064.18 | [6 empty] | 168064.18
|  | 1406 | MOD Coil Winding R&D | 831115.18 | 1292332.71 | 123613.47 | 15582.24 | 607 |  |  | 2263250.6
|  | 1407 | MOD Coil Winding Facility | 267545.14 | 2278305.11 | 98215.16 | 23920.57 |  |  |  | 2667985.98
|  | 1408 | MOD Coil Winding Supplies | 29788.83 | 25826.15 | 523292.18 | 1177200.02 | 690620.83 | 222027.32 |  | 2668755.33
|  | 1409 | MOD Coil Test Stand |  | 343290.09 | 572422.81 | -83142.83 |  |  |  | 832570.07
|  | 1410 | MC Twisted Racetrack |  | 6152.45 | 1044108.95 | -704.47 |  |  |  | 1049556.93
|  | 1411 | Modular Coil Casting Fab |  |  | 4008949.23 | 3939236.41 | 1770453.56 |  |  | 9718639.2
|  | 1412 | Complete Winding Facilities |  |  | 439390.63 | 3127.58 | 5382.31 | 2050.76 |  | 449951.28
|  | 1413 | NCSX MCWF Fracture Analysis |  |  | 27819.24 |  |  |  |  | 27819.24
|  | 1414 | Coil Testing |  |  | 134098.35 | 504576.03 |  |  |  | 638674.38
|  | 1415 | Dimensional Control Testing |  |  | 24038.93 |  |  |  |  | 24038.93
|  | 1416 | Mod Coil Final Design Type A&B Coil |  |  |  | 35268.4 | 4479.13 |  |  | 39747.53
|  | 1419 | NCSX Winding Facility Mode |  |  | 48434.31 | 0 |  |  |  | 48434.31
|  | 1421 | Mod Coil Interface Design & Procurement |  |  |  |  | 270207.1 | 345149.98 |  | 615357.08
|  | 1429 | Mod Coil Interface R&D |  |  |  |  | 241000.22 | 24927.06 |  | 265927.28
|  | 1431 | Mod Coil Interface Hardware Procurements |  |  |  |  | 287675.01 | 430452.44 |  | 718127.45
|  | 1451 | Mod Coil Winding |  |  | 137831.39 | 2948233.28 | 3454362.08 | 1587734.15 |  | 8128160.9
|  | 1459 | MCWF Unplanned Re-Work |  |  |  | 276245.82 | 478139.83 | 306186.3 |  | 1060571.95
|  | 1460 | Mod Coil 3rd Winding Station |  |  |  |  | 55266.09 |  |  | 55266.09
|  | 1480 | NCSX Stellerator & Core (what's this???) |  |  |  | 0 |  |  |  | 0
|  | 1501 | Structures Design |  | 20085.57 | 54556.36 | 38677.78 | 394463.3 | 294926.4 |  | 802709.41
|  | 1550 | Structures Procurement |  |  |  | 4061.19 |  | 17151.42 |  | 21212.61
|  | 1601 | Coil Services Design |  |  |  | 2614.95 |  |  |  | 2614.95
|  | 1701 | Cryostat Design | 12180.31 | 97522.79 | 262052.4 | 45519.57 | 18750.39 | 83425.71 |  | 519451.17
|  | 1702 | Base Support Struct Design | [5 empty] | 184723.32 |  | 184723.32
| ORNL ? | 1801 | Field Period Assembly (ORNL) | 7746.04 | 256.37 |  | 3273.56 |  |  |  | 11275.97
|  | 1802 | FP Assy Oversight&Support |  | 148955.78 | 219130.45 | 307311.76 | 602498.66 | 610178.08 |  | 1888074.73
|  | 1803 | FP Assy Tooling/Constructability |  |  | 450389.2 | 491416.27 | 355436.09 | 511803.55 |  | 1809045.11
|  | 1804 | FP Assy Measurement |  | 181246.77 | 256657.11 | 110337.92 | 10578.06 |  |  | 558819.86
|  | 1805 | FP Assy Hardware & Fixtures |  |  |  |  | 59700.81 | 96763.77 |  | 156464.58
|  | 1806 | FPA Specs and dwgs | [7 empty] | 0
|  | 1808 | TF/Mod Coil Sub-Assembly |  |  |  | 2502.63 | 1517.49 | 4417.03 |  | 8437.15 | x not on Ron's spreadsheet
|  | 1810 | Field Period Assembly |  |  | 5208.87 | 140914.45 | 1157495.68 | 2437047.33 |  | 3740666.33
|  | 1815 | Field Period Assy Station 5 |  |  |  |  | 3.39 |  |  | 3.39
|  | 1859 | FP Assy Prototyping & Unplanned Work |  |  |  |  | 34868.87 |  |  | 34868.87 | x not on Ron's spreadsheet
|  | 1901 | Stellerator Core Mgmt/Integration | 67067.88 | 170309.71 | [5 empty] | 237377.59
| 2*** |  | NCSX Plasma Heat, Fuel & Vac System | [7 empty] | 0
|  | 2001 | VPS Gas & Conditioning | 57500.51 | 2579.37 | [5 empty] | 60079.88
|  | 2501 | Neutral Beam Refurbishment | 146304.79 | 137872.14 |  | 764.52 |  |  |  | 284941.45
| 3*** |  | NCSX Diagnostics | [7 empty] | 0
|  | 3101 | Magnetic Diagnostics |  |  | 131432.46 | 338121.99 | 262613.87 | 157142.64 |  | 889310.96
|  | 3901 | Diagnostics Syst Integration | 155452.17 | 74611.27 | 44349.85 | 43266.74 | 44392.39 | 56550.13 |  | 418622.55
| 4*** |  | NCSX Electrical Power Syst | [7 empty] | 0
|  | 4101 | AC Power |  | 80588.12 | 26761.19 |  | -104102.69 |  |  | 3246.62
|  | 4301 | DC Systems | 2393.4 | 409394 | -224124.01 | 143318.65 |  | 30256.4 |  | 361238.44
|  | 4350 | NCSX Hybrid Power Syst Concept Design |  | 26918.8 | 11861.63 |  |  |  |  | 38780.43 | x not on Ron's spreadsheet
|  | 4401 | Control & Protection |  | 21960.35 | 32639.16 | 25923.51 |  | 11709.81 |  | 92232.83
|  | 4501 | Power Sys Dsn & Integr | 112344.49 | 25955.48 |  | 13251.92 | 8809.27 |  |  | 160361.16
|  | 4601 | FCPC Bldg Modifications | 1305.33 | [6 empty] | 1305.33
| 5*** |  | NCSX Central I&C Syst | [7 empty] | 0
|  | 5801 | Central I&C Integration | 11948.98 | 19155.53 | 1922.75 |  |  | 17390.42 |  | 50417.68
| 6*** |  | NCSX Facility Syst | [7 empty] | 0
|  | 6163 | Facility Systems Support |  | 14873.15 | [5 empty] | 14873.15
|  | 6201 | Cryogenic Systems | [5 empty] | 43761.87 |  | 43761.87 | x not on Ron's spreadsheet
|  | 6501 | Facility Systems Integration | 9376.85 | [6 empty] | 9376.85
| 7*** |  | NCSX Test Cell Prep & Machine Assy | [7 empty] | 0
|  | 7101 | Shield Wall MOD Des | 32149.93 |  |  | 455.03 |  |  |  | 32604.96
|  | 7301 | Platform Design/Fab |  |  | 72996.62 | 2940.94 |  |  |  | 75937.56
|  | 7401 | TC Prep & Mach Assy Planning | 131681.39 | 197551.53 | 465709.6 | 43718.4 | -266744.08 | 82885.4 |  | 654802.24
|  | 7501 | Construction Crew |  |  | 29.03 |  |  |  |  | 29.03
| 8*** |  | NCSX Project Oversight & Suprt | [7 empty] | 0
|  | 8101 | Project Management PPPL | 223477.17 | 877505.48 | 690248.39 | 601950.72 | 559351.58 | 615599.09 |  | 3568132.43
|  | 8102 | Project Management ORNL | [7 empty] | 0
|  | 8202 | Engr Mgmt & Sys Eng Support | 295529.27 | 695078.92 | 624512.44 | 665421.62 | 683516.07 | 558048.28 |  | 3522106.6
|  | 8203 | Design Integration | 178750.93 | 382155.27 | 125603.61 | 166369.8 | 169917.52 | 195944.09 |  | 1218741.22
|  | 8204 | System Analysis | 44613.52 | 176722.18 | 278161.75 | 470716.6 | 532689.73 | 498338.46 |  | 2001242.24
|  | 8205 | NCSX Dimensional Control |  |  | 89668.44 | 149012.51 | 153182.05 | 104052.06 |  | 495915.06
|  | 8210 | Project Rebaseline Estimating |  |  |  |  | 82103.7 | 30891.78 |  | 112995.48
|  | 8215 | Plant Design | [5 empty] | 6062.43 |  | 6062.43
|  | 8220 | NCSX Equip Disposition & Facility Restora | [5 empty] | 111190.66 |  | 111190.66
|  | 8221 | NCSX Documentation for closeout | [5 empty] | 148002.75 |  | 148002.75
|  | 8222 | NCSX Manuscripts and Papers | [5 empty] | 9891.96 |  | 9891.96
|  | 8401 | Project Physics PPPL | 374124.21 | 113027.77 | 355.71 |  |  |  |  | 487507.69
|  | 8402 | Project Physics ORNL | [7 empty] | 0
|  | 8501 | NCSX Integrated Sys test Doc | [5 empty] | 3993.99 |  | 3993.99
|  | 8998 | Allocations | 60666.07 | 289657.03 | 325975.76 | 333797.08 | 321058.76 | 338145.63 |  | 1669300.33
|  |  | (rounding) |  | 0.45 | 0.12 |  |  |  |  | 0.57
|  |  | FY07 Ind Cost write off | -726756.61 | -1610630.37 | -1508229.11 | -1608998.02 | -1521940.99 |  |  | -6976555.1
|  |  | FY08 Ind Cost write off | [5 empty] | -884934.37
| Total Since Inception |  | 74326409.5
| Total Costs Already Assigned |  | 0 | [7 empty] | 0 | UNKNOWN
| Costs Remaining in Job |  | 74326409.5
| Total FY08 to 08/31/08 |  | 11556052
|  |  |  | 4795653.41 | 11391926.32 | 15970771.21 | 17296554.22 | 13317935.77 | 11556052 |  | 74328892.93
|  |  | 74340047.57 | [5 empty] | 74328892.93 | 74328892.93
Note on K24: mcarideo: reversal of pcard accrual in sept 08
Note on I32: Kim Buturla: Mar07 - Proceeds from Kirksite scrap.
Note on H46: Kim Buturla: Reversal of accrual for PE005160 per R. Templon email on 9/27/06.
Note on I70: Kim Buturla: Oct06 - Reversal of FY06 Pcard accrual.
Note on I90: mcarideo: rfba to move to GPP
Note on G91: Kim Buturla: Cost Transfer to 9403
Note on I105: mcarideo: rfba to move to GPP

## ORNL
| ORNL |  |  | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008
9450 | 1*** |  | NCSX Stellerator & Core | [6 empty] | 0
|  | *NUL | Management Reserve | [6 empty] | 0
|  | 1201 | Vacuum Vessel Design | 319109 | [5 empty] | 319109
|  | 1202 | Vacuum Vessel R&D | 58 | 26018 |  |  |  |  | 26076
|  | 1203 | Vacuum Vessel Final Design |  | 461649 | 385942.5 | 305691 |  |  | 1153282.5
|  | 1204 | VV Sys Procurements (non VVSA) |  |  |  |  | 136941 | 25641 | 162582
|  | 1206 | VV Field Weld Joint R&D | [6 empty] | 0
|  | 1250 | Vacuum Vessel Fabrication | [6 empty] | 0
|  | 1260 | NB transition ducts | [5 empty] | 5117 | 5117
|  | 1301 | TF Design | [6 empty] | 0
|  | 1302 | PF Coil Design | [6 empty] | 0
|  | 1303 | NCSX Central Solenoid Support System | [6 empty] | 0
|  | 1350 | TF Coil Fabrication Preparation | [6 empty] | 0
|  | 1351 | TF Coil Materials | [6 empty] | 0
|  | 1352 | PF Coil Fabrication | [6 empty] | 0
|  | 1354 | Trim Coil and I&C | [6 empty] | 0
|  | 1355 | Coil local I&C | [5 empty] | 1169 | 1169
|  | 1361 | TF Coil Fabrication | [6 empty] | 0
|  | 1401 | MOD Coil Design | 303043 | [5 empty] | 303043
|  | 1402 | MOD Coil Analyses | 84219 | 235459 | 74754.5 | 339 |  |  | 394771.5
|  | 1403 | WBS 14 Final Design |  | 1201890 | 1041043.5 | 763024 |  |  | 3005957.5
|  | 1404 | MCWF R&D and Prod Casting | 100223 | 179244 | 25695.5 |  |  |  | 305162.5
|  | 1405 | MOD Coil Winding R&D Pre | [6 empty] | 0
|  | 1406 | MOD Coil Winding R&D | [6 empty] | 0
|  | 1407 | MOD Coil Winding Facility | [6 empty] | 0
|  | 1408 | MOD Coil Winding Supplies | [6 empty] | 0
|  | 1409 | MOD Coil Test Stand | [6 empty] | 0
|  | 1410 | MC Twisted Racetrack | [6 empty] | 0
|  | 1411 | Modular Coil Casting Fab |  |  |  |  | 9813 | 20935 | 30748
|  | 1412 | Complete Winding Facilities | [6 empty] | 0
|  | 1413 | NCSX MCWF Fracture Analysis | [6 empty] | 0
|  | 1414 | Coil Testing | [6 empty] | 0
|  | 1415 | Dimensional Control Testing | [6 empty] | 0
|  | 1416 | Mod Coil Final Design Type A&B Coil |  |  |  |  | 341746 | 207736 | 549482
|  | 1419 | NCSX Winding Facility Mode | [6 empty] | 0
|  | 1421 | Mod Coil Interface Design & Procurement |  |  |  | 32796 | 601770 | 470735 | 1105301
|  | 1429 | Mod Coil Interface R&D | [6 empty] | 0
|  | 1431 | Mod Coil Interface Hardware Procurements | [6 empty] | 0
|  | 1451 | Mod Coil Winding |  |  |  | 33763 | 37045 | 4836 | 75644
|  | 1459 | MCWF Unplanned Re-Work | [6 empty] | 0
|  | 1460 | Mod Coil 3rd Winding Station | [6 empty] | 0
|  | 1480 | NCSX Stellerator & Core (what's this???) | [6 empty] | 0
|  | 1501 | Structures Design | [6 empty] | 0
|  | 1550 | Structures Procurement | [6 empty] | 0
|  | 1601 | Coil Services Design | [5 empty] | 142269 | 142269
|  | 1701 | Cryostat Design | [6 empty] | 0
|  | 1702 | Base Support Struct Design | [6 empty] | 0
|  | 1801 | Field Period Assembly (ORNL) | 53047 | [5 empty] | 53047
|  | 1802 | FP Assy Oversight&Support | [5 empty] | 36819 | 36819
|  | 1803 | FP Assy Tooling/Constructability |  | 8074 | 5465 |  |  |  | 13539
|  | 1804 | FP Assy Measurement | [6 empty] | 0
|  | 1805 | FP Assy Hardware & Fixtures | [6 empty] | 0
|  | 1806 | FPA Specs and dwgs |  |  |  |  | 28524 | 55316 | 83840
|  | 1808 | TF/Mod Coil Sub-Assembly | [6 empty] | 0
|  | 1810 | Field Period Assembly | [6 empty] | 0
|  | 1815 | Field Period Assy Station 5 | [6 empty] | 0
|  | 1859 | FP Assy Prototyping & Unplanned Work | [6 empty] | 0
|  | 1901 | Stellerator Core Mgmt/Integration | 187097 | 536784 | 524031 | 466110 | 286904 | 342716 | 2343642
| 2*** |  | NCSX Plasma Heat, Fuel & Vac System | [6 empty] | 0
|  | 2001 | VPS Gas & Conditioning | [6 empty] | 0
|  | 2501 | Neutral Beam Refurbishment | [6 empty] | 0
| 3*** |  | NCSX Diagnostics | [6 empty] | 0
|  | 3101 | Magnetic Diagnostics | [6 empty] | 0
|  | 3901 | Diagnostics Syst Integration | [6 empty] | 0
| 4*** |  | NCSX Electrical Power Syst | [6 empty] | 0
|  | 4101 | AC Power | [6 empty] | 0
|  | 4301 | DC Systems | [6 empty] | 0
|  | 4350 | NCSX Hybrid Power Syst Concept Design | [6 empty] | 0
|  | 4401 | Control & Protection | [6 empty] | 0
|  | 4501 | Power Sys Dsn & Integr | [6 empty] | 0
|  | 4601 | FCPC Bldg Modifications | [6 empty] | 0
| 5*** |  | NCSX Central I&C Syst | [6 empty] | 0
|  | 5801 | Central I&C Integration | [6 empty] | 0
| 6*** |  | NCSX Facility Syst | [6 empty] | 0
|  | 6163 | Facility Systems Support | [6 empty] | 0
|  | 6201 | Cryogenic Systems | [6 empty] | 0
|  | 6501 | Facility Systems Integration | [6 empty] | 0
| 7*** |  | NCSX Test Cell Prep & Machine Assy | [6 empty] | 0
|  | 7101 | Shield Wall MOD Des | [6 empty] | 0
|  | 7301 | Platform Design/Fab | [6 empty] | 0
|  | 7401 | TC Prep & Mach Assy Planning | [6 empty] | 0
|  | 7501 | Construction Crew | [6 empty] | 0
| 8*** |  | NCSX Project Oversight & Suprt | [6 empty] | 0
|  | 8101 | Project Management PPPL | [6 empty] | 0
|  | 8102 | Project Management ORNL | 58590 | 92821 | 103909 | 174539 | 233271 | 167335 | 830465
|  | 8202 | Engr Mgmt & Sys Eng Support | [6 empty] | 0
|  | 8203 | Design Integration | [6 empty] | 0
|  | 8204 | System Analysis | [6 empty] | 0
|  | 8205 | NCSX Dimensional Control | [6 empty] | 0
|  | 8210 | Project Rebaseline Estimating | [6 empty] | 0
|  | 8215 | Plant Design | [6 empty] | 0
|  | 8220 | NCSX Equip Disposition & Facility Restora | [6 empty] | 0
|  | 8221 | NCSX Documentation for closeout | [5 empty] | 38606 | 38606
|  | 8222 | NCSX Manuscripts and Papers | [6 empty] | 0
|  | 8401 | Project Physics PPPL | [6 empty] | 0
|  | 8402 | Project Physics ORNL | 40984 | 105484 |  |  |  |  | 146468
|  | 8501 | NCSX Integrated Sys test Doc | [6 empty] | 0
|  | 8998 | Allocations | [6 empty] | 0
|  |  |  | 1146370 | 2847423 | 2160841 | 1776262 | 1676014 | 1519230 | 11126140