## Cost Spread Sheet FY 01
ORNL COMPACT STELLARATOR SUPPORT NCSX - MONTHLY COST - FY 2003
PRELIMINARY/FINAL DESIGN - K6872
AT5506000
CAPITAL FUNDS (MIE)
PROPOSED
[15 empty] | Adjusted |  | ORNL/ENGR
|  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Total | Budget | % Used | Account | Remarks
Work Package
Limiter Design | WBS 1101 | [15 empty] | K6872LDD
(Goranson) | Labor | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 58 |  | #DIV/0!
| Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 58 | 100 | 58%
Vacuum Vessel Design & Analysis | WBS 1201 | [15 empty] | K6872VVD
(Goranson) | Labor | 0 | 0 | 0 | 0 | 0 | 0 | 36758 | 39874 | 52966 | 42702 | 56837 | 89914 | 319051
| Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub | 0 | 0 | 0 | 0 | 0 | 0 | 36758 | 39874 | 52966 | 42702 | 56837 | 89914 | 319051 | 341513 | 93.42%
Vacuum Vessel R & D | WBS 1202 | [15 empty] | K6872VVR
(Goranson) | Labor | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 58
| Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 58 | 100 | 58%
Modular Coils Design | WBS 1401 | [15 empty] | K6872MCD
(Williamson) | Labor | 0 | 0 | 0 | 0 | 0 | 49 | 53456 | 28718 | 5990 | 29919 | 68334 | 109315 | 295781
| Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7262 | 7262
| Sub | 0 | 0 | 0 | 0 | 0 | 49 | 53456 | 28718 | 5990 | 29919 | 68334 | 116577 | 303043 | 359000 | 84.41%
Modular Coil Analysis | WBS 1402 | [15 empty] | K6872MCA
(Williamson) | Labor | 0 | 0 | 0 | 0 | 0 | 0 | 20523 | 18758 | 7974 | 2353 | 16144 | 18467 | 84219
| Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub | 0 | 0 | 0 | 0 | 0 | 0 | 20523 | 18758 | 7974 | 2353 | 16144 | 18467 | 84219 | 85755 | 98.21%
Modular Coil R&D | WBS 1404 | [15 empty] | K6872MCR
(Williamson) | Labor | 0 | 0 | 0 | 0 | 0 | 0 | 5337 | 16886 | 21921 | 19552 | 7906 | 27323 | 98925
| Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 634 | 0 | 0 | 664 | 0 | 1298
| Sub | 0 | 0 | 0 | 0 | 0 | 0 | 5337 | 17520 | 21921 | 19552 | 8570 | 27323 | 100223 | 142518 | 70.32%
Field Period Assembly | WBS 1801 | [15 empty] | K6872FPA
| Labor | [10 empty] | 26347 | 26700 | 53047
| Material | [12 empty] | 0
| Sub | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26347 | 26700 | 53047 | 70014 | 75.77%
Stellarator Core Management | WBS 1901 | [15 empty] | K6872SCI
and Integration | Labor | 0 | 0 | 0 | 0 | 0 | 48 | 31723 | 19850 | 8931 | 27463 | 21195 | 73651 | 182861
| Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 0 | 966 | 0 | 3173 | 4236
| Sub | 0 | 0 | 0 | 0 | 0 | 48 | 31723 | 19947 | 8931 | 28429 | 21195 | 76824 | 187097 | 210000 | 89.09%
Project Management and | WBS 8102 | [15 empty] | K6872PMC
Control | Labor | 0 | 0 | 0 | 0 | 0 | 0 | 10479 | 8201 | 8789 | 4380 | 8878 | 13930 | 54657
(Lyon, Benson, Akers) | Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3933 | 0 | 0 | 3933
| Sub | 0 | 0 | 0 | 0 | 0 | 0 | 10479 | 8201 | 8789 | 8313 | 8878 | 13930 | 58590 | 58600 | 99.98%
Project Physics (Off-Site) | WBS 8402 | [15 empty] | K6872PPO
(Lazarus) | Labor | 0 | 0 | 0 | 0 | 0 | 0 | 8897 | 0 | 1167 | 0 | 5834 | 25086 | 40984
| Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub | 0 | 0 | 0 | 0 | 0 | 0 | 8897 | 0 | 1167 | 0 | 5834 | 25086 | 40984 | 41400 | 99%
GRAND | TOTAL | 0 | 0 | 0 | 0 | 0 | 97 | 167289 | 133018 | 107738 | 131268 | 212139 | 394821 | 1146370 | 1309000 | 87.58%
*******
|  |  |  | ****** | NOTE: TOTAL budget shown is reduced by $11,000, which was required for commitments associated with buying engineering support
on MOU's from Y-12 for FY 2004. The MOU's cost will be incorporated in the October monthly report.
Total commitments will be increased as funding guidance is provided by OFES.