## Fab Project
WBS 151 Coil Support Structure | [10 empty] | 17 |  | Duration of activity per fiscal year (weeks)
Labor
| Activity Title |  | Manhours | FY2003 $$ | Labor Type | Start Date Month/Yr | End Date Month/Yr | Comments |  |  |  | duration (weeks) | 2002-10-01 | 2003-10-01 | 2004-10-01 | 2005-10-01 | 2006-10-01 | 2007-10-01 | 2008-10-01
Preliminary Design (Title I)
|  | ( 50% of design schedule) | 501.6 |  | EAEM | 2003-10-26 | 2004-02-29 | PPPL Engineer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0 |  | 50 | 50% | of design is preliminary design
|  |  | 333 |  | EADM | 2003-10-26 | 2004-02-29 | PPPL Designer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 168.6 |  | ORNL Eng | 2003-10-26 | 2004-02-29 | Composite of ORNL Engineer / Designer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 0 |  | ORNL Phys. | 2003-10-26 | 2004-02-29 | Composite of ORNL Physics / scientific |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 0 |  | PPPL Phys. | 2003-10-26 | 2004-02-29 | PPPL Physics/scientific |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
Final Design (Title II)
|  | ( 50% of design schedule) | 501.6 |  | EAEM | 2004-02-29 | 2004-07-04 | PPPL Engineer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0 |  | 50 | 50% | of design schedule is final design
|  |  | 333 |  | EADM | 2004-02-29 | 2004-07-04 | PPPL Designer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 168.6 |  | ORNL Eng | 2004-02-29 | 2004-07-04 | Composite of ORNL Engineer / Designer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 0 |  | ORNL Phys. | 2004-02-29 | 2004-07-04 | Composite of ORNL Physicist |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 0 |  | PPPL Phys. | 2004-02-29 | 2004-07-04 | PPPL Physics/scientific |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
Lab R&D labor
|  |  | 0 |  | EAEM | 2003-10-26 | 2004-02-29 | PPPL Engineer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 0 |  | EADM | 2003-10-26 | 2004-02-29 | PPPL Designer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 0 |  | ORNL Eng | 2003-10-26 | 2004-02-29 | Composite of ORNL Engineer / Designer |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 0 |  | EASM | 2003-10-26 | 2004-02-29 | PPPL monthly support |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
|  |  | 0 |  | EMTB | 2003-10-26 | 2004-02-29 | PPPL Technician |  |  |  | 18 | 0 | 18 | 0 | 0 | 0 | 0
Lab Fab/Assembly/Installation (Title III)
|  |  | 720 |  | EAEM | 2004-07-04 | 2006-01-01 | PPPL Engineer |  |  |  | 78 | 0 | 12.7143 | 52.1429 | 13.1429 | 0 | 0
|  |  | 217.6 |  | EADM | 2004-07-04 | 2006-01-01 | PPPL Designer |  |  |  | 78 | 0 | 12.7143 | 52.1429 | 13.1429 | 0 | 0
|  |  | 62.4 |  | ORNL Eng | 2004-07-04 | 2006-01-01 | Composite of ORNL Engineer / Designer |  |  |  | 78 | 0 | 12.7143 | 52.1429 | 13.1429 | 0 | 0
|  |  | 0 |  | EASM | 2004-07-04 | 2006-01-01 | PPPL monthly support |  |  |  | 78 | 0 | 12.7143 | 52.1429 | 13.1429 | 0 | 0
|  |  | 0 |  | EMTB | 2004-07-04 | 2006-01-01 | PPPL Technician |  |  |  | 78 | 0 | 12.7143 | 52.1429 | 13.1429 | 0 | 0
Labor
Manhours per fiscal year by labor category
Level of Effort |  |  |  | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | TOTAL
| PPPL Engineer |  | EAEM | 0 | 1120.5626 | 481.3187 | 121.3187 | 0 | 0 | 1723.2 |  | 263649.6 | 153 | per hour
| PPPL Designer |  | EADM | 0 | 701.4696 | 145.4652 | 36.6652 | 0 | 0 | 883.6 |  | 88360 | 100 | per hour
| Composite of ORNL Engineer / Designer |  | ORNL Eng | 0 | 347.3714 | 41.7143 | 10.5143 | 0 | 0 | 399.6 |  | 51948 | 130 | per hour
| PPPL monthly support |  | EASM | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 100 | per hour
| PPPL Technician |  | EMTB | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 73 | per hour
| Composite of ORNL Physics / scientific |  | ORNL Phy | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 160 | per hour
| PPPL Physics/scientific |  | PPPL Phy | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 141 | per hour
[12 empty] | 2606.8 | 352009.6 | PPPL
[12 empty] | 399.6 | 51948 | ORNL
M&S Costs
| Activity Title |  |  | FY2002 $$ |  | Comment
Manufacturing Development (R&D)
|  | Purchased Design Services |  | 0
|  | Procured Hardware/Material |  | 0
|  | Profit |  | 0 |  | included in hardware estimate
|  | total, manf/dev (R&D) |  | 0 |  | w/o G&A
Procured Hardware/Material
|  | Integrated TF support structure |  | 653496
|  | PF Coil interface structure |  | 48340
|  | TF to modular coil interface structure |  | 112144
|  | subtotal, purchased parts |  | 813980
|  | Profit |  | 65349.6 |  | included in hardware estimate
|  | total, procured hdwe/matl. |  | 879329.6 |  | w/o G&A
| Purchased Design Services |  |  | 0 |  | no purchased services anticipated
| Procured Installation/Assembly Costs |  |  | 0 |  | All installation and assembly costs are included in WBS 7
Other Costs
| Activity Title |  |  | FY2003 $$ |  | Comment
| Travel |  |  | 2 |  | only one trip is anticipated
Summary Costs
| Activity Title |  | Manhours | FY2003 $$ |  | Comment
Labor
| PPPL Effort |  | 2606.8 | 352009.6 |  | Assumed rates: |  | EASM | 100 $/hr
| ORNL effort |  | 399.6 | 51948 |  | EAEM | 153 $/hr | EMTB | 73 $/hr
|  | subtotal, labor | 3006.4 | 403957.6 |  | EADM | 100 $/hr | PPPL Phys | 141 $/hr
[6 empty] | ORNL Eng | 130 $/hr | ORNL Phys | 160 $/hr
M&S, Other
| Manufacturing Development (R&D) |  |  | 0
| Procured Hardware/Material |  |  | 879329.6
| Purchased Design Services |  |  | 0
| Procured Installation/Assembly Costs |  |  | 0
| Travel |  |  | 2
|  | subtotal, M&S |  | 879331.6
| G&A |  |  | 181458.9 |  | 25% | on all purchased materials, subcontracts, travel
[6 empty] | 38374 | G&A adjustment on large procurement
| Subtotal without contingency |  |  | 1464748.1
| Contingency |  |  | 468719.392 |  | 32% | Overall on this WBS
| Total cost |  |  | 1933467.492
Support Structure Local I&C => Moved from WBS 153 | [10 empty] | 11 |  | Duration of activity per fiscal year (weeks)
Labor
| Activity Title |  | Manhours | FY2003 $$ | Labor Type | Start Date Month/Yr | End Date Month/Yr | Comments |  |  |  | duration (weeks) | 2002-10-01 | 2003-10-01 | 2004-10-01 | 2005-10-01 | 2006-10-01 | 2007-10-01 | 2008-10-01
Preliminary Design (Title I)
|  | (50% 0f design schedule) | 48 |  | EAEM | 2006-05-22 | 2006-07-03 | PPPL Engineer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0 |  | #DIV/0! | #DIV/0! | of design is preliminary design
|  |  | 0 |  | EADM | 2006-05-22 | 2006-07-03 | PPPL Designer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 5 |  | ORNL Eng | 2006-05-22 | 2006-07-03 | Composite of ORNL Engineer / Designer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 0 |  | ORNL Phys. | 2006-05-22 | 2006-07-03 | Composite of ORNL Physics / scientific |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 0 |  | PPPL Phys. | 2006-05-22 | 2006-07-03 | PPPL Physics/scientific |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
Final Design (Title II)
|  | (50% 0f design schedule) | 48 |  | EAEM | 2006-07-03 | 2006-08-14 | PPPL Engineer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0 |  | #DIV/0! | #DIV/0! | of design schedule is final design
|  |  | 0 |  | EADM | 2006-07-03 | 2006-08-14 | PPPL Designer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 5 |  | ORNL Eng | 2006-07-03 | 2006-08-14 | Composite of ORNL Engineer / Designer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 0 |  | ORNL Phys. | 2006-07-03 | 2006-08-14 | Composite of ORNL Physicist |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 0 |  | PPPL Phys. | 2006-07-03 | 2006-08-14 | PPPL Physics/scientific |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
Lab R&D labor
|  |  | 0 |  | EAEM | 2006-05-22 | 2006-07-03 | PPPL Engineer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 0 |  | EADM | 2006-05-22 | 2006-07-03 | PPPL Designer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 0 |  | ORNL Eng | 2006-05-22 | 2006-07-03 | Composite of ORNL Engineer / Designer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 0 |  | EASM | 2006-05-22 | 2006-07-03 | PPPL monthly support |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 0 |  | EMTB | 2006-05-22 | 2006-07-03 | PPPL Technician |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
Lab Fab/Assembly/Installation (Title III)
|  |  | 0 |  | EAEM | 2006-08-14 | 2007-01-01 | PPPL Engineer |  |  |  | 20 | 0 | 0 | 0 | 6.8571 | 13.1429 | 0
|  |  | 0 |  | EADM | 2006-08-14 | 2007-01-01 | PPPL Designer |  |  |  | 20 | 0 | 0 | 0 | 6.8571 | 13.1429 | 0
|  |  | 26 |  | ORNL Eng | 2006-08-14 | 2007-01-01 | Composite of ORNL Engineer / Designer |  |  |  | 20 | 0 | 0 | 0 | 6.8571 | 13.1429 | 0
|  |  | 20 |  | EASM | 2006-08-14 | 2007-01-01 | PPPL monthly support |  |  |  | 20 | 0 | 0 | 0 | 6.8571 | 13.1429 | 0
|  |  | 48 |  | EMTB | 2006-08-14 | 2007-01-01 | PPPL Technician |  |  |  | 20 | 0 | 0 | 0 | 6.8571 | 13.1429 | 0
Labor
Manhours per fiscal year by labor category
Level of Effort |  |  |  | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | TOTAL
| PPPL Engineer |  | EAEM | 0 | 0 | 0 | 96 | 0 | 0 | 96 |  | 14688 | 153 | per hour
| PPPL Designer |  | EADM | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 100 | per hour
| Composite of ORNL Engineer / Designer |  | ORNL Eng | 0 | 0 | 0 | 18.9143 | 17.0857 | 0 | 36 |  | 4680 | 130 | per hour
| PPPL monthly support |  | EASM | 0 | 0 | 0 | 6.8571 | 13.1429 | 0 | 20 |  | 2000 | 100 | per hour
| PPPL Technician |  | EMTB | 0 | 0 | 0 | 16.4571 | 31.5429 | 0 | 48 |  | 3504 | 73 | per hour
| Composite of ORNL Physics / scientific |  | ORNL Phy | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 160 | per hour
| PPPL Physics/scientific |  | PPPL Phy | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 141 | per hour
[12 empty] | 164 | 20192 | PPPL
[12 empty] | 36 | 4680 | ORNL
M&S Costs
| Activity Title |  |  | FY2003 $$ |  | Comment
Manufacturing Development (R&D)
|  | Purchased Design Services |  | 0
|  | Procured Hardware/Material |  | 0
|  | Profit at 10% |  | 0
|  | total, manf/dev (R&D) |  | 0 |  | w/o G&A
Procured Hardware/Material
|  | RTDs |  | 1200
|  | Strain gauges |  | 1200
|  | 0 |  | 0
|  | materials for in-house fab |  | 0
|  | Subtotal, purchased parts |  | 2400
|  | Profit at 10% |  | 120
|  | total, procured hdwe/matl. |  | 2520 |  | w/o G&A
| Purchased Design Services |  |  | 0 |  | no purchased services anticipated
| Procured Installation/Assembly Costs |  |  | 0 |  | All installation and assembly costs are included in WBS 7
Other Costs
| Activity Title |  |  | FY2003 $$ |  | Comment
| Travel |  |  | 0 |  | No travel is anticipated for this WBS
Summary Costs
| Activity Title |  | Manhours | FY2003 $$ |  | Comment
Labor
| PPPL Effort |  | 164 | 20192 |  | Assumed rates: |  | EASM | 100 $/hr
| ORNL effort |  | 36 | 4628 |  | EAEM | 153 $/hr | EMTB | 73 $/hr
|  | subtotal, labor | 200 | 24820 |  | EADM | 100 $/hr | PPPL Phys | 141 $/hr
[6 empty] | ORNL Eng | 130 $/hr | ORNL Phys | 160 $/hr
M&S, Other
| Manufacturing Development (R&D) |  |  | 0
| Procured Hardware/Material |  |  | 2520
| Purchased Design Services |  |  | 0
| Procured Installation/Assembly Costs |  |  | 0
| Travel |  |  | 0
|  | subtotal, M&S |  | 2520
| G&A |  |  | 630 |  | 25% | on all purchased materials, subcontracts, travel
| Subtotal without contingency |  |  | 27970
| Contingency |  |  | 5594 |  | 20% | Overall on this WBS
| Total cost |  |  | 33564
Formulas:
FY2005 = '[1]Engr'!B$39
FY2006 = '[1]Engr'!D$39

## Other Costs
|  | 1808-NCSX-1701 | [5 empty] | XX represents the 2 digit WBS code
| Activity Title |  | Manhours | FY2002 $$ | Labor Type | Start Date Month/Year | End Date Month/Year | Comments
Level of Effort | [7 empty] | Research Prep Activities
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Research Planning/Preparations
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Operational Spares
M&S Costs
Manufacturing Development
Purchased Design Services
|  | Procured Hardware/Material | [5 empty] | Include any M&S carried over from FY2002
| Procured Hardware/Material | [6 empty] | Identify each procurement over $100K individually
Purchased Design Services
Procured Installation/Assembly Costs
Other Costs
Travel
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Allocations (WBS 81 only)
Instructions for Completing Form
(1) One form for each 3 digit WBS element (e.g., 111, 121, 452, etc.) => if no 3 digit WBS, use 2 digit WBS (e.g., 81, 82, 84)
(2) For Lab labor, provide estimate in manhours => provide estimate by specific labor type.
(3) For M&S, provide estimate in FY2002 direct dollars if procured by PPPL, or in fully loaded dollars if procured by ORNL
(4) Start and end date provided in month/year format => March/2003
|  | 1808-NCSX-01 | [5 empty] | XX represents the 2 digit WBS code
| Activity Title |  | Manhours | FY2002 $$ | Labor Type | Start Date Month/Year | End Date Month/Year | Comments
Level of Effort | [7 empty] | Research Prep Activities
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Research Planning/Preparations
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Operational Spares
M&S Costs
Manufacturing Development
Purchased Design Services
|  | Procured Hardware/Material | [5 empty] | Include any M&S carried over from FY2002
| Procured Hardware/Material | [6 empty] | Identify each procurement over $100K individually
Purchased Design Services
Procured Installation/Assembly Costs
Other Costs
Travel
FY2003
[5 empty] | RMRM3 |  |  | SAMPLE - Put in specific labor type
[5 empty] | FCEM |  |  | SAMPLE - Put in specific labor type
FY2004
FY2005
FY2006
FY2007
Allocations (WBS 81 only)
Instructions for Completing Form
(1) One form for each 3 digit WBS element (e.g., 111, 121, 452, etc.) => if no 3 digit WBS, use 2 digit WBS (e.g., 81, 82, 84)
(2) For Lab labor, provide estimate in manhours => provide estimate by specific labor type.
(3) For M&S, provide estimate in FY2002 direct dollars if procured by PPPL, or in fully loaded dollars if procured by ORNL
(4) Start and end date provided in month/year format => March/2003

## Engr
WBS 151 Coil Support Structure
Engineering, Title I, II and III
Description:
This effort covers all Title I, II, and III engineering for the coil support structure, which includes the TF and PF structure, the interface structure between the TF coil structure and the modular coil shell assembly, and the interface structure to the base assembly. The pieces of structure are procured via one or more fixed price contracts. All installation oversight will be performed as part of WBS 7. | [5 empty] | Labor category
[6 empty] | total fraction | EAEM |  | EADM |  | ORNL Eng |  | ORNL Physics |  | PPPL Physics
| multiplier | unit | no. | hours |  |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Title I, II design
Pro-E models (avg) | 24 | hrs/model | 31 | 744 |  | 1 | 0.5 | 372 | 0.25 | 186 | 0.25 | 186 | 0 | 0 | 0 | 0
assy dwgs | 40 | hrs/dwg | 11 | 440 |  | 1 | 0.5 | 220 | 0.5 | 220 | 0 | 0 | 0 | 0 | 0 | 0
Detail drawings | 20 | hrs/dwg | 20 | 400 |  | 1 | 0.5 | 200 | 0.5 | 200 | 0 | 0 | 0 | 0 | 0 | 0
installation dwg | 40 | hrs/dwg | 3 | 120 |  | 1 | 0.5 | 60 | 0.5 | 60 | 0 | 0 | 0 | 0 | 0 | 0
cooling schematic | 20 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
electrical schematic | 20 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
I&C schematic | 20 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
stress analysis | 40 | hrs/calc | 3 | 120 |  | 1 | 0.5 | 60 | 0 | 0 | 0.5 | 60 | 0 | 0 | 0 | 0
thermal analysis | 40 | hrs/calc | 0 | 0 |  | 1 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
special analysis (electromagnetics) | 40 | hrs/calc | 0 | 0 |  | 1 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
procurement/fab specifications | 40 | hrs/spec | 0 | 0 |  | 1 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
preliminary and final design reviews | 80 | hrs/rev | 0 | 0 |  | 1 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
meetings/reporting/presentations | 10% | % of tot | 1824 | 182.4 |  | 1 | 0.5 | 91.2 | 0 | 0 | 0.5 | 91.2 | 0 | 0 | 0 | 0
subtotal |  |  |  | 2006.4 |  |  |  | 1003.2 |  | 666 |  | 337.2 |  | 0 |  | 0
[6 empty] | total fraction | EAEM |  | EASM |  | EADM |  | ORNL Eng
Title III | [6 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
vendor oversight, inspection | 8 | hrs/wk | 52 | 416 |  | 1 | 1 | 416 | 0 | 0 | 0 | 0 | 0 | 0
Disposition of deviation requests and non-conformances | 4 | hrs/wk | 78 | 312 |  | 1 | 0.8 | 249.6 | 0 | 0 | 0 | 0 | 0.2 | 62.4
As-built drawings | 8 | hrs/dwg | 34 | 272 |  | 1 | 0.2 | 54.4 | 0 | 0 | 0.8 | 217.6 | 0 | 0
subtotal |  |  |  | 1000 |  |  |  | 720 |  | 0 |  | 217.6 |  | 62.4
Schedule assumptions | start | duration (weeks) | end
Title I Design | 2003-10-26 | 18 | 2004-02-29
Title II Design | 2004-02-29 | 18 | 2004-07-04
Procurement | 2004-07-04 | 52 | 2005-07-03
In-house fab / sub-assy | 2005-07-03 | 0 | 2005-07-03
Installation / final assembly | 2005-07-03 | 26 | 2006-01-01
Notes and worksheets
Coil support structure
| total | integrated TF assembly |  | PF coil interface structure |  | Interface structure to modular coil shell
Pro-E models | 31 | 9 |  | 13 |  | 9 |  | models of all parts
assy dwgs | 11 | 3 |  | 5 |  | 3 |  | typical assemblies of half field period, whole field period, and full structure
Detail drawings | 20 | 6 |  | 8 |  | 6 |  | each part is detailed
installation dwg | 3 | 1 |  | 1 |  | 1
cooling schematic | 0 | [6 empty] | assume passive cooling of base interface structure
electrical schematic | 0
I&C schematic | 0 | [6 empty] | covered in WBS 153
stress analysis | 3 | 1 |  | 1 |  | 1 |  | local analyses of each subsystem
thermal analysis | 0 | [6 empty] | base interface structure heat leak analysis
special analysis | 0 | [6 empty] | seismic analysis
procurement specifications | 0 | [6 empty] | one procurement specification for each major system
preliminary and final design reviews | 0 | [6 empty] | standard reviews
meetings/reporting/presentations | 10%
Support Strucure I&C => moved from old WBS 153
Engineering, Title I, II and III
Description:
This effort covers all Title I, II, and III engineering for the support structure local I&C for Phases I, II, and III of NCSX operation. The sensors and wires will be procured from a qualified vendor. All installation oversight will be performed as part of WBS 7. | [5 empty] | Labor category
[6 empty] | total fraction | EAEM |  | EADM |  | ORNL Eng |  | ORNL Physics |  | PPPL Physics
| multiplier | unit | no. | hours |  |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Title I, II design
Pro-E models | 8 | hrs/model | 0 | 0 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
assy dwgs | 40 | hrs/dwg | 0 | 0 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Detail drawings | 16 | hrs/dwg | 0 | 0 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
installation dwg | 16 | hrs/dwg | 4 | 64 |  | 1 | 1 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
cooling schematic | 0 | hrs/dwg | 0 | 0 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
electrical schematic | 0 | hrs/dwg | 0 | 0 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I&C schematic | 8 | hrs/dwg | 4 | 32 |  | 1 | 1 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
stress analysis | 0 | hrs/calc | 0 | 0 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
thermal analysis | 0 | hrs/calc | 0 | 0 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
special analysis | 0 | hrs/calc | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
procurement specifications | 16 | hrs/spec | 0 | 0 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
preliminary and final design reviews | 0 | hrs/rev | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
meetings/reporting/presentations | 10% | % of tot | 96 | 9.6 |  | 1 | 0 | 0 | 0 | 0 | 1 | 9.6 | 0 | 0 | 0 | 0
subtotal |  |  |  | 105.6 |  |  |  | 96 |  | 0 |  | 9.6 |  | 0 |  | 0
[6 empty] | total fraction | EAEM |  | EASM |  | EADM |  | ORNL Eng
Title III | [6 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
vendor oversight, inspection | 8 | hrs/lot | 1 | 8 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 8
in-house fab/assy oversight and inspection | 2 | hrs/wk | 4 | 8 |  | 1 | 0 | 0 | 1 | 8 | 0 | 0 | 0 | 0
Disposition of deviation requests and non-conformances | 0.5 | hrs/wk | 20 | 10 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 10
As-built drawings | 2 | hrs/dwg | 4 | 8 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 8
Installation oversight and inspection | 0 | hrs/wk | 4 | 0 |  | 1 | 0.25 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 34 |  |  |  | 0 |  | 8 |  | 0 |  | 26
Schedule assumptions | start | duration (weeks) | end
Title I Design, R&D | 2006-05-22 | 6 | 2006-07-03
Title II Design | 2006-07-03 | 6 | 2006-08-14
Procurement | 2006-08-14 | 12 | 2006-11-06
In-house fab / sub-assy | 2006-11-06 | 4 | 2006-12-04
Installation / final assembly | 2006-12-04 | 4 | 2007-01-01
Notes and worksheets
Support structure local I&C
| total |  | TF integrated structure | central solenoid structure |  | Mod coil interface structure
Pro-E models | 0
assy dwgs | 0
Detail drawings | 0 | [5 empty] | typcial drawing for RTD and Strain gage installation
installation dwg | 4 |  | 1 | 2 |  | 1 | PF-1,2,3 share one drawing for RTDs, one for Strain gages
cooling schematic | 0
electrical schematic | 0
I&C schematic | 4 |  | 1 | 2 |  | 1
stress analysis | 0
thermal analysis | 0
special analysis | 0
procurement specifications | 0 | [5 empty] | one specification for RTDs, one for Strain gages incl in WBS 133
preliminary and final design reviews | 0 | [5 empty] | one review for temp/strain instr. Included in WBS 133
meetings/reporting/presentations | 15%
Support Structure Local I&C => from old WBS 153 | [10 empty] | 11 |  |  | Duration of activity per fiscal year (weeks)
Labor
| Activity Title |  | Manhours | FY2003 $$ | Labor Type | Start Date Month/Yr | End Date Month/Yr | Comments |  |  |  |  | duration (weeks) | 2002-10-01 | 2003-10-01 | 2004-10-01 | 2005-10-01 | 2006-10-01 | 2007-10-01 | 2008-10-01
Preliminary Design (Title I)
|  | #DIV/0! | #DIV/0! |  | EAEM | 2006-05-22 | 2006-07-03 | PPPL Engineer |  |  |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | #DIV/0! | of design is preliminary design
|  |  | #DIV/0! |  | EADM | 2006-05-22 | 2006-07-03 | PPPL Designer |  |  |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #DIV/0! |  | ORNL Eng | 2006-05-22 | 2006-07-03 | Composite of ORNL Engineer / Designer |  |  |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #DIV/0! |  | ORNL Phys. | 2006-05-22 | 2006-07-03 | Composite of ORNL Physics / scientific |  |  |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #DIV/0! |  | PPPL Phys. | 2006-05-22 | 2006-07-03 | PPPL Physics/scientific |  |  |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0
Final Design (Title II)
|  | #DIV/0! | #DIV/0! |  | EAEM | 2006-07-03 | 2006-08-14 | PPPL Engineer |  |  |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0! | #DIV/0! | of design schedule is final design
|  |  | #DIV/0! |  | EADM | 2006-07-03 | 2006-08-14 | PPPL Designer |  |  |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #DIV/0! |  | ORNL Eng | 2006-07-03 | 2006-08-14 | Composite of ORNL Engineer / Designer |  |  |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #DIV/0! |  | ORNL Phys. | 2006-07-03 | 2006-08-14 | Composite of ORNL Physicist |  |  |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | #DIV/0! |  | PPPL Phys. | 2006-07-03 | 2006-08-14 | PPPL Physics/scientific |  |  |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0
Lab R&D labor
|  |  | 0 |  | EAEM | 2006-05-22 | 2006-07-03 | PPPL Engineer |  |  |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | EADM | 2006-05-22 | 2006-07-03 | PPPL Designer |  |  |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | ORNL Eng | 2006-05-22 | 2006-07-03 | Composite of ORNL Engineer / Designer |  |  |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | EASM | 2006-05-22 | 2006-07-03 | PPPL monthly support |  |  |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | EMTB | 2006-05-22 | 2006-07-03 | PPPL Technician |  |  |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0
Lab Fab/Assembly/Installation (Title III)
|  |  | 0 |  | EAEM | 2006-08-14 | 2007-01-01 | PPPL Engineer |  |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | EADM | 2006-08-14 | 2007-01-01 | PPPL Designer |  |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | ORNL Eng | 2006-08-14 | 2007-01-01 | Composite of ORNL Engineer / Designer |  |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | EASM | 2006-08-14 | 2007-01-01 | PPPL monthly support |  |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | EMTB | 2006-08-14 | 2007-01-01 | PPPL Technician |  |  |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0
Labor
Manhours per fiscal year by labor category
Level of Effort |  |  |  | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | TOTAL
| PPPL Engineer |  | EAEM | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | #DIV/0! | 153 | per hour
| PPPL Designer |  | EADM | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | #DIV/0! | 100 | per hour
| Composite of ORNL Engineer / Designer |  | ORNL Eng | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | #DIV/0! | 130 | per hour
| PPPL monthly support |  | EASM | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 100 | per hour
| PPPL Technician |  | EMTB | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 73 | per hour
| Composite of ORNL Physics / scientific |  | ORNL Phy | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | #DIV/0! | 160 | per hour
| PPPL Physics/scientific |  | PPPL Phy | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  |  | #DIV/0! | 141 | per hour
[13 empty] | #DIV/0! | #DIV/0! | PPPL
[13 empty] | #DIV/0! | #DIV/0! | ORNL
M&S Costs
| Activity Title |  |  | FY2003 $$ |  | Comment
Manufacturing Development (R&D)
|  | Purchased Design Services |  | 0
|  | Procured Hardware/Material |  | 0
|  | Profit at 10% |  | 0
|  | total, manf/dev (R&D) |  | 0 |  | w/o G&A
Procured Hardware/Material
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | materials for in-house fab |  | 0
|  | 0 |  | 0
|  | Profit at 10% |  | 0
|  | total, procured hdwe/matl. |  | 0 |  | w/o G&A
| Purchased Design Services |  |  | 0 |  | no purchased services anticipated
| Procured Installation/Assembly Costs |  |  | 0 |  | All installation and assembly costs are included in WBS 7
Other Costs
| Activity Title |  |  | FY2003 $$ |  | Comment
| Travel |  |  | 0 |  | No travel is anticipated for this WBS
Summary Costs
| Activity Title |  | Manhours | FY2003 $$ |  | Comment
Labor
| PPPL Effort |  | #DIV/0! | #DIV/0! |  | Assumed rates: |  | EASM | 100 $/hr
| ORNL effort |  | #DIV/0! | #DIV/0! |  | EAEM | 153 $/hr | EMTB | 73 $/hr
|  | subtotal, labor | #DIV/0! | #DIV/0! |  | EADM | 100 $/hr | PPPL Phys | 141 $/hr
[6 empty] | ORNL Eng | 130 $/hr | ORNL Phys | 160 $/hr
M&S, Other
| Manufacturing Development (R&D) |  |  | 0
| Procured Hardware/Material |  |  | 0
| Purchased Design Services |  |  | 0
| Procured Installation/Assembly Costs |  |  | 0
| Travel |  |  | 0
|  | subtotal, M&S |  | 0
| G&A |  |  | 0 |  | 25% | on all purchased materials, subcontracts, travel
| Subtotal without contingency |  |  | #DIV/0!
| Contingency |  |  | #DIV/0! |  | 20% | Overall on this WBS
| Total cost |  |  | #DIV/0!
Formulas:
multiplier = [no.]-[unit]*7
no. = [multiplier, row below]
total fraction = '[1]Engr'!B$39
EAEM = '[1]Engr'!D$39

## R&D
WBS 151 Coil Support Structure
R&D
Description:
No R&D is associated with this WBS
Summary
Purchased Design Services
Vendor surveillance via | 0
subtotal | 0 |  | w/o G&A
Procured Hardware/Material
Cast and machined winding forms | 0
subtotal | 0 |  | w/o G&A
Subcontractor labor rates:
design rate: | 130 | per hour
fab rate | 60 | per hour
inspection/technician rate | 80 | per hour
Support Structure R&D => Moved from WBS 151
R&D
Description:
No R&D is anticipated for this WBS element
Summary
Purchased Design Services | 0 | w/o G&A
design rate | 50 | per hour
Procured Hardware/Material | 0 | w/o G&A
fab rate | 0 | per hour
inspection/technician rate | 1200 | per hour |  |  | Labor category
R&D design | [5 empty] | total fraction | EAEM |  | EADM |  | ORNL Eng |  | EASM |  | Vendor
|  | unit | no. | hours |  |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Task
Pro-E models | 0 | hrs/model | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
assy dwgs | 0 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Detail drawings | 0 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
installation dwg | 0 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
cooling schematic | 0 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
electrical schematic | 0 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
I&C schematic | 0 | hrs/dwg | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
special analysis | 0 | hrs/calc | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
procurement specifications | 8 | hrs/spec | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
vendor shop drawings | 0 | hrs/dwg | 0 | 0 |  | 1 | [8 empty] | 1 | 0
vendor part programming | 0 | hrs/model | 0 | 0 |  | 1 | [8 empty] | 1 | 0
vendor misc engineering | 20% | % of tot | 0 | 0 |  | 1 | [8 empty] | 1 | 0
preliminary and final design reviews | 0 | hrs/rev | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
meetings/reporting/presentations | 10% | % of tot | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
[5 empty] | total fraction |  | EAEM |  | EADM |  | ORNL Eng |  | EASM |  | EMTB
[7 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
R&D Title III
vendor oversight, inspection | 0 | hrs/wk | 4 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
in-house fab/assy, oversight, and inspection | 0 | hrs/wk | 4 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
Testing and experiments | 0 | hrs/wk | 1 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
subtotal |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Schedule assumptions | start | duration (weeks) | end
R&D planning | -53 | 4 | -25
Bid and award | -25 | 2 | -11
R&D procurement / in-house fab. | -11 | 4 | -7
R&D testing | -7 | 1 | 0
Notes and worksheets
Formulas:
start = [no.]-[unit]*7
start = [no.]-[unit]
no. = [start, row below]
no. = '[1]Engr'!D68

## M&S
WBS 151 Coil Support Structure
Materials and Subcontracts (M&S)
Description:
This effort covers manufacturing of the coil support structure, which includes the TF and PF structure, the interface structure between the TF coil structure and the modular coil shell assembly. The pieces of structure are procured via one or more fixed price contracts.
Purchased parts:
Integrated TF support structure | 653496 | see notes below
PF Coil interface structure | 48340
TF to modular coil interface structure | 112144
subtotal, purchased parts | 813980 |  |  |  | vendor 1 | 438 | w/o machining
[5 empty] | vendor 2 | 120 | tie beams
outside engr rate = | 130 | $ per hour |  |  |  | 300 | outer support castings
outside fab rate = | 60 | $ per hour |  |  |  | 110 | inboard support castings
outside inspection/technician rate = | 80 | $ per hour |  |  |  | 530
[5 empty] | vendor 3 | 894
Worksheet:
Coil Support Structures
Integrated TF support structure
Fabrication / parts costs
Item / description |  |  | Value | Unit | Cost $/unit | No. | Cost $
inboard TF support castings |  |  | 550 | lbs | 6 | 12 | 39600 |  | 6600
Machining of inboard TF support casting, 2 setups |  |  | 40 | hrs | 60 | 18 | 43200
Pattern for TF shelf casting (120 deg.) |  |  | 1 | lot | 20000 | 1 | 20000
outboard TF support castings |  |  | 950 | lbs | 6 | 36 | 205200 |  | 34200
Machining of outboard TF support casting, 2 setups |  |  | 40 | hrs | 60 | 18 | 43200
Pattern for outboard TF support casting (120 deg.) |  |  | 1 | lot | 20000 | 1 | 20000
radial tie beam casting |  |  | 141 | lbs | 6 | 36 | 30456 |  | 5076
Radial tie beam machining |  |  | 24 | hrs | 60 | 18 | 25920
Pattern for radial tie beam |  |  | 1 | lot | 10000 | 1 | 10000
Inspection |  |  | 24 | hrs | 80 | 36 | 69120 | 506696
Insulation and shims between castings |  |  | 1 | interface | 2000 | 18 | 36000
misc bolts and assembly hardware |  |  | 1 | lot | 20000 | 1 | 20000
|  |  |  | subtotal Integrated TF structure fab./matl |  |  | 562696 |  | 45876
Subassembly costs
Item / description |  |  | Value | Unit | Cost $/unit | No. | Cost $
Pre-assembly and fit check, crew of 3, 40 hours/assy |  |  | 120 | hrs | 80 | 2 | 19200
rework |  |  | 250 | hrs | 60 | 2 | 30000
technical oversight |  |  | 160 | hrs | 130 | 2 | 41600
|  |  |  | subtotal Integrated TF structure pre-assembly |  |  | 90800
|  |  |  | total, Integrated TF structure |  |  | 653496
|  |  |  | weights |  | ea | no | total
[6 empty] | (lbs) |  | (lbs)
|  |  |  | inboard TF support casting |  | 550 | 12 | 6600
|  |  |  | outboard TF support casting |  | 950 | 36 | 34200
|  |  |  | radial tie beam casting |  | 141 | 36 | 5076
[7 empty] | total | 45876 | lbs
sjdr130-001-c4.asm
sjdr132-001-
PF Coil interface structure
Fabrication / parts costs
Item / description |  |  | Value | Unit | Cost $/unit | No. | Cost $
(PF1, PF 2, PF3 clamps part of WBS 141)
PF 4 clamps |  |  | 5 | lbs | 50 | 18 | 4500
PF 5 clamps |  |  | 5 | lbs | 50 | 18 | 4500
PF 6 brackets |  |  | 10 | hrs | 50 | 18 | 9000
PF 6 clamps |  |  | 5 | interface | 50 | 18 | 4500
misc bolts and assembly hardware |  |  | 1 | lot | 10000 | 1 | 10000
|  |  |  | subtotal PF Coil interface structure fab./matl |  |  | 4500
Subassembly costs
Item / description |  |  | Value | Unit | Cost $/unit | No. | Cost $
Pre-assembly and fit check, 2 hrs/clamp, crew of 2 |  |  | 144 | hrs | 80 | 2 | 23040
technical oversight (1/2 time) |  |  | 80 | hrs | 130 | 2 | 20800
|  |  |  | subtotal PF Coil interface structure pre-assembly |  |  | 43840
|  |  |  | total, PF Coil interface structure subassembiles |  |  | 48340
TF to modular coil interface structure
Fabrication / parts costs
Item / description |  |  | Value | Unit | Cost $/unit | No. | Cost $
Upper and lower IB brackets to modular coil 1 shell, weldments |  |  | 0 | lbs | 15 | 0 | 0
Upper and lower OB brackets to modular coil 1 shell, weldments |  |  | 0 | lbs | 15 | 0 | 0
Upper and lower IB brackets to modular coil 3 shell, weldments |  |  | 100.8 | lbs | 15 | 12 | 18144 |  | 1209.6
Upper and lower OB brackets to modular coil 3 shell, weldments |  |  | 216 | lbs | 15 | 12 | 38880 |  | 2592
Machining, 4 hours per interface, two interfaces/bracket |  |  | 8 | hrs | 60 | 24 | 11520
Shims for all joints |  |  | 1 | interface | 500 | 24 | 12000
misc bolts and assembly hardware |  |  | 1 | lot | 10000 | 1 | 10000
|  | subtotal TF to modular coil interface structure fab./matl |  |  |  |  | 90544 |  | 3801.6
Subassembly costs
Item / description |  |  | Value | Unit | Cost $/unit | No. | Cost $
Pre-assembly and fit check, 1/2 shift / part, crew of 2 |  |  | 96 | hrs | 80 | 2 | 15360
technical oversight (1/2 time) |  |  | 24 | hrs | 130 | 2 | 6240
|  | subtotal TF to modular coil interface structure pre-assembly |  |  |  |  | 21600
|  | total, TF to modular coil interface structure subassembiles |  |  |  |  | 112144
Bracket weight: |  |  | width | height, avg | depth | thickness | weight
|  |  | (in) | (in) | (in) | (in) | (lbs)
Upper and lower IB brackets to modular coil 1 shell, weldments |  |  | 12 | 0 | 4 | 0 | 0
Upper and lower OB brackets to modular coil 1 shell, weldments |  |  | 20 | 0 | 4 | 0 | 0
Upper and lower IB brackets to modular coil 3 shell, weldments |  |  | 12 | 12 | 4 | 1 | 100.8
Upper and lower OB brackets to modular coil 3 shell, weldments |  |  | 20 | 20 | 4 | 1 | 216
Support Structure I&C M&S => Moved from WBS 153
Materials and Subcontracts (M&S)
Description:
This effort covers sensors and connectors for the Support Structure local I&C for Phases I, II, and III of NCSX operation. The sensors and connectors will be procured from a qualified vendor. All installation will be performed as part of WBS 7. All signal conditioning and data acquisition is part of WBS 5.
Assumptions:
outside engr rate = | 120 | $ per hour
outside fab rate = | 60 | $ per hour
outside inspection/technician rate = | 80 | $ per hour
Purchased parts:
RTDs | 1200
strain gages | 1200
subtotal, purchased parts | 2400
Purchased materials for in-house fabrication and sub-assembly
None required | 0
subtotal purchased materials | 0
Worksheet:
RTDs
Number (2*6*2) | 24 | ea
RTD cost each, with connector | 50 | $ each
total for RTDs | 1200
Strain gages
Number (2*6*2) | 36 | ea
strain gage cost each | 50 | $ each | MTS gage with back to back elements that cancel EM field
total for thermocouples | 1800

## Fab_assy
WBS 151 Coil Support Structure
In-house Fabrication and Assembly
Description:
No fabrication and assembly is associated with this WBS |  |  |  |  | Labor category
[5 empty] | total fraction | EAEM |  | EASM, EMSM |  | EMTB |  | EADM
| multiplier | unit | no. | hours |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Fab operations summary
| 0 | hrs/lot | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 0 | hrs/line | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hrs / coil | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
[5 empty] | total fraction | EAEM |  | EASM, EMSM |  | EMTB |  | EADM
Assembly operations summary | [5 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
| 0 | hr/lot | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| 0 | hr/lot | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hr/coil | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hours | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
Support Structure I&C => Moved from WBs 153
In-house Fabrication and Assembly
Description:
The only local assembly anticipated for the support structure local I&C is installation of the sensors. Connection of the sensors is part of WBS 7. |  |  |  |  | Labor category
[5 empty] | total fraction | EAEM |  | EASM |  | EMTB |  | ORNL Eng
| multiplier | unit | no. | hours |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Fab operations
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
none anticipated | 0 | hrs/tile | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
[5 empty] | total fraction | EAEM |  | EASM |  | EMTB |  | ORNL Eng
Assembly operations | [5 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
install | sensors | 1 | hrs/sensor | 0 | 1 | 0 | 0 | 0.2 | 0 | 0.8 | 0 | 0 | 0
[5 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
subtotal |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0
Schedule assumptions | start | duration (weeks) | end
Title I Design, R&D | 0 | 0 | 0
Title II Design | 0 | 0 | 0
Procurement | 0 | 0 | 0
In-house fab / sub-assy | 0 | 0 | 0
Installation / final assembly | 0 | 0 | 0
Notes and worksheets
Formulas:
multiplier = '[1]Engr'!B67
no. = '[1]Engr'!D67

## Installation
WBS 151 Coil Support Structure
Installation
This element is not part of the WBS 1 scope of work
Support Structure I&C => Moved from WBS 153
Installation
This element is not part of the WBS 1 scope of work