Assembly Steps/Major Activities

Potential Issues

- MC Fit-up Check & Surface Insulation

Major Activity

	Verify MC’s of MCHP will come together (Gross Fitup)

- Pre-Measurement of MHCP Type A/B/C Coil Flanges & Interfacing Type Type A Coil Flange

Major Activities

	Verify that the individual coils can be racked into proper shape.

	Verify that metrology measurements can be accurately taken and reproduced.

- Alumina Shim Sizing & Preparation

Major Activity

- Define shim sizes and compress to arrive at satisfactory shim set for MCHP assembly.

- Pre-Installation Station 2 Set-up (for First Article Only)

Major Activity

- Tooling/fixtures setup.

- Pre-Assembly A-A  - (DELETED – ACCOMPLISHED IN STEP 2.0)

Mitigation Plans

- Tooling not rigid enough - RETIRED

- Coils still to flexible - RETIRED

- Alignment not within tolerances bars- RETIRED

- Shim sizes not consistent and cannot be reproduced

- Tooling Rigidity – wedges determined to be adequate

- Coil Flexibility – physically racked (twisted) coils to re-establish coordinate system

- Alignment – iterated until met requirements

- Shims – redesign/order new shims

Assembly Steps/Major Activities

Potential Issues

- A-B Modular Coil Assembly

Major Activities

- Rack A coil & measure.

- Locate nose shim locations on A nose region & install set of shims.

- Install shim bags in wing areas.

- Lower B & measure – install remaining shims, studs, supernuts and torque to 50%.

- Adjust B coil to install nose shims and measure.

- Measure shim puck height at a number of points around puck, raise B coil & install nose shims, lightly tack weld flex nose shims.

- Recheck A alignment during these processes

- Weld A nose shims – measure alignments.

- Once initial A welding & alignment efforts completed, Back Office assess part for compliance.

- On separate fixture, re-measure B coil fiducials – if okay, weld Type B flex shims to plasma side. Back Office assess part for compliance.

- Remove alumina shims on A coil as needed to facilitate re-mating of  B coil to A coil. Re-measure alignment.

- Once alignment okay, install remaining shims, install FUJI paper to measure load sharing. Based on FUJI paper tests, determine proper shim thicknesses.

- One hole at a time, remove supernut & measure hole eccentricity. Select bushing & machine as necessary & install and re-tighten to 50% torque and recheck alignment.

- Install wing support hardware & tighten all bolts to final torque.

- Weld A/B nose region solenoid side & remeasure.

- Fill bushings with Stycast & scan for use in installing C coil to A-B assembly.

Mitigation Plans

- Alignment not within tolerances

- Weld distortion excessive

- Alignment – iterate until meet requirements

  - Weld distortions

    - Internally Reinforce/Rack MC

    - Back Office determine path forward if unable to meet tolerance requirements.

Assembly Steps/Major Activities

Potential Issues

- A-B Coil Assembly to C Coil

Major Activities

- Attach A-B assembly & fixture to another 20° wedge.

- Locate nose shim locations on B nose region & install set of shims.

- Install shim bags in wing areas.

- Lower C & measure – install remaining shims, studs, supernuts and torque to 50%.

- Adjust C coil to install nose shims and measure.

- Measure shim puck height at a number of points around puck, raise C coil & install nose shims, lightly tack weld flex nose shims.

- Recheck A-B assembly alignment during these processes

- Weld B nose shims – measure alignments.

- Once initial B welding & alignment efforts completed, Back Office assess part for compliance.

- On separate fixture, re-measure  C coil fiducials – if okay, weld Type  C flex shims to plasma side. Back Office assess part for compliance.

- Remove alumina shims on B coil as needed to facilitate re-mating of  C coil to A-B coil assembly. Lower C into postion & install remaining shims, & re-measure alignment.

- One hole at a time, remove supernut & measure hole eccentricity. Select bushing & machine as necessary & install and re-tighten to 50% torque and recheck alignment.

- Install wing support hardware & tighten all bolts to final torque.

- Weld B/C nose region solenoid side & re-measure.

- Fill bushings with Stycast.

Mitigation Plans

- Alignment not within tolerances

- Weld distortion excessive

- Alignment – iterate until meet requirements

  - Weld distortions

    - Internally Reinforce/Rack MC

    - Back Office determine path forward if unable to meet tolerance requirements.

Assembly Steps/Major Activities

Potential Issues

- Inflate All Shim Bags

Major Activity

- Fill wing bladders & cure

- Install Trim Coils (MOVED TO STATION 5)

- Complete Local Services  & Interface Details

Major Activity

- Inject Stycast or other suitable compound to fill all shim spaces to trap VV/MC insulation.

- Final Measurements & Transfer MCHP to Holding Area

Major Activities

- Measure all tooling balls & record/save data & run copies of installation procedures.

- Install/identify 3 primary fiducials to be used on Station 3.

- Do final measurements & record results. Measure bolt lengths on all tension fasteners & record/save results.

- Mark part, install base supports, remove from stand & measure weight of completed MCHP.  Remove to holding area.

REPEAT FOR EACH SUBSEQUENT MCHP

Mitigation Plans

Shim bags rupture when filling

- Use double shims bags

- Cleanup coil and proceed

- Determine if replacement of shim bags needed => will require taking coil all apart => ADD TO RISK REGISTER.

NONE

Stiffen supports.

Alignment not within tolerances