Pre-Installation Set-Up

Pre-Assembly of Left MCHP

Pre-Assembly of Right MCHP

Anchor tooling (floor mounted tracks, support carts, adjuster bar, AirLoc Wedgemounts, temporary scaffolding, etc.

Measure CG of MCHPs

Establish global coordinate system and install laser screens.

Perform Metrology for  alignment

Install Station 3 site monuments as needed to perform metrology measurements.

Measure alignment of left & right MCHPs

Potential Issues

Tooling not rigid enough

Alignment not within tolerances bars

5.0 Pre-Assembly Right MCHP

1

4.0 Install Laser Screens/Dry Runs with MCHPs

Establish required assembly path and mark on screens.

Set up lasers & determine alignment – adjust as needed

Do dry runs with MCHPs and evaluate ability of crane to follow path.

Potential Issues

Lasers do not provide accurate positioning

Screens too far or too close

A-A fitup indicates too much deformation in MCHP

Install VV NBI support stand & install VVSA to base support structure

Using metrology, take tooling ball readings to properly position VVSA to global coordinate system.

Potential Issues

Frame too flexible

VVSA distorts & makes lockin errors too large

6.0 Install Left MCHP over VVSA

7.0 Install Right MCHP over VVSA

Move carts out of way & position AirLoc Wedgemount leveler in lowered position

Using SISSCO crane actuators with laser guidance, move MCHP over the VV.  Bring up AirLoc Wedgemount levelers to stabilize unit and measure alignment.

When satisfactory, transfer full load to AirLoc Wedgemount leveler.

Potential Issues

Alignment of coil to vessel incorrect

Interferences between vessel and coil

1

Weld inboard shims and re-measure alignment

Using metro

8.0 Weld Inboard Shims

Potential Issues

Weld distortions exceed tolerances

Attach VV permanent vertical supports at points on Type A MC

Attach VV temporary vertical supports at points on Type B MC

Transfer loads VV vertical supports

Install VV lateral supports & align VVSA to MC

9.0 VVSA Attachments to MC

Potential Issues

Vertical and lateral supports do not provide sufficient stiffness

Unable to achieve desired tolerances

10.0 Transfer Period to NSTX Test Cell

Transfer period to the transfer support frame

Potential Issues

Transfer support frame too flexible and causes period distortions

Repeat for other two periods

END

Plans for Addressing Potential Issues

| Potential Issue |  | Possible Recovery/Mitigation Plan |
| --- | --- | --- |
| Set Up Activities |  |  |
|  | Tooling not rigid enough | - Reinforce tooling - Redesign tooling – add to Risk Register |
|  | Alignment not within tolerances bars | Adjust coils until meet tolerance bands |
| Dry Runs with MCHPs |  |  |
|  | Lasers do not provide accurate positioning | - Ensure lasers operating properly – did during prototyping of principle - Revert to original fixture scheme – add to Risk Register |
|  | Screens too far or too close | Adjust position of screens |
|  | A-A fitup indicates too much deformation in MCHP | Reinforce MCHP |
| Pre-Assembly of Right MCHP |  |  |
|  | Frame too flexible | Reinforce frame with I-beams, etc. |
|  | VVSA distorts & makes lockin errors too large | Reinforce VV (??) |
| Install MCHP over Vacuum Vessel |  |  |
|  | Alignment of coil to vessel incorrect | - Redo alignment until meet requirements - ?? |
|  | Interferences between vessel and coil | ?? |
| Welding Inboard Shims |  |  |
|  | Weld distortions exceed tolerances | - Rack coils into shape (?) - Remove weld and redo until meet requirements |
| VVSA Attachments to MC |  |  |
|  | Vertical and lateral supports do not provide sufficient stiffness | Stiffen supports. |
|  | Unable to achieve desired tolerances | ?? |
| Transfer Period to NSTX Test Cell |  |  |
|  | Transfer support frame too flexible and causes period distortions | ?? |