Assembly Steps/Major Activities

Potential Issues

Mitigation Plans

Assembly Steps/Major Activities

Potential Issues

Mitigation Plans

# Text boxes

- Pre-Installation Set-Up

- Install monuments, floor mounted tracks & Vaccum Vessel base support, measure MCHP CG

- Pre-Assembly of Left MCHP

- Measure MCHP in vertical orientation, including A-A flange

- Pre-Assembly of Right MCHP

- Anchor tooling (floor mounted tracks, support carts, adjuster bar, AirLoc Wedgemounts, temporary scaffolding, etc.

- Establish global coordinate system and install laser screens.

- Perform Metrology for  alignment

  - Install Station 3 site monuments as needed to perform metrology measurements.

  - Measure alignment of left & right MCHPs

4.0 Install Laser Screens/Dry Runs with MCHPs

- Establish required assembly path and mark on screens.

- Set up lasers & determine alignment – adjust as needed

- Do dry runs with MCHPs and evaluate ability of crane to follow path.

- Pre-Assembly Right MCHP

- Install VV NBI support stand & install VVSA to base support structure

- Using metrology, take tooling ball readings to properly position VVSA to global coordinate system.

- Right MCHP changes shape

- A-A fitup indicates too much deformation in MCHP

- Right MCHP shape changes – Back Office review changes & provides new left to right MCHP orientation

- A-A fitup indicates too much deformation in MCHP  - Reinforce MCHP (unlikely feasible)

- Frame too flexible

- VVSA distorts & makes lock-in errors too large

Tooling – reinforce/redesign tooling

  - Frame - Reinforce frame with I-beams, etc.

  - VVSA distortion – tolerances permit realignment

6.0 Install Left MCHP over VVSA

7.0 Install Right MCHP over VVSA\

Note: 6.0 & 7.0 have identical processes

- Move carts out of way & position AirLoc Wedgemount leveler in lowered position

- Using SISSCO crane actuators with laser guidance, move MCHP over the VV.  Bring up AirLoc Wedgemount levelers to stabilize unit and measure alignment.

- When satisfactory, transfer full load to AirLoc Wedgemount leveler

8.0 Weld Inboard Shims

- Weld inboard shims and re-measure alignment

9.0 VVSA Attachments to MC

- Attach VV permanent vertical supports at points on Type A MC

- Attach VV temporary vertical supports at points on Type B MC

- Transfer loads VV vertical supports

- Install VV lateral supports & align VVSA to MC

10.0 Transfer Period to NSTX Test Cell

- Transfer period to the transfer support frame

REPEAT FOR OTHER TWO PERIODS

- Laser path

  - Remove MCHP from vessel

  - Ensure lasers operating properly – as shown  during prototyping of  principle

  - Sceens - Adjust position of screens/reinforce

- Vessel/MCHP profiles not accurate – install Station 3 tooling earlier to check distortions in vertical position

- Damage to component – remove MCHP from vessel & repair damaged component with existing spare

Weld distortions exceed tolerances

  - Install wing chairs to offset distortions

  - Project determine path forward if unable to meet tolerance requirements.

  - If required, coil welds can be ground out & coil separated

NONE IDENTIFIED

Transfer support frame too flexible and allows components to clash during transport

- Buffer and protect individual components

- Install physical stops to prevent motion

Left MCHP changes shape

Left MCHP shape changes – Back Office review changes & provides new left to right MCHP orientation

- Laser path incorrect

- Vessel & MCHP as-built profiles not accurate

- Components damaged during assembly (highly unlikely).

Crane adjustments too coarse

Tooling not rigid enough

Crane accuracy  – adjust variable frequency drive parameters or replace with Generation 3 VFDs