Assembly Steps/Major Activities

Potential Issues

- Component Preparations

- Pre-InstallationSet-Up

Major Activities

- Cut-off short dome port & install insulation system & heater tape/thermocouples system around all ports

- Install period support fixture.

- Install FPA on support stand & engage base of MC.

- Install internal & external working platforms

- VV Port Installation

- Port Boot Seal Assembly Installation

Major Activities

- Install domes, inserting the long port through the MC hole opening & weld dome shell to VV.

- Install small dome ports & remaining circular ports.

- Leak check after each port is welded.

- Install boots on all ports (except Port 4)

\

- Trim Coil Installation

Major Activities

- ???

Mitigation Plans

- Support fixture not stiff enough

Reinforce support fixture with I-beams, etc

- Leak check fails on one or more ports

Identify leak point(s) and repair weld and re-test Reinforce MCHP (unlikely feasible)

Assembly Steps/Major Activities

Potential Issues

6.0 Install MC Lead/Coolant Connections

Major Activities

- Install MC coolant  lines on each MC & position for TF coil installation & routing through PF structure

- Move working platforms as necessary for TF coil installation

7.0 Install Right TF  Assemblies

- Install Left TF Assemblies

- TF Fit-Up Checks

Major Activities

- Rotate 2 individual TF coils one at a time over the MC & temporarily support them (NOTE: final TF coil for this side and left side of FPA cannot be installed until Station 6)

- Attach to temporarily support them off MCs

- Install TF support brackerts & support plates. Include support brackets for final TF coil assembly in Station 6.

- Perform a fit-up check of the 4 TF coils

- Install Ports 4

- Install PF Structural Members & rout MC leads and coolant lines

- Install MC Coolant Manifold

- Install Rogowski Coils

Major Activities

- Tack weld Ports 4 & boots to VV

- Install PF coil support structure

- Install MC coolant manifold & connect cooling lines

- Install Ragoiwski coils

Mitigation Plans

- TF coils do not meet tolerance requirements.

- Weld distortion at Port 4 welds

Assembly Steps/Major Activities

Potential Issues

- Final Measurements

Major Activities

- Obtain set of Period 1 alignment fiducials for lacatin VV within the MC

- Using laser, align tooling balls on each MCHP

- Using monuments on VV  for alignment, bring VV  into proper alignment, adjusting VV supports as necessary.

- Install/verify three primary fiducials to be used in positioning the period in Station 6.

- Make final measurement of all fiducials, VV end flanges, & Type C end flanges

- Perform final checks and acceptance tests.

- Install Right TF  Assemblies

Major Activities

- Transfer completed period to Station 6

REPEAT FOR PERIODS 2 & 3

Mitigation Plans

- Acceptance tests do not pass.