Assembly Steps/Major Activities

Potential Issues

Mitigation Plans

Assembly Steps/Major Activities

Potential Issues

Mitigation Plans

Assembly Steps/Major Activities

Potential Issues

Mitigation Plans

Assembly Steps/Major Activities

Potential Issues

Mitigation Plans

Assembly Steps/Major Activities

Potential Issues

Mitigation Plans

Assembly Steps/Major Activities

Potential Issues

Mitigation Plans

# Text boxes

- Component Preparations

- Test Cell Metrolgy Set-Up & Floor Deflection Test

- Pre-Installation Set-Up & Test

Major Activities

- Assemble support stands, machine base structure, FPA installation carts, spool support stand platforms, & 3 laser support poles.

- Install test cell metrology monuments and perform checks.

- Install laser support base and poles.

- Establish test cell global coordinate system.

- Establish test cell stability by mearing floor deflections.

- FPA-1 Installation & Assembly Test

- Spool Piece Installation Test

- Verification of Station 5 Metrology Data

Major Activities

- Move FPA-1 support fixture to the assembly position & position FPA-1 on the support stand.

- Iterate movement of FPA-1 & support stand between assembly position & the extracted position and accurately measure positions – first on right side and then left side.

- With FPA-1 in extracted position, install the spool support stand on the FPA-1 platform to check if mating of the spool piece and FPA-1 can occur.

- If spool piece tests satisfactory, machine all spool pieces based on metrology data from Station 5.

- Test cell floor deflections exceed tolerances

- Repair/replace assembly stands, structures carts, spool support stands, etc.

- Reinforce floor

- Alignment – iterate until meet requirement

- ???

- Alignment not within tolerances

- Spool piece does not mate with FPA-1

- Alignment – iterate until meet requirements

- ???

Alignment – iterate until meet requirements

- FPA-2 Installation

- FPA-3 Installation

Major Activities

- Move FPA-1 support fixture to the assembly position & position FPA-1 on the support stand.

- Iterate movement of FPA-1 & support stand between assembly position & the extracted position and accurately measure positions – first on right side and then left side.

REPEAT FOR FPA-3

- Measurement of Remaining Type-C MC Flanges

- Type-C Shim Sizing/Preparations

- Type-C Inboard Shim Installation Check

Major Activities

- Measure the VV & Type-C left & right end flanges of Period 3

- Define C-C shim thicknesses, compress shims, and sort by thickness

- Temporarily attach a set of outboard shims and all inboard shims & measure,

- Slowly return all 3 FPA’s to their installed positions.

- Install studs and supernuts at shimmed locations and tighten to 50% - perform “w\iggle test” and replace shims as necessary, & re-measure.

- Return periods to their retracted postions.

- Alignment not within tolerances

- ???

- Alignment – iterate until meet requirements

- ???

- Tolerances exceed requirements

- ???

- Back Office assess readings and provide guidance on how to proceed.

- ???

- Move Each VV to Final Installed Position

- Move TF Coils to Final Installed Position

- Install Lower PF Coils

Major Activities

- One Period at a time, loosen VV supports to permit movement of VV to its final position.  Use metrology to accurately to aid in positioning.

- With all VV secured, enter each NB port & position spool pieces in preparation to weld spool piece & flanges together.

- Remove spool support stand & weld all spool pieces & final port 4’s welds.

- Place boots on all spool pieces.

- Raise the TF centering discs & loosely secure to MC.

- Align TF centering discs & secure to MC shells. Then ,move facing TF coil into the centering disc, one TF coil at a time until all 18 TF coils in proper wedged position. Ensure metrology tolerances met.

- Remove PF access plates from carts, raise PF-5 & PF-6 off the floor & install them off the lower PF structure.

- Install Remaining TF Coils

- Install PF-4 Lower & Solenoid Support Column

Major Activities

- On Period 1, install TF coils at end of the period with full TF support brackets. Use temporary supports as needed.

- Align fiducials  & position each of the 6 TF coils in each period & secure.

- Do final measurements & record results. Repeat for Periods 2 & 3.

- Place PF-4 lower on a temporary position & temporarily place the TF centering discs on top of PF-4.

- Move All Periods to Installed Position

- Install local platforms between each Period to installation of spool support stands.

- Install spool support stands & spool piece and ensure operability.

- Check metrology & then slowly bring together.

- Install local platforms needed to gain access to C-C interface hardware.

- Install studs & supernuts at shimmed locations & torque to 50%. Perform “hand wiggle” test & replace shims as needed.

- Install local support platform in the solenoid region & the TF support structure between each period that spans the interfacing C-C MC shells.

- Determine eccentricity of each hole, select & machine bushings and install.

- Recheck alignment, adjust as needed, & then tighten all C-C flange bolts

- Alignment – iterate until meet requirement

- ???

- Alignment not within tolerances

- Interferences between PF-4 lower & TF centering discs

- Alignment not within tolerances

- Interferences between PF-4 lower & TF centering discs

- Alignment not within tolerances

- ???

- Alignment – iterate until meet requirement

- ???

- Alignment – iterate until meet requirement

- ???

- Transfer  Weight to Final Machine Support Structure

- Install final machine structures & local machine supports

- Following leveling sequence, slowly transfer machine weight from temporary supports to three final support posts.

- Retract 3 FPA carts & remove the FPA support stands & carts from beneath the machine.

- Install inboard machine supports at A-A interface at each Period & engage the machine, loading as required.

- Install Vacuum Pumping System

- Perform VV Pump Down Test

- Install single pump duct, vacuum valve, & turbo pump at lower Port 12 of Period 1.

- Install pumping rack in Period 1 area & check out all connections & position RGA/IG hook-ups.

- Install gas injector system on upper Port 12 on Period 3 *& E-beam mapping & diagnostic equipment.

- Pimp down VV & perform  vessel operational tests.

- Insulation Fill

- Recheck all VV penetrations & fill MC/VV annulus with pourable aerogel insulation.

- Tolerances exceed requirements

- ???

- Alignment not within tolerances

- ???

- Alignment – iterate until meet requirement

- ???

Penetrations not sealed & aerogel insulation escapes.

???

System operations warm test fails.

- Transfer  Weight to Final Machine Support Structure

- Install final machine structures & local machine supports

- Following leveling sequence, slowly transfer machine weight from temporary supports to three final support posts.

- Retract 3 FPA carts & remove the FPA support stands & carts from beneath the machine.

- Install inboard machine supports at A-A interface at each Period & engage the machine, loading as required.

- Install Solenoid & Remaining PF Coils\

- Assemble solenoid & attach solenoid lead lower section to overall solenoid assembly.

- Install solenoid central support column & lower solenoid assembly & temporarily secure it.

- Install  remaining PF coils (PF-4L, PF5U, PF-6U, PF-5L, PF-6L, & PF-4U) and secure.

- Install Rogowski Services

- Install Electrical Services

- Install All I&C Systems

- Install Nitrogen Services

- Perform a Systems Operations Warm Test

- Install 150°C Bakeout System

- Install Cryostat

- Install All Test Cell Platforms

- Tolerances exceed requirements

- ???

- Alignment not within tolerances

- ???

???

- Alignment – iterate until meet requirement

- ???