TPX                          Tokamak Physics Experiment

Systems Integration Plan

(TPX-PLAN-SIP)

Revision A

28 September    1995

Prepared By: ____________________________

Darrell Shimel, Deputy Project Manager

TPX Systems Integration Support Contractor

Approved by:    ___________________________

W. Robinette, Project Manager

TPX Systems Integration Support Contractor

Approved by:    ___________________________

W. Reiersen, TPX Deputy Project Engineer

Approved by:    ___________________________

J. Sinnis TPX Project Engineer

controlled document

This is a controlled document.

To assure, prior to use, that this document is current check the TPX File Share Server

Table of Contents

Page

1.0  INTRODUCTION	1

1.1  PURPOSE	1

1.2  SCOPE	1

1.3  TPX PROJECT SUMMARY.	1

1.4  Applicable documents	2

2.0  PROJECT ORGANIZATION, ROLES AND RESPONSIBILITIES	2

2.1 SYSTEMS INTEGRATION TEAM	6

2.2  PROJECT REVIEW/TRACKING PROCESS	8

2.3  DECISION-MAKING PROCESS	8

3.0  Systems Engineering Process	8

3.1  Requirements Analysis	12

3.1.1  Requirements Documentation Hierarchy	14

3.1.2  Specification Approach	15

3.1.3  Requirements Allocation and Flowdown	19

3.1.4  Design Constraints Development	19

3.1.5  Formal Subsystem Requirements Analysis	21

3.1.6  System Requirements Analysis Database	27

3.2  Design Definition and Integration	28

3.3 RISK MANAGEMENT	28

3.4  System Build, Test, and Demonstration	30

3.4.1  System Build	30

3.4.1.1  Configuration Development	30

3.4.1.1.1 Tokamak Configuration Model	32

3.4.1.1.2  TPX Plant Model	32

3.4.1.1.3  Detail Design Models	32

3.4.2  Integrated System Test Planning	32

3.4.3  Demonstrations	33

3.5 DATA MANAGEMENT AND CONFIGURATION CONTROL	34

3.5.1  Data Management	34

3.5.2.  Centralized Document Control	34

Table of Contents (Continued)

Page

3.5.3  Centralized Drawing Issuance and Control	35

3.5.4  Change Control for Design, Cost and Schedule Baselines	35

3.6  INTERFACE CONTROL PROGRAM & PROCESS	35

3.7 REVIEWS AND AUDITS	36

3.7.1  Design Reviews	36

3.7.1.1  Systems Engineering Master Logic	37

3.7.2  Data Package Review Process	39

3.7.2  Design Review Conduct	45

3.7.3  Audits and Peer Review Direction	47

3.7.3.1  Action Items	47

4.0  ENGINEERING INTEGRATION	50

4.1  RELIABILITY, AVAILABILITY, MAINTAINABILITY (RAM)	50

4.2  VALUE/COST ENGINEERING	50

4.3  QUALITY ASSURANCE (QA)	51

4.4  PARTS, MATERIALS AND PROCESS STANDARDIZATION AND CONTROL	51

4.5  MANUFACTURING/PRODUCABILITY	52

4.6  CONSTRUCTION	52

4.7  TRAINING	53

4.8 TECHNICAL PUBLICATIONS (O&M MANUALS, ETC.)	54

4.9  SYSTEM SAFETY	54

4.9.1  Safety Assessment/Documentation	55

4.9.2  Operational Health and Safety	56

1.0    INTRODUCTION

1.1    PURPOSE

This document has been prepared for the Tokamak Physics Experiment (TPX) Project to describe how the Systems Integration efforts shall be accomplished.    The purpose of this document is to describe the System Integration processes and management practices to be utilized by the TPX Project in accomplishing this mission.    The process through which this objective shall be achieved is described in this document.

## 1.2      SCOPE

This Systems Integration Plan (SIP) defines the processes, organization and procedures used by the TPX Project Office/Systems Engineering to accomplish the systems integration objectives.    This plan complies with DOE-Order 4700.1, and is divided into three major parts: the Project Organization Roles and Responsibilities, the Systems Engineering Process, and the Engineering Integration Process.    This document has been structured to feature the Systems Engineering processes and controls to be implemented on the TPX Project.

## 1.3      TPX PROJECT SUMMARY.

There are several distinguishing features of the TPX Program.    Programatically, TPX addresses several issues critical to the viability of magnetic fusion power plants.    Organizationally it is a multi-institutional partnership to construct and operate the machine and carry out its program mission.    An important part of the construction partnership is the integrated industrial responsibility for design, R&D and construction.    Participating organizations and their roles are discussed further in Section 2.

The TPX physics design takes advantage of recent research on advanced tokamak operating modes achieved for time scales of the order of seconds that are consistent with continuous operation.    This synergism of high performance (higher power density) modes of plasma current driven mostly by internal pressure (bootstrap effect) points towards tokamak power plants that will be cost competitive and operate continuously.

While the TPX will be built primarily to explore advanced physics regimes in the steady state, doing so will have the added benefit of expanding the Tokamak technology base.    Key technology developments will be in steady state power handling with diverters; low activation material usage to allow access to in vessel components during early phases of operation and work areas external to the vessel components throughout the life of the device; design and operation of integrated superconducting magnet systems; and in vessel remote maintenance techniques.    There will be important developments in steady state auxiliary heating systems and in plasma diagnostics systems.    Experimental data will be accessible through wide area networks that allow distributed computing, storage and analysis of the data by the national fusion community.

The TPX will draw upon facilities and systems currently in existence at Princeton Plasma Physics Laboratory that were developed under the TFTR program.    These systems include the TFTR buildings, power supplies, auxiliary heating systems, motor generators, vacuum pumps, instrumentation systems, water cooling systems, utilities and many diagnostic systems.

## 1.4    Applicable documents

This Systems Engineering Plan draws on the documents listed below for support in the areas of planning and control, interface management, documentation management and plant modeling.    Where discussion in addition to that contained in these documents is required it is provided.    In most cases only a brief discussion along with a note directing the reader to refer to the referenced document is provided.

Documents referenced are the latest issues of the:

Program Management Plan    (TPX-PLAN-PMP)

Program Control System    (TPX-PCS)

Data Management Plan* (TPX-PLAN-DMP)

Configuration Management Plan* (TPX-PLAN-CMP)

Change Control Procedure* (TPX-PROC-CCP)

Interface Control Management Plan* (TPX-PLAN-ICMP)

PPPL TPX Plant Models Description Document*

PPPL TPX Plant Models Naming Paper*

TPX Preliminary System Safety Plan*

TPX Reliability, Availability and Maintainability Plan* (TPX-PLAN-RAM)

Test and Evaluation Plan** (TPX-PLAN-TEP)

Value Engineering Plan with **

* Denotes that this document is Prepared by the SIS Contractor

** To be prepared by the SIS Contractor at a later date.

2.0    PROJECT ORGANIZATION, ROLES AND RESPONSIBILITIES

The TPX Project Organization is shown in Figure 2-1. An in-depth discussion of the    Project organizational responsibilities, the Project WBS and responsible organizations can be found in the TPX Program Management Plan.    The System Integration Support (SIS) contractor is the lead organization for implementing the System Integration Processes.    The SIS organization is shown in Figure 2-2.    Then in the TPX organizational chart or in words here identify the organization providing the individual who fills the organizational box.

The TPX Project is supported by established PPPL organizations: Environmental, Safety & Health (ES&H), Quality Assurance/Reliability (QA/R) and Procurement Organizations.

The TPX Project Team and Systems Engineering Organization is supported by the Systems Integration Support (SIS) Contractor who will be responsible for the following:

•	Systems Integration Support Management

•	Coordination of the generation of the systems requirements documentation

•	Coordination of design reviews and action items (chit) follow-up

•	Coordination of configuration management and change control

•	Data Management tasks

•	Configuration Development and Interface Control

•	Plant Design and Modeling

•	Coordination of Reliability, Availability and Maintainability (RAM)

•	Planning, Scheduling and Cost Baseline Maintenance Support

•	Coordinating of Operations and Maintenance Procedure Development

•	Coordination of integrated test planning

•	A & E Services

For most system integration activities the SIS Manager reports to the Project Engineer.    For all activities related to planning, scheduling and cost baseline control, the SIS Manager reports to the Project Control Manager.    For A & E services, the SIS contractor reports to the WBS 41 (Power), WBS 71 (Building Modifications) and WBS 73 (Heating and Cooling) Managers as appropriate Provided in Figure 2-2 is the organization chart for the SIS Contractor,    This figure shows the organization and functions to be performed by the SIS Contractor.

Figure 2-1    TPX Project Organization

As shown in Figure 2-2, the systems integration architecture incorporates both technical and management disciplines.    Systems integration management covers plans and procedures and project control activities. The systems integration technical areas of functional analysis; functional allocation; design definition and integration; system definition; system build, test and demonstrate; and evaluation/optimization are consistent with DOE Order 4700.1.    The TPX approach to each is addressed in section 3.0 of this document.

The systems integration technical areas of functional analysis, functional allocation, design definition and integration, system definition, system build, test and demonstrate and evaluation/optimization are defined in DOE Order 4700.1.

Roles of the functions of several of the SIS support functions described in Figure 2-2 are described in the following documents

•	Systems Requirements - described herein in section 3

•	Design Reviews- described herein in section 3

•	Configuration Management and Change Control - described in    TPX-PLAN-CMP and TPX-PROC-CCP

•	Data Management - described in TPX-PLAN-DMP

•	Configuration Development - described in TPX-PLAN-CMP

•	Interface Control - described in TPX-PLAN-ICMP

•	Plant Design and Modeling    - described in    PPPL TPX Plant Models Description Document

•	Reliability, Availability and Maintainability (RAM) - described in TPX-PLAN-RAM

•	Planning, Scheduling and Cost Baseline Maintenance Support - described in TPX-PCS

•	Integrated System Test Planning    -    TPX-PLAN-TEP

Coordinating of Operations and Maintenance Procedure Development - The SIS contractor will be responsible for coordinating of the writing and implementation of the TPX Operating and maintenance procedures.    In this capacity they shall; review the current procedures for applicability, identify areas where these procedures are deficient and assist in the correction/upgrades of these procedures. In addition they shall identify those areas where no procedures are in existence and assist the Systems Engineering staff in the development of the missing procedures.

In the development stages of TPX, the TPX Construction Management (TCM) will perform in an advisory role to the management team, primarily system engineering, for activities relating to the constructability of the TPX.    During the construction phase the TCM will be responsible for the constriction of the TPX.

Figure 2-2 SIS Contractor Organization

2.1 SYSTEMS INTEGRATION TEAM

To accomplish the System Integration mission, it is necessary to integrate system activities among many project participants.    A Systems Integration Team (SIT) is planned to facilitate this integration.    The SIT will be organized by the Deputy Project Engineer for System Integration with support from the SIS.    It will have representation from each of the TPX program participants.    The SIT provides the vehicle to review system integration progress, coordinate interfacing participants' activities, identify system issues, develop needed action plans, and assign and track action items.    The SIT will also manage the conduct of system trade studies, providing a forum for identifying, prioritizing, tracking, and implementing the needed actions resulting from trade studies.

The SIT will also orchestrate the risk management activities described in Section 3.    In this capacity the SIT will collectively decide what the project risks are, identify appropriate risk mitigation plans/activities and coordinate and track the progress of the risk management activities.      The SIT is supported by the Interface Control Working Group, the System Test Planning Working Group, and other ad-hock working groups formed as needed to address and resolve specific issues.

The SIT will be co-chaired by the    Deputy Project Engineer for System Integration and the SIS Project Manager.    Members will include the Project Control Manager, the Project Physics Manager, the tokamak Construction Manager, the Project Engineering Managers, and selected WBS managers.    Specialty disciplines and other project personnel will participate as needed to support the agenda topics.    It is the intent that this team ensure that all participating organizations have a forum to provide inputs on and discussion of systems integration matters such as requirements interpretation, potential areas of risk, system level trade studies/analyses, coordination of processes, etc.    The purpose of the SIT is to make sure everyone is working to the same ground rules and understandings and to identify problems/issues and plans for resolution.    Resolutions are worked outside the SIT by the responsible organizations and designated working groups. Results are reported back to the SIT.    The SIT will make decisions or facilitate obtaining project decisions    relative to any implementing actions    required.

The SIT will meet on a regularly scheduled basis with a frequency appropriate to the phase of the program and magnitude of system related activities in progress.    The agenda will normally consist of a standard set of agenda items and one or two special topics of interest.    The standard part of the agenda will usually consist of a review of schedule status including the critical path    schedules to first plasma and major, near term milestones; a review of the near term project calendar relative to    upcoming events of significance to System Integration; status reports from the ICWG chairperson, the System Test Planning Working Group chairperson, the SIS contractor, the Tokamak Construction Manager, ad-hock working groups; and a brief around the table summary of items of interest by SIT members.    All standard agenda item status reports are by exception only, i.e., the focus is on problem areas needing attention by the SIT, not a review of on schedule and business as usual activities.    Special topics are selected to allow a more in-depth review of particularly important issues or activities.    Special agenda items are coordinated with the SIS contractor and approved by the SIT chairpersons. Examples might include the results of a major trade study, progress in preparation for a major milestone, or risk management issues.    The SIS status will include a summary of system trade study progress relative to schedule, system requirements development    and allocation progress, design review readiness and close-out progress, a review of recent decisions made and baseline changes, and risk management activity status.

2.2    PROJECT REVIEW/TRACKING PROCESS

TPX Project is responsible for developing and maintaining an integrated cost and schedule management process.    Initially, this process will be implemented by the PPPL cost and scheduling staff.

Provided in the    Project Control System Plan (TPX-PLAN-PCS) is: a detailed discussions of: the TPX Work Breakdown Structure, Work Authorization Procedures, the TPX Planning and Scheduling Control System,    Schedule Baseline Development and Work Plans.    For a detailed description of the PCS refer to the    Project Control System Plan (TPX-PLAN-PCS) available on the PPPL File Server.

The process for establishing cost and schedule baselines is discussed in the Project Control System Plan (PCS) see this document for detailed discussions.

The SIS contractor shall establish the Change Control Procedure (CCP) by which changes to technical, cost and schedule baselines shall be controlled.    In this procedure the levels at which changes are made, the process for making changes and the required authorizing signatures is detailed.

2.3    DECISION-MAKING PROCESS

The decision making process used on the TPX program is essentially one of allowing decisions to be made at the lowest practical levels of line management with responsibility for all the effected participants.    If a situation arises where a higher approval authority is required to resolve conflicts the TPX Project Manager will be the review and approval authority.    The SIT shall provide guidance and coordination for the resolution of unresolved integration related issues.

# 3.0    Systems Engineering Process

The systems engineering process is a comprehensive and iterative problem solving process that is designed to transform validated user requirements and project objectives into a life-cycle balanced set of product and process designs. The systems engineering process as adopted for the TPX program is guided by a synthesis of the systems engineering processes as described in DOE Order 4700.1 (see Figure 3-1) and draft MIL-STD-499B.    Figure 3-2 depicts the systems engineering process flow as tailored to reflect the needs of the TPX program.    At a top level, this process can be considered as consisting of an iterative flow of effort.    The requirements analysis efforts define the problem and the success criteria for a system that can address the problem.    The development of alternatives, the selection of a life-cycle balanced solution, and the description of the solution as a design package is accomplished via design definition and systems analysis and control.

As depicted graphically in Figures 3-1 and 3-2, the elements of this process are performed iteratively, with the products of one element feeding another.    Feedback from the process output is reviewed to assure that the requirements placed on ensuing processes are compatible and executable. Through this process the system definition evolves from initial user and project requirements into a complete design capable of satisfying the mission requirements.    These elements will be further described as they are specifically tailored and implemented for the TPX program in the sections to follow.

Figure 3-1    Systems Engineering Process (Per DOE Order 4700.1)

Figure 3-2    Systems Engineering Process as Tailored for the TPX Program

## 3.1    Requirements Analysis

The initial, or pre-Conceptual Design Phase, configuration has been developed through a process of trade studies; trading potential configurations vs. cost (see Figure 3-4).    This was achieved by developing a detailed cost model based on a "typical" fusion reactor subsystems and "realistic" estimates of the cost to design, develop, construct and operate the system.    This cost model has been developed in a spread sheet (Excel) format.    From this model the Superconducting tokamak configuration was selected for further development.

Figure 3-4 Pre-Concept Engineering Design Definition Process

Once established this pre-Conceptual Design Phase configuration was further evaluated by performing additional performance vs. cost trades (see Figure 3-5).    This iterative process of cost versus performance evaluation was used to develop an optimal cost TPX system configuration.

This "optimized" TPX configuration was further evolved to generate an initial point design with the allocation of functions and requirements to the individual subsystems (See Figure 3-5).    This process resulted in the TPX General Requirements Document (GRD) and the TPX    Project Definition Statement.    At the Conceptual Design Review subsystem requirements were documented in the System Requirements Document.    This document will be replaced by the TPX System Specification (to be developed by the SIS Contractor and TPX Systems Engineering). The System Specification will be brought under control of the TPX Change Control Board and maintained through the process described in Section 3.4.

Figure 3-5    Systems Engineering Design Development Process Flow

In the initial stages of the requirements allocation and design development process the results of trade studies and requirements allocations were documented in the form of design "memoranda".    These memoranda have been catalogued and the pertinent requirements contained in them incorporated into the TPX System Specification.    The design memoranda which are still applicable will be incorporated into the System Requirements Analysis database as requirements references

### 3.1.1    Requirements Documentation Hierarchy

The system requirements for the TPX Project are captured in a hierarchy of requirements documents which at the system level begin with the top-level requirements in the Project Definition Statement (PDS) and end with the detailed engineering requirements within the TPX System Specification (see Figure 3-6).    The top-level requirements for the TPX Project derive from the PDS which represents the contract between the DOE and TPX project management.    These fundamental requirements are further expanded and derived by the TPX physics community in the General Requirements Document (GRD).    The basis for the physics requirements of the GRD is established in the TPX Physics Description Document (PDD).    The requirements of the GRD are implemented in engineering terms in the System Specification which represents a complete set of performance requirements and constraints at the system level as well as initial allocations to TPX subsystems.    These initial subsystem requirement allocations are then further expanded and derived from within subsystem and other lower level specifications as described in Section 3.1.2.

Figure 3-6.    Hierarchy of TPX System Requirements Documentation

The preparation and maintenance responsibilities for the PDS and GRD requirements documents is the SIS Subcontractor.    Additionally, the SIS is responsible for the preparation, signature coordination and for updating and maintaining the TPX System Specification. The WBS managers and associated development organizations are responsible for lower level specification preparation.

a.    The PDS is the responsibility of the TPX Project Director and shall be coordinated with the TPX Program Director, the PPPL Director, and the DOE.

b.    The GRD is the responsibility of the TPX Systems Engineer and shall be coordinated with the TPX Project Engineer and the TPX Physics Manager.

c.    The PDD is the responsibility of the TPX Physics Manager and shall be coordinated with TPX Project Engineer.

d.    The system specification is the responsibility of the SIS contractor and shall be coordinated with the TPX Systems Engineer, the TPX Project Engineer, the TPX Physics Manager, and the TPX Project Director.    The SIS contractor shall ensure that system requirements are complete and traceable from the PDS to the GRD and the GRD to the system specification, and shall ensure that a database is maintained to document the tractability of these requirements and their rationale.

e.    Subsystem specification(s) are the responsibility of each WBS manager and associated development organizations.    Approval of these documents is specified in the Configuration Management Plan.    WBS managers shall ensure that all applicable system level requirements allocated to their system elements are properly treated and accounted for and shall maintain a tractability database to document the tractability of these requirements and their rationale.

### 3.1.2    Specification Approach

Beginning with the TPX System Specification, the TPX Project shall implement a specification approach that is compliant with MIL-STD-490A.    The standard MIL-STD-490A specification types are shown in Figure 3-7.    The SIS contractor shall provide guidance to the Project with respect to the implementation of MIL-STD-490A including the development and maintenance of a specification tree (see Figures 3-8A and 3-8B).    A specification tree identifies the specification hierarchy and relationship among the specifications. For each specification, the specification tree identifies the scope, specification type, and the organization responsible for its development.    The specification tree shall be used to identify and plan for each specification required by the TPX Project.    WBS Managers shall provide specification tree inputs to the SIS contractor for their respective system elements.

| SPECIFICATION | MIL-STD-490A TYPE | PURPOSE |
| --- | --- | --- |
| SYSTEM | A | • Establishes the requirements for the System and characteristics of WBS elements • Defines requirements based upon user’s mission needs as defined in the GRD |
| DEVELOPMENT HARDWARE SOFTWARE | B B1 B2 B5 | • Allocation of development requirements to the WBS items from the system specification • The performance document applicable to subcontractor’s contracts • Defines the methods used to verify the requirements have been met |
| PRODUCT | C C1b C5 | • Product acceptance requirements • Includes design disclosure package for the fabrication requirements |
| PROCESS | D | • Covers manufacturing techniques which require a specific procedure in order that a satisfactory result may be achieved. • Normally applies to production but may cover “process” development . |
| MATERIALS | E | • Prepared to control the develop. of a material. • Normally a material spec applies to product. |

Figure 3-7.    Selected MIL-STD-490A Specification Types

Figure 3-8A.    Specification Tree Approach

Figure 3-8B    Specification Tree Approach Legend

The SIS contractor shall ensure that particular attention is given to the role of specifications and interface control documents in the TPX development process.    The configuration control of subsystem interface design solution agreements among WBS areas is handled through the Interface Control Working Group (ICWG) and the interface control document (ICD) development process (see section 3.6).

The SIS contractor will assist the WBS managers in aligning their configuration items and specification tree organization to be consistent with their planned acquisition/procurement strategy, the planned design integration steps, the design qualification approach, and the component acceptance test need.    The early focus on the specification tree organization assists the project in giving attention to structuring procurement strategy and associated specifications and statements of work which facilitates design integration, design qualification, and acceptance testing of production hardware and software.    The goal is to have as few specifications as possible, but still have sufficient specifications to support meaningful design qualification testing/analysis and production acceptance testing.    The SIS contractor will conduct workshops with the major developing organizations to facilitate the organization of the system into configuration items and their associated specifications.

### 3.1.3    Requirements Allocation and Flowdown

The TPX system requirements defined in the system specification must be allocated and flowed down into the lower-tier specifications for each system element as defined in the specification tree.    Each WBS manager is responsible for developing the lower-tier specifications for their system elements in order to support continued development and procurement as described in section 3.1.2.    The methodology used to accomplish subsystem level requirements analysis is up to each WBS manager, however, that methodology must be consistent with the design constraints development coordination approach discussed in section 3.1.4.    The use of a formal method as described in section 3.1.5 may be appropriate for high risk and/or more complex system elements.

All requirements captured in subsystem specifications will be traceable to the system specification and other source documents as appropriate.    The WBS managers will ensure the maintenance of a requirements database to capture the source and rationale of each requirement and to ensure traceability is maintained between their specifications and to the system specification.

### 3.1.4    Design Constraints Development

As the requirements of the GRD are primarily reflected in the form of functional or performance requirements, additional requirements in the form of design constraints must be developed to completely define the system requirements.    Design constraints are a class of non-functionally derived requirements.    Requirements which do not have to be derived and cannot be modified or dropped as a result of a tradeoff study can generally be considered a constraint.    Most requirements contained within DOE orders (e.g., DOE 6430.1A), standards, and regulations can be treated as constraints.

To facilitate the collection and organization of design constraints, a design constraint matrix (DCM) is utilized (see Figure 3-9).    The rows of this matrix consist of a hierarchy of constraint headings.    The columns of the matrix are utilized to convey information such as the applicability or criticality of the constraints against the system and each system element (typically at the configuration item level).

Figure 3-9    Design Constraint Matrix

For each heading on the DCM where constraints exist, a constraint allocation sheet (CAS) is utilized to document the constraints, their source, and their allocation to none or more system elements (see Figure 3-10).

Figure 3-10 Constraint Allocation Sheet (CAS)

In coordination with the TPX Systems Engineer, the SIS contractor is responsible for defining an overall project approach to the implementation of a design constraints methodology and for developing a complete set of system level design constraints for incorporation into the system specification.    WBS Managers are responsible for the proper allocation of the system level design constraints to their subsystems and for any additional constraints definition that may be required.

### 3.1.5    Formal Subsystem Requirements Analysis

The majority of the requirement analysis effort is complete for the TPX program.    However, there are some incomplete complex and critical TPX subsystems that may benefit from the use of a more formal requirements analysis methodology.    An example is the Central Instrumentation and Control (I&C) systems.    These I&C systems provide the central supervisory control and data handling systems for the TPX program.    These systems interface with the subsystem local I&C systems and allow for control and monitoring of TPX experiments from a local or remote control room and the analysis of the experiment results.    In a case such as I&C, where this more formal requirements analysis is warranted, the Project shall form a TPX Requirements Working Group (RWG) consisting of the TPX Systems Engineer and representatives from the SIS contractor and applicable WBS areas.    The RWG would be responsible for leading a system requirements analysis effort that is consistent with the TPX system engineering and integration processes defined herein. The RWG will function as one of the natural working groups supporting the SIT (see section 2.1).

There are several requirement analysis methodologies that could be used for the TPX program from the latest object oriented approaches to the more traditional functional and data flow analysis approach.    The key is to select a requirements analysis methodology that the participants are comfortable and familiar with.    The functional analysis approach has the longest and most successful track record.    This methodology has proven to be successful on similar complex programs and there are experienced personnel and computer tools that support the approach.

In a functional analysis the objective is to define what the system will do and not how the system will do it.    Every function the system must accomplish to meet requirements needs to be identified and defined in terms of allocated functional, performance, and constraint requirements.    These functions are then decomposed into sub-functions and the process repeated until the system has been completely defined.    In the process, the interfaces and relationships among all functions and sub-functions are defined.    Functional flow diagrams (FFD) are developed to capture the required performance and interactions of the system and its elements.    Figure 3-11 shows a set of primary system functions that should be represented in some form in the top level FFD for any representative system as well as the tasks, activities and actions for each of those primary functions. Figure 3-12 depicts a notional second level functional flow (“Conduct Experimental Operations”) for the TPX system.

Figure 3-11    Primary System Functions

Figure 3-12    Sample Functional Flow Diagram

Requirement Allocation Sheets (RAS) are used document the translation of functions into technical performance requirements.    A RAS is prepared for each function within a functional flow and contains a description of the function and its scope as well as the requirements for that function.    Figure 3-13 depicts a notional RAS for one of the functions included in Figure 3.-12.

| FUNCTION |  |  |  |  |  | ALLOCATION |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| FUNCTION NUMBER AND NAME | CRIT | AREA | REV | TECHNICAL REQUIREMENTS | ITEM NUMBER AND NAME |  |  |
| TPX-1.10 Provide I&C and Data Acquisition |  |  | 1 | Function Description: This function provides the central and local supervisory control and data handling for the TPX System. The function starts upon facility startup and ends at facility shutdown. |  |  |  |
|  |  |  | 1 | REQ-REF: GRD Section 1.12, dated 12 May 1995. 1.0 The TPX facility shall have an instrumentation, control, and data acquisition system that allows coordination of operations and the acquisition, archiving and display of all pertinent operation. | TPX System Specification |  |  |
|  |  |  | 1 | REQ-REF: Engineering Judgment 1.1 The central I & C system shall provide control and monitoring of TPX experiments from a local or remote control room and the analysis of the experiment results. | WBS 61 Central I & C Specification |  |  |
|  |  |  | 1 | REQ-REF: Engineering Judgment 1.2 The local I & C systems shall provide control and data to the central I & C system to allow the performance of experimental operations and the analysis of the results. | WBS XX Specification |  |  |
|  |  |  | 1 | REQ-REF: GRD Section 1.12, dated 12 May 1995 2.0 The operations environment shall provide real-time display of information and allow changes to be implemented during the course of a discharge. | TPX System Specification |  |  |

Figure 3-13    Sample Requirement Allocation Sheet (RAS)

System trade studies and analysis are performed to evaluate alternate system concepts and architectures, support requirements analysis and allocation, and to optimize system design.    The requirement references in the RAS are used to identify the trade study, analysis, meeting or engineering judgment used to generate or derive the requirement.

The primary objective of the requirements analysis process is to generate requirements that are properly stated and represent cost effective life cycle solutions for the system in the specifications.    The RAS includes an identification of the configuration item (specification) that will perform each requirement.    Sorting the requirements documented within RASs for a particular configuration item provides the functional requirements for the specification for that particular configuration item. Properly constructed and structured RASs map easily into the specifications.    Similarly the design constraints contained within the CASs are also easily grouped and mapped into the appropriate specifications.    Figure 3-14 illustrates the mapping of requirements and design constraints into specifications.

Figure 3-14 Mapping Requirements into Specifications

If further requirement analysis is performed for the TPX program for an area such as Central I&C Systems which impacts multiple WBSs, a RWG will be formed as discussed earlier.    The RWG will provide the forum for the baselining of system concepts and requirements.    This coordination of requirements is necessary to minimize the redundancy of effort by the TPX program when allocating requirements to the lower tier specifications.    The SIS contractor could either assist the WBS representatives by providing training and direction or could be the lead performer for the requirements analysis with assistance from the WBS representatives.    In either case, approval procedures are necessary to manage the requirements baseline.    As a minimum, working and approved copies of the requirements would be maintained by the SIS contractor and WBS areas.    The RWG will perform the requirements analyses necessary to allocate the functional performance requirements and design constraints to the configuration items on the specification tree.    They will then sponsor the recommended allocation of requirements to the SIT.    With SIT concurrence, the developing organizations responsible for the applicable configuration item will develop/modify the applicable configuration item development specification(s) to include the allocated requirements.    The detailed procedures for requirements analysis are documented in System Requirements and Design Reviews document (TBD).

### 3.1.6    System Requirements Analysis Database

As discussed earlier, the SIS contractor will maintain the system requirements as defined by the PDS, GRD and TPX System Specification for the TPX Project.    In order to facilitate this task, a system requirements analysis (SRA) database will be developed by the SIS contractor to support the storage and access of data on requirements traceability and the supporting rationale for each requirement in the PDS, GRD, and the TPX System Specification.    The TPX System Specification and the SRA database provide the basis for the individual WBS managers to develop prime item development or "B" Specifications for their subsystems.

The TPX SRA database will be implemented using a commercial off-the-shelf (COTS) database management system.    As a minimum, the PDS, GRD, and TPX System Specification requirements (including design constraints) will be stored within the SRA database.    The information in the database will include the following for each requirement:

•	Requirement text and its associated specification paragraph reference

•	Parent requirements from next higher level specification or in the same specification for subsystem or major components (See Figure 3.1.4-2 for an example specification tree)

•	Child requirements derived in lower level specifications or in same specification for system requirements

•	TPX Project trade study, analysis, or report which provides the rationale used to generate the requirement or to derive the requirement from the higher level requirement

The SRA database will assist the SIS contractor in reviewing specifications for completeness, consistency, and testability.    The database management system will provide the capability to trace all requirements within a specification to the next higher or lower specification in order to identify missing or inconsistent requirements.    In addition, the database management system will allow any individual requirement to be traced to its parent and child requirements.    This capability is important as it facilitates identifying the program impact of changing a requirement.    For example, it may be possible to relax a requirement in the TPX System Specification that is difficult for the TPX System or WBS area to meet due to technical, cost, or schedule constraints.    The SIS SRA database in conjunction with the WBS area requirements databases identifies all PDS, GRD and lower level "B" Specification requirements affected by the proposed change as well as the rationale used to generate or derive the requirements.    This provides the information needed by the program to make an informed decision on whether a requirement can be changed or deleted.

The SIS contractor will maintain and provide configuration control of the TPX SRA database for the PDS, GRD, and TPX System Specification.    The WBS managers are responsible for maintaining the traceability from the TPX System Specification to their lower level specifications in a similar manner.    The SIS contractor will provide a traceability template that the WBS managers can use for documenting traceability that facilitates the import of data into the TPX SRA database.    However, it is not mandatory for the WBS managers to use the template and each WBS manager is free to use their own database or system for maintaining the traceability to the TPX System Specification.    The only constraint is that the WBS managers must be able to demonstrate consistency and completeness by providing the SIS contractor a trace of their top level specifications to the TPX System Specification.

The use and operation of the SRA database and database management system are described in further detail in System Requirements and Design Reviews document (TBD).

## 3.2    Design Definition and Integration

Design definition is that point in the systems engineering process where a design concept is created to satisfy a given set of requirements.    This step is performed iteratively with the requirements analysis process, resulting in increasingly more detailed design concepts as the requirements grow more detailed and become allocated to lower levels within the system.    Typically a set of alternative concepts will be developed and each in turn evaluated to develop the most cost-effective solution based on specific evaluation criteria.    This process will culminate in a detailed design of the entire TPX system including all subsystem elements.    The TPX requirements as defined in the GRD, TPX System Specification and the associated subsystem development specifications are the genesis of the TPX design.

An essential element of the development, documentation and configuration control of system design concepts is a comprehensive set of system configuration development models.    Supported by the detailed designs of the participating organizations, WBS elements, and industry, these models provide the detailed design configuration of the TPX.    The process by which the models will be used to establish the initial designs, integrate the detailed designs of the participating organizations, ensure the establishment and control of the interfaces, and perform integration/validation of the detailed designs is described in the following paragraphs and the related supporting documentation (Data Management Plan and Plant Modeling Plan/Procedures).

3.3 RISK MANAGEMENT

Risk management is a part of the system engineering process in that it assures that the system defined in the System Specification and Configuration Models are feasible and buildable in a timely and cost effective manner.

For purposes of the risk management process, risk is defined as the probability of an undesirable event occurring plus the severity of occurrence if the event occurred.    Un-mitigated risk will have an adverse effect on program cost and schedule and usually is identified with hardware development activities.    As part of the TPX development program PPPL will provide a risk management program to minimize the TPX systems risk This program will provide for early identification of risk and a procedure for measuring risk and developing mitigation activities.    Minimization of risk will be provided through early management oversight allowing for the application of additional resources or development of alternative technologies.    By the application of a risk management process systems engineering will    ensure that the proper trade-offs are performed to determine the best design for risk reduction approaches.    The process to be employed is an adaptation of the risk management program outlined in MIL-STD 499B.

Systems Engineering will create a risk management team (currently anticipated to be a function of the SIT) who's responsibility it will be to identify areas of risk, coordinate the development of risk mitigation plans and monitor performance against these plans.    This team shall be comprised of experts and hardware developers from contractors and national laboratories.    The SIS contractor shall provide support in the form of developing a plan for identification of and integration of risk management into the TPX Project and will track and report on risk management activities.

MIL-STD 499B outlines a risk mitigation program/process and suggests the use of "technical performance measurement" (TPM) as a method of tracking progress against plans for the development of architectures and hardware designs.

A TPM is usually associated with a schedule for the development of hardware or software and is applied through a Technical Achievement Plan (TAP).    A TAP clearly states the objectives relative to the achievement of the development activity and provides a schedule for periodic measuring of achievement against this plan.    Also provided in this plan is a discussion alternative activities should the activity encounter an un-resolvable problem.    Essential to this process is the identification of key milestone events and their dates.    By the identification of milestones and allowing sufficient lead time for decision points actions can be planned and taken in a timely manner to reduce the impact of problems encountered.      The TAP need not be an extensive document.    It should be only sufficiently large and comprehensive as to clearly identify the risk and a scheduled plan to mitigate the risk,      Provided below is a candidate outline for a TAP.

1.0	Introduction (states purpose of the plan and the risk to be reduced)

2.0 	Project impacts (impact if the risk mitigation actions were not taken)

3.0	Risk Drivers    (provides a discussion of those issues which are driving this risk)

4.0	Quantification of the risk    (cost, schedule or performance) including level of risk (high, medium, low) and impact of the risk (high, medium or low)

5.0	Actions being taken to mitigate the risk

6.0	Schedule of development activities being employed to measure progress

7.0	Alternative approaches to mitigate the risk

The calculation of programmatic risk is:

Identified risk items will be assigned a number 3 for high risk, 2 for moderate risk and 1 for low risk.    Summarily, impact will be assigned in the same fashion.    These two numbers will be multiplied and the resultant number used in establishing the program impact.    Values of 8 or 9 will be carried as high programmatic risk items and will be closely monitored for implementation of mitigation actions.    Values of 4 to 6 will be considered moderate risk and will be tracked and reviewed for potential change of status to high risk.    Remaining items will be identified as low risk and will be periodically reviewed (typically on a 6 month interval) for a change of status.    Tracking of risk items will be the responsibility of the SIT supported by the SIS contractor.

To successfully implement this process it is necessary that each laboratory develop a risk management activity to report progress on risk    management activities.

## 3.4    System Build, Test, and Demonstration

The system build process begins design definition and continues until the system is constructed and is ready for its first demonstration.    As part of the systems engineering process, the "build" of this system must be considered as an extension of the requirements analysis and design tasks for all subsystems and components.

3.4.1    System Build

3.4.1.1    Configuration Development

As discussed in the previous section the development models are an extension of the systems requirements allocation process.    These models provide, at the top level, a hardware implementation of the design requirements as defined in Section 3.7 of the TPX System Specification.    An example might be that the TPX System Specification defines the location of the plasma as related to a set of physical dimensions.    To implement this requirement necessitates that the magnets, toroidal, poloidal and error correction, be located in a specific location relative to the plasma.    The "3 dimensional" Tokamak Configuration Model described below is the document which places physical dimensions on the placement of these magnets. These models provide interface design constraints--not functional performance requirements.    This process of developing physical relationships for the subsystems described in the TPX System Specification (Section 3.7) is the primary purpose of the configuration development models.

For this project the configuration development model has been divided into two separate but interrelated models.    These models are: the Tokamak Configuration Model and the TPX Plant Model    These models provide representations of the overall TPX design configuration and provide the allocation of volumetric space to each of the subsystems. The models have two basic functions: A "top down" design function and a composite representation of the bottoms up design.    The    "top down" design function is accomplished early in conceptual design phases to develop a general layout of the tokamak and to provide routing and space allocations requirements and constraints. Although the drawings leading to these allocations are made available to project designers as they are being developed, these space allocations must eventually be captured in specifications or ICD's.

The composite representation of the "bottoms up" design can be used in conjunction with the "top down" design model to check for compliance of the "bottoms- up" designs with the system specifications and ICD space allocations.

Inputs to these models will be provided by the individual WBS elements for inclusion into the Tokamak Configuration Model and the TPX Plant Model.    The combination of all three models provide the mechanical configuration design of the entire TPX System.

The Tokamak Configuration Model and the TPX Plant Model are administered under the Systems Engineering offices by the System Integration Support Contractor as described in the Plant Model Guidance Paper (provided by the SIS contractor as a description of the modeling tools).    These models will be compatible with the automated data storage and retrieval system as described in TPX Data Management Plan .

Provided in the PPPL TPX Plant Models Description Document is an in-depth discussion of the interrelationship of these models.    Also provided is the process for the inclusion of the design details into the Tokamak Configuration Model and the TPX Plant Model and how these models will be used for verification that the individual subsystems meet the design space allocation constraints.    Provided below is a brief overview of these models.

3.4.1.1.1 Tokamak Configuration Model

The Tokamak Configuration Model is used to allocate the finite amount of space available inside and immediately adjacent to the cryostat.    Its primary purpose is to develop a machine topology and design envelope (defining approximate physical size, location and interface designs) for significant components and structures.    It also provides for allocation of "keep-out-areas, manned access portals and maintenance access spaces.

Like the 3.7 Section of the System Specification, which allocates requirements to the subsystems, the envelopes defined in the tokamak configuration model are provided to the WBS managers as a starting point for their detail designs.    These drawings contained in these models will be placed in the TPX automated data storage and retrieval system as described in TPX Data Management Plan for retrieval and use in the control of volumetric and interface designs within and adjacent to the cryostat.

3.4.1.1.2    TPX Plant Model

The purpose of the TPX Plant Model is essentially the same as that described above for the Tokamak Configuration Model, namely to allocate volumetric space for WBS elements.    The TPX Plant Model initially addresses itself to the space outside of the cryostat but will gradually include design representations of components inside the cryostat.    This model uses as baseline inputs the designs of hardware to be retained (e.g., the neutral beam generators), "Test Cell" building, structures and space around the perimeter of the current TFTR facility.    In addition this model will utilize the detailed designs provided by the individual    WBS organizations as inputs.

3.4.1.1.3    Detail Design Models

The detail design models (drawings) will be developed by the individual WBS functions or hardware contractors,    Each configuration item (WBS level) will provide specific system design details in electronic media .    These drawings will provide the details of the designs of the systems or components supplied to the TPX Project and will be the drawings that will govern the design and fabrication of the TPX System.

### 3.4.2    Integrated System Test Planning

System verification is accomplished through a combination of inspection, demonstration, test and analysis activities.    The SIS contractor and the TPX Systems Engineer will establish a cost effective approach to verifying system performance.    Emphasis will be placed on the reduction of overall verification costs and timelines by choosing the lowest level of verification required to verify each system requirement, performing verification at the lowest level of system assembly possible, and by maximizing the number of test objectives that may be satisfied by each test. A verification compliance matrix will be developed and maintained that identifies the verification method and status of each system requirement in order to ensure that all system performance requirements, as documented in the TPX system specification, are verified and all maintenance and operations procedures are validated.

As a large number of system requirements will require verification via test methods, an integrated test planning approach will be utilized in which the various program participants, including Engineering and WBS managers, play a significant role.    System level tests will include activities to verify that subsystems interface properly and individual performance requirements are met, as well as verifying full system operation.    A Test and Evaluation Plan (TEP) will be developed and maintained by the SIS Contractor to establish how the integrated system testing will be performed and managed.

The TEP will include an overview and schedule of the integrated system test program and the purpose, scope, and objective of each system test; test configurations; and test responsibilities.    The SIT will have the additional responsibility of    coordination of the TEP for ultimate approval by the TPX Project Director.    The SIS contractor system test responsible engineer will assist the SIT Chairman in planning agendas, tracking action items, and managing the test planning effort.

The TEP will be developed during the early stages of the program to provide the hardware subcontractors knowledge as to what their system test responsibilities are and within what time frame they occur.    This will enable the subcontractors to do the long range planning necessary to support system testing.    It is expected that, as the design evolves, the system test program may go through changes and the TEP will need to be updated.

In support of specific system test activities, the SIS contractor will provide support to PPPL in conducting and preparing for test readiness reviews (TRRs), tracking test activities, and resolving test issues.

### 3.4.3    Demonstrations

Demonstration or prototyping of critical technologies and development hardware is a cost effective method of reducing risk and will be monitored and controlled through the Risk Management process described in Section 3.3 above.    Demonstrations provide assurance that the system under development is feasible.    Prototypes will developed and evaluated in the earliest stages of the TPX program to assure that the critical components of the system can be manufactured by processes and of materials necessary to meet the mission performance requirements.

For the TPX program it is planned that prototypes of various critical elements of the system will be developed.      System elements which are expected to addressed by demonstration during their development include the superconducting magnet systems, plasma facing components, and the remote maintenance system.

The superconducting magnet system demonstration may consist of a scale model of a TPX magnet built using the same materials and processes as those which will be used in the construction of the toroidal field (TF) and poloidal field (PF) magnet systems.    The plasma facing component demonstrator shall be representative (same configuration and of the same materials fabricated by the same processes) of those materials which will be used in the TPX reactor facility.    Demonstrators of remote maintenance system components shall be prototypes and demonstrated in a "mock up" facility similar to the TPX environment in which they will be operating.    This system shall demonstrate the feasibility and practicality of performing remote maintenance of the plasma facing components including removal and replacement of individual tiles and panels as well as the welding of connecting tubing.

Because of the criticality of the performance of these subsystems it is recommended that the Final Design Reviews of these subsystems not be considered as completed until such a time that the prototype demonstrations have been successfully performed.

### 3.5 DATA MANAGEMENT AND CONFIGURATION CONTROL

#### 3.5.1    Data Management

Data Management is a support function under the auspices of Configuration Management as defined in the Configuration Management Plan (TPX-PLAN-CMP) within the SIS contract.    TPX data management supports reliable integration of TPX component elements through the use defined procedures implemented with an integrated document and drawing control system    (Data Management System).    The TPX Data Management System (DMS) is an automated data management system which encompasses the existing TPX Drawing Control System, the TPX File Sharing System,    as well as a planned commercially-based final DMS to be used for the project.

Please refer to TPX-PLAN-DMP    for details of its function and roles and responsibilities.

3.5.2.    Centralized Document Control

The centralized document and drawing control system using the tools described above and in the Data Management Plan (TPX-PLAN-DMP) provides the mechanism through which review, authentication and configuration control of all TPX drawings and documents will be provided.    The Systems Integration Support contractor shall be responsible for developing, implementing and administering the document and drawing control and configuration management processes and tools.    The SIS contractor is responsible for the development and implementation of a automated storage and retrieval system for all TPX documentation.

3.5.3    Centralized Drawing Issuance and Control

The electronic document and drawing control system will provide access to the TPX drawings.    The drawings located on this system will be essentially of two types, preliminary and controlled.    All participating organizations will have access to the document stored on this system.    However, the system will provide the capability to prevent the change of released documents by persons other than those authorized.    This control shall be maintained through the use of passwords or other methods of controlling changes.    All drawings currently in use on the TFTR will be brought under TPX configuration control and be available through the TPX Configuration Control Secretariat.    The Configuration Control Secretariat is a member of the SIS team who has the responsibilities for recording and tracking the status of all TPX System level released documentation including controlled drawings, program documents and cost and schedule baseline data.

3.5.4    Change Control for Design, Cost and Schedule Baselines

Change Control provides baseline tracking and data management for the TPX program.    The Change Control Process (as defined in the Change Control Procedure (TPX-PROC-CCP)) incorporates the integration of the Change Control Board, electronic databases and file sharing to provide for the participant a means of quick retrieval and accessibility to the real time baseline.

The Change Control Process (CCP) will be organized through the incorporation of a formal board called the Change Control Board (CCB).    The CCB is a nonvoting organization with the Chairperson making all final decisions. The CCB Secretariat or his delegate is the Configuration Control Engineer.    All WBS elements will be represented on the CCB through their functional Engineering Manager.    The change control process is described in the Change Control Procedure (TPX-PROC-CCP), please refer to this document for details.

3.6    INTERFACE CONTROL PROGRAM & PROCESS

Interface Control is that part of the system design integration task that generates and administers technical agreements between two or more activities, when the products, for which management has responsibility, must assemble and/or function together. The Interface Control Working Group (ICWG) is the forum used to reach agreements and control interface activity among the participants (Government, Contractors, or other agencies) including the resolution of interface problems and the documentation of interface agreements.    ICWGs are established to support the development, modification and maintenance of selected interfaces.    Regularly scheduled ICWG meetings manage agreements and establish ICDs to document both functional and physical interface characteristics.

For a detailed discussion of the, functions, operations and roles and responsibilities of the ICWG and its members refer to the Interface Control Management Plan (TPX-PLAN-ICMP).

3.7 REVIEWS AND AUDITS

### 3.7.1    Design Reviews

Design reviews are conducted to assess the technical adequacy of the system baseline as it is developed.    These reviews are conducted in accordance with DOE Order 4700.1A, Project Management System, and tailored to ensure proper development, establishment and control of the TPX Project technical baseline.    They are used to verify conformance with requirements at both the system and element level.

Successful completion of the reviews described below is required for approval to progress from one phase of the program development to the next.    Three formal design reviews are scheduled during the design phase of TPX.    These design reviews are intended to be a formal review and critique of the system, system element, or grouping of related system elements by qualified individuals to verify compliance with system requirements.    Design reviews will also serve as an appropriate point to evaluate and update cost estimates and schedules for completeness and validity.    The three formal review points are:

•	Conceptual Design Review (CDR) - a review of the total project design after the initial scooping of the project and prior to the start of preliminary design.    The TPX system level CDR was accomplished in March, 1993.    The subsystem CDR update for the Heating and Cooling Subsystem (WBS 73) is the only remaining major CDR activity and is scheduled for September, 1995.

•	Preliminary Design Review (PDR) - a review of the completed layout and preliminary design to be accomplished before the start of detailed design.    The PDR is planned to be accomplished on a subsystem by subsystem basis.

•	Final Design Review (FDR) - a review at the completion of the detailed design.    The FDR is also planned to be accomplished on a subsystem by subsystem basis.

In practice, there will be a continuing review of the system and subsystem designs from the beginning of the conceptual design phase through pre-operational testing, and less-formal interim reviews may be scheduled as appropriate.    The design review data package, provided prior to the actual conduct of the review, will be the primary vehicle for communicating the necessary information to assess the completeness and adequacy of the current baseline.

The overall strategy and schedule for TPX design reviews is the responsibility of the TPX Systems Engineer.    Guidance and general support to the TPX Systems Engineer will be provided by the SIS contractor.    The planning, preparation, and conduct of each design review is the responsibility of the applicable WBS Manager for the system element(s) under review.    Any review held at the system level is the responsibility of the TPX Systems Engineer.

### 3.7.1.1    Systems Engineering Master Logic

Successful completion of a design review requires that the design has matured to a level appropriate for the review and that all data necessary to properly evaluate that design is complete.    To facilitate this goal, a systems engineering master logic (SEML) approach will be implemented for the TPX.    The SEML approach is based on the identification of entry requirements that indicate readiness for a review and exit requirements that define review close-out. Success criteria are then established to provide a means to assess satisfaction of the entry and exit requirements.    These data items, as captured by the SEML, establish the essential work flow for successful review of system development.

The SEML is organized around an outline (see Figure 3.-15) that is tailored towards the efforts and products that are required in support of each type of review (e.g., CDR, PDR, FDR).    Entry and exit requirements and their associated success criteria will be established for each applicable element of the outline and captured on the form shown in Figure 3.-16.

Figure 3-15. SEML Outline for a TPX design review meeting

The SIS contractor is responsible for providing guidance on the overall conduct of the SEML approach and for developing the appropriate SEML outline for each review.    The specific content of the SEML will be provided by the applicable WBS manager sufficiently in advance of each design review to ensure that any impacted work plans can be modified, if necessary, to ensure all required tasks are accomplished.    The effort captured by the SEML will be reflected in the work plan schedules to permit an assessment of the overall readiness for the design review.

An example SEML excerpt for the Magnet Systems PDR is provided as Figure 3-17.

Figure 3-16.    Annotated SEML Format

Figure 3-17    Excerpt from the Magnet Systems PDR SEML

#### 3.7.2    Data Package Review Process

Each WBS Manager is responsible for ensuring all necessary tasks are completed in time to support the preparation of the design review data package and the review itself.    Status with respect to SEML task completion will be captured in the regular work plan updates.    The SIS contractor will provide a general assessment with respect to the SEML and design review readiness and closure to the TPX Systems Engineer.

As a goal, WBS Managers will ensure that design review data packages are scheduled for delivery 60 days prior to the start of the review.    This will ensure reviewers have sufficient time to prepare chits against the data package and return them to the performing organization 30 days prior to the review.    This, in turn, allows the performing organization(s) time to prepare responses that can be presented at the review.

During the review of the data package and questions or perceived problems may arise which can not be resolved to the satisfaction of the reviewer.    Chits (formal requests for action to resolve perceived issues) will be prepared (see Figure 3-18 and 3-19) and will be processed as shown in Figure 3-20.    Chit collection and review should be centralized at each organization to ensure appropriateness and to avoid duplication.    Chits will then be submitted to the SIS contractor, who will maintain a log of the chits and assign a draft category per Figure 3-21.    The logged chits are then provided to the design review steering committee to receive a final categorization and disposition.    Only chits designated as requests for action (RFAs) or action items will be assigned for formal action by the steering committee.

The steering committee will consist of representatives from the TPX Project Engineer, TPX Systems Engineer, the appropriate WBS Manager, the SIS contractor and other Project personnel and stakeholders as required.    Non-voting representatives of the applicable contractor/performing organization may called upon to facilitate development of chit resolution plans.    The steering committee will meet as required prior to the design review to review chits against the data package to disposition all chits.    Should a chit originator believe the intent of their chit was misunderstood, that individual can appeal for reconsideration with their appropriate representative on the steering committee.

WBS Managers are responsible for ensuring adequate progress is maintained towards resolving chits and for providing regular status to the SIS contractor.    The SIS contractor will facilitate proper coordination of chit responses and will continue to maintain the chit log and monitor chit progress.

Figure 3-18A Typical Chit Format

Figure 3-19 A Typical Chit Format (Continued)

Figure 3-20A    Chit Action Process

Figure 3-20B    Chit Action Process    (Continued)

| CHIT CATEGORY | DESCRIPTION |
| --- | --- |
| Category 1 | Design review contingent, must be resolved before design review can be closed.. |
| Category 2 | Not necessary for the closure of the present design review, but of enough significance to require formal tracking relative to a downstream project milestone such as the next design review. The chit is associated with another specific milestone and given to the responsible organization for that milestone as well as the SIS to track and make sure resolved by the assigned milestone. |
| Category 3 | rejected as not requiring formal tracking. Where appropriate the chit will be forwarded to the affected development organization for their disposition. |

Figure 3-21.    Chit Categories

3.7.2    Design Review Conduct

Design review meetings (CDR, PDR, FDR FCA and PCA) shall be conducted in an manner to facilitate a thorough exchange of data while maintaining a reasonable pace.    This shall be achieved through the developing and maintaining a detailed agenda for the meeting.    It is advised that "side sessions" be planned to facilitate the exchange of data which may be of particular interest to a particular group.    A proposed meeting agenda shall be submitted with the design review data package and shall generally conform to the outline provided in figure 2.9-1.    The agenda shall be coordinated with and approved by the steering committee chairman prior to the meeting.

Every reasonable attempt shall be made to commence the meetings at the scheduled time and maintain the schedule.    To facilitate this process it is recommended that discussions from the floor, although encouraged, should be limited in duration.    If is should become obvious that a particular discussion is of sufficient content and interest then a separate "off line" meeting should be created for the discussion of this topic.

The design review will be reviewed by a design review steering committee and a project designated review committee.    Roles, responsibilities and membership of these committees are:

DESIGN REVIEW STEERING COMMITTEE

The Design Review Steering Committee will be chaired by the TPX Project Engineer or his designee.    Its membership will include the SIS contractor as the secretariat, the WBS manager responsible for the design review and others as selected by the Steering Committee chairman.    The purpose of the Steering Committee is to orchestrate the design review process including the dispositioning of all chits and other actions required to close the design review.

The Steering Committee membership is selected to allow consideration of budget, schedule and contractual issues in addition to design performance issues when dispositioning chits.

The Steering committee will formally function until the design review has been closed, including the required authentication of specifications and the approval of any required project cost and schedule baseline changes.

The steering committee will meet as required prior to the design review to review chits against the data package to disposition all chits.    Chits against the data package and other open action items will be included as an agenda topic at each design review meeting.    Relevant action items and chits shall be presented in a tabular fashion with disposition/status clearly indicated.    The steering committee shall meet and during, typically at the end of each day of the design review to review the chits/action items generated during that day and disposition each.    The process provided in Figure 3-20A and 3-20B provides a method for the disposition of action items.

PROJECT DESIGNATED REVIEW COMMITTEE

The Project Designated Review Committee members have been selected for their expertise in the critical areas of the design being reviewed.    It is the role of the chairman of this committee to organize the exact manner in which the committee is to operate and to coordinate the committee’s review of the design and design requirements.    The review committee is expected to prepare chits identifying their concerns and requesting project actions to address those concerns.    The review committee is also expected to issue a Design Review Evaluation Report which summarizes their evaluation based upon their “charge letter” from the TPX Project Engineer.    To assure that the Project Designated Review Committee members have the full knowledge of design review related activities, the Steering Committee chairman and SIS contractor will provide the Review Committee chairman and their interested committee members with summary briefings of chits received during the design review from non-review committee members and the projects proposed dispositioning of those chits.    Review Committee members are also welcome to participate in Steering Committee chit disposition meetings.

The Project Designated Review Committee’s formal responsibilities end with the issuance of the Design Review Evaluation Report.

Although the formal design review meeting will be considered closed when discussions on all relevant topics are completed the design review process is not closed until all approved chits and action items are formally dispositioned.

3.7.3    Audits and Peer Review Direction

Independent review and audit groups are sometimes called in to monitor programs such as TPX.    For each formal audit/review event, the SIS contractor will prepare options for the disposition of review findings.    Findings will be assessed with the help of experts as needed and in partnership with PPPL TPX personnel to assure suitable disposition.    This approach assures that findings are handled appropriately and consistent with the objectives of the event.

Findings logs will be used to identify and record, as a minimum:    the findings, reviewer/ auditor who assigned actions, the person responsible for an action, and an agreed time for completion.    This SIS contractor will maintain contact with the assigned performer to ensure that actions are carried out in a timely manner and that the reviewer/auditor of the finding concurs that completion is satisfactory including needed documentation.

3.7.3.1    Action Items

All action items generated at Technical Interchange, SIT    and other program level meetings shall be documented for tracking and closure.    This process is similar to, but less formal that used for tracking "Chits" from design reviews as described above.    The process is as follows:

Action items    will be generated on the form provided in Figure 3-22 by the requesting individual.    All action item forms will be collected and reviewed by the sponsor organization WBS manager for discussion, typically, at the end of day or at the end of the meeting.    The sponsoring organization manager will; 1)attempt to have the appropriate individual answer the action "in real time",    2) accept the action item as written and assign a responsible individual to answer the action item and agree on a date for the completion of the action,    or 3) ask that the action item be rewritten to better describe the action requested and then perform step 1 or 2 above.    Action items may be "rejected" by the manager of the receiving organization if it is agreed that the requested action is "out-of-scope" of his/her current statement of work and or funding constraints.    A manager may not accept an action item for any other performing organization (WBS Element institution or contractor) than his own.    In cases where the requested action lies outside his/her purview the action will be either rejected or reassigned to the correct organization for resolution.    In those cases where more than one performing organization is involved in the resolution of the action item both must accept and agree on the assignee(s) and response date.    All action items must be signed by the requester and accepting WBS manager(s) before being considered as accepted.

Each action item will be assigned a unique number which will allow tracking by the TPX Project and the WBS manager.    The action item numbering shall include the sponsor organization identifier usually an acronym such as LLNL, PPPL ORNL etc., the date of that the action was accepted and a unique identifying number.    An example is LLNL-95-07-10-001.    This would be the first action item accepted at the meeting held on 10 July 1995    sponsored by LLNL.

Figure 3-22    Action Item Request form

4.0    ENGINEERING INTEGRATION

4.1    RELIABILITY, AVAILABILITY, MAINTAINABILITY (RAM)

The TPX RAM Plan describes the requirements, functions, processes and procedures required to effectively implement a RAM Program for the TPX Project.    Specific procedures for RAM program conduct are contained in the RAM Plan.    RAM applies to all TPX Project hardware design, development, production, operations, and support. equipment and software.    Subsystems and critical items produced by WBS contractors and their    subtier contractors are also covered by this Plan.

The SIS contractor shall prepare, publish and maintain the TPX RAM Plan to provide a description of how the RAM effort and tasks will be conducted and integrated into the TPX design to ensure that quantitative reliability requirements and program objectives are met.    Each task will be described in detail with its intended result and output.      The SIS subcontractor is responsible for integrating TPX design, development, testing, production and operational support activities to include the TPX RAM program requirements.

WBS Managers are responsible for optimizing designs for reliability and maintainability through systematic evaluation of design options, and for performing failure modes, effects and criticality analysis (FMECAs) for RAM design improvement and verification.

The SIS contractor will conduct in-process audits and review completed WBS subsystem FMECAs to validate the adequacy of FMECA conduct. As part of the TPX WBS program reviews (PDRs, FDRs, and TIMs) and the WBS RAM program assessment task , the SIS contractor will assist PPPL in conducting WBS RAM program reviews, recommend corrective action where necessary, and follow-up to help assure WBS RAM design optimization.

4.2    VALUE/COST ENGINEERING

The SIS contractor will initiate and administer the TPX Value Engineering (VE) program.    This effort will be accomplished in accordance with DOE 4010.1a and OMB Circular A-131.    The TPX VE program execution will follow the approved plan.

A SIS value engineer will    prepare a Value Engineering Plan (VEP).      This plan will cover VE training for approximately 30 TPX project participants.    This training will be conducted by a certified value specialist (CVS) and discuss VE as applied to one or more TPX processes/activities.

This document will be prepared and delivered at a time mutually agreeable to the SIS Contractor and TPX System Engineering

4.3    QUALITY ASSURANCE (QA)

The TPX QA System provides a framework that defines quality in terms of goals and expectations and establishes processes to fully integrate the quality function into all phases of the program by providing continual, independent, and disciplined reviews/audits of all processes, products, and services.    QA trend analyses against compliance standards and metrics, performed at different points throughout processes, provide conformance assessments over time.    The Quality Assurance Program Plan (QAPP) establishes requirements for measuring and controlling work and for providing management and independent self assessments to find, report, and solve problems.    The describes procedures and practices to meet the specific requirements of the TPX Project.    Revisions or changes to the plan will be subject to review and approval by the project prior to use.

While performing their assigned duties and responsibilities, workers, line management, and immediate supervisors are assigned immediate responsibility for the quality of the project's efforts.    Personnel independent of the activities being performed are assigned the responsibility of verifying and validating that the project's efforts are commensurate with project standards.    All personnel have a responsibility to identify quality problems and to recommend solutions.

This PPPL TPX QAPP describes the Quality Assurance Program established for PPPL TPX activities.    The PPPL TPX QAPP responds to the TPX Project Quality Assurance Program    which requires that Project participants establish plans for implementing the Project quality requirements.    The TPX Project quality requirements are set forth in the TPX Project QA Plan and Project procedures.

Additionally, the QAP defines policies that pertain to the quality of each subcontractor's support services—on-site or off-site.

4.4    PARTS, MATERIALS AND PROCESS STANDARDIZATION AND CONTROL

The purpose of the TPX parts standardization program is to reduce the number of parts types, improve system maintainability, and optimize logistics support by standardizing part types and selecting parts with two or more reliable sources wherever practical.    The SIS contractor will maintain a Master Parts Listing of the TPX parts and materials    The parts    materials list currently in use on the TFTR Project will be used as a starting point the for the TPX Parts and Materials list.    Based on these data and updates provided by the individual WBS organizations, SIS will update and maintain the Master Parts list.      The Master Parts List will be maintained in the TPX Structured Database.    The Master Parts List will be available to the WBS hardware designers in the TPX Structured Database for the purpose of standard parts selection.    The Master Parts list will also be available to WBS logistics support personnel for the purpose of selecting and/or verifying multiple sources for parts procurement and reprocurement.

In addition to the Master Parts List the TPX Project will develop a Vacuum Materials List.    Like the Master Parts List, this list will use the current Vacuum Materials List and as a point of departure.    Additionally, the Vacuum Materials Review committee currently operating on the TFTR Project will continue to be employed as the TPX Materials Review Committee.    All parts and materials used in the vacuum vessels and in a neutron environment will be reviewed by this committee to determine suitability before being incorporated in the design.

4.5    MANUFACTURING/PRODUCABILITY

Each WBS organization assisted by the supporting contractor(s) shall develop a producability and manufacturability plan.    This plan will be the controlling document by which the manufacturability of each configuration item will be evaluated.    The plan shall include a process flow diagram showing each of the major manufacturing operations.    Also    to be identified and draft documents of any special process procedures required to produce the configuration item to be fabricated.    These plans and drafts of the procedures will be provided for review at each contractor’s Preliminary Design Review.      Review will be performed by the SIS and the Tokamak Construction Manager for issues pertaining to manufacturability and constructability issues.

During detailed design these documents will be under the purview of each WBS manager for control and review.    Each WBS manager shall assure that producability and manufacturability are a subject of discussion during each major design review and technical interchange meeting.    As part of the Final Design Review the Producability and Manufacturing Plan for each configuration item    shall be reviewed and approved.

At the time of the Physical Configuration Audit (FCA)    document than will be brought under configuration control to assure that processes are documented and maintained.

4.6    CONSTRUCTION

The Tokamak Construction Manager (TCM) is a support function to the systems integration process through out the preliminary and detailed design phases of the program and shall provide advice on all matters relating to constructability.    Once on contract the TCM will be responsible for creation of the TPX Constructability Plan.    The goal of this plan is to provide guidance on the optimum use of the knowledge and experience of the TCM in the planning, procurement and field assembly of the Tokamak to achieve overall project objectives.    The plan will define the roles and responsibilities of the TCM in the design and construction of the TPX Reactor and associated facilities.

The TPX constructability Plan established the requirements for initial constructability discussions with the designers as well as formal constructability reviews that consider the following main aspects of constructability:

•    Space allocation for ease of construction and maintenance

•    Access for assembly

•    Required assembly sequence

•    Identify construction issues to provide early identification and mitigation of constructability risk issues

•    Encourage designs that enhance development and use of innovative techniques

•    Identify designs features to reduce construction costs

The TPX constructability Plan shall be prepared and delivered on a schedule mutually acceptable to both the TCM and TPX management.

After the program has progressed to the stage of construction the TCM will be responsible for all phases of the construction of the TPX System.    The TCM contractor shall support the CDRs, PDRs, FDRs, FCAs, PCAs and program level technical interchange meetings to review all designs for issues relating to constructability.

4.7    TRAINING

Training for the TPX program will lie within two primary areas.    These are:    Safety and Operation and Maintenance of the TPX.

Safety Training:  is considered to be an important aspect of the Project's program.    The Project's training program will follow the PPPL policy stated in P-008 (“Staff Training”), P-028 (“Subcontractor Training Requirements for the PPPL Site”), and P-029 (“Testing for Training Courses”).    Safety training will be coordinated by the PPPL Certification and Training Division and the PPPL ES&H Division.

O & M Training:  Each organization (laboratory or contractors) shall be responsible for providing initial training and training materials for the operation and maintenance of the systems they provide.    They shall create a plan to provide training on the operation and maintenance of their system    This plan shall include details of the training to be provided including documentation materials and a schedule for the training of experimenters as well as the end user operators.    This plan shall be included as part of the Final Design Review Data Package and shall reviewed and approved by the TPX management, the PPPL Certification and Training Division and the PPPL ES&H Division.

As an integral part of the O&M activities the SIS contractor will provide training of personnel from TPX O&M in use and maintenance of the TPX Data Management System so as to provide access to documents and drawings for operations, maintenance and possible modifications.    This training will include document and drawing control systems as well as the electronic database.

4.8 TECHNICAL PUBLICATIONS (O&M MANUALS, ETC.)

The SIS Contractor will be responsible for the collection and maintenance of a TPX Library containing all technical publications/documents created by support organizations.    This library shall contain all documentation required for the operation and maintenance of the TPX System including plans, procedures and all training materials.    This library will support the centralized document and drawing control system by providing additional documentation required to design, build and maintain the TPX.    After the development phase of the program (after first plasma and the SIS contractor has completed their role) the maintenance of the library shall be the responsibility of PPPL.

The SIS contractor will be responsible for coordinating of the writing and implementation of the TPX Operating and maintenance procedures.    In this capacity they shall; review the current procedures for applicability, identify areas where these procedures are deficient and assist in the correction/upgrades of these procedures. In addition they shall identify those areas where no procedures are in existence and assist the Systems Engineering staff in the development of the missing procedures.    Creation and maintenance of the O&M Manuals including operation and maintenance plans and procedures will be the responsibility of each participating organization.

4.9    SYSTEM SAFETY

The TPX Project uses the PPPL and TFTR Safety Plans as a baseline from which the TPX Safety Plan has been derived.    The TPX Safety Plan is documented in the Program Management Plan Annex II.    In part this plans states:

Safety and protecting the environment have the highest priority in the TPX Project.    PPPL will ensure that the design, development, procurement, manufacture, fabrication, construction, installation, testing, operation, maintenance, modification, and eventual decommissioning of the TPX is accomplished in accordance with the Environment, Safety and Health (ES&H) provisions of:    applicable DOE Orders and other requirements the PPPL Environmental, Safety, and Health Directives (ESHDs); environmental regulations and guidelines of the U. S. Environmental Protection Agency (EPA); and, state and local requirements.    In particular, applicable criteria for routine and accidental occupational and public exposure to radiation will be established in accordance with the requirements of DOE Order 5480.11, DOE Order 5400.5, and USEPA 40 CFR 61, Sub-part H.    Other participants will follow their own ES&H requirements within their own organizations, but must ensure the design, procurement, and manufacture of components destined for PPPL conform to PPPL ES&H requirements.    In the event of conflicts among ES&H requirements, Federal/DOE requirements shall govern (followed by PPPL's requirements) on TPX components.

The PPPL Environment, Safety, and Health Division (ES&HD) is the ultimate authority for ES&H on the TPX Project, and will monitor all aspects of the project to assure that potential hazards are minimized.    Potential hazards will be identified and evaluated, techniques for elimination and/or control of such hazards will be studied, alternatives will be proposed, and risks will be assessed.    The goals of the ES&H function will be the accomplishment of TPX program objectives, within reasonable and acceptable risk, and with the least practicable number of undesirable results (i.e., occurrences, incidents, accidents).

4.9.1    Safety Assessment/Documentation

Safety review and approval of the TPX design by the DOE to permit construction and operation will be facilitated through the preparation of a Preliminary Safety Analysis Report (PSAR) and a Final Safety Analysis Report (FSAR), and through one or more Operational Readiness Reviews (ORRs).    The Idaho National Engineering Laboratory (INEL) has responsibility for preparing the PSAR and FSAR, which will require detailed contributions from Engineering Managers, System Managers, and other members of the TPX management structure and review by the PPPL ES&H Division.    The PSAR will require review and formal acceptance by DOE prior to the start of excavation.    FSAR formal acceptance by DOE will be required to obtain authorization for initial TPX integrated systems testing and subsequent operation.    An ORR will be conducted by a panel of experts to assure that all facility and management systems are in place for safe operation of TPX.    The PSAR and FSAR will document the potential effects on personnel, the public, and the environment associated with the normal and potentially abnormal (accidental) operation of the TPX.    The consequences of operation will be determined, quantified, assigned a specific level of risk and ameliorated through methods of detection and mitigation.

The PPPL ES&HD will provide ES&H review and approval of TPX equipment specifications    and    design drawings prior to their final issuance for use in procurement, construction, and/or installation.    ES&H review and approval will also be required for all written procedures for installation, testing, operation and maintenance, for all proposed changes to items under configuration control, and at all formal design reviews.

Other participants in the TPX Project will design and procure to PPPL ES&H requirements.    This will be accomplished through the participant's implementation of applicable DOE orders and PPPL ES&HDs and by the participation of the PPPL ES&H Division personnel in design reviews.

4.9.2    Operational Health and Safety

The ES&H Division monitors potential hazards for all PPPL projects, and this function will be extended to all aspects of TPX.    Throughout the life of the project, safety aspects in the following areas will be routinely appraised:

•	Construction/Industrial Safety;

•	Electrical Safety;

•	Fire/Emergency Preparedness (with PPPL's Facilities

Engineering and Emergency Preparedness Divisions);

•	Health Physics;

•	Industrial Hygiene;

•	Mechanical/Cryogenic Safety;

•	Nuclear Safety; and

•	Training (through PPPL Certification and Training Division).

For detailed discussions of these topics refer to Attachment II of the TPX PMP