National Compact Stellarator Experiment

NCSX

CD-4 STARTUP PLAN

(WBS-85)

March 25 2008

Prepared by: _______________________________________

C. A. Gentile

Prepared by: _______________________________________

Reviewed by: _______________________________________

Reviewed by: _______________________________________

Approved by:  ______________________________________

D. Rej

# PURPOSE AND SCOPE

The purpose of this Startup Plan is to identify those tasks, documents, actions, and reviews required for meeting the requirements of Critical Decision 4 (CD-4), NCSX First Plasma.  NCSX will be commissioned in a safe, efficient, and compliant manner in accordance with PPPL policies, directives, procedures and DOE orders. It is expected that many of the items required to successfully startup NCSX will occur in parallel with NCSX construction. These tasks include development of NCSX specific procedures and documents including the development of pre-operational test procedures (PTPs) and configuration of existing C-Site subsystems to support experimental operations.

Upon completion of construction, a limited safety certificate will be issued for First Plasma and e-beam mapping.  This plan provides an overview of the Facility Startup Integrated Systems Testing Program, the approval process to proceed to First Plasma, and cost and schedule estimates for accomplishing that program.

# Definitions

## End of Construction

“End of construction” is defined as that physical condition when the NCSX device and facility are assembled. Appropriate sub-systems are available to support Startup ISTP, the hardwired interlock system (HIS) and hardwired control system (HCS) are configured and available to support safe startup activities (per document NCSX-PLAN-SSU-00).

## Startup

“Startup” is defined as that condition where the NCSX (Startup) Test Director has assumed control of NCSX from the NCSX Construction Manager and has configured the device for integrated systems testing as part of the initial facility startup. Such configuration should include safe access control in accordance with subsystem safing procedures.

## first plasma and e-beam TESTING

NCSX will undergo a series of low power (combined field) physics tests for machine characterization and to ensure the proper alignment of field(s).  First Plasma requirements are defined as an ohmically heated discharge with a major radius of 1.4 m, magnetic field of > 0.5 T, plasma current of  > 25 kA, at least 50 % of the rotational transform to be provided by stellarator fields. The tree-dimensional stellarator geometry to be confirmed and documented by video.

Prior to commencement of the NCSX ISTP there are two required reviews. The first of these reviews is an Operational Readiness Assessment (ORA). The second review is performed by the PPPL NCSX Activity Certification Committee (ACC), which will conduct a comprehensive review of NCSX, including physical "walk-downs" and inspections of the machine and appropriate sub-systems to ensure the safety of personnel and machine during low power testing and startup. Upon successful completion of the ACC review a recommendation will be made to the PPPL Environmental Safety & Health (ES&H) Executive Board for the issuance of a limited safety certificate to support NCSX low power testing, first plasma and e-beam mapping in accordance with CD-4.

## ISSUANCE OF A FIRST PLASMA / OPERATIONS SAFETY CERTIFICATE

The issuance of a First Plasma / Operations Safety Certificate by the PPPL ES&H Executive Board, based on the recommendations of the NCSX ACC and the successful completion of the NCSX Operational Readiness Assessment (ORA). should be secured prior to the commencement of the startup ISTP. Upon issuance of the First Plasma / Operations Safety Certificate, and with concurrence of the NCSX Project Manager, the device can then be configured for the CD-4  ISTP, NCSX first plasma and e-beam mapping. The following are applicable documents associated with CD-4 Startup.

- NCSX Facility Startup Integrated Systems Test Procedure (to be provided)

- NCSX Safety Assessment Document (to be provided)

- PPPL ESHD-5008, "Environmental, Safety, and Health Manual"

- NCSX Systems Engineering Management Plan (NCSX-PLAN-SEMP)

# NCSX Subsystems

Table 3-1 provides the listing of the NCSX subsystems that are required for First Plasma and assumed to be available and properly configured for operation before the start of the Facility Startup Integrated Systems Test Procedure (ISTP).

Table 3-1 NCSX Subsystems Needed for Facility Startup ISTP

| WBS | Name |
| --- | --- |
| WBS 12 | Vacuum Vessel Systems |
| WBS 13 | Conventional Coil Systems |
| WBS 14 | Modular Coil Systems |
| WBS 15 | Coil Support Structure Systems |
| WBS 16 WBS 171 | Coil Services Cryostat |
| WBS 172 | Base Support Structure Systems |
| WBS 211 | Gas Fueling Systems |
| WBS 22 | Torus Vacuum Pumping Systems |
| WBS 4 | Power Systems |
| WBS 5 | Central I&C Systems |
| WBS 61 | Water Cooling Systems |
| WBS 62 | Cryogenic Systems |
| WBS 63 | Utility Systems |

# Documents and Procedures

Table 4-1 provides a listing of the PPPL and NCSX documents and procedures anticipated to be needed to support the Facility Startup ISTP.

Table 4-1 Documents and Procedures Needed for Facility Startup ISTP

| Name | Identifier |
| --- | --- |
| Safety Documents |  |
| NCSX Safety Assessment Document (SAD) | TBD |
| PPPL Environmental, Safety, and Health Manual | ESHD-5008 |
| PPPL Engineering & Safety Procedures |  |
| NEPA Review System | ESH-014 |
| Control of Hazardous Energy Sources via Lockout Tagout of Energy Isolation Devices | ESH-016 |
| PPPL Technical Procedures for Experimental Facilities | ENG-030 |
| PPPL Work Planning Procedure | ENG-032 |
| PPPL Engineering Design Verification | ENG-033 |
| NCSX System Engineering Procedures |  |
| NCSX Configuration Control Procedures | NCSX-PROC-002 |
| NCSX Interface Control Procedures | NCSX-PROC-003 |
| NCSX Work Planning Procedures | NCSX-PROC-004 |
| PPPL Operating Procedures |  |
| Control of Workplace Cleanliness Around D-Site Experimental Area | OP-AD-24D |
| Control Of Temporary Modifications | OP-AD-31D |
| Conduct of Operations | OP-AD-39 |
| Control of Equipment and System Status (Chain of Command) | OP-AD-56 |
| NCSX Operating Procedures |  |
| Preparations of Experimental Areas for Machine Operations | TBD |
| Testing the NCSX (High Power Interlock System (HIS) with Areas Safe for Access | TBD |
| Testing the NCSX Emergency Stop System | TBD |
| Operation of the NCSX Access System | TDB |
| NCSX Training Matrix | TBD |
| NCSX Operations Guide for Startup and Shutdown | TBD |
| High Power Pulsing (HPP) Daily Operations | TBD |
| Preparation for NCSX Pumpdown | TBD |
| Daily Hi-Pot Test of the NCSX Vacuum Vessel | TBD |
| Leak Checking of NCSX Cryostat Operation | TBD TBD |
| Pre-Operational Test Procedures (PTPs) |  |
| Coil Energization Tests | TBD |
| NCSX De-Ionized Water/System Testing | TBD |
| NCSX Coil System Preoperational Tests | TBD |
| ECS HiPot Tests Cryostat | TBD TBD |

# Elements of the Facility Startup ISTP

The Facility Startup Integrated Systems Test Procedure (ISTP) will be executed to establish the readiness of the device and facility for First Plasma and subsequent experimental operations.  The ISTP is expected to include the following steps. Section 6.1, 6.3, 6.4, 6.5 are required to be in place for Low Power Physics Testing.

## Facility Preparations

- Machine area scrubs complete.

- Work permits reviewed and closed out as appropriate.

- Installation procedure run copies reviewed and closed out as appropriate.

- Status of temporary modifications to NCSX operating equipment reviewed.

- Bus/coil/power systems walkdown complete.

- Testing of the Hardwired Interlock System (HIS) with areas safe for access complete.

- Emergency Stop system testing complete.

## Vacuum Vessel Pumpdown and Testing

- Preliminary vacuum vessel high-pots successfully completed.

- Preparations for NCSX pump down complete.

- Vacuum vessel pumpdown complete.

- Leak checking of Vacuum Vessel successfully completed in preparation for bakeout.

## Preparations for Coil Energization

- NCSX prepared for operations per the daily start-up procedure.

- NCSX prepared for high power pulsing (HPP) operations.

- Coil and bus system high potential and circuit resistance measurements complete.

- Pre-operational testing of coil systems complete.

# Approval for Coil Energization and First Plasma

The coil energization tests represent the first time the coils have been subject to design-level currents and voltages in situ and the first time there has been the potential for plasma formation with the associated radiation hazards.  Detailed requirements for coil energization will be documented in appropriate field coil Pre-operational Test Procedures (PTP's) and in the startup Integrated System Test Procedure (PTP's).  During certain phases of testing the vacuum vessel will be maintained at atmosphere to ensure that a  plasma will not form during the early testing phase.

## Coil Energization Approval Requirments

Prior to coil energization testing, a Safety Certificate for (limited) operation must be issued. The Safety Certificate is issued after the Activity Certification Committee (ACC) has made appropriate presentation and recommendation to the PPPL ES&H Executive Board for the safe startup and operation of the device.

## First Plasma Approval Requirements

The following reviews and approvals will need to occur prior to First Plasma:

- SRC review and approval of NCSX SAD;

- Review and approval of technical documents in Section 4 of this plan;

- Operational Readiness Assessment Review (ORA)

- ACC review and walk-down of NCSX and MIE subsystems;

- Approval by ES&H Executive Board for issuance of Safety Certificate;

- Concurrence from the Test Director, NCSX Chief Operating Engineer, and ACC that all subsystem PTPs (for First Plasma) have been successfully completed; and

- Approval by the NCSX Project Manager to commence First Plasma.

# Cost and Schedule

It is estimated that it will take approximately 10 weeks from issuance of the Limited Safety Certificate through First Plasma, including e-beam mapping. This estimate is based on past experience with the execution of ISTPs on similar devices at PPPL, such as the National Spherical Torus Experiment (NSTX). The estimate assumes that after the issuance of the safety certificate the required subsystems listed in Section 3 are available and configured to support the integrated systems testing. In addition, this schedule assumes that the required documents identified in Section 4 have been completed.

The cost associated with these activities is TBD.  These costs will include the startup staff, subsystem staff, completion of the ISTP and costs associated with preparation of required documentation leading to First Plasma and e-beam mapping.

The startup staff for the 10 week duration should include:

1 Test Director/Physicist in Charge (PIC)	1.00 FTE @10 weeks of effort

1 Chief Operations Engineer (COE)		0.85 FTE @10 weeks of effort

1 Project Engineer				1.00 FTE @10 weeks of effort

2 Machine Technicians			0.85 FTE @10 weeks of effort

1 FCPC Technician				0.75 FTE @ 10 weeks of effort

The subsystem staff should include:

1 Cryo Systems Technician			0.75 FTE @10 weeks of effort

1 Power Engineer				0.75 FTE @10 weeks of effort

1 Computer Engineer				0.75 FTE @10 weeks of effort

The estimated cost for this staff is TBD which includes First Plasma and e-beam mapping (without contingency).

Labor costs for preparing the documentation required for Facility Startup were estimated by considering the documents that would have to be prepared and estimating the resource requirements to prepare each document.  Table 7-1 provides a representative list of documents and the resource requirements to complete preparation of each document.

Table 7-1 Facility Startup Documentation Requirements

| Document ID | Documents Required for NCSX Startup and Operations | Status | Person-weeks |
| --- | --- | --- | --- |
|  | *NCSX Safety Assessment Document (SAD) | 1 | 8 |
| *ESHD-5008 | Environmental, Safety, and Health Manual | 2 | 0 |
| *ESH-014 | NEPA Review System | 2 | 0 |
| *ESH-016 | Control of Hazardous Energy Sources Via Lockout Tagout of Energy Isolation Devices | 2 | 0 |
| *ENG-030 | PPPL Technical Procedures for Experimental Facilities | 2 | 0 |
| *ENG-032 | PPPL Work Planning Procedure | 2 | 0 |
| *ENG-033 | PPPL Engineering Design Verification | 2 | 0 |
| *NCSX-XX, | Administrative Control of Procedures | 5 | 4 |
| *OP-AD-39, | Conduct of Operations | 6 | 1 |
| *OP-AD-56, | Control of Equipment and System Status (chain of command) | 6 | 1 |
| *OP-AD-24, | Control of Workplace Cleanliness Around D-Site Experimental | 6 | 1 |
| *OP-AD-31, | D- Site Fire Watch Requirements | 6 | 1 |
| *OP-AD-03, | Experimental Proposals for NCSX | 6 | 1 |
| *OP-AD-117 | Operation of the NCSX Access System | 6 | 1 |
| *NCSX-OP-XX, | Preparations of Experimental Areas for Machine Operations | 5 | 3 |
| *NCSX-OP-XX, | Operation of the NCSX TVPS | 5 | 3 |
| *NCSX-OP-XX, | Testing the NCSX HIS with Areas Safe for Access | 5 | 3 |
| *NCSX-OP-XX, | Testing the NCSX Emergency Stop System | 5 | 3 |
| *NCSX-OP-XX, | NCSX Training Matrix | 1 | 3 |
| *NCSX-OP-XX, | NCSX Operations Guide for Startup and Shutdown | 5 | 3 |
| NCSX-OP-XX, | HPP Daily Operations | 5 | 2 |
| *NCSX-OP-XX, | ACP & PDP Trip Control Settings | 5 | 2 |
| *NCSX-OP-G-XX | Preparation for NCSX pumpdown | 5 | 3 |
| NCSX-OP-XX | Helium Heating and Cooling System Operations Procedure | 5 | 3 |
| *NCSX-OP-G-XX | Daily Hi-Pot Test of the NCSX Inner/Outer Vacuum Vessel | 5 | 3 |
| *ISTP-NCSX-01 | Coil EnergizationTests | 1 | 4 |
| *OP-ECS-245 | FCPC Daily Startup/Shutdown Procedure | 6 | 2 |
| *NCSX-XX | Leak Checking of NCSX | 5 | 2 |

Legend: 	1 - Document in development

2 - Current document satisfactory for NCSX startup and operation

3 - Document requires minor revision

4 - Document requires major revision

5 - Document needs to be developed

6 - Need a NCSX Project specific version

* - Required for First Plasma

9.0  Final Conditions.

The following items are the conditions for meeting the CD-4 First Plasma requirements.

- ORA successfully completed.

- NCSX ACC review completed.

- PPPL Executive Safety Board Issues a limited First Plasma  (CD-4) Safety Certificate.

- Applicable (sub-system) PTP's are completed.

- ISTP leading to First Plasma is completed.

- e-beam mapping on at least two surfaces is demonstrated.

CD-4 in accordance with the NCSX Project Execution Plan ( per the above items listed in section 9 " Final Conditions" )  Complete

# Footnotes

Preparation and implementation of Pre-Operational Test Procedures (PTPs) are the responsibly of the individual WBS elements, and is outside scope of the Integrated Systems Test Program.