National Compact Stellarator Experiment

###### NCSX

CONFIGURATION MANAGEMENT PLAN

(NCSX-PLAN-CMP)

DRAFT B

August 6, 2002

Prepared by:

R. Simmons, Systems Engineering Support Manager

Reviewed by:

R. Strykowsky, Project Control			  P. Heitzenroeder, Deputy Project

Manager						Manager for Engineering

M. Zarnstorff, Physics Manager			W. Reiersen, Engineering Manager

Approved by:

G.H. Neilson, Project Manager

| Revision | Date | Description of Changes |
| --- | --- | --- |
| DRAFT A | July 5, 2002 | Initial draft |
| DRAFT B | August 6, 2002 | Incorporated comments from WTR, PH, & GHN |

Table of Contents

1.0	BACKGROUND AND INTRODUCTION	1

1.1	Program Description	1

1.2	Overview of the NCSX Configuration Management Program	1

1.3	Relationships to Other DOE and NCSX Plans and Procedures	2

2.0	ORGANIZATION AND RESPONSIBILITY	4

3.0	CONFIGURATION MANAGEMENT	5

3.1	Definition of the CM Process	5

3.2	Configuration Identification	6

3.3	Configuration Change Control	6

3.3.1	Phased Approach to Configuration Change Control	6

3.3.2	Engineering Change Proposal	8

3.3.2	Change Control Board	11

3.4	Status Accounting	11

3.5	Configuration Verification and Audit	11

3.6	Baseline Documentation	11

3.6.1	Technical Baseline	11

3.6.2	Cost and Schedule Baselines	15

Annex I – Engineering Change Proposal (ECP) Form

Figures and Tables

Figure 1.3-1	NCSX Change Classification Matrix	3

Figure 1.3-2	Key Elements of the NCSX Configuration Management Program	4

Figure 3.3-1	Managing the Development of Project Baselines	7

Figure 3.3-2	The Change Control Process	8

Figure 3.3-3	ECP Tracking Log	10

Figure 3.3-4	ECP Implementation Log	10

Figure 3.6-1	NCSX Specification Types	12

# 1.0	BACKGROUND AND INTRODUCTION

## 1.1	Program Description

The National Compact Stellarator Experiment (NCSX) is an experimental research facility that is to be designed and constructed at the Department of Energy’s Princeton Plasma Physics Laboratory (PPPL). Its purpose is to develop the physics of compact stellarators, an innovative fusion confinement concept.  The facility will include the stellarator device and ancillary support systems. The design and fabrication project will be led by PPPL, in partnership with the Oak Ridge National Laboratory (ORNL).  This partnership approach is being used to effectively take advantage of each laboratory’s specific expertise to provide the best possible facility for the fusion research community.

## 1.2	Overview of the NCSX Configuration Management Program

The NCSX project and details of its design configuration is progressively described in greater detail as it proceeds through the design process.  At the end of the fabrication project, as the NCSX enters its operational phase, the actual physical and functional configuration is documented in as-built documents.  Configuration Management (CM) is used to identify and document the configuration of NCSX and control changes to the configuration during this life cycle.  The NCSX Configuration Management program described in this plan is intended to:

- provide the technical and administrative direction and surveillance actions taken to identify and document the physical characteristics of a configuration item;

- control changes to a configuration item and its characteristics; and

- record and report change processing and implementation status.

At selected points in the NCSX life cycle, the current configuration and non-configuration activities such as fabrication and testing established as a technical baseline.  The cost and schedule estimates to accomplish this technical baseline are developed to form the cost baseline and schedule baselines.  These three baselines are fully integrated since they are derived from the same configuration.  The combination of technical, cost, and schedule baselines forms the basis for project authorization, and management.   This becomes the basis against which the status of resources and the progress of the NCSX Project are measured.  Consequently, there are three baselines:  technical, cost, and schedule.  Any proposed change to one baseline must be evaluated from the perspective of its impact on the other two baselines.

The NCSX Configuration Management Program supports all NCSX functional groups and institutions.  The objectives of NCSX configuration management are to:

- ensure the integrity and continuity of changes are documented and recorded within the structure of the scope, cost, and schedule baselines;

- provide the identification, control, and status reporting necessary to assist management in achieving timely system readiness, visibility, traceability, and field support;

- provide managers at all levels with sufficient information for making appropriate, timely decisions throughout the life of the project;

- ensure that the evaluation of proposed configuration changes is timely and includes a thorough consideration of the proposed change’s total impact on technical, cost, schedule, operational capability, and support documentation.

## 1.3	Relationships to Other DOE and NCSX Plans and Procedures

DOE Order 413.3 Attachment 5 identifies the baseline change control (technical, cost, and schedule) approval thresholds for Other Projects (Not Major System Projects) for Level 0 (Secretarial Acquisition Executive) and Level 1 (Program Secretarial Officer).  Baseline change control for Level 2 (Federal Project Manager) and Level 3 (Project) are outlined in the NCSX Project Execution Plan (NCSX-PLAN-PEP). The PEP provides policy guidance for the overall planning and execution approach being used on the project and invokes this Configuration Management Plan (NCSX-PLAN-CMP) as the vehicle for maintaining the technical, cost, and schedule baselines for NCSX.  While this CMP focuses on Level 3 baseline changes, proposed changes requiring high approval level are essentially handled the same way.  Figure 1.3-1 depicts the Level 0, Level 1, Level 2, and Level 3 NCSX baseline change control approval thresholds.  In addition, several other NCSX plans, procedures, and documents support and implement other specific details outlined in this CMP.  These include the:

- Systems Engineering Management Plan (NCSX-PLAN-SEMP);

- NCSX Quality Assurance Plan (NCSX-PLAN-QAP);

- NCSX Data Management Plan (NCSX-PLAN-DMP)

- NCSX Document and Records Plan (NCSX-PLAN-DOC)

- Interface Control Management Plan (NCSX-PLAN-ICMP)

- WBS Dictionaries

- PPPL Engineering Procedures and Standards, including, but not limited to the latest version of:

  - ENG-006 “Review and Approval of Specifications and Statement of Work”;

  - ENG-010 “Control of Drawings, Software, and Firmware”;

  - ENG-019 “PPPL Engineering Standards”;

  - ENG-029 “Technical Definitions and Acronyms”; and

  - ENG-033 “Design Verification”

- Detailed configuration control procedures that might be developed to supplement the guidance contained in this CMP.

Figure 1.3-1
NCSX Change Classification Matrix

| Change Level | Approval Level | Technical Scope | Schedule | Cost |
| --- | --- | --- | --- | --- |
| 0 | Under Secretary of Energy | New scope/performance requirements not in conformance with current OMB-300 Changes to the AEP | ( 6 months cumulative increase in a DOE Level 1 milestone date | Baseline change of ($5M in TEC |
| 1 | Associate Director OFES | Changes to the mission or technical objectives Changes to the PEP | 3-6 months cumulative increase in a DOE Level 1 milestone date | Any increase in the TEC |
| 2 | NCSX Federal Project Manager | Changes to the GRD Changes with ES&H impacts significant enough to affect the approved NEPA documentation | < 3 months change to a DOE Level 1 milestone date Changes to DOE Level 2 Milestones Changes requiring the use of contingency funds | Changes requiring the use of contingency funds |
| 3 | NCSX Project Manager | All other changes to the configuration and/or documentation under configuration control | All other changes to the performance measurement baseline schedules | All other changes to the performance measurement baseline costs |

Figure 1.3-2 depicts these principle elements of the NCSX CM Program.

Figure 1.3-2
Key Elements of the NCSX Configuration Management Program

# ORGANIZATION AND RESPONSIBILITY

The NCSX Engineering Manager is responsible for the overall CM Program.  Within his organization, the Systems Engineering Support Manager is responsible for the implementation and administration of the CM process and update of the technical, cost, and schedule baselines as described in this CMP.  The NCSX Project Control Manager provides support to the CM process in the area of cost and schedule assessments of proposed changes and implementation of approved changes to the cost and schedule baselines.

The breakdown of work scope for the NCSX Project is defined in the NCSX Work Breakdown Structure (WBS).  This WBS defines and divides all the work to be accomplished into specific elements of work and specific WBS Managers are assigned for each WBS element.  While the WBS specifies the general work to be accomplished, it does not define the configuration around which this work will proceed.  That is left to the technical baseline documentation.  The WBS Managers are responsible for the establishment and maintenance of the technical, cost, and schedule baselines in their specific areas of responsibility, including identifying any proposed changes.  They are also responsible for identifying impacts of other proposed changes on their areas of responsibility.

# CONFIGURATION MANAGEMENT

## 3.1	Definition of the CM Process

CM is a process for identifying and documenting project technical, cost, and schedule baselines to be established and controlled in accordance with the change control requirements of this plan.  The combination of these baselines define the functional, physical and interface requirements and the related verification methods that assure that the requirements have been achieved and cost and schedule are adjusted appropriately.  The CM process described in this CMP is used to ensure and document that all facilities, structures, systems, subsystems, and components, as well as supporting documentation of the NCSX Project, interface physically and functionally.  This process must also ensure that the configuration is in agreement with the performance objectives in the technical baseline.  In addition, CM is a critical component of the Integrated Safety Management (ISM) Program.

The CM Program for the NCSX Project follows a tailored approach that is appropriate for a project of its complexity and relative costs.  The WBS Managers are afforded a great deal of flexibility and authority in revising configuration items not yet under formal change control, if the impact of these revisions do not impact other WBS elements outside their responsibility.

The CM process includes the following attributes:

- Configuration Identification – a process for identifying the configuration items and development of the appropriate configuration documentation to define each configuration item.

- Change Control – a process for the development, review and disposition of changes to the authenticated documentation.  The process includes the procedures for assessing the impact of changes and for monitoring their implementation.

- Status Accounting – an information system that provides precise identification of the project, performance baselines and the status of all changes to those baselines.

- Audits – a process for auditing the design and fabrication efforts for the achievement or non-achievement of the performance measurement baselines as defined by the technical, cost, and schedule baselines.

This CMP documents the approach and processes for implementing a systematic and measurable change process that is consistent with higher-level DOE orders and procedures.  While this CMP focuses on the Project (Level 3) change control process, it will feed into higher-level DOE change control boards as shown in Figure 1.3-1 previously.  The implemented change process ensures that proposed changes are properly identified, prioritized, documented, coordinated, evaluated, and adjudicated.  Approved changes will be properly documented, implemented, verified, and tracked to ensure incorporation into all involved systems and components.

Formal change control will be implemented at the start of Title I (Preliminary Design).  However, not all items will come under formal configuration control at that time.  Items will come under control from a top-down perspective with the higher-level requirements being placed under formal configuration control early in the design process and more detailed requirements and configuration defining documentation being delayed until sufficient design details evolve.  While formal change control process will envelope more and more configuration items as the design progresses, the overall approach to evaluating the impact of proposed changes to configuration items, whether under formal change control or not, will be the same.

Once a change is approved for implementation, it is critical that the CM process provide for a discipline and formal follow-up program to ensure that the impacted systems, subsystems, documentation, cost, and schedule items are updated to reflect the approved change.  This CMP details how the NCSX CM Program implements this key statusing requirement and how periodic independent verification of implemented changes is accomplished.

## Configuration Identification

Configuration Identification begins during the earliest phase of the project and continues throughout the life cycle of the project.  The WBS Manager is responsible for identifying configuration items needed in his WBS element.  These configuration items should be identified as early in the design process as feasible, although the specific configuration item may not come under formal configuration change control until sufficient design details have evolved.  In general, configuration items will include all project hardware and software/firmware.  Technical documentation, models, drawings, requirement documentation, etc. that describe the configuration items will also come under the CM.

## 3.3	Configuration Change Control

### 3.3.1	Phased Approach to Configuration Change Control

Configuration items and their associated documentation will come under formal change control in a phased manner; high level requirements and cost and schedule targets will come under change control by the start of Title I (Preliminary Design) whereas more detailed information on the design will not come under formal change control until later.  From a CM perspective, this delay in placing all technical baseline elements under configuration control until sufficient design has been accomplished will significantly enhance the flexibility of the Project to respond and incorporate changes on a design that is still evolving.  Figure 3.3-1 provides a flow chart of managing the development of the project baselines.  Figure 3.3-2 provides a flow chart of the change control process.

In general, project design reviews will determine when specific configuration items come under formal change control.  As a guideline, the following project design review points will result in more configuration items coming under change control:

- Conceptual Design Review (CDR) – CDR recommendations and impact analyses of these CDR recommendations are completed, the technical baseline and its cost and schedule targets will come under change control and will be defined as developmental baselines.  In addition, top-level requirements document, the General Requirements Document (GRD) will be finalized and approved and also placed under change control.  The developmental baselines will serve as a point of departure for implementing the CM process.  Although DOE Order 413.3 specifically delays finalizing the cost and schedule baselines until completion of the Critical Decision 2 (CD-2) milestone from a DOE perspective, the Project considers the developmental baseline as the point at which formal cost and schedule control is established.

- Preliminary Design Reviews (PDRs) – systems and subsystems or grouping of systems and subsystems will undergo formal preliminary design reviews or PDRs at the completion of Title I design.  At the completion of the PDRs, “design to specifications” and interface control documents will come under formal change control.

- Final Design Reviews (FDRs) – following completion of the preliminary design reviews, systems and subsystems will proceed into final design or Title II design.  At the completion of the final design process, a series of final design reviews or FDRs will be conducted.  At the completion of the FDRs, “design to build” specifications and fabrication drawings will come under configuration control.

Figure 3.3-1
Managing the Development of Project Baselines

Figure 3.3-2
The Change Control Process

### 3.3.2	Engineering Change Proposal

The change control process begins with the initiation of the Engineering Change Proposal (ECP).  Annex I to this CMP provides a sample of the ECP form and instructions for completing the ECP form – it is anticipated that the ECP will eventually be on the NCSX Engineering Web Page:   < http://www.pppl.gov/me/NCSX_Engineering/ >.  The ECP form will be a three part form:

- Cover Page providing ECP numbering and title, suggested reviewers, and the approval signature blocks.

- Part I to be filled in by the originator and submitted to the Systems Engineering Support Manager for processing.  Amplifying information to the ECP such as design memoranda that provide a rationale/need for the proposed change, sketches, Engineering Change Notices (ECN), Interface Change Notices (ICNs), cost and schedule impacts are prepared and attached.  These attachments are prepared in accordance with the following plans and procedures:

  - Sketches and ECNs – PPPL Engineering Procedure ENG-010, “Control of Drawings, Software, and Firmware”

  - ICNs – the NCSX Interface Control Management Plan (NCSX-PLAN-ICMP)

  - Cost and Schedule impacts – prepared using the Primavera Project Planner (P3) software.

- Part II to be completed by each reviewer.

ECPs should be limited to those necessary to correct deficiencies, those that affect cost and/or schedule, or that significantly affect technical performance.  A change request can be initiated by anyone associated with the Project.  The initiator identifies the affected documentation; outlines the reasons for the change; quantifies the technical, cost, and schedule impacts; and describes the change in detail.  The ECP form allows for review of all changes in a consistent manner.  The adjudicating body for each ECP is the Change Control Board (CCB).  Section 3.3.3 that follows describes the makeup and operation of the CCB.  ECPs will be numbered sequentially as follows:  FY-XXX, where FY is the current fiscal year and XXX the sequential number of the ECP.

Once the ECP is adjudicated, a statusing system is in place to report approval or non-approval of the proposed change.  If an ECP is approved, the ECP is then implemented and the affected documentation is revised accordingly.  Sections 3.4 and 3.5 that follow expand on the statusing and verification processes.

Once the ECP is dispositioned, the Project will be notified as to whether the ECP is approved or  not approved.  If approved, the Project will implement the change in a timely manner.  The ECP and an updated list of approved, disapproved, and pending changes will be maintained electronically by the Systems Engineering Support Manager on the NCSX Engineering Web Page < http://www.pppl.gov/me/NCSX_Engineering/ >.  Figure 3.3-3 is a sample of the ECP Status Log.  Figure 3.3-4 is a sample of the ECP Implementation Log to track the incorporation of the ECP into specific impacted documents.

The NCSX Project is considering utilizing the Project Data Management (PDM) capabilities of ProINTRALINK to track the implementation of ECPs into specific technical baseline documents (e.g., requirement documents such as the GRD and specifications, Interface Control Documents (ICDs)/Interface Change Notices (ICNs), drawings and models via Engineering Change Notices (ECNs), and environmental documentation.  Until such time that a decision is reached, the Project will pursue a web-based tracking system.

Figure 3.3-3
Sample ECP Tracking Log

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) Status Log |
| --- |
| ECP Number | Version/Date | ECP Title | Status* |
| Status Notes: Submitted – ECP submitted and impact statements being prepared Pending – ECP complete and awaiting CCB disposition Level 3 Approved – Level 3 ECP approved and ready for implementation DOE Pending – DOE Level 2 ECP or higher approval needed DOE Approved – Level 2 ECP or higher approved and ready for implementation Disapproved – Either Project or DOE rejected ECP |

Figure 3.3-4
Sample ECP Detailed Implementation

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) Implementation Log Status Date: |
| --- |
| ECP No: | ECP Title: |
| Document | Revised? | Date Revised | Revision Number |
| Requirements Documents GRD Specifications (List Each) Spec Spec | ( Yes ( No ( Yes ( No ( Yes ( No |  |  |
| Interface Control Documents ICN # => ICD # ICN # => ICD # | ( Yes ( No ( Yes ( No |  |  |
| Drawings/Model ECN #=> Dwg # ECN #=> Dwg # | ( Yes ( No ( Yes ( No |  |  |
| Environmental Documents EA SAD | ( Yes ( No ( Yes ( No |  |  |
| Cost Baseline | ( Yes ( No |  |  |
| Schedule Baseline | ( Yes ( No |  |  |

### Change Control Board

Once an ECP has been prepared and the impacts fully documented, the ECP will come before a Project Change Control Board (CCB) that is comprised of senior members of the NCSX management team.  The NCSX Project Manager or his designee will chair the CCB.  Other members of the CCB will be assigned as appropriate, but may include the following:

- Systems Engineering Support Manager (Secretary of the CCB);

- Project Control Manager;

- Engineering Manager;

- Physics Head;

- Project Engineers impacted by the proposed change

- WBS Managers impacted by the proposed change;

- ES&H Manager;

- QA Manager;

- Other impacted managers; and

- NCSX Project Manager.

The chairperson shall have the ultimate authority to recommend/approve changes for the final approval; other CCB members act solely as advisors.  In instances where the ultimate approval authority is DOE, the NCSX Project Manager shall indicate his approval and forward it for DOE disposition.

## 3.4	Status Accounting

The effectiveness of the NCSX Configuration Management Program is closely linked to the flow and availability of configuration information about the Project.  This configuration information will evolve and be captured over the life cycle of NCSX, starting with the configuration defining technical baseline, and cost and schedule baseline documentation.  The NCSX Systems Engineering Support Manager shall be responsible to the NCSX Project Engineering Manager for developing and implementing the web-based status accounting system.

As indicated in the previous section and Figure 3.3-3, an ECP status log will be maintained that provides the current status of ECPs and the impacted documents affected by that ECP.  In addition, the monthly engineering status meetings will specifically address the status of implementing approved ECPs into impacted documents.

## 3.5	Configuration Verification and Audit

As part of the plan outlined in the NCSX Quality Assurance Plan (NCSX-PLAN-QAP), verification and audits of the implementation of the NCSX Configuration Management Program shall occur.  This will not be limited to check of the configuration management documentation, but will also include physical inspection of the Project’s configuration relative to the documentation of the technical, cost, and schedule baselines.

## 3.6	Baseline Documentation

### 3.6.1	Technical Baseline

The technical baseline is defined by the following configuration defining documents:

- Requirement documents (specifications) that clearly define the performance requirements and constraints that need to be satisfied;

- System Design Description (SDDs) that define the design upon which the cost and schedule baselines are predicated;

- Interfaces Control Documents (ICDs) that define the interfaces between WBS elements; and

- Drawings , models, and technical data that physically define the configuration.

#### When these configuration-defining documents are combined with non-configuration defining documents and plans such as assembly and integrated systems test procedures, the scope baseline is defined.

#### 3.6.1.1	Requirements Documents

The NCSX requirements flow from its mission.  Requirements for the NCSX Project are captured in a hierarchy of requirements, which begin with the system/project (top-level) requirements in the General Requirements Document (GRD).  The GRD represents a compete set of performance requirements and constraints at the system level and provides the initial subsystem level (2 digit WBS level).  These initial subsystem requirement allocations in the GRD are expanded and developed in subsystem and lower level specifications as describe in the following paragraph.  As described in the Systems Engineering Plan (NCSX-PLAN-SEMP), this approach has two key features:

- Specifications with different functions will have different formats.  Five types of specifications have been identified for NCSX as shown in Figure 3.6-1.

- A specification tree shall be used to identify and plan for each specification required by the NCSX Project.  For each specification, the specification tree will identify the scope, specification type, and the organization responsible for its development.

The NCSX Project shall develop and implement a project-specific approach for developing specifications that meets the requirements set forth in most recent revision to PPPL Engineering Procedure ENG-006, “Review and Approval of Specifications and Work.”

Figure 3.6-1
NCSX Specification Types

| SPECIFICATION | PURPOSE |
| --- | --- |
| SYSTEM/SUBSYSTEM | • Establishes the requirements for the System and characteristics of WBS elements • Defines requirements based upon user’s mission needs as defined in the GRD |
| DEVELOPMENT | • Allocation of development requirements to the WBS items from the system specification • The performance document applicable to subcontractor’s contracts • Defines the methods used to verify the requirements have been met |
| PRODUCT | • Product acceptance requirements • Includes design disclosure package for the fabrication requirements |
| PROCESS | • Covers manufacturing techniques that require a specific procedure in order that a satisfactory result may be achieved. • Normally applies to production but may cover “process” development. |
| MATERIALS | • Prepared to control the development of a material. • Normally a material spec applies to product. |

By the start of Preliminary (Title I) Design, the GRD and WBS will be approved and placed under configuration control as the scope baseline.  The system performance requirements will be allocated within the GRD down to individual subsystems.  These allocated performance requirements will serve as the basis for developing subsystem performance specifications.  During Preliminary Design, the subsystem performance specifications will be formally approved and placed under configuration control.  Subsystem performance specifications will allocate the requirements down to lower level subsystems or configuration items.  During Final Design, product or “build-to” specifications and drawings will be developed, formally approved, and placed under configuration control.

#### 3.6.1.2	System Design Descriptions

System Design Descriptions (SDDs) are comprehensive design basis that describe (but not define) the design of each subsystem and how the design satisfies the requirements specified in the requirements documents.  The SDDs will be prepared or updated for each major design review (e.g., conceptual design review, preliminary design review, and final design review) to reflect the current technical baseline.

The SDDs describe the technical baseline upon which the cost and schedule baselines are predicated.  At each point in time when the developmental cost and schedule baselines are adopted as the project baselines, the SDDs will be updated to provide a description of the companion technical baseline.

SDDs will be prepared and updated by WBS Managers according to a format appropriate for each WBS.  SDDs are historical documents NOT subject to configuration control.

#### 3.6.1.3	Interface Control Documents

Interface requirements are functional, performance, and physical characteristics required to exist at a common boundary.  This boundary consists of performance/physical design constraints between systems and subsystems.  The interface may define either the physical boundary conditions or the functional or performance boundary conditions.  Two types of interfaces exist. Primary interfaces between configuration items managed by different WBS Managers.  Secondary interfaces exist between different configuration items managed by the same WBS Manager.

The ICMP defines the process and format for defining interfaces.  Primary interfaces will be brought under configuration control by completion of preliminary design.  Scope sheets will be developed early in Preliminary Design.  The scope sheets defines what interfaces exist, who will be responsible for developing the interface definition, and when the interface needs to be defined.  The interface will be documented in an Interface Control Document (ICD) and may also be physically depicted on a drawing. The ICDs represent agreements by the participants that:

- The interfacing designs are within the parameters specified by the ICD;

- The interfaces on either side of the WBS-WBS boundary are physically and functionally compatible with one another; and

- No change affecting interface compatibility is made to a design without coordination and agreement between the affected participants.

Once an ICD is approved, it is under formal configuration change control.  An approved Interface Change Notice (ICN) is required to change an ICD.  Any responsible participant may submit an ICN against their ICD.  Proposed ICNs will be handled under the configuration control processes and procedures outlined in this CMP.  In the case where the interface is also physically depicted on a drawing the ICN must also reference an ECN; changes to the drawing to update the interface can only be accomplished via the ECN as per PPPL Procedure ENG-010, “Control of Drawings, Software, and Firmware”.

#### 3.6.1.4	Drawings and Models

Project drawings and models will be prepared in accordance with the PPPL Engineering Design/Drafting Standard ES-DRFT-001, that implements the latest version of the PPPL Drafting Standards Manual.  As indicated in the NCSX Data Management Plan (NCSX-PLAN-DMP), the majority of the drawings and models will be developed using Computer Aided Design (CAD) software; e.g., ProEngineer (ProE) for mechanical 2D and 3D drawings and models and AutoCAD for electrical drawings.  It should be noted that all drawings and models that interface with the stellarator core shall be prepared in 3D using ProE.  These CAD drawings and models represent an extension of the systems requirements allocation process.  The CAD drawings and models provide, at a top-level, a physical and functional hardware implementation of the design requirements.  In the conceptual design phase developmental drawings and models of the stellarator core and facility were developed.  They are representative of the overall design configuration and provide the allocation of volumetric space to each of the subsystems.  These drawings and models have two basic functions:

- A “top-down” design function that develops a general layout of the stellarator core and facility and provides routing and space allocations requirements and constraints.

- A “bottoms up” design function that represents the composite physical layout of the design.

The combination of the “bottoms up” design with the “top down” design model is used to check the compliance of the design with the space allocations.

Bob the above statement (“top-down” “bottoms up” design function) is confusing.  How is this used to check compliance of the design with space allocations?

As the design progresses, drawings will be promoted to the next release level in accordance the process outlined in the DMP.  However, drawings will not come under formal configuration control until such time that they reach the fabrication release level.  At that time, an ECP with its accompanying ECN is required to effect changes to the drawing.  After coming under configuration control, changes to drawings and models are processed via an ECN in accordance with the latest revision to PPPL Engineering Procedure ENG-010, “Control of Drawings, Software, and Firmware.”

Bob do you mean AFTER coming under configuration control drawings released for fabrication can be changed via an ECN and the PPPL Engineering Procedure ENG-010?

Drawings and models will not be placed under formal configuration change control before completion of the final design, although proposed changes to drawings and models will be closely monitored and coordinated with higher level requirements and interface documents.

#### 3.6.1.5	Supporting Calculations and Design Memoranda

Calculations and design memoranda that support and substantiate the design will not be placed under formal configuration control.  As the design evolves, it is anticipated that these calculations and design memoranda will be controlled, checked, and approved in accordance with the processes set forth in the latest version of PPPL Engineering Procedure ENG-033, “Design Verification.”  WBS Managers will maintain copies of approved and checked calculations and design.

### 3.6.2	Cost and Schedule Baselines

The cost and schedule baselines are defined by a resource-loaded schedule stored in a Primavera Project Planner (P3) Database.  Adopting changes to the cost and schedule baselines will be done in accordance with approved change control procedures.  When the project changes the project baselines, the data files defining the new cost and schedule baselines will be uniquely identified and locked, preventing further changes under that identifier.  Viewable files will be generated for project use in PDF format.  The viewable files will include the identifier for the data files from which they were generated.

NCSX Configuration Management Plan

Annex I

Engineering Change Proposal (ECP) Form

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |
| Originator: | Date: |
| ECP No: | ECP Title: |
| Required Reviewers |
| Name | Review? | Name | Review? |
| NCSX Systems Engrg Support Mgr. | ( Yes ( No | NCSX ES&H Manager | ( Yes ( No |
| NCSX Project Control Mgr. | ( Yes ( No | NCSX QA Manager | ( Yes ( No |
| Project Engineer (Stellarator Core Systems) | ( Yes ( No | NCSX Physics Head | ( Yes ( No |
| Project Engineer (Ancillary Systems) | ( Yes ( No | NCSX Engineering Mgr | ( Yes ( No |
| Project Engineer (Assembly Operations) | ( Yes ( No | Others: | ( Yes ( No |
| WBS Manager: WBS | ( Yes ( No | Others: | ( Yes ( No |
| WBS Manager: WBS | ( Yes ( No | Others: | ( Yes ( No |
| WBS Manager: WBS | ( Yes ( No | Others: | ( Yes ( No |
| ECP Approval Level Change Level: Approving Official: |
| Comments |

| APROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |
| --- |
| Change Level | Approving Official | Approval? | Signature |
| 3 | NCSX Project Manager | ( Yes ( No |  |
| 2 | NCSX Federal Project Manager | ( Yes ( No |  |
| 1 | NCSX Program Manager | ( Yes ( No |  |
| 0 | Acquisition Executive | ( Yes ( No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: | Date: |
| Overview of Change Type of Change: ( TECHNICAL ( COST ( SCHEDULE (Check all that Apply) Reason for Change: Directed Change? ( Yes ( No Urgent Change? ( Yes ( No Impacted WBS Elements: Impacts of Change (Briefly Describe): Design: Performance: Requirements: Cost: Schedule: Maintenance: ES&H: RAM: Assessment of Other Options: |
| Detailed Description of the Change: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) Attachments (List): List of Impacted Documents : Description of Change: |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I CONTINUATION SHEET (TO BE COMPLETED BY ORIGINATOR) |
| Originator: | Date: |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART II (TO BE COMPLETED BY REVIEWERS) |
| ECP No: | ECP Title: |
| Reviewer: Corrections Needed? ( Yes ( No If yes, identify corrections needed: Concur? ( Yes ( No Provide reasons for concurrence/rejection: Other Recommendations? ( Yes ( No Identify Recommendations Signature: |

NOTE:  Part II – Review Form will be multiple forms

Instructions for Completing the ECP Form

- Initiating an ECP

  - Initiator fills out Part I:

    - Originator:  Name of Person Initiating the ECP

    - Date:  Date ECP Prepared

    - Type of Change:  Check all blocks that are applicable => Technical, Cost, or Schedule

    - Reason for Change:  Brief explanation on why the change is necessary and check off blocks on whether this is directed change necessitated by external (e.g., DOE actions) or if it is an urgent change

    - Impacted WBS Elements:  Identify impacted WBS elements

    - Impact of Change:  Check off applicable blocks and provide brief impact statement of the expected impact of this proposed change:

- Design

  - Performance

  - Requuirements

  - Cost

  - Schedule

  - Maintenance

  - ES&H

  - RAM

    - Assessment of Other Options:  Provide brief discussion of other options considered and why this option selected

    - Detailed Description	of Change:  Using the continuation page if needed, provide a reasonably detailed explanation of the change, including identification of any attachments and a list of impacted documents

  - Initiator sends completed Part I and any attachments and continuation pages to the Systems Engineering Support Manager for further processing

  - Systems Engineering Support Manager reviews proposed change and, if required, requests additional amplifying information to complete the package

  - Once the change package is complete, the Systems Engineering Support Manager fills out top portion of the ECP Cover Page:

    - Identifies Originator of the ECP and Date ECP prepared

    - Assigns ECP Number in accordance with the scheme outlined in this CMP

    - Assigns ECP Title that is descriptive of the proposed change

    - Identifies required reviewers by checking yes or no blocks

    - Based on information provided in Part I, identify Change Level of this proposed change and the final approving official:

| Change Level | Approving Official |
| --- | --- |
| 3 | NCSX Project Manager |
| 2 | NCSX Federal Project Manager |
| 1 | NCSX Program Manager |
| 0 | Acquisition Executive |

    - Provides any amplifying comments to assist in the review and disposition of the proposed change

    - Posts proposed ECP on the Engineering Web Page: http://www.pppl.gov/me/NCSX_Engineering/

    - Notifies required reviewers that the ECP is now posted on the Engineering Web Page

  - Reviewers fill out Part II:

    - Fill out ECP Number and Title

    - Identify reviewer name

    - Check block indicating whether or not corrections needed (e.g., additional reviewers, correction to impact statements, etc. and the specific corrections needed.  Return Part II to Systems Engineering Manager for recycling ECP to obtain corrections needed

    - If no corrections needed, check block on whether or not the reviewer concurs in the ECP and provide reason for concurrence or rejection recommendation

    - Identify if there are other recommendations (e.g., modified ECP to include other impacted documents, etc. and specifically identify those recommendations

    - Electronically sign the ECP using the Adobe Signature feature.

    - Return completed Part II to the Systems Engineering Support Manager electronically

  - Once all the Part II review sheets are completed, the Systems Engineering Support Manager re-reviews ECP to ensure completeness and schedules the ECP for a CCB Meeting.  Prepares minutes from the CCB.

  - If the ECP is a Class 3 ECP (NCSX Project Manager is the approving official), annotate the ECP Tracking Log (Figure 3.3-3) indicating the disposition and complete the ECP Implementation Log (Figure 3.3-4) to track implementation of the incorporation of the ECP into the affected documents.

  - If the ECP is a Class 2 or higher level ECP, requiring DOE approval, prepare the transmittal letter for NCSX Project Manager signature.  Once the ECP is dispositioned, repeat step 7 above.

  - Monthly identify the implementation status of each ECP as part of the monthly status meetings to ensure visibility of the implementation of the ECP.