National Compact Stellarator Experiment

###### NCSX

CONFIGURATION MANAGEMENT PLAN

(NCSX-PLAN-CMP)

DRAFT C

August 16, 2002

Prepared by:

R. Simmons, Systems Engineering Support Manager

Concurrences:

R. Strykowsky, Project Control			  P. Heitzenroeder, Deputy Project

Manager						Manager for Engineering

M. Zarnstorff, Physics Manager			W. Reiersen, Engineering Manager

Approved by:

G.H. Neilson, Project Manager

| Revision | Date | Description of Changes |
| --- | --- | --- |
| DRAFT A | July 5, 2002 | Initial draft |
| DRAFT B | August 6, 2002 | Incorporated comments from WTR, PH, & GHN |
| DRAFT C | August 16, 2002 | Reformatted to incorporate comments |

Table of Contents

1.0	BACKGROUND AND INTRODUCTION	1

1.1	Program Description	1

1.2	Overview of the NCSX Configuration Management Program	1

1.3	Relationships to Other DOE and NCSX Plans and Procedures	2

2.0	ORGANIZATION AND RESPONSIBILITY	4

3.0	CONFIGURATION MANAGEMENT	5

3.1	The NCSX Project Configuration Management Process	5

3.2	Configuration Change Control	5

3.2.1	Phased Approach to Configuration Change Control	5

3.2.2	Engineering Change Proposal	9

3.2.3	Expedited ECPs	12

3.2.4	Change Control Board	12

3.3	Baseline Documentation	13

3.3.1	Technical Baseline	13

3.3.1.1	Requirements/Specification Documents	13

3.3.1.2	Interface Control Documents	14

3.3.1.3	Drawings and Models and Supporting Technical Data	15

3.3.1.3.1	Drawings and Models	15

3.3.1.3.2	Supporting Technical Data	16

3.3.1.4	System Design Descriptions	16

3.3.2	Cost and Schedule Baselines	16

Annex I – Engineering Change Proposal (ECP) Form

Figures and Tables

Figure 1.3-1 NCSX Change Classification Matrix	3

Figure 1.3-2 Key Elements of the NCSX Configuration Management Program	4

Figure 3.2-1 Managing the Evolution of Project Baselines	7

Figure 3.2-2 The Change Control Process	8

Figure 3.2-3 Sample ECP Tracking Log	10

Figure 3.2-4 Sample ECP Detailed Implementation Log	11

Figure 3.3-1 NCSX Specification Types	13

# 1.0	BACKGROUND AND INTRODUCTION

## 1.1	Program Description

The National Compact Stellarator Experiment (NCSX) is an experimental research facility that is to be designed and constructed at the Department of Energy’s Princeton Plasma Physics Laboratory (PPPL). Its purpose is to develop the physics of compact stellarators, an innovative fusion confinement concept.  The facility will include the stellarator device and ancillary support systems. The design and fabrication project will be led by PPPL, in partnership with the Oak Ridge National Laboratory (ORNL).  This partnership approach is being used to effectively take advantage of each laboratory’s specific expertise to provide the best possible facility for the fusion research community.

## 1.2	Overview of the NCSX Configuration Management Program

The physical and functional description of the components, systems, and software/firmware comprise the “configuration” of the NCSX Project.  The NCSX project and details of its design configuration is progressively described in greater detail as it proceeds through the design process.  At the end of the fabrication project, as the NCSX enters its operational phase, the actual physical and functional configuration is documented in as-built documents.  Configuration Management (CM) is an integrated program that ensures that the configuration is identified and properly document and that changes to the configuration are controlled during this life cycle.

At selected points in the NCSX life cycle, the current design configuration, including fabrication and testing define the technical baseline.  The cost and schedule estimates to accomplish this technical baseline are developed to form the cost baseline and schedule baselines.  These three baselines are fully integrated since they are derived from the same configuration.  The combination of technical, cost, and schedule baselines forms the basis for project authorization, and management.   This becomes the basis against which the status of resources and the progress of the NCSX Project are measured.  Consequently, there are three baselines:  technical, cost, and schedule.  Any proposed change to one baseline must be evaluated from the perspective of its impact on the other two baselines.

The NCSX Configuration Management program described in this plan is intended to:

- Provide a process for identifying configuration items and development of the appropriate configuration documentation to define the physical and functional characteristics of each configuration item.  This is sometimes called configuration identification.

- Provide a process for identifying and managing proposed changes to a configuration item and its characteristics and the impact of the proposed change on the documentation describing the technical, cost, and schedule baselines.  This includes evolution of the design of the configuration item over time and tracking of the status of proposed changes to the configuration item until the change is approved or rejected.  This is sometimes called configuration change control.

- Provide a process for tracking the status of the implementation of approved changes in detail down to each impacted document.  This is sometimes called status accounting.

- Provide a process for verifying that the latest approved documents are used to fabricate/test configuration items and that the as-built physical and functional configuration is accurately reflected in the supporting documentation.  This is sometimes called configuration verification.  It is anticipated that most of this effort will occur under the existing PPPL QA program.

What does this add?

## 1.3	Relationships to Other DOE and NCSX Plans and Procedures

In accordance with DOE Order 413.3, the NCSX Project is classified in the category of Other Projects (Not Major System Projects).  Baseline change control (technical, cost, and schedule) approval thresholds for Level 0 (Secretarial Acquisition Executive) and Level 1 (Program Secretarial Officer) are defined in Attachment 5 to this order.  Baseline change control for Level 2 (Federal Project Manager) and Level 3 (Project) are outlined in the NCSX Project Execution Plan (NCSX-PLAN-PEP). The PEP provides policy guidance for the overall planning and execution approach being used on the project and invokes this Configuration Management Plan (NCSX-PLAN-CMP) as the vehicle for maintaining the technical, cost, and schedule baselines for NCSX. Figure 1.3-1 depicts the Level 0, Level 1, Level 2, and Level 3 NCSX baseline change control approval thresholds.  In addition, several other NCSX plans, procedures, and documents support and implement other specific details outlined in this CMP.  These include the:

- Systems Engineering Management Plan (NCSX-PLAN-SEMP);

- NCSX Quality Assurance Plan (NCSX-PLAN-QAP);

- NCSX Data Management Plan (NCSX-PLAN-DMP)

- NCSX Document and Records Plan (NCSX-PLAN-DOC)

- Interface Control Management Plan (NCSX-PLAN-ICMP)

- WBS Dictionaries

- PPPL Engineering Procedures and Standards, including, but not limited to the latest version of:

  - ENG-006 “Review and Approval of Specifications and Statement of Work”;

  - ENG-010 “Control of Drawings, Software, and Firmware”;

  - ENG-019 “PPPL Engineering Standards”;

  - ENG-029 “Technical Definitions and Acronyms”; and

  - ENG-033 “Design Verification”

If deemed necessary as this program is implemented, the NCSX Project may develop project-specific configuration management and control procedures to augment the above documents.

Figure 1.3-1
NCSX Change Classification Matrix

| Change Level | Approval Level | Technical Scope | Schedule | Cost |
| --- | --- | --- | --- | --- |
| 0 | Under Secretary of Energy | New scope/performance requirements not in conformance with current OMB-300 Changes to the AEP | ( 6 months cumulative increase in a DOE Level 1 milestone date | Baseline change of ($5M in TEC |
| 1 | Associate Director OFES | Changes to the mission or technical objectives Changes to the PEP | 3-6 months cumulative increase in a DOE Level 1 milestone date | Any increase in the TEC |
| 2 | NCSX Federal Project Manager | Changes to the GRD Changes with ES&H impacts significant enough to affect the approved NEPA documentation | < 3 months change to a DOE Level 1 milestone date Changes to DOE Level 2 Milestones | Changes requiring the use of contingency funds |
| 3 | NCSX Project Manager | All other changes to the configuration and/or documentation under configuration control | All other changes to the performance measurement baseline schedules | All other changes to the performance measurement baseline costs |

Figure 1.3-2 depicts these principle elements of the NCSX CM Program.

Figure 1.3-2
Key Elements of the NCSX Configuration Management Program

# ORGANIZATION AND RESPONSIBILITY

The NCSX Engineering Manager is responsible for the overall CM Program.  Within his organization, the Systems Engineering Support Manager is responsible for the implementation and administration of the CM process and update of the technical baselines as described in this CMP.  The NCSX Project Control Manager supports cost and schedule assessments of proposed changes and implementation of approved changes to the cost and schedule baselines.

The breakdown of work scope for the NCSX Project is defined in the NCSX Work Breakdown Structure (WBS).  This WBS defines and divides all the work to be accomplished into specific elements of work and specific WBS Managers are assigned for each WBS element. The WBS Managers are responsible for identifying the physical and functional configuration items that comprise their WBS elements and for establishing and maintaining the technical, cost, and schedule baselines in their specific areas of responsibility what does this mean? WBS mgrs. develop their designs and estimate cost and schedule, but I am not sure they “establish and maintain” the baseline, including proposing changes to the baselines.  They are also responsible for assessing impacts of other proposed changes on their areas of responsibility.

The NCSX Project Manager is responsible for approving changes to the established technical, cost, and schedule baselines or, for those changes requiring DOE approval, making project recommendations.  In some instances where the scope of the change is urgent or a relatively minor nature, the NCSX Project Manager may authorize the NCSX Engineering Manager to disposition and implement the proposed change in an expedited fashion.

# CONFIGURATION MANAGEMENT

## 3.1	The NCSX Project Configuration Management Process

What does this add?

## 3.2	Configuration Change Control

### 3.2.1	Placement of Documents under Configuration Control

At the start of Title I (Preliminary Design), the initial technical, cost, and schedule baselines will be established and will form the basis for the performance measurement baseline in the NCSX Project Control System (PCS). The project baseline starts as a high-level specification and evolves to greater levels of detail as the design is developed and finally to as-built documentation of the final configuaration. This process is controlled by the manner in which documents are progressively placed under configuration controlDetails of the design that are not under formal configuration control are controlled in a less formal manner by the engineering manager and WBS managers. Figure 3.3-1 provides a flow chart of managing the development of the project baselines.  Figure 3.3-2 provides a flow chart of the change control process.

In general, project design reviews will determine when specific configuration items come under formal change control.  As a guideline, the following project design review points will result in more configuration items coming under change control:

- Conceptual Design Review (CDR) – Once the CDR recommendations and the impact analyses of these CDR recommendations are completed, the initial baselines will be established for the start of preliminary design.  at that time, the General Requirements Document (GRD), the technical data that constitutes the fundamental agreements between engineering and physics (e.g., the coil geometries, coil currents for the reference scenarios, and the first-wall envelope), and the ProEngineer (ProE) models will constitute the technical baseline. The associated cost and schedule data base,  will consistute the cost and schedule baseline. These baselines will serve as a point of departure for implementing the CM process and the elements identified here will be under change control. The project will begin using these baselines for performance measurement, although under DOE Order 413.3 the performance baselines is not officially established until the Critical Decision 2 (CD-2) milestone from a DOE perspective.

- Preliminary Design Reviews (PDRs) – At the completion of preliminary design, the system requirements (flowed down from the GRD), interface control documents (ICDs – representing interface agreements between systems), and any other technical data (e.g., tables, sketches, computer files, etc.) that are needed to constrain the WBS manager’s final design, will be defined. At the completion of the PDR for a system, its, “design to” specifications listed here will come under formal configuration control.

- Final Design Reviews (FDRs) – At the completion of final design the specifications and interfaces are defined to a degree of detail required for fabrication and assembly. The key documents are manufacturing specifications, assembly procedures, fabrication drawings, and any other technical data that is needed to constrain the fabricator or assembler . At the completion of the FDR for a system, its “build to” specifications lister here will come under configuration control. Near the end of project fabrication, testing procedures will also be developed and placed under configuration control.

- Project Completion – at completion, the project documentation should reflect what is actually built.  The technical baseline will consist of “as-built” drawings and specifications and accompanying technical data that satisfy PPPL’s and Project’s requirements for configuration control of its facilities.

Figure 3.2-1
Managing the Evolution of Project Baselines

Figure 3.2-2
The Change Control Process

### 3.2.2	Engineering Change Proposal

All changes to project baselines will be accomplished by the Engineering Change Proposal (ECP).  Evolutionary changes to baselines (technical, cost, and schedule), as the design (and the associated cost and schedule impacts) advances in a level of detail or adjustments to reconcile actual cost and schedule performance against established baselines, will be handled by periodically updating the baselines to incorporate these developments.  As indicated on Figure 3.2-1, these “omnibus” ECPs will be processed to capture multiple changes.  Major changes will typically be handled by a stand-alone ECP.  The ECP process was previously outlined in Figures 3.2-1 and 3.2-2 above.  Annex I to this CMP provides a sample of the ECP form and instructions for completing the ECP form – it is anticipated that the ECP will eventually be on the NCSX Engineering Web Page:   < http://www.pppl.gov/me/NCSX_Engineering/ >.  The ECP form will be a three part form:

- Cover Page providing ECP numbering and title, suggested reviewers, and the approval signature blocks.

- Part I to be filled in by the originator and submitted to the Systems Engineering Support Manager for processing.  Amplifying information to the ECP such as design memoranda that provide a rationale/need for the proposed change, sketches, Engineering Change Notices (ECN), Interface Change Notices (ICNs), cost and schedule impacts are prepared and attached.  These attachments are prepared in accordance with the following plans and procedures:

  - Sketches and ECNs – PPPL Engineering Procedure ENG-010, “Control of Drawings, Software, and Firmware”

  - ICNs – the NCSX Interface Control Management Plan (NCSX-PLAN-ICMP)

  - Cost and Schedule impacts – prepared using the Primavera Project Planner (P3) software.

- Part II to be completed by each reviewer.

A change request can be initiated by anyone associated with the Project.  The initiator identifies the affected documentation; outlines the reasons for the change; quantifies the technical, cost, and schedule impacts; and describes the change in detail.  The ECP form allows for review of all changes in a consistent manner.  The normal adjudicating body for each ECP is the Change Control Board (CCB) and Section 3.2.4 that follows describes the makeup and operation of the CCB.  However, in some instances, a process for “expedited” ECPs may be appropriate and Section 3.2.3 that follows addresses when this might be applicable.  ECPs will be numbered sequentially as follows:  FY-XXX, where FY is the current fiscal year and XXX the sequential number of the ECP.

Once the ECP is dispositioned, the Project will be notified as to whether the ECP is approved on not approved.  If an ECP is approved, the ECP is then implemented and the affected documentation is revised accordingly in a timely manner.  The NCSX Systems Engineering Support Manager shall be responsible to the NCSX Project Engineering Manager for developing and implementing the web-based status accounting system.  The ECP and an updated list of approved, disapproved, and pending changes will be maintained electronically by the Systems Engineering Support Manager on the NCSX Engineering Web Page < http://www.pppl.gov/me/NCSX_Engineering/ >.  Figure 3.2-3 is a sample of the ECP Status Log.  Figure 3.2-4 is a sample of the ECP Implementation Log to track the incorporation of each specific approved ECP into each impacted document. Address responsibility for implementation.

The NCSX Project will use the Project Data Management (PDM) capabilities of ProINTRALINK to track the implementation of ECPs into specific technical baseline documents (e.g., requirement documents such as the GRD and specifications, Interface Control Documents (ICDs)/Interface Change Notices (ICNs), drawings and models via Engineering Change Notices (ECNs), and environmental documentation.  Details of the ProINTRALINK capabilities and processes for maintaining documentation are contained in the NCSX Project Data Management Plan (NCSX-PLAN-DMP).  At completion of the fabrication project, the as-built design documentation will be coordinated with PPPL’s existing document storage and retrieval systems.

Figure 3.2-3
Sample ECP Tracking Log

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) Status Log |
| --- |
| ECP Number | Version/Date | ECP Title | Status* |
| Status Notes: Submitted – ECP submitted and impact statements being prepared Pending – ECP complete and awaiting CCB disposition Level 3 Approved – Level 3 ECP approved and ready for implementation DOE Pending – DOE Level 2 ECP or higher approval needed DOE Approved – Level 2 ECP or higher approved and ready for implementation Disapproved – Either Project or DOE rejected ECP |

Figure 3.2-4
Sample ECP Detailed Implementation Log

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) Implementation Log Status Date: |
| --- |
| ECP No: | ECP Title: |
| Document | Revised? | Date Revised | Revision Number |
| Requirements Documents GRD Specifications (List Each) Spec Spec | ( Yes ( No ( Yes ( No ( Yes ( No |  |  |
| Interface Control Documents ICN # => ICD # ICN # => ICD # | ( Yes ( No ( Yes ( No |  |  |
| Drawings/Model ECN #=> Dwg # ECN #=> Dwg # | ( Yes ( No ( Yes ( No |  |  |
| Environmental Documents EA SAD | ( Yes ( No ( Yes ( No |  |  |
| Cost Baseline | ( Yes ( No |  |  |
| Schedule Baseline | ( Yes ( No |  |  |

### Expedited ECPs

Although any change to established baselines (technical, cost, and schedule) requires an ECP, an expedited approval process may be used in some cases, when deemed appropriate by the EM.  Instances where an “expedited” ECP might be appropriate is when a change is either urgent or minor.  However, any “expedited” ECPs will be reviewed “after-the-fact” by the full CCB.

### 3.2.4	Change Control Board

Once an ECP has been prepared and the impacts fully documented, the ECP will come before a Project Change Control Board (CCB) that is comprised of senior members of the NCSX management team.  The NCSX Project Manager or his designee will chair the CCB.  Other members of the CCB will be assigned as appropriate, but may include the following:

- Systems Engineering Support Manager (Secretary of the CCB);

- Project Control Manager;

- Engineering Manager;

- Physics Head;

- Project Engineers impacted by the proposed change

- WBS Managers impacted by the proposed change;

- ES&H Manager;

- QA Manager;

- Other impacted managers; and

- NCSX Project Manager.

The chairperson shall have the ultimate authority to recommend/approve changes for the final approval; other CCB members act solely as advisors. For changes requiring DOE approval, the NCSX Project Manager shall indicate his approval and forward it for DOE disposition with his recommendation to approve.

## 3.3	Baseline Documentation

### 3.3.1	Technical Baseline

As explained in Sect. 3.2.1, The technical baseline at any stage of the project is defined by any or all of the following configuration defining documents:

- Requirement documents (specifications) that clearly define the performance requirements and constraints that need to be satisfied;

- Interfaces Control Documents (ICDs) that define the interfaces between WBS elements; and

- Drawings , models, and technical data that physically define the configuration.

#### 3.3.1.1	Requirements/Specification Documents

Requirements/specifications for the NCSX Project are captured in a hierarchy of requirements, which begin with the system/project (top-level) requirements in the General Requirements Document (GRD).  The GRD provides performance requirements and constraints at the system level and and the allocation of each requirement to affected subsystems.  These initial subsystem requirement allocations in the GRD are expanded and developed in subsystem and lower level specifications as described in the following paragraphs.  As described in the Systems Engineering Plan (NCSX-PLAN-SEMP), the requirement/specifications may be classified in two basic categories:

- “Design to” Specifications – these documents encompass the GRD and the System Requirements Documents  (SRDs).  These documents provide the design requirements by system, envelopes, and boundary conditions that constrain the development of the final design.  As indicated earlier, the bulk of these documents will be placed under formal configuration control at the completion of preliminary design.

- “Build to” Specifications – these documents provide the details to enable a manufacturer to build or assembler to assemble the component, system, or subsystem.  Included in this category would be procurement specifications, detailed assembly and fabrication procedures, and detailed testing procedures.

Specifications with different functions will have different formats.  Five types of specifications have been identified for NCSX as shown in Figure 3.3-1, but these specifications still fall under the two basic specification categories described above.  In addition, a specification tree shall be used to identify and plan for each specification required by the NCSX Project.  For each specification, the specification tree will identify the scope, specification type, and the organization responsible for its development.

Wasn’t this adequately covered in an earlier section? Not good to define twice.

The NCSX Project shall develop and implement a project-specific approach for developing specifications that meets the requirements set forth in most recent revision to PPPL Engineering Procedure ENG-006, “Review and Approval of Specifications and Work.” What does this mean?  Also, what is the purpose of the table?

Figure 3.3-1
NCSX Specification Types

| SPECIFICATION | PURPOSE |
| --- | --- |
| SYSTEM/SUBSYSTEM | • Establishes the requirements for the System and characteristics of WBS elements • Defines requirements based upon user’s mission needs as defined in the GRD |
| DEVELOPMENT | • Allocation of development requirements to the WBS items from the system specification • The performance document applicable to subcontractor’s contracts • Defines the methods used to verify the requirements have been met |
| PRODUCT | • Product acceptance requirements • Includes design disclosure package for the fabrication requirements |
| PROCESS | • Covers manufacturing techniques that require a specific procedure in order that a satisfactory result may be achieved. • Normally applies to production but may cover “process” development. |
| MATERIALS | • Prepared to control the development of a material. • Normally a material spec applies to product. |

#### 3.3.1.2	Interface Control Documents

Interface requirements are functional, performance, and physical characteristics required to exist at a common boundary.  This boundary consists of performance/physical design constraints between systems and subsystems. Two types of interfaces exist. Primary interfaces between configuration items managed by different WBS Managers.  Secondary interfaces exist between different configuration items managed by the same WBS Manager. Do we handle them any differently?

The ICMP defines the process and format for defining interfaces.  Primary interfaces will be brought under configuration control by completion of preliminary design. Already said that Scope sheets will be developed early in Preliminary Design.  The scope sheets what primary interfaces exist, who will be responsible for developing the interface definition, and when the interface needs to be defined.  The interface will be documented in an Interface Control Document (ICD) and may also be physically depicted on a drawing. The ICDs represent agreements by the participants that:

- The interfacing designs are within the parameters specified by the ICD;

- The interfaces on either side of the WBS-WBS boundary are physically and functionally compatible with one another; and

- No change affecting interface compatibility is made to a design without coordination and agreement between the affected participants.

Once an ICD is approved, it is under formal configuration change control and therefore an ECP is required to change an ICD.  The approved ECP will identify an Interface Change Notice (ICN) that details the changes to be made to an ICD.  Any responsible participant may submit an ECP and proposed ICN against their ICD.  In the case where the interface is also physically depicted on a drawing the ICN must also reference an ECN; changes to the drawing to update the interface can only be accomplished via the ECN as per PPPL Procedure ENG-010, “Control of Drawings, Software, and Firmware”.

This seems pretty complete. What do we need the ICMP for?

#### 3.3.1.3	Drawings and Models and Supporting Technical Data

##### 3.3.1.3.1	Drawings and Models

Project drawings and models will be prepared in accordance with the PPPL Engineering Design/Drafting Standard ES-DRFT-001, which implements the latest version of the PPPL Drafting Standards Manual.  As indicated in the NCSX Data Management Plan (NCSX-PLAN-DMP), the majority of the drawings and models will be developed using Computer Aided Design (CAD) software; e.g., ProE for mechanical 2D and 3D drawings and models and AutoCAD for electrical drawings.  All drawings and models that interface with the stellarator core will be prepared in 3D using ProE.

These CAD models and drawings are an extension of the systems requirements allocation process.  When developed as three-dimensional models and managed within an integrated product data management (PDM) tool they provide, at the top level, a physical and functional hardware implementation of the design requirements as defined in the GRD.  In the Conceptual Design stage, models of the stellarator core and facility were developed and exist in varying degrees of detail, representing the overall design configuration.  Some models will have a high level of development while others will provide the allocation of volumetric space of a subsystem. As described in the DMP, using the PDM tool, models and drawings progress though various design stages (Conceptual Design, Preliminary Design, Prototype, Final Design) to fabrication will be managed and stored with promotions among stages following a prescribed controlled plan.  Upon completion of the fabrication and assembly, a set of as-built drawings and models will be developed to ensure consistency between the design documentation and the physical configuration in the field.  Storage of all release points of the design process will allow models to be checked to assure compliance to earlier space allocations.

As the design progresses, drawings will be promoted to the next release level in accordance the process outlined in the DMP.  However, drawings will not come under formal configuration control until such time that they reach the fabrication release level, approximately at completion of the final design, although proposed changes to drawings and models will be closely monitored and coordinated with higher level requirements and interface document.  Once these models and drawings come under formal configuration control, an ECP with its accompanying ECN is required to effect changes to the drawing. The ECN will be processed in accordance with the latest revision to PPPL Engineering Procedure ENG-010, “Control of Drawings, Software, and Firmware.”  Prior to coming under configuration control, changes to drawings and models are processed via the NCSX project review process and the release procedures established within the Pro/INTRALINK data management system. .

##### 3.3.1.3.2	Supporting Technical Data

Technical data (e.g., coil geometries, coil currents for the reference scenarios, first-wall envelopes, tables, computer files, etc.) that support and substantiate the design will placed under formal configuration control on a case-by-case basis and at appropriate stages of the design when needed.  As the design evolves, it is anticipated that technical data will be controlled, checked, and approved in accordance with the processes set forth in the latest version of PPPL Engineering Procedure ENG-033, “Design Verification.”  WBS Managers will maintain copies of approved and checked calculations and design.

Among the critical documentation supporting the PDRs will be the System Design Descriptions (SDDs).  System Design Descriptions (SDDs) are comprehensive design basis that describe (but not define) the design of each subsystem and how the design satisfies the requirements specified in the requirements documents.  The SDDs will be prepared or updated for each major design review (e.g., conceptual design review, preliminary design review, and final design review) to reflect the current technical baseline. The SDDs describe the technical baseline upon which the cost and schedule baselines are predicated.  At each point in time when the developmental cost and schedule baselines are adopted as the project baselines, the SDDs will be updated to provide a description of the companion technical baseline. SDDs will be prepared and updated by WBS Managers according to a format appropriate for each WBS.  SDDs are historical documents NOT subject to configuration control

#### 3.3.1.4	System Design Descriptions

System Design Descriptions (SDDs) are historical documents NOT subject to configuration control.  Nonetheless, SDDs are important documents in the design evolution process.  SDDs are the comprehensive design basis that describes (but not defines) the design of each subsystem and how the design satisfies the requirements specified in the requirements documents.  SDDs will be prepared and updated by WBS Managers according to a format appropriate for each major design review (e.g., conceptual design review, preliminary design review, and final design review.  The SDDs describe the technical baseline upon which the cost and schedule baselines are predicated at each major design review point.  At each major review point, the cost and schedule baselines are updated and the SDDs are also updated to provide a description of the companion technical baseline at that point in time.

### 3.3.2	Cost and Schedule Baselines

The cost and schedule baselines are defined by a resource-loaded schedule stored in a Primavera Project Planner (P3) Database.  Adopting changes to the cost and schedule baselines will be done in accordance with the change control procedures described earlier.  When the project changes the project baselines, the data files defining the new cost and schedule baselines will be uniquely identified and locked, preventing further changes under that identifier.  Viewable files will be generated for project use in PDF format.  The viewable files will include the identifier for the data files from which they were generated.

NCSX Configuration Management Plan

Annex I

Engineering Change Proposal (ECP) Form

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |
| Originator: | Date: |
| ECP No: | ECP Title: |
| Required Reviewers |
| Name | Review? | Name | Review? |
| NCSX Systems Engrg Support Mgr. | ( Yes ( No | NCSX ES&H Manager | ( Yes ( No |
| NCSX Project Control Mgr. | ( Yes ( No | NCSX QA Manager | ( Yes ( No |
| Project Engineer (Stellarator Core Systems) | ( Yes ( No | NCSX Physics Head | ( Yes ( No |
| Project Engineer (Ancillary Systems) | ( Yes ( No | NCSX Engineering Mgr | ( Yes ( No |
| Project Engineer (Assembly Operations) | ( Yes ( No | Others: | ( Yes ( No |
| WBS Manager: WBS | ( Yes ( No | Others: | ( Yes ( No |
| WBS Manager: WBS | ( Yes ( No | Others: | ( Yes ( No |
| WBS Manager: WBS | ( Yes ( No | Others: | ( Yes ( No |
| ECP Approval Level Expedited ECP? ( Yes ( No Change Level: Approving Official: |
| Comments |

| APROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |
| --- |
| Change Level | Approving Official | Approval? | Signature |
| 3 | NCSX Project Manager | ( Yes ( No |  |
| 2 | NCSX Federal Project Manager | ( Yes ( No |  |
| 1 | NCSX Program Manager | ( Yes ( No |  |
| 0 | Acquisition Executive | ( Yes ( No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: | Date: |
| Overview of Change Type of Change: ( TECHNICAL ( COST ( SCHEDULE (Check all that Apply) Reason for Change: Impacted WBS Elements: Impacts of Change (Briefly Describe): Design (Including Interfaces): Performance: Requirements: Cost: Schedule: Maintenance: ES&H: RAM: Assessment of Other Options: |
| Detailed Description of the Change: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) Attachments (List): List of Impacted Documents : Description of Change: |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I CONTINUATION SHEET (TO BE COMPLETED BY ORIGINATOR) |
| Originator: | Date: |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART II (TO BE COMPLETED BY REVIEWERS) |
| ECP No: | ECP Title: |
| Reviewer: Corrections Needed? ( Yes ( No If yes, identify corrections needed: Concur? ( Yes ( No Provide reasons for concurrence/rejection: Other Recommendations? ( Yes ( No Identify Recommendations Signature: |

NOTE:  Part II – Review Form will be multiple forms

Instructions for Completing the ECP Form

- Initiating an ECP

  - Initiator fills out Part I:

    - Originator:  Name of Person Initiating the ECP

    - Date:  Date ECP Prepared

    - Type of Change:  Check all blocks that are applicable => Technical, Cost, or Schedule

    - Reason for Change:  Brief explanation on why the change is necessary

    - Impacted WBS Elements:  Identify impacted WBS elements

    - Impact of Change:  Check off applicable blocks and provide brief impact statement of the expected impact of this proposed change:

- Design (Including Interfaces)

  - Performance

  - Requuirements

  - Cost

  - Schedule

  - Maintenance

  - ES&H

  - RAM

    - Assessment of Other Options:  Provide brief discussion of other options considered and why this option selected

    - Detailed Description	of Change:  Using the continuation page if needed, provide a reasonably detailed explanation of the change, including identification of any attachments and a list of impacted documents

  - Initiator sends completed Part I and any attachments and continuation pages to the Systems Engineering Support Manager for further processing

  - Systems Engineering Support Manager reviews proposed change and, if required, requests additional amplifying information to complete the package

  - Once the change package is complete, the Systems Engineering Support Manager fills out top portion of the ECP Cover Page:

    - Identifies Originator of the ECP and Date ECP prepared

    - Assigns ECP Number in accordance with the scheme outlined in this CMP

    - Assigns ECP Title that is descriptive of the proposed change

    - Identifies required reviewers by checking yes or no blocks

    - Based on information provided in Part I, identify whether this ECP should be processed as an “expedited” ECP, the Change Level of this proposed change and the final approving official:

| Change Level | Approving Official |
| --- | --- |
| 3 | NCSX Project Manager |
| 2 | NCSX Federal Project Manager |
| 1 | NCSX Program Manager |
| 0 | Acquisition Executive |

    - Provides any amplifying comments to assist in the review and disposition of the proposed change

    - Posts proposed ECP on the Engineering Web Page: http://www.pppl.gov/me/NCSX_Engineering/

    - Notifies required reviewers that the ECP is now posted on the Engineering Web Page

  - Reviewers fill out Part II:

    - Fill out ECP Number and Title

    - Identify reviewer name

    - Check block indicating whether or not corrections needed (e.g., additional reviewers, correction to impact statements, etc. and the specific corrections needed.  Return Part II to Systems Engineering Manager for recycling ECP to obtain corrections needed

    - If no corrections needed, check block on whether or not the reviewer concurs in the ECP and provide reason for concurrence or rejection recommendation

    - Identify if there are other recommendations (e.g., modified ECP to include other impacted documents, etc. and specifically identify those recommendations

    - Electronically sign the ECP using the Adobe Signature feature.

    - Return completed Part II to the Systems Engineering Support Manager electronically

  - Once all the Part II review sheets are completed, the Systems Engineering Support Manager re-reviews ECP to ensure completeness and schedules the ECP for a CCB Meeting.  Prepares minutes from the CCB.

  - If the ECP is a Class 3 ECP (NCSX Project Manager is the approving official), annotate the ECP Tracking Log (Figure 3.3-3) indicating the disposition and complete the ECP Implementation Log (Figure 3.3-4) to track implementation of the incorporation of the ECP into the affected documents.

  - If the ECP is a Class 2 or higher level ECP, requiring DOE approval, prepare the transmittal letter for NCSX Project Manager signature.  Once the ECP is dispositioned, repeat step 7 above.

  - Monthly identify the implementation status of each ECP as part of the monthly status meetings to ensure visibility of the implementation of the ECP.

# Text boxes

What’s this?

I think this is the CCB decision