###### NCSX

CONFIGURATION MANAGEMENT PLAN

(NCSX-PLAN-CMP)

DRAFT G

November 26, 2002

Prepared by:													R. Simmons, Systems Engineering

Support Manager

Concurrences:

R. Strykowsky, Project Control			  P. Heitzenroeder, Deputy Project

Manager						Manager for Engineering

J. Malsbury, QA Manager		   M. Zarnstorff, Physics Manager

_____________________________  		_____________________________

B. Nelson, Stellarator Core Systems		L. Dudek, Ancillary Systems

Project Engineer					Project Engineer

_____________________________  		_____________________________

E. Perry, Assembly Operations		W. Reiersen, Engineering Manager

Project Engineer

Approved by:

G.H Neilson, Project Manager

| Revision | Date | Description of Changes |
| --- | --- | --- |
| DRAFT G | November 12, 2002 | Incorporated comments from GHN, WTR, JM & LD and WTR input to GHN comments. |

Table of Contents

1	BACKGROUND AND INTRODUCTION	i

1.1	Program Description	1

1.2	Overview of the NCSX Configuration Management Program	1

1.3	Relationships to Other DOE and NCSX Plans and Procedures	2

2	ORGANIZATION AND RESPONSIBILITY	4

3	CONFIGURATION MANAGEMENT	4

3.1	Configuration Change Control	4

3.1.1	Placement of Documents Under Configuration Change Control	4

3.1.2	Evolution of the Baselines	5

3.1.3	Engineering Change Proposal	7

3.1.4	Expedited ECPs	10

3.1.5	Change Control Board	10

3.2	Baseline Documentation	10

3.2.1.	Technical Baseline	10

3.2.2.	Design Basis Documents	14

3.2.3	Cost and Schedule Baselines	14

List of Figures

Figure 3.1-1 Managing the Evolution of Project Baselines	6

Figure 3.1-2 The Change Control Process	8

Figure 3.1-3 Sample ECP Status Log	9

Figure 3.1-4 Sample ECP Detailed Implementation Log	9

List of Tables

Table 1.3-1 NCSX Project Change Classification Matrix	3

# BACKGROUND AND INTRODUCTION

## Program Description

The National Compact Stellarator Experiment (NCSX) is an experimental research facility that is to be designed and constructed at the Department of Energy’s Princeton Plasma Physics Laboratory (PPPL). Its purpose is to develop the physics of compact stellarators, an innovative fusion confinement concept.  The facility will include the stellarator device and ancillary support systems. The design and fabrication project will be led by PPPL, in partnership with the Oak Ridge National Laboratory (ORNL).  This partnership approach is being used to effectively take advantage of each laboratory’s specific expertise to provide the best possible facility for the fusion research community.

## Overview of the NCSX Configuration Management Program

Configuration Management (CM) is an integrated program that ensures that the configuration is identified and properly documented and that changes to the configuration are controlled during this life cycle.  However, this Configuration Management Plan (CMP) focuses on the design and fabrication phases of the NCSX Project, including the integrated systems testing and producing the first plasma. The Office of Fusion Energy Sciences (OFES) has identified the NCSX Project as a Major Item of Equipment (MIE).

The physical and functional description of the components, systems, and software/firmware comprise the “configuration” of the NCSX MIE Project.  The NCSX project and details of its design configuration is progressively described in greater detail as it proceeds through the design process, fabrication, assembly, and installation.  The goal of the NCSX Configuration Management Program is to ensure that the configuration design evolution is controlled and that the documentation of the configuration design shown in electronic drawings and models accurately reflects what is installed in the field to the extent practicable.

At selected points in the NCSX life cycle, the current design configuration, including fabrication and testing define the technical baseline.  The cost and schedule estimates to accomplish this technical baseline are developed to form the cost baseline and schedule baselines.  These three baselines are fully integrated since they are derived from the same configuration.  The combination of technical, cost, and schedule baselines forms the basis for project work authorization and management.   This becomes the basis against which the status of resources and the progress of the NCSX Project are measured.  Consequently, there are three baselines:  technical, cost, and schedule.  Any proposed change to one baseline must be evaluated from the perspective of its impact on the other two baselines.

The CM program described in this NCSX Configuration Management Plan (CMP) is consistent with higher-level DOE orders and procedures.  The CMP is intended to provide the following processes:

- Configuration Identification - a process for identifying configuration items and development of the appropriate configuration documentation to define the physical and functional characteristics of each configuration item.

- Configuration Change Control - a process for identifying and managing proposed changes to a configuration item and its characteristics and the impact of the proposed change on the documentation describing the technical, cost, and schedule baselines.  This includes evolution of the design of the configuration item over time and tracking of the status of proposed changes to the configuration item until the change is approved or rejected.

- Configuration Status Accounting - a process for tracking the status of the implementation of approved changes in detail down to each impacted document.

- Configuration Verification - a process for verifying that the latest approved documents are used to fabricate/test configuration items and that the as-built physical and functional configuration is accurately reflected in the supporting documentation.  It is anticipated that most of this effort will occur under the existing PPPL QA program.

While the NCSX Configuration Management Program is implemented immediately when the initial technical, cost, and schedule baselines are established, not all design information will be under formal configuration control at the same time.  Rather, progressively more and more detailed information and documentation is placed under formal configuration control as the design matures.

## Relationships to Other DOE and NCSX Plans and Procedures

In accordance with DOE Order 413.3, the NCSX Project is classified in the category of Other Projects (Not Major System Projects).  Baseline change control (technical, cost, and schedule) approval thresholds for Level 0 (Secretarial Acquisition Executive) and Level 1 (Program Secretarial Officer) are defined in Attachment 5 to this order.  Baseline change control for Level 2 (Federal Project Manager) and Level 3 (Project) are outlined in the NCSX Project Execution Plan (NCSX-PLAN-PEP). The PEP provides policy guidance for the overall planning and execution approach being used on the project and invokes this Configuration Management Plan (NCSX-PLAN-CMP) as the vehicle for maintaining the technical, cost, and schedule baselines for NCSX.  Error! Reference source not found. depicts the Level 0, Level 1, Level 2, and Level 3 NCSX baseline change control approval thresholds.  In addition, several other NCSX plans, procedures, and documents support and implement other specific details outlined in this CMP.  These include the:

- Systems Engineering Management Plan (NCSX-PLAN-SEMP);

- NCSX Quality Assurance Plan (NCSX-PLAN-QAP);

- NCSX Data Management Plan (NCSX-PLAN-DMP)

- NCSX Document and Records Plan (NCSX-PLAN-DOC)

- Interface Control Management Plan (NCSX-PLAN-ICMP)

- Pro/INTRALINK Users Guide

- WBS Dictionary (NCSX-WBS)

- NCSX Procedure (NCSX-PROC-001), NCSX Glossary of Acronyms and Definitions

- NCSX Procedure (NCSX-PROC-002), NCSX Configuration Control

- PPPL Engineering Procedures and Standards, including, but not limited to the latest version of:

  - ENG-006 “Review and Approval of Specifications and Statement of Work”;

  - ENG-010 “Control of Drawings, Software, and Firmware”;

  - ENG-019 “PPPL Engineering Standards”;

  - ENG-029 “Technical Definitions and Acronyms”; and

  - ENG-033 “Design Verification”

If deemed necessary as this program is implemented, the NCSX Project may develop project-specific configuration management and control procedures to augment the above documents.

| Change Level | Approval Level | Technical Scope | Schedule | Cost |
| --- | --- | --- | --- | --- |
| 1 | Under Secretary of Energy | Changes to the technical requirements and parameters that do not meet mission need objectives. Changes to the Acquisition Execution Plan (AEP) | ( 6 months cumulative increase in a DOE Level 1 milestone date | Baseline change of ($50M in TEC and/or increase in TEC requiring Congressional reporting |
| 2 | Associate Director OFES | Changes to technical requirements and parameters that affect safety basis and operation function, but do not affect mission need objectives Changes to the PEP | 3-6 months cumulative increase in a DOE Level 1 milestone date | Baseline change of ($25M in TEC |
| 3 | NCSX Federal Project Manager | Changes to the GRD Changes with ES&H impacts significant enough to affect the approved NEPA/EA documentation | < 3 months change to a DOE Level 1 milestone date Changes to DOE Level 2 Milestones | Baseline change of <$25M in TEC Changes requiring the use of contingency funds |
| 4 | NCSX Project Manager | All other changes to the configuration and/or documentation under configuration control | All other changes to the performance measurement baseline schedules | All other changes to the performance measurement baseline costs |

Table 1.3-1 NCSX Project Change Classification Matrix

The CMP is the next most senior of the NCSX Project Plans following the Systems Engineering Management Plan (SEMP).  All other NCSX project plans are subservient to the CMP.

# ORGANIZATION AND RESPONSIBILITY

The NCSX Engineering Manager is responsible for the overall CM Program, including the establishment and monitoring of the technical, cost, and schedule baselines.  The Engineering Manager is also responsible for identifying which configuration items will come under configuration control and when.  Within his organization, the Systems Engineering Support Manager is responsible for the implementation and administration of the CM process and update of the technical, cost, and schedule baselines as described in this CMP.  The NCSX Project Control Manager provides support to the CM process in the area of cost and schedule assessments of proposed changes and implementation of approved changes to the cost and schedule baselines.

The NCSX WBS Managers are responsible for identifying the physical and functional configuration items that comprise their WBS elements and for developing the designs and the associated costs and schedule in their specific areas of responsibility, including proposing changes to those designs, costs, and schedules.  They are also responsible for assessing impacts of other proposed changes on their areas of responsibility.

The NCSX Project Manager is responsible for approving changes to the established technical, cost, and schedule baselines or, for those changes requiring DOE approval, making project recommendations.  In some instances where the scope of the change is urgent or a relatively minor nature, the NCSX Project Manager may authorize the NCSX Engineering Manager to disposition and implement the proposed change in an expedited fashion.  This process is described later in Section 3.1.4 of the CMP.

# CONFIGURATION MANAGEMENT

## Configuration Change Control

### Placement of Documents Under Configuration Change Control

At the start of Title I (Preliminary Design), the initial technical, cost, and schedule baselines will be established and will form the basis for the performance measurement baseline in the NCSX Project Control System (PCS).  The project technical baseline starts as a high-level specification and evolves to greater level of detail as the design progresses.  This process is controlled by the manner in which documents are progressively placed under configuration control as the design details mature.  Details of the design that are not under formal configuration control are controlled in less formal manner by the engineering manager and WBS managers.

In general, project design reviews will determine when specific configuration items come under formal change control.  As a guideline, the following configuration items will come under configuration control at the following design review points:

- Conceptual Design Review (CDR) – The CDR was successfully completed in May, 2002.  Following resolution of the major CDR recommendations and comments, including some changes in schedule logic,  and revised DOE funding guidance, the Advanced Conceptual Design Baseline was established at the start of the Advanced Conceptual Design Phase in late summer, 2002.  This baseline is the source of the baseline cost and schedule information documented in the NCSX Project Execution Plan (PEP) that was approved as part of the CD-1 milestone achievement. at that time, the General Requirements Document (GRD), the technical data that constitutes the fundamental agreements between engineering and physics (e.g., the coil geometries, coil currents for the reference scenarios, and the first-wall envelope), and the Pro/Engineer (Pro/E) models and drawings will constitute the technical baseline.  The cost estimate and schedules that are consistent with this technical baseline will constitute the cost and schedule baselines.  These baselines will serve as a point of departure for implementing the CM process internally and the elements described here will be under formal change control.  While the project will begin using these developmental Advanced Conceptual Design baselines for performance measurement, under DOE Order 413.3, the overall project technical, cost, and schedule baselines are not officially established from a DOE perspective until the Critical Decision 2 (CD-2) milestone (Approve Acquisition Performance Baseline/APB).

- Preliminary Design Reviews (PDRs) – At the completion of preliminary design, subsystems or grouping of subsystems will undergo formal preliminary design reviews or PDRs.  At the completion of these PDRs, the subsystem requirements expressed in System Requirements Documents/SRDs (flowed down from the GRD), interface control documents (ICDs – representing interface agreements between systems), updated models/drawings, and any other supporting technical data (e.g., tables, sketches, computer files, etc.) will be defined and placed under configuration control.  These “design-to” specifications and constraints let the each WBS manager know what they have to design to and what are the envelope and boundary conditions for final design.

- Final Design Reviews (FDRs) – At the completion of the final design process, specifications, interfaces, models/drawings, and supporting technical information will have matured to a level of detail sufficient to permit fabrication and assembly.  A series of final design reviews or FDRs will be conducted to mark the transition point from design to fabrication.  The key “build-to” documents that will now come under configuration control include manufacturing specifications, assembly procedures, fabrication drawings, and any other technical data that is needed to constrain the fabricator or assembler.  Near the end of project fabrication, testing procedures will also be developed and placed under configuration control.

- Project Completion –The goal of the NCSX configuration management program is to ensure that the documentation reflected in electronic drawings and models accurately reflect what is installed in the field to the extent practicable.  The DMP summarizes how the Project will make every reasonable effort to achieve this goal.

### Evolution of the Baselines

As indicated in Section 3.1.1 above, the initial technical, cost and schedule baselines will be established at the start of preliminary design.  During preliminary design or final design the level of detail and understanding of the constraints and envelopes of the design will evolve.  Between the time that the initial technical, cost, and schedule baselines are established and the periodic cost and schedule reviews outlined in the PEP and/or the technical design reviews outlined in the SEMP and this CMP, the technical baseline and its associated cost and schedule details will evolve.  These will be documented in “developmental baselines” that will be controlled at the WBS manager level, but will not be under formal configuration control.  In preparation for the periodic cost and schedule reviews and/or technical design reviews (e.g., PDR or FDR), the WBS Manager will develop and promote models and documentation in accordance with the Pro/INTRALINK provisions described in the DMP.  Once the appropriate cost and schedule and/or technical design review is completed and the recommendations incorporated, the responsible WBS Manager will prepare a formal ECP (or a global ECP) to initiate the process to formally change the existing technical, cost, and schedule baselines that are the basis for the NCSX Project’s performance measurement baseline.  Once the ECP is approved, a revised baseline is then established for performance measurement.  Figure 3.1-1 provides a flow chart of managing the development of the project baselines.

Figure 3.1-1 Managing the Evolution of Project Baselines

### Engineering Change Proposal

All changes to project baselines will be accomplished by the Engineering Change Proposal (ECP).  Evolutionary changes to baselines (technical, cost, and schedule), in which the design (and the associated cost and schedule impacts) advances in a level of detail, moving beyond but not necessarily changing that which is already under formal change control or adjustments due to actual cost and schedule performance against established baselines, will be handled by periodically updating the reference design to incorporate these developments.  As indicated on Figure 3.1-1, these “omnibus” ECPs will be processed to capture multiple small changes.  Discrete and significant changes, in which a change of thinking or understanding causes the project to change something that is already under formal configuration change control, will be handled by a stand-alone ECP.  NCSX Procedure NCSX-PROC-002, NCSX Configuration Management, provides the details of the process for completing and processing an ECP.  It is anticipated that the ECP will eventually be on an interactive Configuration Management Web Page that will be sub-page to the NCSX Engineering Web Page.   The ECP form has three sections:

- Cover Page providing ECP numbering and title, suggested reviewers, and the approval signature blocks.

- Part I to be filled in by the originator and submitted to the Systems Engineering Support Manager for processing.  Amplifying information to the ECP such as design memoranda that provide a rationale/need for the proposed change, sketches, Engineering Change Notices (ECN), and cost and schedule impacts are prepared and attached.  These attachments are prepared in accordance with the following plans and procedures:

  - Sketches and ECNs – PPPL Engineering Procedure ENG-010, “Control of Drawings, Software, and Firmware”

  - Cost and Schedule impacts – prepared using the Primavera Project Planner (P3) software.

- Part II to be completed by each reviewer.

A change request can be initiated by anyone associated with the Project.  The initiator identifies the affected documentation, outlines the reasons for the change, quantifies the technical, cost, and schedule impacts, and describes the change in detail.  The ECP form allows for review of all changes in a consistent manner.  The normal adjudicating body for each ECP is the Change Control Board (CCB) and Section 3.1.5 that follows describes the makeup and operation of the CCB.  However, in some instances, a process for “expedited” ECPs may be appropriate and Section 3.1.4 that follows addresses when this might be applicable.  ECPs will be numbered sequentially as follows:  FY-XXX, where FY is the current fiscal year and XXX the sequential number of the ECP.

Once the ECP is adjudicated, the Project will be notified as to whether the ECP is approved or not approved.  If an ECP is approved, the ECP is then implemented and the affected documentation is revised accordingly in a timely manner.  The NCSX Systems Engineering Support Manager shall be responsible to the NCSX Project Engineering Manager for developing and implementing the web-based status accounting system.  The ECP and an updated list of approved, disapproved, and pending changes will be maintained electronically by the Systems Engineering Support Manager on the NCSX Configuration Management Web Page.  Figure 3.1-2 illustrates the change control process.

The WBS Manager is responsible for implementing approved ECPs, including coordinating the revision of impacted documents.  During the monthly status review meetings with each WBS Manager, the status of implementing the approved ECP into the impacted documents will be addressed.

Figure 3.1-2 The Change Control Process

To facilitate tracking of the status of ECP approval a web-based status log has been developed.  A sample of this ECP status log is depicted in Figure 3.1-1.  Additionally, another web-based status log has been developed to track the implementation status of approved ECPs.  A sample of this web-based page is depicted in Figure 3.1-4.

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) Status Log |
| --- |
| ECP Number | Version/Date | ECP Title | Status* |
| Status Notes: Submitted – ECP submitted and impact statements being prepared Pending – ECP complete and awaiting CCB disposition Level 4 Approved – Level 4 ECP approved and ready for implementation DOE Pending – DOE Level 3 ECP or higher approval needed DOE Approved – Level 3 ECP or higher approved and ready for implementation Disapproved – Either Project or DOE rejected ECP |

Figure 3.1-3 Sample ECP Status Log

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) Implementation Log Status Date: |
| --- |
| ECP No: | ECP Title: |
| Document | Revised? | Date Revised | Revision Number |
| Requirements Documents GRD Specifications (List Each) Spec Spec Procurement Documents | ( Yes ( No ( Yes ( No ( Yes ( No ( Yes ( No |  |  |
| Drawings/Model ECN #=> Dwg # ECN #=> Dwg # | ( Yes ( No ( Yes ( No |  |  |
| Environmental Documents EA SAD | ( Yes ( No ( Yes ( No |  |  |
| Cost Baseline | ( Yes ( No |  |  |
| Schedule Baseline | ( Yes ( No |  |  |

Figure 3.1-4 Sample ECP Detailed Implementation Log

### Expedited ECPs

Although any change to established baselines (technical, cost, and schedule) requires an ECP, it may not always be practical to follow the full-blown ECP processing system shown on Figure 3.1-2.  Instances where an “expedited” ECP might be appropriate is when a pending critical procurement needs to reflect the proposed change or if field activities may be delayed by the normal ECP process involving full reviews and the CCB.  The NCSX Engineering Manager, in consultation with the NCSX Project Manager, may direct the Systems Engineering Support Manager to implement an “expedited” ECP process in which the NCSX Engineering Manager may review and approve the ECP with only an abbreviated review.  However, any “expedited” ECPs will be reviewed “after-the-fact” by the full CCB to ensure that major errors and/or omissions were not made.

### Change Control Board

Once an ECP has been prepared, the determination made that this ECP does not qualify for “expedited” ECP processing, and the impacts fully documented, the ECP will come before a Project Change Control Board (CCB) that is comprised of senior members of the NCSX management team.  The NCSX Project Manager or his designee will chair the CCB.  Other members of the CCB will be assigned as appropriate, but may include the following:

- Systems Engineering Support Manager (Secretary of the CCB);

- Project Control Manager;

- Engineering Manager;

- Physics Head;

- Project Engineers impacted by the proposed change

- WBS Managers impacted by the proposed change;

- ES&H Manager;

- QA Manager;

- Other impacted managers; and

- NCSX Project Manager.

The chairperson shall have the ultimate authority to recommend/approve changes for the final approval; other CCB members act solely as advisors.  In instances where the ultimate approval authority is DOE, the NCSX Project Manager shall indicate his approval and forward it for DOE disposition with his recommendation to approve.

## Baseline Documentation

### Technical Baseline

The technical baseline at any stage of the project is defined by any or all of the following configuration defining documents:

- Requirement documents (specifications) that clearly define the performance requirements and constraints that need to be satisfied;

- Interfaces Control Documents (ICDs) that define the interfaces between WBS elements; and

- Drawings , models, and technical data that physically define the configuration.

#### Requirements/Specification Documents

Requirements/specifications for the NCSX Project are captured in a hierarchy of requirements, which begin with the system/project (top-level) requirements in the General Requirements Document (GRD).  The GRD provides performance requirements and constraints at the overall system (project) level and the allocation of each requirement to affected subsystems.  These initial subsystem requirement allocations in the GRD are expanded and developed in subsystem and lower level specifications as described in the following paragraphs.  As described in the Systems Engineering Plan (NCSX-PLAN-SEMP), the requirement/specifications may be classified in two basic categories:

- Developmental or “Design to” Specifications – these documents encompass the GRD and SRDs.  These documents provide the design requirements by system, envelopes, and boundary conditions that constrain the development of the final design.  As indicated earlier, the bulk of these documents will be placed under formal configuration control by the completion of preliminary design.

- “Build to” Specifications – these documents provide the details to enable a manufacturer to build or assembler to assemble the component, system, or subsystem.  Included in this category would be procurement specifications, detailed assembly and fabrication procedures, and detailed testing procedures.

The SEMP has identified five types of specifications with different functions for NCSX and these will naturally have different formats as appropriate. A specification tree shall be used to identify and plan for each specification required by the NCSX Project.  For each specification, the specification tree will identify the scope, specification type, and the organization responsible for its development.

The NCSX Project shall develop and implement a project-specific approach for developing specifications that meets the requirements set forth in most recent revision to PPPL Engineering Procedure ENG-006, “Review and Approval of Specifications and Work.”

#### Interface Control Documents

Interface requirements are functional, performance, and physical characteristics required to exist at a common boundary.  This boundary consists of performance/physical design constraints between systems and subsystems.  The interface may define either the physical boundary conditions or the functional or performance boundary conditions.

The ICMP defines the process and format for defining interfaces.  Two types of interfaces exist; primary and secondary interfaces.  Primary interfaces define those interfaces between systems with different developmental or “design to” specifications or external interfaces outside the project (as identified in the General Requirements Document/GRD).  Secondary interfaces define those interfaces between systems with the same developmental or “design to” specifications.  Interface Control Documents (ICDs) are only required for primary interfaces.

Development of the ICD is a two step process.  The first step is the development of  scope sheets.  These scope sheets, normally in the form of e-mail agreements, will be developed early in the preliminary design phase and document the agreements as to what primary interfaces exist, who will be responsible for developing the interface definition in the form of an ICD, and when the interface needs to be finalized.  Primary interfaces documented in ICDs will be brought under configuration control by completion of preliminary design.  Once an ICD is under configuration control, the informal scope sheet agreements disappear.  The interface will be documented in an Interface Control Document (ICD) and may also be physically depicted on a drawing/model. The ICDs represent agreements by the participants that:

- The interfacing designs are within the parameters specified by the ICD;

- The interfaces on either side of the WBS-WBS boundary are physically and functionally compatible with one another; and

- No change affecting interface compatibility is made to a design without coordination and agreement between the affected participants.

Secondary interface definition and management is left to the cognizant WBS Manager to define and manage.  Secondary interfaces should also be developed and defined on a time scale parallel to that of primary interfaces, but these secondary interfaces will not come under configuration control and their definition documentation is left to the needs of each WBS Manager; scope sheets may be used, but are not required.

Once an ICD is approved, it is under formal configuration change control and therefore an ECP is required to change an ICD.  The approved ECP will detail the changes to be made to an ICD.  Any responsible participant may submit an ECP against their ICD.  In the case where the interface is also physically depicted on a drawing the ECP must also reference an ECN if the drawing has been released for fabrication; changes to the drawing to update the interface can only be accomplished via the ECN as per PPPL Procedure ENG-010, “Control of Drawings, Software, and Firmware”.

#### Drawings and Models and Supporting Technical Data

##### Drawings and Models

Project drawings and models will be prepared in accordance with the PPPL Engineering Design/Drafting Standard ES-DRFT-001, which implements the latest version of the PPPL Drafting Standards Manual.  As indicated in the NCSX Data Management Plan (NCSX-PLAN-DMP), the majority of the drawings and models will be developed using Computer Aided Design (CAD) software; e.g., Pro/Engineer for mechanical 2D and 3D drawings and models and AutoCAD for electrical drawings.  All drawings and models that interface with the stellarator core will be prepared in 3D using Pro/Engineer.

The initial Pro/Engineer model will come under configuration control at the start of preliminary design.  Once these models and drawings come under formal configuration control, an ECP is required to effect changes to the drawing/model that impact the established technical, cost, and schedule baselines.  If a model or drawing has been released for fabrication and changes are required, an Engineering Change Notice (ECN) will also be prepared as an attachment to the ECP.  The ECN will be processed in accordance with the latest revision to PPPL Engineering Procedure ENG-010, “Control of Drawings, Software, and Firmware” with one alteration.  When an ECN is pending on a particular drawing the Drafting Supervisor will extract the affected drawing from the NCSX Pro/INTRALINK drawing released folder and add an Acrobat stamp that states “ECN Pending” along with the ECN number and any summary description added to the drop-down note.  Once the Acrobat stamp is added, the Drafting supervisor will place the drawing back into the released drawing folder.  This process allows all viewers of drawings in the Released Drawing folder to be made aware that an ECN is pending on a particular drawing.  After the ECN changes have been completed a PDF file will be made of the revised drawing and placed in the Release Drawing folder and the drawing with the ECN Acrobat stamp removed.

The CAD models and drawings are an extension of the systems requirements allocation process.  When developed as three-dimensional models and managed within an integrated product data management tool (Pro/INTRALINK) they provide, at the top level, a physical and functional hardware implementation of the design requirements as defined in the GRD.  In the Conceptual Design stage, models of the stellarator core and facility were developed and exist in varying degrees of detail, representing the overall design configuration.  Some models will have a high level of development while others will provide the allocation of volumetric space of a subsystem.

As described in the DMP and Section 3.1.2 of this CMP, models and drawings will progress though various interim design stages (Conceptual Design, Preliminary Design, Prototype, Final Design) to the fabrication release stage.  Each interim stage will be promoted, managed, and stored in accordance with the controlled processes described in the DMP.  These processes will support the periodic cost and schedule reviews, technical design reviews, and changes to the technical, cost, and schedule baselines whenever the design evolves to a point that a technical, cost, or schedule baseline change is deemed necessary.

Upon completion of the fabrication and assembly, a set of as-built drawings and models will be developed to ensure consistency between the design documentation and the physical configuration in the field.  Storage of all release points of the design process will allow models to be checked to assure compliance to earlier space allocations.

##### Supporting Technical Data

Technical data (e.g., coil geometries, coil currents for the reference scenarios, first-wall envelopes, tables, computer files, etc.) that support and substantiate the design will placed under formal configuration control on a case-by-case basis and at appropriate stages of the design when needed.  As the design evolves, it is anticipated that technical data will be controlled, checked, and approved in accordance with the processes set forth in the latest version of PPPL Engineering Procedure ENG-033, “Design Verification.”  WBS Managers will maintain copies of approved and checked calculations and design confirmatory information.

#### Procurement Support Documents

Procurement support documents include statements of work (SOW), specifications, and associated drawings and models.  While the same degree of configuration control as discussed for each of these items apply also to procurement support documents that form the basis of a procurement contract, the changes to these documents do not become applicable to the vendor until such time that the contract is changed.  Thus, while an ECP might change a technical document, not until the contract is also changes will this change be applicable to the vendor.

### Design Basis Documents

Another critical set of documentation that supports design reviews will be the Design Basis Documents (DBDs).  DBDs are historical documents NOT subject to configuration control.  Nonetheless, DBDs are important documents in the design evolution process.  DBDs are the comprehensive design basis that describes (but not defines) the design of each subsystem and how the design satisfies the requirements specified in the requirements documents.  DBDs will be prepared and updated by WBS Managers according to a format appropriate for each major design review (e.g., conceptual design review, preliminary design review, and final design review.  The DBDs describe the technical baseline upon which the cost and schedule baselines are predicated at each major design review point.  At each major review point, the cost and schedule baselines are updated and the DBDs are also updated to provide a description of the companion technical baseline at that point in time.

### Cost and Schedule Baselines

The cost and schedule baselines are derived from the Project’s technical baseline; the scheduled tasks and their estimated costs provide a time scale and cost for completing activities that make up the technical baseline.  The cost and schedule baselines reside in a Primavera Project Planner (P3) database that is controlled and maintained by the NCSX Project Control Manager.  The Level 2 resource-loaded schedules and associated milestones contained in this database, including year-by-year contingency utilization estimates, constitutes the controlled cost and schedule baseline for completing the NCSX Project.

Level 3 resource-loaded schedules and milestones, expanded in detail from the Level 2 baseline, are incorporated in Work Authorization Forms (WAFs).  The WAFs are used to authorized work and measure performance at the task level and those constitute the controlled performance measurement baseline for authorized work.

Adopting changes to the controlled cost and schedule baselines will be done in accordance with approved change control procedures outlined in this CMP.  When the project changes the project baselines, the data files that underpin the new cost and schedule baselines will be uniquely identified and locked, preventing further changes under that identifier. Viewable files will be generated for project use in PDF format.  The viewable files will include the identifier for the data files from which they were generated.

# Text boxes

Controlled Document

THIS IS AN UNCONTROLLED DOCUMENT ONCE PRINTED.  Check the NCSX Engineering Web prior to use to assure that this document is current.