## Project Baseline Objectives

The key technical objective of the NCSX project is the fabrication and assembly of the NCSX experimental facility. The facility will be capable of producing magnetized plasmas with a well-defined set of configuration properties, such as size, shape, magnetic field strength, and pressure, which in turn determine its physics properties. The NCSX will provide the flexibility to vary the configuration parameters over a range.

The plasmas to be studied are three-dimensional toroids, that is, doughnut-shaped plasmas whose cross sectional shape varies depending on where it is sliced. The magnetic field coils, which control the plasma shape, must be accurately constructed to precise shape specifications. The NCSX will provide an initial set of plasma control, heating, diagnostic, and power and particle handling systems and will be able to accommodate later upgrades, to meet the needs of the research program.

### Performance Baseline Parameters and Trade Space

A project’s Performance Baseline is defined by key performance, scope, cost, and schedule parameters [DOE M413.3-1, Chapter 10].  For NCSX, the key baseline parameters are:

Performance	The system performance levels to be demonstrated at project completion (First Plasma). These include quantitative metrics such as plasma parameters, coil and power supply currents, vacuum pressure and leak rate, etc., as well as certain subsystem functional tests.

Scope	A quantitative description of the equipment to be provided.

Cost	The total estimated cost of the project.

Schedule	The estimated project completion date.

The self-consistent set of values of these key parameters that describe the Performance Baseline are called the objective values. The project’s objective cost and schedule baseline are supported by bottoms-up estimates of costs and risk-based contingencies, whose technical basis is consistent with the objective performance and scope parameters.

We also identify a more conservative set of values for the performance and scope parameters, known as threshold values, to define the minimum acceptable level of project accomplishment. In spite of sound estimates, prudent risk mitigation measures, and reasonable contingency reserves when initially baselined, the risk of future baseline deviations cannot be totally eliminated. Should that occur, the project’s contingency plan, after all reasonable corrective measures are exhausted, is to reduce performance or scope, remaining above the minimum, or threshold, values of these parameters. The space between the objectives and the thresholds is normally referred to as the “trade space.”  The threshold performance and scope parameters are documented here to provide up-front ground rules for the tradeoffs that might have to be made in the execution of the project, should it become necessary.

The implementation of any such changes in the baseline would be made in accordance with the change control procedures and approval thresholds specified in this Project Execution Plan. Once a change in the baseline is approved, the new baseline parameters become the objective parameters, so that the objective performance, scope, cost, and schedule parameters are made self-consistent.

### Fabrication Project Objectives and Thresholds for Performance at Project Completion

The major radius of the NCSX plasma is 1.4 m.  The facility will initially support an ohmic (OH) scenario with a magnetic field strength of 1.5T and a plasma current of 150 kA for a 0.3 second flattop.  Refurbishment and installation of 3 MW of Neutral Beams (NBI) will be done as part of the NCSX MIE project.

The NCSX facility will initially support operation with room-temperature coils, including: 1) First Plasma operation with a magnetic field strength of 0.5T and a plasma current of 25 kA, 2) field-line mapping operation with a magnetic field strength of 0.5 T and no plasma, and maybe 3) limited Ohmically-heated (OH) plasma operation with a magnetic field strength of ≤1 T (tbd) and a plasma current of ≤100 kA (tbd) for a tbd second flattop.  Identification and testing of legacy equipment (tbd) for 3 MW of Neutral Beam Injection (NBI) heating will be done as part of the NCSX MIE project.

Plasma performance requirements for later phases of the research program are documented in the preliminary NCSX Experimental Plan (part of the conceptual design documentation).  The plan will evolve during the NCSX fabrication phase as the research program, including its hardware and plasma performance requirements as a function of time, are defined in more detail. (This paragraph seems superfluous, but somebody in DOE may have wanted it.)

The milestone marking the transition from a fabrication project to an operating facility is the DOE Critical Decision 4 (CD-4) milestone, also known as “First Plasma”. The Operations phase will begin upon completion of the First Plasma milestone.  The First Plasma milestone will demonstrate a level of system performance sufficient for the start of research operations. The performance objective and thresholds at Project Completions are tabulated at the end of this sub-section:

As required by DOE, a Project Completion Report will be prepared and submitted to DOE/PAO within six months of completion of the Project. This report will provide the following information:

- The actual schedule on which the project will have been completed;

- The actual total project costs;

- he technical performance of the systems at project completion; and

- Itemized changes in cost, schedule, and technical parameters as compared to the initial baseline.

##### Table. XX.  NCSX Performance Objectives and Threshold at Project Completion

|  | - Objective Performance | - Threshold Performance |
| --- | --- | --- |
| - First Plasma | - An Ohmically heated stellarator discharge will be produced with: - major radius 1.4 m. - magnetic field of ≥ 0.5 T - plasma current of ≥25kA - at least 50% of the rotational transform provided by stellarator fields. - The three-dimensional stellarator geometry will be confirmed by taking video images of the plasma. |  |
| - Coils and - Power Supply Performance. | - The coils will be cooled down to cryogenic operated at room temperature and energized with their own power supplies (except as noted) to the following currents: - Modular coils: 5 kA - TF Coils: 3 kA - PF1 & PF2 Coils: 6 kA - PF3-4 Coils: 4 kA - PF5-6 Coils: 2 kA - External Trim Coils: 1 kA. (w/ temp. power supplies). |  |
| - Magnet System Rating | - It will be demonstrated by analysis that the stellarator magnet system of modular coils, TF coils, and PF coils is rated for operation at cryogenic temperatures to support plasma conditions with: - high beta (4%) - magnetic field up to 2 T (0.2) or 1.2 T (1.7s) - Ohmic current drive up to 320 kA - full flexibility, per the GRD. | Magnet system rating reduced to: - magnetic field up to 1.6 T (0.2) or 1.2 T (tbd s) - Ohmic current drive up to 255 kA - reduced flexibility |
| - Vacuum | The following will be achieved: - A vacuum vessel base pressure of 210-7 torr. - A maximum global leak rate of <1x10-4 torr-l/s. |  |
| - Vacuum Vessel System rating | It will be demonstrated by analysis that the vacuum vessel system is rated for high-vacuum performance with: - base pressure less than or equal to 210-8 torr @293K - global leak rate less than or equal to 210-5 torr-l/s @293K. - bakeable at 150 C | Vacuum vessel system rating reduced to: - base pressure less than or equal to 810-8 torr @293K - global leak rate less than or equal to 510-5 torr-l/s @293K |
| - Controls | Integrated subsystem tests, to the level required for First Plasma, will be completed for the following systems: - Safety interlocks. - Timing and synchronization. - Power supply real time control. - Data acquisition. |  |
| - Neutral beams | - Beamlines will be mechanically installed on NCSX. - All cabling and other connections will be installed. - Beamline operating vacuum will be achieved. - Beamline cryopanels will be cooled down to cryogenic temperatures. |  |

### Fabrication Project Objectives and Thresholds for Scope

The NCSX fabrication project scope includes all the equipment required at the start of operations (First Plasma and initial field mapping) plus refurbishment and installation of identification and testing of legacy equipment for 3 MW of neutral beam heating power. The scope includes Title I through Title III engineering, physics analyses in support of the design, manufacturing development for certain components, fabrication, assembly and installation, integrated systems testing, and project management associated with producing the in-scope equipment. It includes achievement of First Plasma. See Annex I for detailed scope objectives and thresholds.

The NCSX will be designed so that anticipated equipment upgrades can be accommodated when needed. Specifically, the system is designed to accommodate the following upgrades: a total of 6 MW of neutral beam injection (NBI) heating power, 6 MW of ion cyclotron radiofrequency (ICRF) heating power (tbd), 3 MW of electron cyclotron heating (ECH) power, a pellet injector, trim coils, power supplies and cryogenic cooling systems for higher B-field, power supplies for faster startup or increased flexibility, additional plasma facing components and internal pumps for divertor operation, alternate first-wall materials, additional wall conditioning systems, and additional diagnostics) can be accommodated when needed. (See Annex I). The NCSX Project scope does not include the actual implementation of these upgrades, which will be funded out of research program budgets, depending on program needs.

Activities to support NCSX research planning and preparation that will proceed in parallel with NCSX fabrication are not included in the NCSX MIE Fabrication Project scope.

### Fabrication Project Cost Objective

As indicated in Section 1.0 of  this PEP, the NCSX Project has been designated as a Major Item of Equipment (MIE) by OFES and will be built using Capital Equipment Funds. At the completion of the Conceptual Design Review and as part of the CD-1 approval process, a baseline total estimated cost (TEC) range of $69M - $83M for the MIE fabrication project was established and approved by DOE.  Now as part of the CD-2 approval process, a baseline TEC objective has been established as $73.5M.

### Fabrication Project Schedule  Objective

- The project’s schedule objective is to complete the project with the Achievement of First Plasma by June 30, 2007. The DOE Level schedule objectives (Level 1 and 2) for the NCSX project are summarized in Figure XX-1. For the NCSX Project, the Acquisition Executive Officer will be the Associate Director for Fusion Energy Sciences, Office of Science.

Figure XX-1 NCSX DOE Milestones (BOB & RON FINALIZE)

| - Milestone |  |  | - Schedule |  | - DOE Acquisition Executive - (Level 1) |  | - DOE Federal Project Director - (Level 2) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Complete Physics Validation Review |  |  | March 2001A |  |  |  | X |
| Complete CD-0 Milestone |  |  | May 2001A |  | X |  |  |
| Select Conceptual Design Configuration |  |  | December 2001A |  |  |  | X |
| Submit NEPA Preliminary Hazards Analyses |  |  | April 2002A |  |  |  | X |
| Complete Conceptual Design Review |  |  | May 2002A |  |  |  | X |
| Complete CD-1 Milestone |  |  | November 2002A |  | X |  |  |
| Receive FONSI |  |  | October 2002 A |  |  |  | X |
| Award Prototype Contract(s) for Modular Coils Winding Forms |  |  | March 2003 A |  |  |  | X |
| Award Prototype Contract(s) for Vacuum Vessel |  |  | April 2003 A |  |  |  | X |
| Start Preliminary Design (Title I) |  |  | April 2003 A |  |  |  | X |
| Complete Preliminary Design Review |  |  | September 2003 |  |  |  | X |
| Complete External Independent Review |  |  | October 2003 |  |  |  | X |
| Complete CD-2 Milestone |  |  | November 2003 |  | X |  |  |
| Complete Final Design Review for Modular Coils Winding Forms |  |  | March 2004 |  |  |  | X |
| Complete CD-3 Milestone for Procurement and Fabrication of Components | April 2004 |  |  | X |  |  |  |
| Award Production Contract for Modular Coils Winding Forms | June 2004 |  |  |  |  | X |  |
| Complete Final Design Review for Vacuum Vessel | February 2004 |  |  |  |  | X |  |
| Award Production Contract for Vacuum Vessel | May 2004 |  |  |  |  | X |  |
| Award Production Contract for TF Coils |  | July 2004 |  |  |  |  | X |
| Award Conductor Procurement for Production Modular Coils |  | August 2004 |  |  |  |  | X |
| Award Production Contract for PF Coils |  | October 2004 |  |  |  |  | X |
| First Modular Coil Winding Forms Delivered |  | September 2004 |  |  |  |  |  |
| Complete First Modular Coil Fabrication |  | December 2004 |  |  |  |  | X |
| 1st Period of Vacuum Vessel Shell Delivered |  | May 2005 |  |  |  |  | X |
| Begin Assembly of First Field Period |  | May 2005 |  |  |  |  | X |
| Last Modular Coil Winding Form Delivered |  | September 2005 |  |  |  |  | X |
| Last Field Period Assembled |  | July 2006 |  |  |  |  | X |
| Pump Down of Vacuum Vessel |  | January 2007 |  |  |  |  | X |
| Complete Operational Readiness Assessment |  | May 2007 |  |  |  |  | X |
| Complete CD-4 Milestone (First Plasma and Completion of MIE Project) |  | June 2007 |  |  | X |  |  |

Note:  	“A” => Achieved

##### Annex I. NCSX Scope Objectives and Thresholds

The NCSX Performance Baseline Scope objectives are listed, by WBS, in the second column of the table. The third column lists the Scope thresholds, representing the minimum scope in that system, should de-scoping be in the course of project execution. The first column lists, for comparison, the project scope as presented in the Preliminary Project Execution Plan at the time of the Conceptual Design Review. The last column list the upgrades that the system is designed to accommodate, without regard to their implementation schedule

| - CDR Scope - Differences | - Objective Scope @PDR - (Performance Baseline) | - Threshold Scope | - Future Upgrades Accommodated By Design |
| --- | --- | --- | --- |
| - WBS 1. Stellarator Core |  |  |  |
| - Ex-vessel magnetic diagnostic assembly was not included. - Health Physics oversight costs were not included. - Cryostat was fully assembled. | - Vacuum vessel system including all ports and port covers. - Initial limiters. - Stellarator magnet system, consisting of modular coils, toroidal field coils, and poloidal field coils. - External trim coils. - Coil services (electrical and coolant feeds) - Support base and structures. - Cryostat (partially assembled) | - Same as objective. | - Plasma-facing component upgrades for: - power handling up to 12 MW - pumped divertor - alternate materials (e.g., C, Li, W). - Internal trim coils - Remainder of cryostat assembly. |
| - WBS 21, 22, 23. Fueling, Vacuum Pumping and Wall Conditioning Systems |  |  |  |
| - Torus vacuum pumping system was four TMPs, 2 ducts, 2,600 l/s. - Glow discharge cleaning (GDC) system was included. | - Torus vacuum pumping system based on two of the PBX-M turbomolecular pumps mounted on a single duct. Pumping speed approx. 1,500 l/s. - Residual gas analyzer. - Gas injection system based on 3 injectors @50 torr-l/s each for H, D, and He. | - Same as objective. | - Two additional turbomolecular pumps on a second duct with, for a total pumping speed of 2,600 l/s. - Wall conditioning systems: - GDC, boronization, lithiumization. - Pellet injector. |
| - WBS 25 Neutral Beam Injection Systems |  |  |  |
| Equipment refurbishment and installation was planned: - Two PBX-M neutral beam lines refurbished, repaired as needed, installed in new location, mechanically connected to torus. - Beam lines under vacuum. - Sources refurbished & installed. - Beam line cryopanels cooled to cryogenic temperatures. - Power systems for 2 beams refurbished, repaired as necessary, and tested. - Neutral beam PLC’s installed and tested. - Cables from power supply to beam lines installed. - Vacuum, cryogenic, air, water, and diagnostic connections made up. | Legacy equipment identification and testing: - Two PBX-M neutral beam lines, sources, and power supplies identified. - Legacy equipment tested. | Same as objective. | - 3MW of NBI based on first two sets of legacy equipment. - Additional 3 MW of NBI based on remaining legacy equipment. - 6 MW of ICRF heating (tbd) - 3 MW of ECH. |
| - WBS 3. Diagnostics |  |  |  |
| - 100 magnetic sensors, fully operational. - Fast visible camera was permanently mounted. - 1 mm interferometer was included. | - Ex-vessel magnetic sensors installed; eight fully operational. - Fast visible camera on simple mount. - Electron-beam field mapping apparatus | Objective scope, less… - Electron-beam field mapping apparatus | - In-vessel magnetic sensors. - All magnetic diagnostics fully operational. - Permanent installation of fast visible camera. - Physics diagnostic system, per GRD. |
| - WBS 4. Power Systems |  |  |  |
| - Coil power systems for First Plasma, initial field mapping, and initial Ohmic operation with cryogenically-cooled coils, consisting of: - 9 circuits. - 30 power supply sections. - ?? DC output cables. | - Coil power systems for First Plasma and initial field mapping operation with room temperature coils, consisting of: - 6 circuits. - 14 power supply sections. - 12 DC output cables. - Associated AC, DC, control, and protection systems. | - Same as objective. | - Coil power upgrades for high-beta plasma operation up to 2 T (short pulse), 1.2 T (long pulse), Ohmic current drive up to 320 kA, and full flexibility with coils cooled to cryogenic temperatures, consisting of: - 9 circuits (total). - 38 power supply sections (total). - 24 DC output cables (total). - Trim coil power supplies. - Associated AC, DC, control, and protection systems. |
| - WBS 5. Central I&C System |  |  |  |
| More elaborate system - Dedicated network infrastructure. - More remote operator interface. - Greater control and data acquisition requirements. | Computer system consistent with control and data acquisition requirements of in-scope equipment: - Computer network infrastructure. - Data acquisition and facility computing. - Facility timing and synchronization. - Real-time power supply control. - Central safety interlocks. - Control room facility. | - Same as objective. | - Expansions consistent with requirements of upgrade equipment. |
| - WBS 6. Facility Systems |  |  |  |
| Also included: - Water cooling system for neutral beams and diagnostics. - Cryogenic supply and transfer systems. - 150 C Vacuum Vessel Bakeout system. Did not include: - Temporary utilities for operation with room temperature coils. - C-Site water system re-commissioning. | - Water cooling system for vacuum pumps. - Temporary utilities for operation with room temperature coils. - Utility systems (venting, GN2, compressed air) - C-Site water system re-commissioning. | - Same as objective. | - Water cooling for neutral beams and diagnostics - Cryogenic supply and transfer systems. - 150 C Vacuum Vessel Bakeout system. - 350 C PFC Bakeout system. |
| - WBS 7. Test Cell Preparation and Machine Assembly |  |  |  |
|  | - Shield wall reconfiguration. - Control Room Refurbishment - Access Platform. - Machine assembly. - Integrated System Testing. | - Same as objective. | - N/A |
| - WBS 8 Project Oversight and Support |  |  |  |
| - Limited project management. - Limited system engineering, analysis, design integration. - No DCMA auditing services costs. | - Project Management - Project Control - System Engineering Management - System analysis - Design integration. - Environment, Safety, and Health - Quality Assurance, including DCMA auditing services costs. - Project physics | - Same as objective. | - N/A |
| - WBS 9 Preparation for Operations |  |  |  |
|  | - Pre-operations planning. - First Plasma. | - Same as objective. | - N/A |