National Compact Stellarator Experiment

NCSX

PROJECT EXECUTION PLAN

(NCSX-PLAN-PEP)

Revision 0, Draft C3

January 8, 2002

Prepared by:

______________________________

R.T. Simmons

NCSX Project Control Manager

Approvals:

______________________________

J.F. Lyon

NCSX Deputy Project Manager

for Program

______________________________

G. H. Neilson 			J.A. Schmidt

NCSX Project Manager 	PPPL Advanced Projects Dept. Head

______________________________	______________________________

R.J. Goldston			G. Pitonak

PPPL Director 		DOE NCSX Project Manager

| Revision | Date | Description of Changes |
| --- | --- | --- |
| Draft C3 | 1/8/02 | Incorporates latest changes proposed by GHN and Judy Malsbury |

##### Table of Contents

1.0	INTRODUCTION AND SCOPE OF THIS DOCUMENT	1

2.0	MISSION NEED JUSTIFICATION/PROJECT OBJECTIVES	1

2.1	Mission Need	1

2.2	Project Objectives	2

2.2.1	Technical Objective	2

2.2.2	Schedule Objectives	3

2.2.3	Fabrication Project Cost Objective	3

3.0	PROJECT DESCRIPTION	4

4.0	MANAGEMENT STRUCTURE AND RESPONSIBILITIES	6

4.1	NCSX Project Organization Structure	6

4.1.1	U.S. Department of Energy (DOE)	8

4.1.2	DOE Contractor Organizations	8

4.2	NCSX Management Team	9

4.2.1	Senior Laboratory Managers	9

4.2.2	NCSX Project Management Team	9

4.3	Program Advisory Committee	12

5.0	WORK BREAKDOWN STRUCTURE (WBS)	12

6.0	RESOURCE PLAN	13

6.1	NCSX Costs	13

6.2	Funding Profiles	14

7.0	PROJECT BASELINES	15

7.1	Configuration Baseline	15

7.2	Cost and Schedule Baselines	16

8.0	Control of Project Baselines	18

8.1	Configuration Management Approach	18

8.2	Change Control Process	18

8.3	Change Control Levels	19

9.0	Project Management and Control Systems	20

9.1	Project Management Systems Approach	20

9.2	Project Control System Overview	21

9.3	Cost and Schedule Reviews	22

10.0	 Funds Management	23

10.1	Project Funding Mechanisms	23

10.2	Management Reserve Funds	23

11.0	RISK MANAGEMENT	24

12.0	ACQUISITION STATEGY	25

12.1	Overview	25

12.2	Stellarator Core Systems Procurement	25

13.0	DOCUMENT CONTROL SYSTEM	26

13.1	Overview	26

13.2	Document and Records Plan	27

13.3	Project Completion Documentation	27

14.0	SYSTEMS ENGINEERING AND TECHNICAL MANAGEMENT	27

14.1	Systems Engineering	27

14.2	Quality Assurance	28

14.3 	NEPA Documentation And Safety Assessment	28

15.0	INTEGRATED SAFETY MANAGEMENT PLAN	28

16.0	REVISIONS TO THE PROJECT EXECUTION PLAN	29

LIST OF FIGURES AND TABLES

Table 2-1	NCSX Key Project Milestones	3

Figure 3-1	NCSX Stellarator Core	5

Figure 4-1	NCSX Project Organization Structure	7

Table 5-1	NCSX Project WBS Level 2 Matrix	13

Table 6-1	NCSX Project Preliminary Funding Profile	14

Table 8-1	NCSX Change Classification Matrix	20

ANNEX I – CONTINGENCY GUIDELINES

# 1.0	INTRODUCTION AND SCOPE OF THIS DOCUMENT

The National Compact Stellarator Experiment (NCSX) is an experimental research facility that is to be designed and constructed at the Department of Energy’s Princeton Plasma Physics Laboratory (PPPL). Its purpose is to develop the physics of compact stellarators, an innovative fusion confinement concept.  The facility will include the stellarator device and ancillary support systems. The design and fabrication project will be led by PPPL, in partnership with the Oak Ridge National Laboratory (ORNL).

This Project Execution Plan (PEP) covers the design and fabrication phase of the NCSX Project, including the integrated systems testing and producing the first plasma. The NCSX is a Major Item of Equipment (MIE) and therefore does not fall under the definition of a “project” in the strict DOE sense and definition.  Nonetheless, the NCSX project management will, in a graded approach, follow the concepts outlined in DOE Order 413.3 and the implementing Project Management Guide and Best Practices Manual.

- Where there are guiding PPPL documents (e.g., Project Control Systems Description and Integrated Safety Management Plan) and/or more detailed lower level documents [e.g., the Systems Engineering Management Plan (SEMP), Document and Records Plan (DCR) Plan, Quality Assurance Plan (QAP), etc.], only a brief overview of the approach is included in this PEP.

# 2.0	MISSION NEED JUSTIFICATION/PROJECT OBJECTIVES

## 2.1	Mission Need

- The National Compact Stellarator Experiment (NCSX) is needed to address one of the goals of the Department’s Office of Fusion Energy Sciences program, namely to determine the attractiveness of the compact stellarator concept.  It will address plasma physics questions that are critical to understanding magnetic confinement and which cannot be addressed with existing facilities. The NCSX mission need (Critical Decision 0) was approved by the Office of Fusion Energy Sciences in May, 2001.

- A program of experimental research will be carried out to accomplish this mission. The critical physics issues to be addressed– stability at high beta, confinement at high temperature, and divertor operation– set minimum plasma performance requirements. These considerations define the scale and scope of facility which is needed. They set the requirements on plasma size, magnetic field strength, plasma control, plasma heating, diagnostic access, and flexibility that the facility must satisfy. In the fusion program’s concept development hierarchy, NCSX is in a class of facilities called proof-of-principle (PoP) experiments.  The National Spherical Torus Experiment (NSTX) at PPPL, which is of a scale similar to NCSX, is another example. The NCSX design and fabrication project addressed by this plan will provide an operational facility which meets the physics requirements necessary to support the NCSX physics mission. The mission itself will be carried out in the Operations phase.

## Project Objectives

As part of the Conceptual Design process, the Project will develop a Project Execution Summary/Statement of Work (PES/SOW) that will represent a high-level DOE-project agreement on the mission, the technical objectives, the major milestones, the cost objective, and the high-level summary of the project work scope.

### 2.2.1	Technical Objective

- The key technical objective of the NCSX project is the fabrication and assembly of an experimental facility capable of accomplishing the NCSX’s physics mission. The facility will be capable of producing magnetized plasmas with a well defined set of configuration properties, namely size, shape, magnetic field strength, and pressure; these in turn determine its physics properties. Moreover, the NCSX will provide the flexibility to vary the plasma configuration over a range of flexibility. The plasmas to be studied are three-dimensional toroids, that is, doughnut-shaped plasmas whose cross sectional shape varies depending on where it is sliced. The magnetic field coils, which control the plasma shape, must be accurately made to precise shape specifications. The NCSX will provide plasma control, heating, diagnostic, and power and particle handling systems sufficient for first few phases of experimental operation and will be able to accommodate later upgrades to these cabilities, depending on research needs.

- The specific parameter objectives are as follows:

- Major radius R = 1.4 m;

- Toroidal field strength B0 = 1.7 T for 0.2 second flattop in a reference plasma configuration;

- Neutral beam heating power PNB = 3 MW

### 2.2.2	Schedule Objectives

- The schedule objectives for the NCSX project are summarized in Table 2-1:

| Table 2-1 - Milestone | - Schedule |
| --- | --- |
| - Physics Validation Review Completed | #### March 2001A |
| - CD-0 Milestone Completed | - May 2001A |
| - Conceptual Design Review Completed | - May 2002 |
| - CD-1 Milestone Completed | - May 2002 |
| - Start Preliminary Design (Title I) | - October 2002 |
| - CD-2 Milestone Completed | - September 2003 |
| - CD-3 Milestone Completed | - April 2004 |
| - Start Fabrication Activities | - April 2004 |
| - Procurement, Fabrication, and Asssembly Completed | - November 2006 |
| - Start Pre-Ops Testing | - November 2006 |
| - CD-4 Milestone Completed | - December 2006 |
| - First Plasma | - March 2007 |

##### NCSX Project Key Milestones

### 2.2.3	Fabrication Project Cost Objective

- The NCSX operational phase will be divided into a series of distinct research phases, of which the first four are expected to be:

- Initial Operation;

- Field Line Mapping;

- Initial Ohmic Heating; and

- Initial Auxiliary Heating;

- The NCSX Fabrication Project includes all the equipment required through the Initial Ohmic Heating phase of operation (i.e., Phases 1, 2, and 3), any modifications necessary to support installation and testing of 3MW of neutral beams for phase 4, and sufficient design work to ensure that all hardware upgrade requuirements can be accommodated.  The Fabrication Project cost objective is approximately $69M as-spent, assuming project execution in FY-2003 through 2007 and DOE escalation guidelines.  This includes Title I through Title III engineering, physics requirements definition and analyses in support of this design,  supporting manufacturing development, fabrication/assembly and installation activities, and commissioning and integrated systems tests.

- Activities to support NCSX research planning and preparation that will be funded annually, but separately from the Fabrication Project, are not included in the overall project cost objective..

# 3.0	PROJECT DESCRIPTION

- The NCSX project involves the design and fabrication of the NCSX facility. At the heart of the facility is the plasma confinement device, or stellarator core. This will be an assembly of several magnet systems that surround a highly shaped plasma.  Coils provide the magnetic field for plasma shape control, inductive current drive, and field error correction. The vacuum vessel and plasma facing components produce a high vacuum plasma environment with access for heating, pumping, diagnostics, and maintenance.  The entire system is surrounded by a cryostat to permit cooling of the magnets at cryogenic temperature.  Figure 3-1 shows a cutaway view of the stellarator core assembly.

- Figure 3-1   NCSX Stellarator Core

- The NCSX core will be assembled in the combined Princeton Beta Experiment/Princeton Large Torus (PBX/PLT) test cell at the Princeton Plasma Physics Laboratory (PPPL). It will be equipped with neutral-beam heating systems, pumps, fueling systems, diagnostics, control systems, and data acquisition systems. Site infrastructure such as cryogenic systems and utility services will be included. The PBX/PLT computer and control rooms, which are contiguous to the test cell, will be refurbished and utilized. Power supplies located at D-site will be used.

- The design of the stellarator core and facility re-configuration will be done by Laboratory (PPPL and ORNL) researchers and engineers. Development and manufacture of the major stellarator core components such as the coils and vacuum vessel will be done in industry, under contract to PPPL, or by a combination of industry and Laboratory efforts. The device will be assembled by Laboratory personnel. Ancillary systems will be assembled from a combination of new and existing equipment. Major site credits to be used are the PBX-M neutral beams, D-site magnet power supplies originally used on TFTR, some C-site power supplies, the PBX-M vacuum pumping and gas injection systems, the test cell and associated infrastructure, and the adjacent control and computer rooms. As part of the project, the facilities and equipment to be re-used will be reconfigured or refurbished as needed to meet NCSX requirements. In the final stage of the project, an integrated testing program will be carried out and a plasma (“first plasma”) will be produced in the device to make it ready for experimental operations.

# 4.0	MANAGEMENT STRUCTURE AND RESPONSIBILITIES

## 4.1	NCSX Project Organization Structure

- The NCSX project will be led by the Princeton Plasma Physics Laboratory (PPPL) with the Oak Ridge National Laboratory (ORNL) providing major leadership and support as a partner. The partners have formed an integrated team to carry out the NCSX project, where engineers and scientists from PPPL and ORNL work together to bring the necessary expertise to the project.   This means that PPPL engineers and scientists will support areas in which ORNL has the lead and similarly, ORNL engineers and scientists will support areas in which PPPL has the lead.  Management responsibilities are clearly assigned to one partner or the other, and PPPL has overall responsibility for the project. Figure 4-1 depicts the NCSX project organization structure and the key management responsibilities of the partner institutions.

- DOE

- Program Advisory Committee

- PPPL Director

- Deputy Director

- PPPL

- Advanced Projects Department Head

- PPPL

- NCSX Project

- Project Manager, PPPL

- Deputy Project Manager for Program, ORNL

- Deputy Project Manager for

- Engineering, PPPL

- Project Control

- PPPL

- ES&H

- Quality Assurance

- PPPL

- Project Engineering

- PPPL

- Project Physics

- PPPL

- Stellarator Core

- ORNL

- Diagnostic Systems

PPPL

- Site &

- Facilities

PPPL

- Plasma Heating, Fueling, & Vacuum Systems

PPPL

- Power

- Systems

PPPL

- Machine Assembly

- PPPL

- Central I&C

- Systems

- PPPL

- Figure 4-1  NCSX Project Organization Structure

- The following subsections describe the relationships between the elements of the organization and their responsibilities.

### 4.1.1	U.S. Department of Energy (DOE)

- Within the DOE, the responsibility for the NCSX Program resides in the Office of Fusion Energy Science (OFES) and an OFES NCSX Program Manager has been assigned.  The management responsibility, authority, and accountability for the day-to-day execution of the NCSX Project within the DOE are the responsibility of the Manager of the Chicago Operations Office (CH). CH has delegated major authorities and responsibilities for the NCSX Project to the Manager of the Princeton Area Office (PAO), who has designated a DOE NCSX Project Manager.

### 4.1.2	DOE Contractor Organizations

#### 4.1.2.1	Princeton Plasma Physics Laboratory (PPPL)

- PPPL has overall responsibility for NCSX project execution, reporting to DOE through the Laboratory Director. The NCSX Project is assigned to PPPL’s Advanced Projects Department. The Project Manager, the Deputy Project Manager for Engineering, the Engineering Manager, the Physics Head, and the Project Control Manager are PPPL positions.  Project support in the areas of Quality Assurance and Environment, Safety and Health are provided by PPPL. Major hardware procurements will be placed through PPPL’s procurement organization.

#### 4.1.2.2	Oak Ridge National Laboratory (ORNL)

- ORNL is a partner in the NCSX project with key management responsibilities. ORNL has management responsibility for the stellarator core (WBS 1). The position of Deputy Project Manager for Program is the senior NCSX project position at ORNL.  Within the ORNL organizational structure, the NCSX Project is managed within the Fusion Energy Division.  .

#### 4.1.2.3	Other Organizations

- All other participants (i.e., industrial or university organizations) are subcontractors to either PPPL or ORNL.

## 4.2	NCSX Management Team

- Key project positions and responsibilities are as follows:

### 4.2.1	Senior Laboratory Managers

#### 4.2.1.1	PPPL Director

- The PPPL Director has overall responsibility to DOE for the execution of the NCSX Project. He is supported by the Deputy Director.

#### 4.2.1.2	PPPL Advanced Projects Department Head

- The responsibility for NCSX is assigned to the PPPL Advanced Projects Department.  The PPPL Advanced Projects Department Head reports to the PPPL Director.

### 4.2.2	NCSX Project Management Team

#### 4.2.2.1	NCSX Project Manager

- The NCSX Project Manager is responsible for execution of the NCSX project, including technical, cost, schedule, project control, ES&H, and quality assurance aspects. He is the project’s primary point of contact with DOE and with the Program Advisory Committee. He reports to the PPPL Advanced Projects Department Head.

#### 4.2.2.2 	Deputy Project Manager for Program

The NCSX Deputy Project Manager for Program is an ORNL position. He supports the Project Manager especially on programmatic issues, and is the senior NCSX manager at ORNL.  He reports to the Project Manager.

#### 4.2.2.3	Deputy Project Manager for Engineering

- The NCSX Deputy Project Manager for Engineering is a PPPL position. He supports the Project Manager, especially on engineering issues. He is the project’s senior management representative in the PPPL engineering organization.  He reports to the Project Manager.

#### 4.2.2.4	NCSX Project Physics Head

- The NCSX Project Physics Head is responsible for the physics requirements and supporting physics analyses as necessary. He reports to the Project Manager.

#### 4.2.2.5	NCSX Project Engineering Manager

- The NCSX Project Engineering Manager is responsible for carrying out the NCSX engineering design and fabrication to meet project requirements. He reports to the Project Manager.

#### 4.2.2.6	WBS Managers

The project engineering work organization is structured according to the work breakdown structure (WBS). Each WBS Level 2 element has a WBS Manager, who is responsible for the execution of the work scope. The WBS managers report to the Project Engineering Manager.

#### 4.2.2.7	NCSX Project Control Manager

The Project Control Manager reports to the NCSX Project Manager and is responsible for all project control and administrative functions necessary to support NCSX Project activities.

The NCSX Project Control Manager’s support responsibilities include:

- Coordinating the development of project plans and administering the centralized Work Authorization system;

- Maintaining up-to-date NCSX cost and schedule baselines that are consistent with the technical baseline;

- Coordinating the preparation of statements of work, sole source justifications (as appropriate), the processing of requisitions, and tracking of procurements and subcontracts supporting the project;

- 	Establishing, maintaining, and monitoring project budgets and schedules to ensure consistency with project control milestones and funding;

- Operating the PPPL Project Control System (PCS) as the Project Control System for the NCSX Project.

- Assisting the Project Engineering Manager in administering the operation of the NCSX documentation, configuration management, requirements definition, and design description systems;

- Serving as the primary point-of-contact to the PPPL Business Operations Department; and

- 	Performing administrative functions such as space planning, facility maintenance coordination, travel approvals and vouchers, and overall personnel planning.

#### 4.2.2.8	Quality Assurance and Environment, Safety & Health (ES&H)

- A NCSX Quality Assurance Engineer and a NCSX Safety Engineer are assigned to support the NCSX Project Manager.  A brief description of their responsibilities follows:

Quality Assurance Engineer support responsibilities - The NCSX QA Engineer, with the support of the entire Quality Assurance Division, will assist the project in meeting quality assurance/control objectives. Support tasks include:

- Preparing a project QA plan;

- Assisting in the development of project procedures,  policies, and other plans, as requested by project management;

- Providing quality related services such as inspections and support of procurements; and

- Performing both compliance-based and performance-based audits of the project and its associated plans and procedures

Safety Engineer support responsibilities - The NCSX Safety Engineer will assist the project in meeting ES&H objectives. These include safe execution of the project and producing a facility that will be safe to operate. He will assist in implementing PPPL ES&H policies and procedures. The NCSX ES&H Engineer will prepare any required NEPA documentation and a Safety Assessment Document (SAD).

## 4.3	Program Advisory Committee

- Advice by the U.S. and world fusion community on the NCSX Project scientific and technical issues is being obtained through the NCSX Program Advisory Committee (PAC).  The NCSX PAC is composed of a broad spectrum of technical experts of the U.S. and world fusion community.  The PAC provides this advice to the PPPL Director.  It addresses key technical issues identified by the NCSX Project.  It meets periodically at the request of the PPPL Director.

# 5.0	WORK BREAKDOWN STRUCTURE (WBS)

- The WBS organizes the NCSX project work scope and provides the logical structure that will be used to control the project. The WBS is composed of a few levels as required for work definition and control.  By convention, the first digit in the WBS is designated "level 2,” the second "level 3,” etc. The Level 2 WBS matrix is provided in Table 5-1 below.  This WBS is expanded and more completely defined in a series of separately issued and approved set of WBS dictionaries.  The WBS Dictionary for each WBS element contains a brief description of the work scope for each element.  For completeness, these WBS dictionaries contain elements not in the initial Fabrication Project, but considered for potential later upgrades during the operations phases.

- NCSX Project Work Breakdown Structure

- Table 5-1

| - WBS | - Description - (WBS Level 2) |
| --- | --- |
| - 1 | - Stellarator Core Systems |
| - 2 | - Plasma Heating, Fueling, and Vacuum Systems |
| - 3 | - Diagnostic Systems |
| - 4 | - Power Systems Modifications |
| - 5 | - Central I&C Systems |
| - 6 | - Site and Facilities |
| - 7 | - Machine Assembly |
| - 8 | - Project Oversight and Support |
| - 9 | - Preparations for Operations |

# 6.0	RESOURCE PLAN

## 6.1	NCSX Costs

- As a Major Item of Equipment (MIE) the NCSX project will be funded primarily with Capital Equipment Funds.   As a MIE project, the cost objective is measured by the Total Estimated Cost (TEC) – this cost encompasses all the costs to design and fabricate NCSX, starting with Title I design and ending with completion of integrated testing activities within the defined MIE project scope.  In addition, manufacturing development activities and physics requirements and analyses in support of the design are included in the TEC. These TEC cost activities will be used to measure the performance of the NCSX Project against its technical, cost, and schedule baselines.  Section 2.2.3 previously identified the cost objective for this project.

- Other project activities occurring in parallel with design and fabrication scope of the MIE project include NCSX research preparation activities. These will be funded with by Operating (OPEX) funds.  These costs are not considered part of the overall cost objective outline in Section 2.2.3 of this PEP.

- In accordance with DOE guidance, the historical costs for pre-conceptual and conceptual design of NCSX through FY-2002 were funded via OPEX funds and are not part of the TEC costs to design and fabricate NCSX.

## 6.2	Funding Profiles

- Table 6-1 provides the NCSX funding profiles according to current project planning (October, 2001).  It is assumed that Budget Outlay (BO) will equal Budget Authority (BA) each fiscal year.

##### Table 6-1

##### Preliminary NCSX Funding Profiles for the Project Execution Phase

|  | - FY2003 | - FY2004 | - FY2005 | - FY2006 | - First Half of FY2007 | - Totals |
| --- | --- | --- | --- | --- | --- | --- |
| - NCSX Fabrication - Project | - $11.1M | - $16.0M | - $17.0M | - $17.0M | - $7.9M | - $69.0M |
| - Research Preparations | - $0.8M | - $0.8M | - $1.2M | - $1.6M | - $0.8M | - $ 5.2M |
| - TOTALS | - $11.9M | - $16.8M | - $18.2M | - $18.6M | - $8.7M | - $74.2M |

# 7.0	PROJECT BASELINES

- The initial NCSX Project configuration, schedule, and cost baselines will be developed in the conceptual design phase of the project.  Once these baselines are developed, the configuration, cost, and schedule targets are established for Title I planning.  However, in accordance with the DOE’s baseline management policies, the cost and schedule performance baselines will not be established until the completion of the Title I (Preliminary) design.  At that time, they will come under the configuration control processes that are outlined later in this PEP.

- The highest level baseline control document is the Project Expectations Summary/Statement of Work (PES/SOW).  This document serve as the high level agreement between the project and DOE to define the:

- Mission;

- Technical objectives;

- Cost target;

- Major milestones; and

- Project description.

## 7.1	Configuration Baseline

The configuration baseline is the configuration documentation formally designated at a specific time during the Project.  Configuration baselines, plus approved changes to those baselines, constitute the current configuration documentation.  Establishment of configuration baselines will follow the industry standard for systems engineering, EIA/IS-632 Systems Engineering.  There are three formally designated configuration baselines, namely the functional, allocated, and product baselines.

The functional baseline is the initially approved documentation describing the system’s functional, performance, and interface requirements and the verification required to demonstrate the achievement of those requirements.  The functional baseline is established when the system (top-level) specification, the General Requirements Document, is approved.

Lower level development or “design-to” specifications will be developed from requirements allocated from the system specification.  The allocated baseline is the initially approved documentation describing subsystem functional, performance, and interface requirements that are allocated for those of the system or higher level subsystem; interface requirements with interfacing subsystems; design constraints; derived requirements; and verification requirements and methods to demonstrate the achievement of those requirements and constraints.  Generally, there is an allocated baseline for each subsystem to be developed.  The allocated baseline is typically established late in preliminary design with the validation of the subsystem development specification.

The product baseline is the initially approved documentation describing all of the necessary functional, performance, and physical requirements of the subsystem; and the functional and physical requirements designated for production acceptance testing.  Product or “build to” specifications and engineering drawings are part of the product baseline.  Generally, there is a product baseline for each subsystem, component, and part.  The product baseline is typically established late in final design or early in the fabrication phase with the validation of the product specification and supporting documentation.

## 7.2	Cost and Schedule Baselines

The cost and schedule baselines are documented in the NCSX project resource-loaded schedule. The Primavera Project Planner (P3) commercial scheduling module will be the standard software used for the NCSX project. There will be a minimum of four levels of detail starting with the Level I or Project Summary Schedule.   This summary level schedule will identify significant DOE and project milestones and summary logic for the entire project.  The other three levels of schedule are as follows and provide increasingly greater level of detail:

- Level II or Intermediate Schedules – will show major milestones and key tasks summarized by WBS, including key interrelationships.

- Level III or Job Level Schedules – are the detailed schedules prepared by the job manager.  This schedule is established as part of the Work Authorization process and will span at least the current fiscal year.  Since this schedule is the basis for each approved job or task, it is the heart of the cost and schedule baseline.  These schedules will be resource loaded at the activity level and will form the basis for the NCSX Project Control System described in Section 10.0 of this PEP. Progress against established technical, cost, and schedule targets will be measured and evaluated monthly using the information contained in the Level III schedules.

The activity detail that provides basis for these resource loaded schedules will be documented in a separate Cost and Schedule Document.  These baselines will represent more refined versions of those presented at the time of the PVR and FY-2003 Project Validation.  Specific contingencies will be presented and detailed resource-loaded schedules will be available.  These schedules will clearly demonstrate the critical path activities, major milestones at both the summary and detailed levels. Level IV or Working Level Schedules – depending on the needs of the project, detailed working level schedules are prepared as needed.  As critical tasks occur (e.g., complex hardware procurement, fabrication and installation tasks, etc.), activities that are covered in the Level III job schedules may be broken down into additional detail to allow for coordination of work by the responsible manager.  Level IV schedules may also be developed by cognizant job managers to aid in the performance and control of their jobs.  This level of schedule detail is normally not controlled at the same rigor as higher level schedules, but efforts are made to ensure continuity to established project milestones and Level III schedules.

# 8.0	Control of Project Baselines

## 8.1	Configuration Management Approach

- Changes to the NCSX configuration, cost, and schedule baselines will be controlled using a disciplined, yet flexible configuration management approach.  This approach will ensure that the configuration, cost, and schedule baselines are controlled at the appropriate level for the respective stages of the Project and that changes to the baseline will be carefully considered and evaluated for impact before proceeding

## 8.2	Change Control Process

- The NCSX change control process ensures that changes to the NCSX design and requirements are properly identified, screened, evaluated, implemented, and documented. A formal procedure will be established prior to the beginning of Preliminary Design to implement the process of change classification and submittal of supporting documentation.

- Once an Engineering Change Proposal (ECP) has been prepared and the impacts fully documented, the ECP will come before a project Change Review Board (CRB) that is comprised of senior members of the NCSX management team. The NCSX Project Manager will chair the CRB. Other members of the CRB will be assigned as appropriate, but may include the following:

- NCSX Project Control Manager

- NCSX Engineering Manager

- NCSX Physics Head

- WBS Managers

- ES&H representative

- QA representative

- Other cognizant job managers impacted by the proposed change

- The chairperson shall have the ultimate authority to recommend changes for the final approval; other board members act solely as advisors.

- Once a proposed change is approved, the project will implement the change in a timely manner. An updated list of approved, disapproved, and pending changes will be maintained electronically by Project Engineering on the NCSX File Share System.

## 8.3	Change Control Levels

- Changes to the NCSX configuration, cost, or schedule baselines will be classified according to their impact on the project.  The change approval levels are established consistent with the technical, cost, and schedule risk and are intended to feed into the higher level DOE configuration change system.  Table 8-1 summarizes the change classification and criteria.

- Table 8-1

- NCSX Change Classification Matrix

| - Category | - Highest Level - Approval | - Criteria |
| --- | --- | --- |
| - A | - DOE | - Changes affecting the PES/SOE, namely - Changes to the mission; - Changes to the technical objectives; - Changes to the project cost target; - Changes to DOE milestones; and - Changes to the project description at the PES/SOW level - Changes requiring use of Contingency funds - Changes to the Project Execution Plan (PEP) - Changes with ES&H impacts significant enough to affect the approved NEPA documentation |
| - B | - NCSX Project Manager | -  Changes to the configuration, cost and schedule baselines not affecting the PES/SOW - Changes to the Acquisition Plan -  Changes to the lower level management plans (e.g., Systems Engineering Management Plan, Quality Assurance Plan, Document and Records Plan, etc.) |

# 9.0	Project Management and Control Systems

## 9.1	Project Management Systems Approach

- The NCSX Project Manager will ensure that all project activities are properly controlled using PPPL’s Project Control System (PCS).  This system will be used as a management aid in planning and executing the project work scope and evaluation of schedule and budget performance.  The status of progress and variance in the WBS elements will be reported monthly to the NCSX Project Manager.

- The NCSX Project Manager will work to ensure early detection of technical, schedule or cost problems through routine project meetings with the NCSX project team.  In addition to these routine meetings, periodic meetings attended by appropriate Project personnel will be held to report and discuss the Project overall status.  Technical, cost, and schedule problems will be brought to the attention of the DOE Project Manager as soon as they are identified.

## 9.2	Project Control System Overview

- The NCSX Project will use the existing PPPL Project Control System (PCS) as described in the PPPL Project Control System Description. This description describes the “graded approach” concept to be applied to PPPL projects and is available as a separate lab document.  This document was reviewed and approved by DOE in 1996.  The PPPL PCS satisfies the principles of project management and control systems outlined in this PEP and DOE Order 430.1 ("Life-cycle asset-management").  ORNL and other participants will utilize the PPPL PCS to ensure that the entire project cost and schedule performance is measured.  The PCS provides a centralized work authorization system that the project will use.

- The PCS is an integrated management control and reporting system that establishes the documentation, data requirements, information flow, and system disciplines necessary to operate and maintain a system for control of the NCSX Project work, costs, and schedules.  The overall objective of the PCS is to provide PPPL and DOE with timely and auditable cost and schedule performance information that can be used to monitor, control and manage Project progress.  To accomplish this objective, the PCS provides a formal process for:

- 	Organizing the project work scope via the WBS;

- 	Planning and estimating the work scope via the project resource loaded schedule;

- 	Authorizing work and forecasting resource requirements via the WAF;

- 	Controlling management reserve and authorized allocated contingency via the change control process;

- 	Monitoring progress relative to schedule status and completion estimates and reporting cost and schedule performance against established cost and schedule baselines using the Level III schedules ;

- 	Documenting approved changes to the performance measurement technical, cost, and schedule baselines via the change control process; and

- Analyzing variances to the cost and schedule baselines, including critical path analyses resulting from status results of the Level III schedules.

The key planning and measurement tool for the project is the Level III schedule, but the PPPL work authorization process forms the basis for development of these schedules. Through the work authorization process, details of work scope, schedule, budget, and responsibility will be integrated, documented, reviewed, and agreed to by both project management and the performing organization.  The cognizant job manager will be responsible and accountable for accomplishing the scope of the work, as defined, with established schedule and cost targets.  The vehicle for documenting and authorizing work is the Work Approval Form (WAF).  The WAF formally documents the work scope to be performed, establishes a schedule, provides a cost estimate, identifies a responsible person for accomplishing the work, and provides time phased cost and manpower profiles.

## 9.3	Cost and Schedule Reviews

Nominally the Project will schedule two Cost and Schedule reviews with DOE each fiscal year.  One review will be scheduled near the middle of the fiscal year during the period preceding the presentation of the Field Work Proposal and one near the end of the fiscal year.  At these meetings the project will report the status of the project in general and the cost variances that potentially impact the level of contingency in particular.  Information from progress in detailed planning will also be reported.  Based on these inputs the project will recommend to DOE changes to the Project Baseline.  This recommendation will be documented in the form of a formal change.

9.4	Reporting

- Quarterly project reports will be prepared for the DOE NCSX Project Manager. However, to foster and facilitate visibility into project status all monthly PCS status will be provided to the DOE NCSX Project Manager. Additionally, DOE-PG participation in monthly meetings as well as design reviews will be encouraged.

# 10.0	 Funds Management

## 10.1	Project Funding Mechanisms

- PPPL and ORNL will each be funded directly via DOE B&R line.  Participation of other organizations will be funded by either PPPL or ORNL through subcontracts.  The annual NCSX funding requirements will be updated each year by PPPL and ORNL through their respective DOE Field Work Proposal (FWP) processes. Transfer of funds from PPPL to ORNL or vice versa will be accomplished by Financial Plan transfer requests to DOE.    All project work and expenditure of project funds will be centrally authorized and controlled by the project office via the PCS.

## 10.2	Management Reserve Funds

- Within the NCSX Project annual funding authorization, management reserve is a funding allowance for uncertainties or problems in the current year’s work scope. At the beginning of each fiscal year, a separate management reserve account is funded by the NCSX Project Manager by not authorizing a small fraction of the work against the total year’s funding. Management reserve funds, whether held at PPPL or ORNL, are controlled by the NCSX Project Manager. As needs arise, the NCSX Project Manager will authorize disbursements of this management reserve to fund problem areas arising within the approved scope of work.

# 11.0	RISK MANAGEMENT

- The NCSX project will manage risks, where “risk” refers to factors within the project’s control that threaten project performance, namely:

- Technical risk- the possibility that the product might not meet requirements

- Cost risk- the possibility that the cost might exceed the target value.

- Schedule risk- the possibility that the project might take longer to complete than planned.

Control of environment, safety, and health hazards, while part of risk management in a broader sense, is covered in other sections.

- The project’s risk management approach, as defined here, has two main components:

- Risk as a criterion in decision-making.- Simply put, risk reduction is a consideration in decision-making in all phases of the project. For example, when selecting among design options, potential vendors, or processes, the risks associated with the various choices will be assessed and factored into the decision.

- Management of contingency - A contingency allowance is established at the beginning of the project to provide for unanticipated scope changes and increases in in-scope costs.  This contingency allowance is not included in the cost and schedule performance measurement baselines by which the project is measured and controlled, but is part of the approved cost baseline. It is a part of the project’s budget whose purpose is to reduce risk. The amount of contingency is established initially based on a risk assessment performed as part of the cost estimating process in preparation for the Conceptual Design Review. A formal risk-assessment methodology that considers technical, cost, and schedule risks at WBS Level 3 is applied, using a high-medium-low risk classification. This methodology is outlined in Annex I to this plan.  The initial project contingency level is approved by DOE.  During execution, contingency reductions are approved by the DOE NCSX Project Manager through the change control process. The Project Manager will maintain an up-to-date estimate of the remaining work scope and the cost to complete it, will assess the outstanding risks, and will strive to the keep the remaining contingency high enough to reduce the risks to an acceptable level. This will be a key feature of semi-annual project review meetings.

# 12.0	ACQUISITION STATEGY

## 12.1	Overview

- The key feature of the NCSX acquisition strategy and planning is the procurement of the critical components that comprise the stellarator core.   The stellarator core includes the modular coils, vacuum vessel, supplementary coil systems (e.g., TF and PF), and plasma facing components (PFCs).  The procured components will be assembled by Laboratory labor into the completed stellarator core assembly.

- Although the design of the stellarator core systems will be led by ORNL, all major procurements for all systems will be placed by the PPPL Procurement Department.

## 12.2	Stellarator Core Systems Procurement

- The Project has developed and is implementing the following acquisition strategy for the procurement of the NCSX stellarator core:

- Conduct an information meeting at PPPL on the NCSX project and our procurement plans.  An information meeting was held at PPPL in August, 2001, to explain NCSX and the scope and timing of our major procurements.  The Project solicited expressions of interest in the major procurements at the information meeting.

- Selected vendors to conduct manufacturing studies as part of the conceptual design. Following the information meeting, the Project placed fixed-price contracts with several vendors for manufacturing studies of the vacuum vessel and modular coils.  The deliverables include recommended manufacturing processes, an assessment of the feasibility and technical risks, recommended R&D activities to mitigate those risks, an estimate of the expected cost, and suggestions for alternate approaches.

- Select one or more vendors to carry out the R&D required for the design and fabrication of the vacuum vessel and modular coils.  The project design activities, including the industrial manufacturing studies, will identify the R&D required for the vacuum vessel and magnets.  Cost reimbursable contracts will be placed to carry out this R&D.

- Select the vendors for the full-scale prototype Cost reimbursable contracts will be placed with multiple vendors to construct full scale prototypes of a sector of the vacuum vessel and individual modular coils.  These prototypes will confirm the fabrication process and provide cost and schedule information that will provide adequate control of the risk associated with the full fabrication contracts.  The prototype fabrication will also provide input to fabrication vendor selection.

- Select vendors for the production units. The contract for the production units would be fixed-price.  The contract for the vacuum vessel and modular coil production units would be open to bidding for all vendors who had satisfactorily completed the full-scale prototype.  The fabrication of the TF and PF coils will also be through a fixed price contract.   The PFC’s, cryostat, and structure are not expected to offer significant challenges.  The plan is to procure each of these under a fixed price contract.

- Since the majority of the other systems will primarily be upgrades and/or modifications to existing PPPL systems and structures, it is anticipated that simple build-to-print of fixed price procurements based on firm specifications are feasible.

# DOCUMENT CONTROL SYSTEM

## 13.1	Overview

- A Document Control System (DCS), adapted from existing PPPL document and drawing control systems using hard copy and electronic media, will be developed to ensure the organized and consistent treatment and format of NCSX documents including procedures, plans, memos, drawings, calculations, requirements documents, design documents, and procurement documents.  This DCS will utilize a standardized document numbering system and a World Wide Web (WWW) based file server (NCSX File Share) system to help ensure rapid review, authorization, updating, and retrieval of documents.  Designated NCSX staff will maintain the NCSX File Share, with assistance from the PPPL Computer Systems Division.  The URL for the NCSX Web page is http://www.pppl.gov/ncsx and the NCSX File Share is located on that page.  Document identification and approval for NCSX documents is defined in the NCSX Document and Records Plan (DCRP). All participants are encouraged to use the project standards for documents of either the MAC or PC versions of Microsoft Word, Microsoft Excel, or Microsoft PowerPoint.

## Document and Records Plan

The NCSX Project has developed a separate Document and Records Plan (DRP) that identifies the official documents to be controlled on the project, including the document’s purpose, the review and approval cycle, format, naming convention, and records retention requirements.

## Project Completion Documentation

- As required by DOE, a Project Completion Report will be prepared and submitted to DOE/PG within six months of completion of the Project. This report will provide the following information:

- The actual schedule on which the project will have been completed;

- 	The actual total project costs;

- 	he technical performance of the systems at project completion; and

-  	Itemized changes in cost, schedule, and technical parameters as compared to the initial baseline.

# SYSTEMS ENGINEERING AND TECHNICAL MANAGEMENT

## 14.1	Systems Engineering

Project Engineering has responsibility for implementing a systems engineering program on NCSX.  The systems engineering program includes the development and allocation of requirements; system design and verification; risk management; value engineering; configuration management; interface management; data management; and technical reviews.  The systems engineering program is described in the Systems Engineering Management Plan (SEMP).

## 14.2	Quality Assurance

- The NCSX Project QA Plan (QAP) will demonstrate how the existing PPPL and ORNL-FED Quality Assurance Plans and implementing policies and procedures, in conjunction with additional NCSX specific plans, policies, and procedures will satisfy the requirements of the DOE Order on Quality Assurance, 414.1A, and provide an appropriate level of quality on the project.

## 14.3 	NEPA Documentation And Safety Assessment

- NEPA Documentation [currently believed to be a request for a Categorical Exclusion (CX) determination] will be prepared for DOE-PAO approval prior to the CDR. The Safety Assessment Document (SAD) will be prepared and approved by PPPL prior to the start of operations.

# 15.0	INTEGRATED SAFETY MANAGEMENT PLAN

- PPPL follows the institutional Integrated Safety Management Plan (ISM) that has been approved by DOE.  The NCSX Project intends to follow that ISM and to adopt this plan as its own for the conduct of the design, fabrication, and operation of NCSX.

- The Integrated Safety Management (ISM) at PPPL is comprised of:

- The governing policy that safety be integrated into work management and work practices at all levels.

- The distinct policies, programs, procedures, and cultural beliefs that PPPL has developed as the structure that PPPL workers utilize in fulfilling PPPL’s environmental, safety, and health responsibilities.

The NCSX project will incorporate ISM into its management approach as follows:

- By accepting responsibility for safety as a line management responsibility. The project manager is responsible for safe execution of the project.

- By following PPPL procedures for work planning (e.g., ENG-032, etc.), where applicable. These procedures incorporate the ISM core functions of folding safety into the work planning, establishing appropriate controls, operating within established parameters, feedback.  The “core functions” of ISM include the following 5 step process:

- Defining the scope of work;

- Analyzing the hazard;

- Developing and implement hazard controls;

- Performing the work within these controls; and

- Providing feedback and continuous improvement to this process.

Where project-specific procedures must be developed, ISM principles will be incorporated into them.

# 16.0	REVISIONS TO THE PROJECT EXECUTION PLAN

This plan, when adopted and approved following completion of the CDR, will remain in effect until the completion of the NCSX fabrication project.  An annual review of the NCSX Project Execution Plan will be conducted, jointly by the PPPL Advanced Projects Department Head, the NCSX Project Manager, and the NCSX Engineering Manager to determine possible recommendations for update and/or revision. Revision and/or changes to this document will require approval of all the original signers of this document or their successors.