NCSX

Systems Engineering Management Plan

NCSX-PLAN-SEMP-00_dH

February 25, 2003

Prepared by:

W. Reiersen, Engineering Manager

Concurrences:

R. Simmons, Systems Engineering			  	J. Malsbury, QA Manager

Support Manager

_____________________________  		_____________________________

B. Nelson, Stellarator Core Systems		L. Dudek, Ancillary Systems

Project Engineer					Project Engineer

_____________________________

E. Perry, Assembly Operations		Project Engineer

Approved by:

_____________________________

G.H Neilson, Project Manager

Record of Revisions

| Revision | Date | Description of Changes |
| --- | --- | --- |
| Draft D | 8/23/02 | Incorporated RJH comments, guidelines from industry standards, and incremental improvements |
| Draft E | 9/3/02 | Incorporated RTS comments |
| Draft F | 9/18/02 | Removed reference to Mgmt Web |
| Draft G1 | 2/14/03 | Incorporated comments |
| DRAFT H | 2/25/03 | Incorporated GHN, WTR, & RJH comments |

Table of Contents

1	INTRODUCTION	1

1.1	PURPOSE	1

1.2	SCOPE	2

1.3	Applicable documents	2

2	TECHNICAL PROGRAM PLANNING AND CONTROL	4

2.1	Project Organization and Decision Making	4

2.1.1	Systems Engineering and Project Management	4

2.1.2	Systems Integration Team	6

2.1.3	Decision Making Philosophy	7

2.2	Project Planning	7

2.2.1	NCSX Integrated Cost and Schedule Management	7

2.2.2	Work Planning	8

2.3	work authorization anD Performance Measurement	9

3	Systems Engineering Process	12

3.1	NCSX Fabrication Project Cycle	12

3.2	Requirements Analysis	15

3.2.1	Requirements Documentation Hierarchy	15

3.2.2	Specification Approach	17

3.3	Design Definition and Integration	18

3.4	RISK MANAGEMENT	18

3.5	System Build, Test, and Demonstration	19

3.5.1	System Build	19

3.5.2	System Test	20

3.5.3	Demonstrations	20

3.6	Configuration Management	21

3.6.1	Overview of the Configuration Management Program	21

3.6.2	Overview of Data Management Processes	25

3.7	INTERFACE CONTROL	26

3.8	design REVIEWS	27

4	Engineering Specialty Integration	29

4.1	RELIABILITY, AVAILABILITY, MAINTAINABILITY (RAM)	29

4.2	VALUE ENGINEERING	29

4.3	QUALITY ASSURANCE (QA)	30

4.4	PARTS, MATERIALS AND PROCESS STANDARDIZATION AND CONTROL	30

4.5	Manufacturability	31

4.6	CONSTRUCTability	31

4.7	TRAINING	31

4.7.1	Safety Training	31

4.7.2	Operations and Maintenance (O & M) Training	32

4.8	TECHNICAL PUBLICATIONS (O&M MANUALS, ETC.)	32

4.9	ES&H	32

Figure 2-1 NCSX Project Organization	6

Figure 2-2 Work Authorization Process	10

Figure 2-3 Cost Performance Reporting	11

Figure 3-1NCSX Project Cycle	13

Figure 3-2 Flow Down of Requirements	16

Table of Tables

Table 3-1 NCSX Specification Types	18

# INTRODUCTION

## PURPOSE

This document has been prepared for the National Compact Stellarator Experiment (NCSX) Project to describe the systems engineering process and management practices to be utilized by the NCSX Project in accomplishing its mission.

Systems engineering (SE) basically consists of three elements:

SE Management applies the systems engineering process to the development of the system design

Requirements and Architecture Definition defines the technical requirements, defines a structure (or architecture) for the system components, and allocates these requirements to the components of the architecture

System Integration and Verification integrates the components of the architecture at each level of the architecture and verifies that the requirements for those components are met

The NCSX Systems Engineering Management Plan (SEMP) has the following key features:

The NCSX Project will be executed by a fully integrated team, even though the participants may be geographically and institutionally distributed.  Work will be governed by project-wide plans and procedures.

Common databases will be established for documents and drawings to ensure that everyone is using the same information.

System requirements will be developed through an iterative process in which the overall objective is to develop an optimally balanced and robust design that meets cost and schedule objectives.

System requirements and design constraints will be allocated to subsystems and configuration items (CIs) through a hierarchy of specifications defined in a specification tree.  Requirements will be traceable and verifiable.  CIs represent the lowest level of control under configuration management and may be a single physical or functional item or collection of items that will satisfy a final end product or deliverable.

Design reviews will be conducted during the project cycle to identify deficiencies and allow correction in a timely manner.

Verification will be conducted at the CI, subsystem, and system levels to assure that the “as-built” design meets specifications.

## SCOPE

NCSX is a Major Item of Equipment (MIE). The NCSX MIE project formally begins with Title I (Preliminary) Design and ends at first plasma. This SEMP defines the processes, organization and procedures used by the NCSX MIE project to accomplish the systems engineering objectives.  This plan is divided into three major parts:

Technical Program Planning and Control

Systems Engineering Process

Engineering Specialty Integration

## Applicable documents

This SEMP draws on the documents listed below.  In general, the NCSX Project (including ORNL) will follow the existing PPPL plans and procedures.  In cases where the NCSX Project is implementing systems and procedures that are somewhat more rigorous than the existing PPPL plans and procedures, specific note will be made.  In no instances are the NCSX plans and procedures in conflict or a dilution of the existing PPPL plans and procedures.  Unless specifically modified or superceded by NCSX-specific plans and procedures, the NCSX Project is committed to following existing relevant DOE orders and PPPL plans, procedures, and standards.  NCSX-specific plansreferenced are the latest issues of the:

NCSX Documents

- Project Execution Plan (NCSX-PLAN-PEP)

- Work Breakdown Structure (WBS) Dictionary (NCSX-WBS)

- Quality Assurance Plan (NCSX-PLAN-QAP)

- Data Management Plan (NCSX-PLAN-DMP)

- Document and Records Plan (NCSX-PLAN-DOC)

- Configuration Management Plan (NCSX-PLAN-CMP)

- Interface Control Management Plan (NCSX-PLAN-ICMP)

- Test and Evaluation Plan (NCSX-PLAN-TEP)

- Reliability, Availability, and Maintainability Plan (NCSX-PLAN-RAM)

In addition, there are related NCSX-specific procedures that have been developed to expand on the requirements and processes outlined in several of the above plans.  These NCSX-specific procedures will also govern the systems engineering processes described in this SEMP.

# TECHNICAL PROGRAM PLANNING AND CONTROL

## Project Organization and Decision Making

### Systems Engineering and Project Management

A Work Breakdown Structure (WBS) has been defined for the NCSX Project.  A WBS is:

A product-oriented family tree composed of hardware, software, data, facilities, and services which result from systems engineering efforts during the development and production of system elements.  Displays and defines the product(s) to be developed or produced, and relates the elements of work to be accomplished to each other and to the end product.  Provides structure for guiding multi-disciplinary team assignment and cost tracking and control.

A broader discussion of the WBS, including the NCSX WBS and the definition of each WBS element, can be found in the NCSX Project Execution Plan (NCSX-PLAN-PEP) and the Work Breakdown Structure Dictionary (NCSX-WBS).  The NCSX team organizational structure has been aligned with the Work Breakdown Structure. The organizational structure within the NCSX Project is depicted inFigure 2-1.

Systems Engineering is integral to the NCSX management approach.  The Engineering Manager has overall responsibility for implementing the SE program on the NCSX Project.  The Systems Engineering Support Manager and the Design Integration Manager support the Engineering Manager in implementing the SE program.  In the line organization, four project engineers report to the Engineering Manager – the Stellarator Core Systems Project Engineer, the Ancillary Systems Project Engineer, the Assembly Operations Project Engineer, and the Operations Project Engineer.  WBS Managers in WBS 1 report to the Stellarator Core Systems Project Engineer.  WBS Managers in WBS 2-6 report to the Ancillary Systems Project Engineer.  WBS Managers in WBS 7 report to the Assembly Operations Project Engineer.  An Operations Project Engineer will be assigned prior to first plasma to conduct integrated systems testing, coordinate the development of operations and maintenance procedures, and assume other responsibilities related to preparation for operation

Systems engineering functions include:

Systems engineering management

Generation of requirements documentation

Conduct of design reviews

Configuration management and change control

Data management

Interface control

Reliability, Availability and Maintainability (RAM) program implementation

Integrated system test planning

Overall design integration

.

A broader discussion of NCSX Project Management, including the roles of DOE and PPPL and ORNL Management and the Integrated Project Team (IPT), can be found in the NCSX Project Execution Plan (NCSX-PLAN-PEP).  The NCSX Engineering Manager has been designated the Responsible Line Manager (RLM) for the NCSX Project by the PPPL Engineering Department Head.

Figure 2-1 NCSX Project Organization

### Systems Integration Team

To accomplish these functions, it is necessary to have broad and coordinated participation by project participants.  A Systems Integration Team (SIT) facilitatse this integration. The Project Manager or the Engineering Manager chairs the SIT, depending on the phase of the project.  Members will include the Project Manager, the Engineering Manager, the Project Control Manager, the Project Physics Manager, the Stellarator Core Systems Project Engineer, the Ancillary Systems Project Engineer, the Assembly Operations Project Engineer, and the Systems Engineering Support Manager.  Specialty disciplines, other WBS managers, and other project personnel will participate as needed to support the agenda topics.

The SIT will ensure that the project has an established a forum for discussion of systems engineering matters such as requirements interpretation, potential areas of risk, system level trade studies/analyses, coordination of processes, and resolution of issues.  Resolutions are worked outside the SIT by the responsible organizations and designated working groups formed as needed to address and resolve specific issues.  Results are reported back to the SIT. The SIT will facilitate obtaining decisions through line management that are best for the project as a whole.

The SIT will meet on a regularly scheduled basis with a frequency appropriate to the phase of the program and magnitude of system related activities in progress.  All standard agenda item status reports are by exception only, i.e., the focus is on problem areas needing attention by the SIT, not a review of schedule and usual business activities.

### Decision Making Philosophy

The decision-making philosophy used on the NCSX program is allowing decisions to be made at the lowest practical levels of line management with responsibility for all the affected participants.  If a situation arises where a higher approval authority is required to resolve conflicts, the NCSX Project Manager will be the review and approval authority.  The SIT provides the forum for resolution of unresolved integration issues.

## Project Planning

### NCSX Integrated Cost and Schedule Management

The NCSX Project is responsible for developing and maintaining an integrated cost and schedule management process.  This process is described in the Project Execution Plan (NCSX-PLAN-PEP).  NCSX will use the existing PPPL Project Control System (PCS) as described in the PPPL Project Control System Description.  Key features of this system include the following:

Work is organized through the establishment of a Work Breakdown Structure (WBS)

Work is planned and costs and schedules are estimated and integrated in a resource-loaded project schedule

Work is authorized with Work Approval Forms (WAFs) that document the work scope, schedule, resource requirements, and deliverables, and identify the job manager

Work is tracked by regularly comparing reported cost and schedule performance against the cost and schedule baselines as documented in the resource-loaded project schedule

WBS Managers develop detailed, resource-loaded schedules in collaboration with the Project Control Manager that include all the labor and procurements required to complete the required scope of work.  The detailed schedule defines the cost and schedule baselines and will be put under change control at the start of Preliminary Design.  The detailed schedule will be maintained in a Primavera Project Planning (P3) database.

### Work Planning

The basic element of the NCSX configuration is the Configuration Item (CI).  A CI may be established at the total system level, at the subsystem level, or at the component/assembly level, depending on complexity and risk consideration.  During the design phases of the project, the key work planning document for each NCSX CI is the Systems Engineering Master Logic (SEML).  A SEML will be developed for each phase of the project design (Preliminary Design and Final Design) by the cognizant WBS Manager in collaboration with the cognizant Project Engineer and Engineering Manager (or Systems Engineering Support Manager).  The SEML defines project expectations for the WBS Managers for each design phase of the project in the form of a checklist of activities and deliverables that need to be provided for a design review.  These activities and deliverables are addressed by WBS Managers in the development of the detailed schedules and completed prior to the next major design review.  The SEML will include all the applicable items from the PPPL Work Planning Procedure ENG-032 (as well as additional detail), but in a format specifically geared to the needs of the NCSX Project.   Although PPPL Procedure ENG-032, Work Planning Procedure, is not directly applicable to the design activities for NCSX, the concepts therein are indeed applicable.  Accordingly, WBS Managers shall, as part of the planning process consider the following:

- Necessary documentation (e.g., drawings, models, specifications, etc.) that are necessary to adequately document the design;

- Engineering controls (e.g., reviews, analyses, calculations, etc) that are necessary to assure the design meets requirements; and

- Safety controls and procedures (e.g., NEPA documentation, procedures, testing etc.) that are necessary to ensure the safety of the environment, the equipment, personnel, and the public during the implementation of the design.

If desired by the responsible Project Engineer or RLM, the actual Work Planning (WP) form may be used as a check list for planning his work during the design phase.

For any on-site or off-site work involving field work, fabrication, and physical changes to facilities, control computing, the Work Planning (WP) Form specified in ENG-032 shall govern all work planning.  This includes any fabrication of components and test stands/equipment during design for R&D activities and for any design work entailing modifications to modifications to an existing system and/or facility.  As specified in ENG-032, the NCSX RLM has the authority to modify or delete the requirements of a WP.

## work authorization anD Performance Measurement

Figure 2-2 illustrates the work authorization process, starting with the SEML guidelines and completing with a series of planned, resource-loaded and authorized jobs.  The Work Authorization Form (WAF) is the heart of this work planning and authorization process.

Using the SEML guidelines, WBS Managers submit job estimates that include the work scope, schedule, resource requirements, and deliverables.  Each job maps cleanly into activities in the detailed schedule.  Resource requests will be consistent with the cost estimates reflected in the detailed schedule.  Job estimates will be made at the beginning of each fiscal year to cover all the work to be accomplished in that fiscal year.

The Project Control Manager will enter the job estimate into the P3 database and generate a Work Authorization Form (WAF).  Work will be authorized in advance of the scheduled start date, but not necessarily at the beginning of each fiscal year.  Once the WAF is approved, the job manager is authorized to start work unless the job entails modifications to an existing system and/or facility, in which case it is also necessary to generate an approved Work Planning Form (WP) as required by PPPL Procedure ENG-032.  Work Planning Forms are not formally required for design-only activities.  However, applicable elements of the Work Planning Form will be addressed in the SEML development and subsequently, in job planning.

Monthly status meetings will be held to review cost and schedule performance. The process for generating cost performance reports is illustrated inFigure 2-3.

Figure 2-2 Work Authorization Process

Figure 2-3 Cost Performance Reporting

# Systems Engineering Process

The systems engineering process is a comprehensive and iterative problem solving process that is designed to transform validated user requirements and project objectives into a functional system that optimally meets the mission requirements. At a top level, this process can be considered as consisting of an iterative flow of effort.  The requirements analysis efforts define the problem and the success criteria for a system that can address the problem.  The development of alternatives, the selection of a balanced solution, and the description of the solution as a design package is accomplished via design definition and systems analysis and control.

## NCSX Fabrication Project Cycle

The physical and functional description of the CIs comprises the “configuration” of the NCSX Project.  At selected points in the NCSX fabrication project, the current design configuration, including fabrication and testing define the technical baseline.  As described in greater detail in NCSX Configuration Management Plan (NCSX-PLAN-CMP) and summarized Section 3.2 that follows, the NCSX Project technical baseline is defined by a series of specifications and computer aided design (CAD) models and drawings.

Technical aspects of the project cycle for the NCSX Project are illustrated in Figure 3-1.  .  This chart depicts the various DOE Critical Decision milestones (CD-0 through CD-4) and the major systems engineering processes and deliverables expected at each stage of the project.  The DOE Critical Decision milestones are outlined in DOE O 413.3 Program and Project Management for the Acquisition of Capital Assets.  Inherent in the completion of the CD milestones as well as project design reviews is the attention and priority given to safety and quality as underpinnings of the successful evolution of the design and subsequent assembly, installation and testing.  The NCSX Project will adhere to the PPPL ISM processes in the PPPL ISM Document and the PPPL Quality Assurance Program as outlined in the NCSX Quality Assurance Plan (NCSX-PLAN-QAP).

Figure 3-1NCSX Project Cycle

As indicated in the NCSX Project Execution Plan (NCSX-PLAN-PEP), the project has evolved from the Pre-Conceptual Design phase in which the mission need and requirements were explored and defined.  In this phase, numerous design alternatives were explored, including a wide range of plasma and coil configurations and site options.  In March 2001, the NCSX Project successfully conducted a Physics Validation Review (PVR), based on a 3-period quasi-axisymmetric plasma with the external transform generated by a set of modular coils.  The proposed site was the test cell formerly occupied by the PLT and PBX-M experiments.

During the subsequent period of Conceptual Design, the plasma, stellarator core, ancillary systems, and facility concepts were refined.  Manufacturing studies of critical, developmental components were conducted by industry.  Mission requirements were translated into a formal system specification, the General Requirements Document (GRD).  Detailed, bottoms-up cost and schedule estimates were generated with substantial input from industry.  A procurement strategy was developed.  Major risks were identified and risk mitigation plans developed.  A successful Conceptual Design Review (CDR) was conducted at PPPL in May 2002.  The Project is presently addressing the recommendations of the CDR Review Committee and is awaiting Approval of the Baseline Range (CD-1), required to start Preliminary Design. A formal review of the system specification, i.e. the General Requirements Document (GRD), is planned prior to the start of Preliminary Design.  From a configuration management perspective, the approved GRD and the associated CAD model that represents a system concept that satisfies the performance requirements in the GRD will constitute the initial technical baseline for start of preliminary design.

During Preliminary Design, functions and more detailed requirements are successively allocated to subsystems and configuration items (CIs).  A series of performance specifications are generated down to the CI level.  In parallel with the development of “Design-to” specifications, subsystem and CI concepts are developed and refined.  Analyses and R&D required to establish the feasibility of the design concepts are completed.  Verification plans for testing during assembly and installation are developed.  Interfaces are identified and plans developed at the start of Preliminary Design to define the interfaces.  Interface specifications are documented in Interface Control Documents (ICDs) during Preliminary Design.  Following a successful CI Preliminary Design Review (PDR), the “Design-to” specifications (including interface specifications) are placed under change control.  Following successful completion of the PDR, the technical baseline and self-consistent cost and schedule baseline are also updated to reflect the “design-to” specifications, verification plans, and associated design concepts, and the SEML updated to reflect the items necessary to be completed during final design.

During Final Design, the designs of the hardware and software required to satisfy the “Design-to” specifications are completed.  Analyses of critical design basis calculations performed earlier are checked and any additonal analysis needed to confirm the adequacy of the detailed designs is performed and checked.  “Build-to” documentation is developed and placed under change control following a successful Final Design review (FDR). The technical, cost, and schedule baselines are also updated completion of  the FDR.   All of the major procurements on NCSX are expected to be “built to print”, with only minor engineering being done at the supplier to enhance manufacturability.

Once construction is authorized, work on the assembly, installation, and testing can proceed with due diligence to safety and quality. Test readiness reviews will be conducted in advance of actual testing to ensure that all of the elements required for testing are in place, especially provisions to ensure safety.  The final phase of integration and verification activities is integrated systems testing.  Integrated systems testing will culminate in the production of the first plasma, which is a demonstration that the device and facility are operating at the specified level of performance.

Based on experience with previous fusion experiments built at PPPL, it is anticipated that NCSX will be classified as a high hazard facility per ES&HD 5008 Section 11.  Accordingly, a Safety Assessment Document (SAD) will be prepared and a Safety Certificate be issued by the PPPL ES&H Executive Board prior to the start of operations. An Activity Certification Committee (ACC) will be formed during the FAIT phase to provide an independent safety review of plans and readiness for integrated systems testing and first plasma.  The ACC will advise the PPPL ES&H Executive Board with respect to issuance of the Safety Certificate.

Prior to the start of operations, an Operational Readiness Assessment (ORA) will be conducted by DOE.  NCSX intends to emulate the highly successful NSTX model where the ORA was conducted in concert with the activities of the ACC, which proved to be a highly effective model.

## Requirements Analysis

### Requirements Documentation Hierarchy

Requirements for the NCSX Project are captured in a hierarchy of requirements documents, which begin with the system (top-level) requirements in the General Requirements Document (GRD).  The GRD represents a complete set of performance requirements and constraints at the system/project level and initial subsystem allocations.  The top-level system requirements in the GRD flow down to a set of “Design-to” requirements at the subsystem (Systems Requirements Documents/SRDs) level which in turn, flow down to more detailed “Design-to” requirements at the configuration item (CI) level.  The “Design-to” requirements then flow down to “Build-to” requirements that get translated into products and services by the builders.  This flow down of requirements is illustrated inFigure 2-1.

Figure 3-2 Flow Down of Requirements

Cognizant WBS Managers are responsible for the preparation and maintenance of specifications below the GRD. WBS Managers shall ensure that all applicable system level requirements allocated to their system elements are properly treated in lower level specifications.  Traceability of requirements shall be provided.

A specification tree illustrates the hierarchy of requirements documents and is an important planning tool that will be developed early in Preliminary Design.  The specification tree defines the set of specifications required to execute the fabrication project and the order in which they need to be approved and placed under change control.  Development of the specification tree must be coupled with the development of an acquisition strategy, because the technical specifications provide the basis for the acquisitions and should be structured accordingly.

As the requirements of the GRD are primarily reflected in the form of functional or performance requirements, additional requirements in the form of design constraints must be developed to completely define the system requirements.  Design constraints are a class of non-functionally derived requirements.  Requirements that do not have to be derived and cannot be modified or dropped as a result of a tradeoff study can generally be considered a constraint.  Typical design constraint categories include environmental conditions, transportability, interchangeability, workmanship, etc. The Engineering Manager is responsible for defining an overall project approach to the implementation of a design constraints methodology and for developing a complete set of system level design constraints for incorporation into the system specification.  WBS Managers are responsible for properly treating system level design constraints allocated to their subsystem and for any additional constraint definition that may be required.

### Specification Approach

Beginning with the GRD, the NCSX Project shall develop and implement a project-specific approach for developing requirement specifications that meets that requirements set forth in the PPPL ENG-006 "Review and Approval of Specifications & Statements of Work".  As indicated previously, there are only two categories of specifications; “design to” and “build to” specifications.  “Design to” specifications provide the design constraints to meet performance requirements flowed down from higher level specifications where as “build to” specifications provide specific assembly and fabrication details and constraints.  A graded approach will be applied where new and complex systems and components will require extensive and detailed specifications whereas catalogue items such a some electronic components will not require as detailed specifications. Two key features of this approach are:

Tailored formats. Several specification types have been identified for NCSX and are listed in Table 3-1. Each type of specifications will have a format that is tailored to the purpose of the specification.

Specification tree. A spec tree illustrates the hierarchy of requirements documents and is an important identification and planning tool that will be developed early in Preliminary Design for each specification required by the NCSX Project.  WBS Managers shall provide specification tree inputs to the Engineering Manager for their respective system elements.  For each specification, the specification tree will identify the scope, specification type, and the individual responsible for its development.

| SPECIFICATION | PURPOSE |
| --- | --- |
| SYSTEM | • Establishes the requirements for the system/project and characteristics of lower level WBS elements. The GRD will be the system specification. |
| DEVELOPMENT (“Design to”) | • Allocation of development requirements to the subsystem and CI from the GRD specification (e.g., to SRDs and then to lower level CI’s) • Defines the methods used to verify the requirements have been met |
| PRODUCT (“Build to”) | • Defines product acceptance requirements |
| PROCESS | • Prepared for manufacturing techniques that require a specific procedure in order that a satisfactory result may be achieved. |
| MATERIALS | • Prepared to control the development of a material. |

Table 3-1 NCSX Specification Types

NCSX is planning to re-use much equipment previously used on other PPPL experiments, including vacuum pumping equipment, neutral beam injection systems, and power supplies.  Performance requirements will be generated that the legacy equipment must satisfy.  Verification that the legacy equipment satisfies the performance requirements will be provided.  Product specifications and detailed component drawings for legacy equipment will not be developed as part of the NCSX Project.  However, specific attention will be paid to defining the interfaces of and interlocks between new NCSX systems to legacy equipment.

## Design Definition and Integration

Design definition is that point in the systems engineering process where a design concept is created to satisfy a given set of requirements.  This step is performed iteratively with the requirements analysis process, resulting in increasingly more detailed design concepts as the requirements grow more detailed and become allocated to lower levels within the system.  Typically, a set of alternative concepts will be developed and each in turn evaluated to develop the most cost-effective solution based on specific evaluation criteria.  This process will culminate in a detailed design of the entire NCSX system including all subsystem elements.

## RISK MANAGEMENT

Risk management is a process to assure that the system design is feasible and can be built in a timely and cost effective manner.  For purposes of the risk management process, risk is defined as the probability of an undesirable event occurring multiplied by the severity of the event.  Unmitigated risk could have an adverse effect on program cost and schedule.  Responsibility for risk management lies with NCSX line management.  The Systems Integration Team (SIT) will facilitate identifying  areas of risk, coordinating the development of risk mitigation plans, and monitoring performance against these plans.

Minimization and mitigation of risk on the NCSX Project will be provided through early management oversight allowing the application of additional resources, development of alternative technologies, and appropriate contingency allowances.    It should be noted that the NCSX Project has already implemented a proactive approach to risk management.  Early in the conceptual design phase appropriate contingency levels were assigned based on the state of the design and perceived risks and a series of manufacturing studies were conducted to mitigate manufacturing risk in the critical path components, including the modular coils and vacuum vessel.

## System Build, Test, and Demonstration

### System Build

The system build process begins with design definition and continues until the system is constructed and is ready for integrated systems testing.  As part of the systems engineering process, the build of the system is an extension of the requirements analysis and design tasks for all subsystems and components.

The stellarator core and interfacing components will be defined in 3D CAD models generated in Pro/Engineer to facilitate the building of a unified assembly.  The Stellarator Core Systems Project Engineer is responsible for the development of the integrated model of the stellarator core.  A Pro/Engineer model of the facility shall also be generated to define space envelopes for locating ancillary equipment and routing of cables and piping.  All 3D models and 2D drawings shall reside in a common database.  The Design Integration Manager is responsible for developing a model of the NCSX facility, which includes the integrated model of the stellarator core.

NCSX will be constructed at PPPL using existing procedures and practices that are familiar to PPPL technicians.  Hazard controls include: work planning; installation, test, and operating procedures; design reviews; job hazard analyses; pre- and post-job briefings; protective equipment; and worker training. The Field Period Assembly (WBS 18) Manager is responsible for coordinating all fabrication and assembly activities in the TFTR Test Cell.  The Assembly Operations Project Engineer is responsible for coordinating all assembly activities in the NCSX Test Cell and Basement.  Coordination of assembly activities outside the TFTR Test Cell and NCSX Test Cell and Basement are the responsibility of the cognizant WBS Manager.

### System Test

System verification is accomplished through a combination of inspection, demonstration, test, and analysis activities.  The Engineering Manager will establish a cost effective approach to verifying system performance.  Emphasis will be placed on the reduction of overall verification costs and timelines. A verification compliance matrix will be developed and maintained that identifies the verification method and status of each system requirement in order to ensure that system performance requirements, as documented in the GRD, are verified and maintenance and operations procedures are validated.

As some system requirements will require verification via test methods, an integrated test planning approach will be utilized.  System level tests will include activities to verify that subsystems interface properly and individual performance requirements are met, as well as verifying full system operation.  A Test and Evaluation Plan (TEP) will be developed and maintained by Project Engineering to establish how the integrated system testing will be performed and managed. The TEP will include an overview and schedule of the integrated system test program and the purpose, scope, and objective of each system test; test configurations; and test responsibilities.  WBS Managers are responsible for developing plans for subsystem testing.

Early development of test plans is essential because it may drive when certain capabilities and interfaces are required to be operational.    The TEP will be developed during Preliminary Design to provide the WBS Managers knowledge as to what their system test responsibilities are and within what time frame they occur.  This will enable the WBS Managers to do the planning necessary to support system testing.  Initial subsystem test plans will also be developed during Preliminary Design. In support of testing activities, Project Engineering will conduct test readiness reviews (TRRs), track test activities, and resolve test issues.

### Demonstrations

Demonstration or prototyping of critical technologies and development hardware is a cost effective method of reducing risk and will be monitored and controlled through the Risk Management process described in Section 3.3.  Demonstrations provide assurance that the system under development is feasible.  Prototypes will be developed and evaluated to ensure that the critical components of the system can be manufactured to meet performance requirements.

## Configuration Management

### Overview of the Configuration Management Program

The physical and functional description of the components, systems, and software/firmware comprise the “configuration” of the NCSX Project.  The NCSX project (and details of its design configuration) is progressively described in greater detail as it proceeds through the design process.  At the end of the fabrication project, as the NCSX enters its operational phase, the actual physical and functional configuration is documented.  It is not deemed necessary for all drawings to be updated to reflect the as-built condition.  It is considered acceptable to call out on affected drawings the approved NCR that documents each nonconformance..  Configuration Management (CM) is an integrated program that ensures that the configuration is identified and properly document and that changes to the configuration are controlled during this life cycle.  The Engineering Manager is responsible for implementing an effective CM program.  The Systems Engineering Support Manager will assist in developing the CM program and will be responsible for its administration.

The CM program is described in the NCSX Configuration Management Plan (NCSX-PLAN-CMP).  The key feature of the configuration management program is careful identification of the Configuration Items (CIs).  Depending on the complexity and risk considerations, CIs may be established at the system, subsystem, or component/assembly level.  The CMP will be reviewed and approved at the start of preliminary design.

As outlined in the CMP, there are three project baselines – the technical, cost, and schedule baselines.  These three baselines are fully integrated since they are derived from the same configuration.  The technical baseline starts with the definition of the system requirements and the system concept that is developed to satisfy those requirements.  Over time, the system concept will evolve and more detail will be added in each subsystem and configuration item.  An effective CM program must allow for design evolution without compromising cost and schedule objectives.

Figure 3-3 illustrates the process for managing the development and changing of project baselines.  The technical baseline is defined by the General Requirements Document (GRD), the system concept defined by the Pro/Engineer model of the stellarator core, and supporting technical documentation.  During Preliminary Design and Final Design, subsystem and configuration item designs will evolve as changes are made and more detail is added.  This process is natural and must be encouraged.  However, there are two risks that the project needs to manage:

Proposed changes may compromise cost and schedule objectives

Proposed changes may compromise the ability of interfacing systems to meet their technical, cost, and schedule objectives.

WBS Managers have the responsibility to identify changes and the impact of the proposed change on cost, schedule, or interfacing systems.  For significant changes, the WBS Managers are obligated to initiate Engineering Change Proposals (ECPs) for updating the project cost, schedule, and technical baselines prior to proceeding with the design.  The project will also require WBS Managers to periodically reconcile the cost and schedule baselines with proposed design changes that have occurred since the project baselines were last changed.  These periodic updates will typically be coordinated with the semi-annual DOE cost and schedule reviews and formal design reviews (such as the Preliminary Design Review and Final Design Review).  “Omnibus” ECPs will be required for these periodic updates to formally update the project baselines and proceed with the design.  The ECPs for these periodic updates will also reflect the actual cost and schedule performance.  An electronic system for preparing and processing ECPs is available via a link from the NCSX Engineering Web page < http://www.pppl.gov/me/NCSX_Engineering/ >.

Figure 3-3Updating Project Baselines

The normal adjudicating body for each ECP is the Change Control Board (CCB).  The CCB is comprised of senior members of the NCSX management team and is chaired by the Project Manager.  Change classifications and approval thresholds for change control are defined in the NCSX Project Execution Plan (NCSX-PLAN-PEP) consistent with DOE Order 413.3.  In instances where the approval authority is in DOE, the Project Manager shall forward the ECP to DOE with a recommendation to approve.

In some instances (e.g., when a pending critical procurement needs to reflect the proposed change, if field activities may be delayed by the normal ECP process involving full reviews and the CCB, or if the proposed change is primarily editorial or minor in scope), a process for “expedited” ECPs may be appropriate.  The NCSX Engineering Manager, in consultation with the NCSX Project Manager, may determine to implement an “expedited” ECP process in which the NCSX Engineering Manager may review and approve the ECP with only an abbreviated review.  However, any “expedited” ECPs will be reviewed “after-the-fact” by the full CCB to ensure that major errors and/or omissions were not made.

### Overview of Data Management Processes

Data management is provided through defined procedures and the document and drawing control systems.  The Data Management Plan (NCSX-PLAN-DMP) describes the processes to be used for document and drawing control.  The DMP will be reviewed and approved at the start of preliminary design.

The majority of project documents will be accessible electronically. Electronic Data will be stored in seven sites and physical data not readily convertible to electronic format will be stored in hardcopy format in the PPPL Operations Center.  The purpose and general content contained in each storage site is summarized below:

- Electronic Sites

  - Project Web – contains general project information, external design review data, physics meeting records, PAC meeting records, publications, and the project directory;

  - Procurement Web – contains all documentation required for potential suppliers to develop proposals;

  - Manufacturing Web – contains all project documentation required for suppliers to execute their scope of work;

  - Engineering Web – contains all other project documentation including cost and schedule information, design criteria, internal design review data, engineering and project meeting minutes, memoranda, analysis reports, controlled documents not otherwise posted, and work plans;

  - Pro/INTRALINK Database – contains CAD drawings and models for project use;

  - Project FTP Server – contains large Data Files primarily used in physics analyses; and

  - Supplier FTP Server – contains CAD drawings and models for use by suppliers.

- PPPL Operations Center – contains that information not readily convertible to an electronic format (e.g., hardcopy supplier contract deliverables, hardcopy field activity documentation, etc.)

A more detailed table listing the seven sites and their customers, custodians, document types, and access restrictions is provided in the NCSX Data Management Plan (NCSX-PLAN-DMP).

The NCSX Document and Records Plan (NCSX-PLAN-DOC) identifies the controlled documents on the NCSX Project.  The DOC will be reviewed and approved at the start of preliminary design and defines the following:

Identifiers of all project documents, including controlled documents and memoranda

Approval authority for controlled documents

Location for storage and retrieval

Records retention requirements

## INTERFACE CONTROL

Interface Control is that part of system design integration that generates and administers technical agreements between two or more activities, when the products must assemble and/or function together. An interface may define a written agreement between WBS systems or define a physical boundary, mating surface geometry or attachment details that exist between two adjoining WBS components.  There are two types of interfaces. A primary interface exists between two separately deliverable items (referred to as Configuration Items/CIs in systems engineering terms) when the mutual boundary area is not controlled by a single developmental or “design to” specification, when the interface is with systems outside the project (external interfaces identified in the General Requirements Document/GRD), or when, at the discretion of the cognizant Project Engineer, the interface is determined to be critical to the performance of the NCSX program.  Secondary interfaces represent technical agreements entirely within a single WBS element or between two WBS elements, but with the same WBS Manager.  Only primary interfaces will come under the configuration control program described in Section 3.6.

Project Engineering is responsible for establishing the processes and procedures for effecting interface control.  The Interface Control Management Plan (NCSX-PLAN-ICMP) will describe the processes to be used in managing interfaces.  The ICMP will be reviewed and approved at the start of preliminary design.  The Systems Engineering Support Manager will administer the interface control management program.  WBS Managers shall jointly develop scope sheet agreements at the start of Preliminary Design that identify what interfaces exist and document work plans to finalize the interface definitions.  Working groups shall be established to support the development, modification, and maintenance of selected interfaces as required.  Interface control documents (ICDs) will be established to document both functional and physical interface characteristics.  ICDs should be in place by the time of the Preliminary Design Review (the earliest PDR among the affected WBS elements) in order to facilitate completion of Final Design.

## design REVIEWS

On NCSX, both external and internal design reviews are planned.  External design reviews are determined by DOE and conducted to support DOE Critical Decisions.  Internal design reviews are conducted to assess the technical adequacy of the configuration baseline as it is developed, consistent with ENG-033 Design Verification and P-010 Design Reviews.  These reviews verify the proper development, establishment, and control of the configuration baseline.  They are used to verify conformance with requirements at the system, subsystem, and configuration item (CI) levels.  They also serve as an appropriate point to update project technical, cost, and schedule baselines.

The review process is continual throughout design, fabrication, and assembly.  The Conceptual Design review was conducted in May 2002.  There will be a series of specification validations and design reviews during Preliminary and Final Design as the design evolves from the system level to the CI level.  Test readiness reviews will be conducted during the Fabrication, Assembly, Installation, and Test (FAIT) phase.  The final review, which follows completion of integrated systems testing, will be the Operations Readiness Assessment (ORA).

Design reviews will be conducted at the appropriate time for all systems and components.  The planning, preparation, and conduct of each design review are the responsibility of the cognizant WBS Manager for the system element(s) under review and by the responsible Project Engineer for system-level reviews.

The schedule for design reviews for major systems or critical components will be determined by the Engineering Manager (or Systems Engineering Support Manager) in consultation with the responsible Project Engineer and WBS Managers.  Responsibility for scheduling design reviews for other systems and components will be delegated to the responsible Project Engineer.  .  Before a design review is scheduled, the responsible official (Project Engineer/Systems Engineering Support Manager) or responsible Project Engineer shall confirm that the required documentation specified in the SEML is completed (e.g., drawings promoted to the appropriate level, specifications approved, analyses completed and checked, etc.).

Successful completion of a design review requires that the design has matured to a level appropriate for the review and that all data necessary to properly evaluate that design is complete, including successful resolution of the design review CHITs.  To facilitate this goal, a systems engineering master logic (SEML) approach will be implemented for the design phases of the project.  The SEML will identify entry requirements that indicate readiness for a review and exit requirements that define review closeout. Success criteria are then established to provide a means to assess satisfaction of the entry and exit requirements.  These data items establish project requirements for readiness for a design review.  The SEML will be documented during each phase of the design by the cognizant WBS Manager in conjunction with the cognizant Project Engineer and Engineering Manager (or Systems Engineering Support Manager) so that the required supporting activities can be properly planned.

# Engineering Specialty Integration

## RELIABILITY, AVAILABILITY, MAINTAINABILITY (RAM)

The RAM program to be implemented on NCSX is defined in the NCSX RAM Plan (NCSX-PLAN-RAM).  A draft RAM Plan will be provided for review at the Preliminary Design Review  (PDR).  The RAM Plan will be reviewed and approved as part of the Final Design Review (FDR).  The RAM program will utilize a graded approach that is based on consideration of risk.  WBS Managers are responsible for optimizing designs for reliability and maintainability through systematic evaluation of design options, and for performing failure modes, effects and criticality analysis (FMECAs) for RAM design improvement and verification.

## VALUE ENGINEERING

Value Engineering (VE) is the systematic application of recognized techniques by a multi-disciplinary team to identify the function of a product or service, establish a worth for that function, generate alternatives through the use of creative thinking, and provide the needed functions to accomplish the original purpose of the project at the lowest life-cycle cost without sacrificing safety, necessary quality, and or environmental attributes of the project.  The NCSX Project will apply VE methodologies following a graded approach to the formal elements of VE.

On NCSX, value engineering methods have already been applied during Conceptual Design.  Specific examples include:

Coil topology studies conducted by a multi-disciplinary team of physicists and engineers that led to the selection of modular coils for providing helical fields

Manufacturing studies of the vacuum vessel and modular coils conducted by manufacturing engineers in industry (and supported by laboratory design engineers) that identified and evaluated a variety of fabrication options

Project Engineering and the individual WBS Managers will review each subsystem during Preliminary Design and determine what design areas would likely benefit from additional value engineering.  These value engineering studies would be completed prior to the subsystem PDR.

## QUALITY ASSURANCE (QA)

The NCSX QA program provides a framework that defines quality in terms of goals and expectations and establishes processes to fully integrate the quality function into all phases of the program by providing continual, independent, and disciplined reviews/audits of all processes, products, and services.  The Quality Assurance Plan (NCSX-PLAN-QAP) establishes the requirements for measuring and controlling work and for providing management and independent self-assessments to find, report, and solve problems.  The plan identifies implementing policies, plans, and procedures for the NCSX QA program.  The QAP has been reviewed and approved.

While performing their assigned duties and responsibilities, workers, line management, and immediate supervisors are assigned immediate responsibility for the quality of the project's efforts.  Personnel independent of the activities being performed are assigned the responsibility of verifying and validating that the project's efforts are commensurate with project standards.  All personnel have a responsibility to identify quality problems and to recommend solutions.

## PARTS, MATERIALS AND PROCESS STANDARDIZATION AND CONTROL

The purpose of the NCSX parts standardization program is to reduce the number of part types, improve system maintainability, and optimize logistics support by standardizing part types and selecting parts with two or more reliable sources wherever practical.  Project Engineering will maintain a Master Parts List of NCSX parts and materials.

In addition to the Master Parts List, the NCSX Project will develop a Vacuum Materials List.  A Vacuum Materials Review Committee will be established.  This committee will establish the suitability of all parts and materials to be used in the plasma vacuum.

These lists will be developed for review by the time of the PDR and be finalized by the FDR.

## Manufacturability

A Manufacturing, Inspection, and Test Plan (MITP) shall be produced for each configuration item.  This plan will be the controlling document by which the manufacturability of each configuration item will be evaluated.  The plan shall include a process flow diagram showing each of the major manufacturing operations.  The plan will identify any special process procedures required to produce the configuration item to be fabricated.  Inspection and test plans shall also be described.  A draft MITP will be provided for review at the Preliminary Design Review  (PDR).  The MITP will be reviewed and approved as part of the Final Design Review (FDR).  Cognizant WBS managers are responsible for the development of MITPs for each of their configuration items.  The MITPs along with product specifications provide the technical basis for the procurement of configuration items.

## CONSTRUCTability

The Assembly Operations Project Engineer (AOPE) is responsible for coordinating all assembly activities in the NCSX Test Cell and Basement.  The AOPE will be a member of the Systems Integration Team (SIT), provide input for risk management, and participate in all design reviews for issues of constructability. The AOPE shall have discussions with designers and review designs for constructability, covering the following topics:

Space allocations for ease of construction and maintenance

Access for assembly

Required assembly sequence

Early identification and mitigation of constructability risk issues

Design features to reduce construction costs

## TRAINING

Training for the NCSX Project will lie within two primary areas.  These are:  Safety and Operation and Maintenance.

### Safety Training

Safety training is an important aspect of the Project's program.  The Project's training program will follow the PPPL policy stated in P-008 (“Staff Training”), P-028 (“Subcontractor Training Requirements for the PPPL Site”), and P-029 (“Testing for Training Courses”).  Safety training will be coordinated by the PPPL Certification and Training Division and the PPPL ES&H Division.

### Operations and Maintenance (O & M) Training

Cognizant WBS Managers shall be responsible for providing initial training and training materials for the operation and maintenance of the subsystems they provide.  They shall create a plan to provide training on the operation and maintenance of their system.  This plan shall include details of the training to be provided including documentation materials and a schedule for the training of experimenters as well as the end user operators.  This plan shall be included as part of the Final Design Review Data Package and shall be reviewed and approved by the NCSX Project and PPPL Management.

## TECHNICAL PUBLICATIONS (O&M MANUALS, ETC.)

Project Engineering will be responsible for the storage and retrieval of all technical publications/documents created by support organizations.  This database shall contain all documentation required for the operation and maintenance of the NCSX system including plans, procedures, and training materials.

The Operations Project Engineer (OPE) will be responsible for coordinating of the writing and implementation of the NCSX operating and maintenance procedures.  The OPE shall: review procedures for applicability; identify areas where these procedures are deficient; and assist in the correction/upgrades of these procedures. In addition, the OPE shall identify those areas where no procedures are in existence and coordinate the development of the missing procedures.  Creation and maintenance of the O&M Manuals including operation and maintenance plans and procedures will be the responsibility of cognizant WBS Managers.

## ES&H

NCSX will fully subscribe to the PPPL policy on Integrated Safety Management (ISM) as indicated in the Project Execution Plan (NCSX-PLAN-PEP).  PPPL will furthermore ensure that the design, development, procurement, manufacture, fabrication, construction, installation, testing, operation, maintenance, modification, and eventual decommissioning of the NCSX is accomplished in accordance with the Environment, Safety and Health (ES&H) provisions of:  applicable DOE Orders and other requirements the PPPL Environmental, Safety, and Health Directives (ESHDs); environmental regulations and guidelines of the U. S. Environmental Protection Agency (EPA); and, state and local requirements.

NCSX Project Management is responsible for the safe execution of the NCSX Project.  The PPPL Environment, Safety, and Health Division (ES&HD) provides support to the Project and will monitor all aspects of the project to assure that potential hazards are minimized.  Potential hazards will be identified and evaluated, techniques for elimination and/or control of such hazards will be studied, alternatives will be proposed, and risks will be assessed.  The goals of the ES&H function will be the accomplishment of NCSX program objectives, within reasonable and acceptable risk, and with the least practicable number of undesirable results (i.e., occurrences, incidents, accidents).

The ES&H review and approval process for NCSX will begin with review under the National Environmental Policy Act (NEPA) as prescribed by 10 CFR 1021, DOE Order 451.1B, and PPPL Procedure ESH-014.  An Environmental Assessment (EA) will be prepared by PPPL and submitted to DOE-PAO and DOE-CH (including review by the New Jersey Department of Environmental Protection), and a Finding of No Significant Impact (FONSI) sought from DOE-CH.  The NCSX NEPA process should be completed within about 12 months.

ES&H review of systems designs, drawings and procedures will be conducted by the NCSX ES&H professionals throughout the course of the design and installation stages.  Electrical safety, industrial hygiene, and construction safety staff will support the Project installation activities by performing inspections, in accordance with the installation procedures. The NCSX Project Manager will make a determination as to the hazard level of upcoming NCSX operations, in accordance with PPPL ES&H Directive 5008, Section 11, Chapter 1.  If this determination is for "High Hazard", the PPPL ES&H Executive Board will appoint an Activity Certification Committee (ACC) to perform an independent ES&H review of the NCSX Project's readiness for operation.  A Safety Assessment Document (SAD) will be prepared to provide an overview of the operation; descriptions of structures, systems and components relevant to the operation, with emphasis on environment, safety and health (ES&H) features; identification of hazards associated with the operation and methods employed for their mitigation; and a description of how operations will be conducted with emphasis on ES&H features.  The SAD will be reviewed and approved by the PPPL Safety Review Committee and the ACC.  Based on its review of the SAD and operating plans and procedures, and physical walkdowns of the facility, the ACC will recommend to the PPPL ES&H Executive Board whether to issue a Safety Certificate to commence NCSX operations, including any limiting conditions (see ES&H Directive 5008, Section 11, Chapter 2).

# Footnotes

Martin, J.M., Systems Engineering Guidebook, CRC Press, 1996, pg. 3

Systems Engineering Management Guide, Defense Systems Management College, 1990

J. Martin, Systems Engineering Guidebook (CRC Press, 1996) p. 216

# Text boxes

Controlled Document

THIS IS AN UNCONTROLLED DOCUMENT ONCE PRINTED.  Check the NCSX Engineering Web prior to use to assure that this document is current.