NCSX

Systems Engineering Management Plan

NCSX-PLAN-SEMP-dI-RTS

December 17, 2003

Prepared by:

R. Simmons, Systems Engineering

Support Manager

Concurrences:

W. Reiersen, Engineering Manager			  	J. Malsbury, QA Manager

_____________________________  		_____________________________

B. Nelson, Stellarator Core Systems		L. Dudek, Ancillary Systems

Project Engineer					Project Engineer

_____________________________  		_____________________________

E. Perry, Assembly Operations		M Williams, Head Engineering and

Project Engineer		Technical Infrastructure

Approved by:

_____________________________

G.H Neilson, Project Manager

Record of Revisions

Controlled Document

THIS IS AN UNCONTROLLED DOCUMENT ONCE PRINTED.  Check the NCSX Engineering Web prior to use to assure that this document is current.

| Revision | Date | Description of Changes |
| --- | --- | --- |
| DRAFT H1 | 5/13/03 | Peer Review Copy |
| DRAFT I | 12/1/03 | Complete Rewrite to Incorporate Peer Review Comments |
| DRAFT I-RTS | 12/17/03 | Incorporated recommendations from PDR, PBR, and EIR |

Table of Contents

1	INTRODUCTION	1

1.1	PURPOSE AND SCOPE	1

1.2	Applicable documents	1

2	TECHNICAL PROGRAM PLANNING AND CONTROL	3

2.1	Project Organization and Decision Making	3

2.1.1	Systems Engineering and Project Management	3

2.1.2	Systems Integration Team	5

2.2	Project Planning AND STATUSING	6

2.2.1	NCSX Integrated Cost and Schedule Management	6

2.2.2	Configuration Items	6

2.2.3	Work Planning	6

2.2.4	The Work Authorization Process	7

3	Systems Engineering Process	9

3.1	NCSX MIE Project Cycle	10

3.2	Requirement DEVELOPMENT PROCESS	12

3.2.1	Requirements Documentation Hierarchy	12

3.2.2	Specification Approach	13

3.3	RISK MANAGEMENT PROCESS	14

3.4	System Build, Test, and Demonstration PROCESS	15

3.4.1	System Build	15

3.4.2	System Test	16

3.4.3	Demonstrations	17

3.5	Configuration Management PROCESS	17

3.6	Data Management Process	19

3.7	INTERFACE CONTROL PROCESS	20

3.8	design REVIEW PROCESS	21

4	RELATED ENGINEERING PROCESSES	22

4.1	RELIABILITY, AVAILABILITY, MAINTAINABILITY (RAM)	22

4.2	VALUE ENGINEERING	22

4.3	QUALITY ASSURANCE (QA)	22

4.4	PARTS, MATERIALS AND PROCESS STANDARDIZATION AND CONTROL	23

4.5	Manufacturability	23

4.6	CONSTRUCTability	23

4.7	TRAINING	24

4.7.1	Lab Wide Training	24

4.7.2	NCSX Project Specific Training	24

4.8	TECHNICAL PUBLICATIONS (O&M MANUALS, ETC.)	24

4.9	ES&H	25

Table of Contents

Figure 1-1 NCSX Project Document Heirarchy	3

Figure 2-1 NCSX Project Organization	4

Figure 2-2 Work Planning, Authorization, and Statusing Process	9

Figure 3-1 NCSX Project Cycle	12

Figure 3-3Updating Project Baselines	18

# INTRODUCTION

## PURPOSE AND SCOPE

This document has been prepared for the National Compact Stellarator Experiment (NCSX) Project to describe the systems engineering process and management practices to be utilized by the NCSX Project in accomplishing its mission.  NCSX has been designated as a Major Item of Equipment (MIE) by the Department of Energy. The NCSX MIE project formally begins with Title I (Preliminary) Design and ends at first plasma.

This Systems Engineering Management Plan (SEMP) defines the processes, organization and procedures used by the NCSX MIE project to accomplish the systems engineering objectives.  It  does not cover the operations phase.  Systems Engineering (SE) is a disciplined process for engineering development that started in Department of Defense programs and has evolved into a discipline that includes three main elements:

- SE Management – applies the system engineering processes to the development of the project’s design;

- Requirements and Architecture Definition defines the technical requirements, defines a structure (or architecture) for the project and subsystem components, and allocates these requirements to the components of the architecture; and

- System Integration and Verification integrates the components of the architecture at each level of the architecture and verifies that the requirements for those components are met

## Applicable documents

This SEMP draws on the documents listed below.  In general, the NCSX Project (including ORNL) will follow the existing PPPL plans and procedures.  Unless specifically augmented or superceded by NCSX-specific plans and procedures, the NCSX Project is committed to following the existing relevant DOE orders specified in the PPPL Master Contract and PPPL plans, procedures, and standards.  This SEMP is consistent with the latest issues of the following NCSX-specific plans and documents :

- Acquisition Execution Plan (NCSX-PLAN-AEP)

- Project Execution Plan (NCSX-PLAN-PEP)

- Work Breakdown Structure (WBS) Dictionary (NCSX-WBS)

- Quality Assurance Plan (NCSX-PLAN-QAP)

- Data Management Plan (NCSX-PLAN-DMP)

- Document and Records Plan (NCSX-PLAN-DOC)

- Configuration Management Plan (NCSX-PLAN-CMP)

- Interface Control Management Plan (NCSX-PLAN-ICMP)

- Test and Evaluation Plan (NCSX-PLAN-TEP)

- Reliability, Availability, and Maintainability Plan (NCSX-PLAN-RAM)

- In addition, there are related NCSX-specific procedures that have been developed to expand on the requirements and processes outlined in several of the above plans.  These NCSX-specific procedures will also govern the systems engineering processes described in this SEMP. Annex I to this SEMP contains the list of current NCSX-specific procedures and the relevant PPPL procedures that these procedures augment or supercede.

- The SEMP is the key engineering management plan.  All engineering plans are derived from the concepts and approaches outlined in this SEMP.  Rather than repeat the details contained in other plans, this SEMP will limit itself to an overview discussion.  Figure 1-1 below provides the relevant document hierarchy of the SEMP to other NCSX Project, PPPL, and NCSX Engineering plans:

Figure 1-1 NCSX Project Document Heirarchy

# TECHNICAL PROGRAM PLANNING AND CONTROL

## Project Organization and Decision Making

### Systems Engineering and Project Management

A Work Breakdown Structure (WBS) has been defined for the NCSX Project.  The WBS is a product-oriented family tree consisting of components and services that define the scope of the NCSX Project.  It provides the overall architecture on how work is organized and is the starting point for planning and executing work on the NCSX Project.  The Project Execution Plan (NCSX-PLAN-PEP) provides a more global discussion of the NCSX WBS and the definition of each WBS element can be found in the Work Breakdown Structure Dictionary (NCSX-WBS).

The NCSX team organizational structure has been aligned with the Work Breakdown Structure. A fully integrated team is executing the NCSX Project, even though the participants may be geographically and institutionally distributed.  Work will be governed by project-wide plans and procedures.  The WBS-oriented organizational structure within the NCSX Project is depicted below in Figure 2-2Error: Reference source not found.

Figure 2-2 NCSX Project Organization

Systems Engineering is integral to the NCSX management approach.  The application of System Engineering principles has driven the development of the following processes to ensure that:

- Common databases are established and controlled for documents and drawings to ensure that everyone is using the same information.  This includes the establishment and implementation of controlled configuration control processes to ensure that proposed changes to system configurations are properly processed and approved and that the common databases are updated in a timely manner.

- System requirements are developed through an iterative process in which the overall objective is to develop an optimally balanced and robust design that meets cost and schedule objectives.

- System requirements and design constraints are allocated to subsystems and configuration items (CIs) through a hierarchy of specifications defined in a specification tree.  Requirements will be traceable and verifiable.  CIs represent the lowest level of control under configuration management and may be a single physical or functional item or collection of items that will satisfy a final end product or deliverable.  The process of identifying and agreeing to the interfaces between WBS and/or CIs is key to fully understanding requirements and design constraints.

- Design reviews are conducted during the project cycle to ensure that the design is robust and meets requirements at all levels, identifies deficiencies, and allows correction in a timely manner.

- Verifications are conducted at the CI, subsystem, and system levels to assure that the “as-built” design meets specifications.  This may take the form of testing, prototypes, and/or analyses.

The Engineering Manager has overall responsibility for implementing the SE program on the NCSX Project.  He has also been designated the Responsible Line Manager (RLM) for the NCSX Project by the PPPL Engineering Department Head.  The Systems Engineering Support Manager and the Design Integration Manager support the Engineering Manager in implementing the SE program.  In the line organization, four project engineers report to the Engineering Manager – the Stellarator Core Systems Project Engineer, the Ancillary Systems Project Engineer, the Machine Assembly Project Engineer, and the Operations Project Engineer.  The Operations Project Engineer will be assigned prior to first plasma to conduct integrated systems testing, coordinate the development of operations and maintenance procedures, and assume other responsibilities related to preparation for operation.  Individual WBS Managers report to the Project Engineers.

### Systems Integration Team

To be successful, the SE approach requires a have broad and coordinated participation by project participants.  The NCSX Systems Integration Team (SIT) has been established with the charter to facilitate this integration. The Project Manager or the Engineering Manager chairs the SIT, depending on the phase of the project.  Permanent members of the SIT include the Project Manager, the Deputy Project Manager for Program, the Engineering Manager, the Project Control Manager, the Project Physics Manager, and the Systems Engineering Support Manager. As appropriate and needed to support SIT agenda items, the Deputy Project Manager for Engineering, the Stellarator Core Systems Project Engineer, the Ancillary Systems Project Engineer, the Machine Assembly Project Engineer, the Design Integration Manager, specialty disciplines, other WBS managers, or other project personnel will be requested to participate.

The SIT will ensure that the project has an established a forum for discussion of systems engineering matters such as requirements interpretation, potential areas of risk, system level trade studies/analyses, coordination of processes, and resolution of issues.  Resolutions are worked outside the SIT by the responsible organizations and designated working groups formed as needed to address and resolve specific issues.  Results are reported back to the SIT. The SIT will facilitate obtaining decisions through line management that are best for the project as a whole.

The SIT will meet on a regularly scheduled basis with a frequency appropriate to the phase of the program and magnitude of system related activities in progress.  All standard agenda item status reports are by exception only, i.e., the focus is on problem areas needing attention by the SIT, not a review of schedule and usual business activities.

## Project Planning AND STATUSING

### NCSX Integrated Cost and Schedule Management

- As described in the in the Project Execution Plan (NCSX-PLAN-PEP), the NCSX Project is responsible for developing and maintaining an integrated cost and schedule management process.  NCSX will use the existing PPPL Project Control System (PCS) as described in the PPPL Project Control System Description.

- WBS Managers develop detailed, resource-loaded schedules in collaboration with the Project Control Manager that include all the labor and procurements required to complete the required scope of work.  The detailed schedule defines the cost and schedule baselines and will be put under change control at the start of Preliminary Design.  The detailed schedule will be maintained in a Primavera Project Planning (P3) database.

### Configuration Items

The basic element of the NCSX configuration is the Configuration Item (CI).  A CI may be established at the total project level, at the subsystem (WBS) level, or at the component/assembly level, depending on complexity and risk consideration. The definition and scope of a CI will evolve as the design evolves.  For example, during the preliminary design phase, the CI level will most likely be at the subsystem or WBS level.  However, as the design progresses into final design, it will likely become more appropriate that the CI definition be lowered to the major component or major procurement level.  It is not anticipated that the CI level will ever be at the piece assembly level.

### Work Planning

Many different types of planning documents will be used on the NCSX MIE Project to define the work that needs to be accomplished. While many different planning tools and documents will contribute to ensuring that the necessary activities are properly identified, planned, and executed, the focal point for planning work on NCSX is the NCSX Work Planning Form (NCSX WP).  The NCSX WP will include all the applicable items from the PPPL Work Planning Procedure ENG-032 (as well as additional detail), but in a format specifically geared to the needs of the NCSX Project.   A specific NCSX WP will be developed for each phase of the project design (Preliminary Design, Final Design, and Fabrication/Assembly).  The NCSX WP defines project expectations for the WBS Managers for each phase of the project in the form of a checklist of activities and deliverables that need to be provided for a design review and/or field-related activities.  These activities and deliverables are addressed by WBS Managers in the development of the detailed schedules.  The completed NCSX WP represents an agreement between the NCSX Engineering Manager (NCSX RLM) and the Cognizant Engineer/WBS Manager that the work activity has been adequately defined and that appropriate controls have been implemented.

During the preliminary design phase, the NCSX WP will necessarily focus on those activities and analyses needed to demonstrate that the design satisfies the design requirements and is sufficiently robust within the cost and schedule constraints.  As the design transitions to final design, the focus of the NCSX WP shifts to demonstrating that the proposed design can be fabricated.  Once the fabrication phase commences, the NCSX WP will transition to include the Manufacturing, Installation, and Test Plans (MITP) and Quality Assurance Plans to define the activities that need to occur during fabrication.  Once the items are fabricated, the NCSX WP will include definition of those installation and test plans and procedures needed to accomplish the installation and the tests needed to demonstrate that the installed components satisfy the design requirements. The NCSX WP will also cover including any design work entailing modifications to modifications to an existing system and/or facility, on-site or off-site work involving fieldwork, fabrication, physical changes to facilities, control computing, and fabrication of components and test stands/equipment during design for R&D.

An NCSX-specific procedure (NCSX-PROC-004) has been developed that implements the NCSX WP.  Only the NCSX RLM (NCSX Project Engineering Manager) has the authority to modify or delete the requirements of a NCSX WP.

### The Work Authorization Process

The NCSX WP is the starting point in the work planning process and will eventually evolve into a Work Authorization Form (WAF) to authorized work to proceed. For NCSX engineering-related work, including fabrication, assembly, installation, and testing, the WAF represents the agreements between the NCSX Engineering Manager (also NCSX RLM) and the Cognizant Engineer/WBS Manager on what will be done, on what schedule, and at what cost.  The NCSX WP will reference the appropriate WAF to ensure a one-for-one linkage.

As a first step in the work planning process, a NCSX WP is developed by the Cognizant Engineer/WBS Manager and approved by the responsible Project Engineer, Systems Engineering Support Manager, and Project Engineering Manager. For work involving field work, involving physical changes to engineering facilities, control computing, technical infrastructure and equipment, involving collaborations with others such as R&D activities on or off-site, or prototype fabrication, special attention will have to be paid to safety and environmental controls and procedures, and formal approval of the NCSX WP by the NCSX Engineering Manager (NCSX RLM) is required.  Using the NCSX WP guidelines found in NCSX-PROC-004, the Cognizant Engineer/WBS Managers submit job estimates that include the work scope, schedule, resource requirements, and deliverables.  Each job maps cleanly into activities in the detailed schedule.  Resource requests will be consistent with the cost estimates reflected in the detailed schedule.  Job estimates will be made at the beginning of each fiscal year to cover all the work to be accomplished in that fiscal year.

The Project Control Manager will enter the job estimate into the P3 database and generate a Work Authorization Form (WAF).  Work will be authorized in advance of the scheduled start date, but not necessarily at the beginning of each fiscal year.  Once the WAF is approved, the WAF will be the basis for work authorization (the job manager can start work) and for obtaining monthly status.  These monthly status meetings will not only address cost and schedule performance, but will also review potential and defined risks and the steps being planned or taken to mitigate those risks.

Figure 2-3 illustrates the work authorization process, starting with development of a NCSX WP and completing with a series of planned, resource-loaded and authorized jobs.  It should be noted that NCSX WP’s addressing fieldwork or physical changes to facilities, infrastructure, off-site prototyping activities, or on-site R&D activities require a degree more of formality in approving the NCSX WP.

Figure 2-3 Work Planning, Authorization, and Statusing Process

# Systems Engineering Process

The systems engineering process is a comprehensive and iterative problem solving process that is designed to transform validated user requirements and project objectives into a functional system that optimally meets the mission requirements. Requirements analysis efforts define the problem and the success criteria for a system that can address the problem.  Then development of alternatives, the selection of a balanced solution, and the description of the solution as a design package is accomplished via design definition and systems analysis and control.

## NCSX MIE Project Cycle

Technical aspects of a project cycle are illustrated in 1.  .  This chart depicts the various DOE Critical Decision milestones (CD-0 through CD-4), as outlined in DOE O 413.3 Program and Project Management for the Acquisition of Capital Assets, and the major systems engineering processes and deliverables expected at each stage of a project.

At selected points in the NCSX fabrication project, the current design configuration (comprised of CIs making up the “configuration”, including fabrication and testing define the technical baseline.  As described in greater detail in NCSX Configuration Management Plan (NCSX-PLAN-CMP) and summarized in Section 3.2 that follows, the NCSX Project technical baseline is defined by a series of specifications and computer aided design (CAD) models and drawings.

Inherent in the completion of the CD milestones as well as project design reviews is the attention and priority given to safety and quality as underpinnings of the successful evolution of the design and subsequent assembly, installation and testing.  The NCSX Project adheres to the spirit of and procedures specified in the PPPL Integrated Safety Management Plan. In addition, the NCSX Project adheres to the requirements of the PPPL Quality Assurance Plan via the project specific Quality Assurance Plan (NCSX-PLAN-QAP).

Since it inception in 1997, the NCSX Project has evolved from the Pre-Conceptual Design phase where the mission need and requirements were explored and defined. The successful Physics Validation Review (PVR) in March 2001, confirmed the design concept and the use of the test cell formerly occupied by the PLT and PBX-M experiments.  Following approval of the DOE CD-0 milestone in the summer of 2001, the Conceptual Design Phase commenced.  During the Conceptual Design, the plasma, stellarator core, ancillary systems, and facility concepts were refined.  Manufacturing studies of critical, developmental components were conducted by industry.  Mission requirements were translated into a formal system specification, the General Requirements Document (GRD).  Detailed, bottoms-up cost and schedule estimates were generated with substantial input from industry.  A procurement strategy was developed.  Major risks were identified and risk mitigation plans developed.  A successful Conceptual Design Review (CDR) was conducted at PPPL in May 2002 and the DOE CD-1 milestone was achieved in November 2002.  The Project is currently completing the preliminary design with the goal to the achieve DOE CD-2 milestone in the seceond quarter or FY2004.

During Preliminary Design, more detailed functional and performance requirements are successively allocated to subsystems and configuration items (CIs).  A series of performance specifications are generated down to the appropriate CI level.  Analyses and R&D required to establish the feasibility of the design concepts are completed.  Verification plans for testing during assembly and installation are developed.  Interfaces are identified and plans developed at the start of Preliminary Design to define the interfaces.  Interface specifications are documented in Interface Control Documents (ICDs) during Preliminary Design.  Following a successful Preliminary Design Review (PDR) of one or more CIs, the specifications developed in preparation for the PDR (including interface specifications) are placed under change control.  Following successful completion of the PDR, the technical baseline and self-consistent cost and schedule baseline are also updated to reflect these specifications, verification plans, and associated design concepts, and the NCSX WP updated to reflect the items necessary to be completed during final design.

During Final Design, the designs of the hardware and software required to satisfy the performance requirements specifications are completed.  Analyses of critical design basis calculations performed earlier are checked and any additional analyses needed to confirm the adequacy of the detailed designs is performed and checked.  Detailed requirements for building  or fabricating the CI is developed and placed under change control following a successful Final Design review (FDR). The technical, cost, and schedule baselines are also updated completion of the FDR.   All of the major procurements on NCSX are expected to be “built to print”, with only minor engineering being done at the supplier to enhance manufacturability.

Once construction is authorized by the achievement of the DOE CD-3 milestone, work on the assembly, installation, and testing can proceed with due respect to safety and quality. Test readiness reviews will be conducted in advance of actual testing to ensure that all of the elements required for testing are in place, especially provisions to ensure safety. Based on experience with previous fusion experiments built at PPPL, it is anticipated that NCSX will be classified as a high hazard facility per ES&HD 5008 Section 11.  Accordingly, a Safety Assessment Document (SAD) will be prepared and a Safety Certificate be issued by the PPPL ES&H Executive Board prior to the start of operations.

The final phase of integration and verification activities is integrated systems testing.  Integrated systems testing will culminate in the production of the first plasma, which is a demonstration that the device and facility are operating as intended at the initial performance levels specified for the first plasma milestone (DOE CD-4). An Activity Certification Committee (ACC) will be formed during the Final Assembly, Installation and Test (FAIT) phase to provide an independent safety review of plans and readiness for integrated systems testing and first plasma.  The ACC will advise the PPPL ES&H Executive Board with respect to issuance of the Safety Certificate. Prior to the start of operations, DOE will conduct an Operational Readiness Assessment (ORA).  NCSX intends to emulate the successful NSTX model wherein the ORA and activities  of the ACC were conducted in concert.

Figure 3-4 NCSX Project Cycle

## Requirement DEVELOPMENT PROCESS

### Requirements Documentation Hierarchy

Requirements for the NCSX Project are captured in a hierarchy of requirements documents, which begin with the system (top-level) engineering requirements in the General Requirements Document (GRD).  The GRD represents a complete set of performance requirements and constraints at the system/project level and initial subsystem allocations.  The top-level system requirements in the GRD flow down to a set of specific functional or “design to” requirements at the appropriate subsystem or major component/procurement level.  These functional or “design to” requirements then flow down to specific fabrication requirements that get translated into products and services by the builders (“build to”).  As the requirements of the GRD are primarily reflected in the form of functional or performance requirements, additional requirements in the form of design specifications and/or design constraints must be developed to completely define the deliverable item.

Design constraints are a class of non-functionally derived requirements.  Requirements that do not have to be derived and cannot be modified or dropped as a result of a tradeoff study can generally be considered a constraint.  Typical design constraint categories include environmental conditions, transportability, interchangeability, workmanship, etc. The Engineering Manager is responsible for defining an overall project approach to the implementation of a design constraints methodology and for developing a complete set of system level design constraints for incorporation into the system specification.  Cognizant WBS Managers are responsible for properly treating system level design constraints allocated to their subsystem and for any additional constraint definition that may be required.

A specification tree illustrates the relative hierarchy of requirements documents and is an important identification and planning tool that will be developed early in Preliminary Design for each specification required by the NCSX Project.  WBS Managers shall provide specification tree inputs to the Engineering Manager for their respective system elements.  For each specification, the specification tree will identify the scope, specification type, and the individual responsible for its development. The specification tree defines the set of specifications required to execute the NCSX MIE project and the order in which they need to be approved and placed under change control.  Development of the specification tree must be coupled with the development of an acquisition strategy, because the technical specifications provide the basis for the acquisitions and should be structured accordingly.

It is important to note that the evolution of the design is an iterative approach where the design concept is created to satisfy a given set of requirements. The design then evolves and matures with more detailed analyses, resulting in increasingly more detailed design concepts as the requirements grow more detailed and become allocated to lower levels within the system.  Typically, a set of alternative concepts will be developed and each in turn evaluated to develop the most cost-effective solution based on specific evaluation criteria.  This process will culminate in a detailed design of the entire NCSX system including all subsystem elements.

### Specification Approach

- Beginning with the GRD, the NCSX Project shall develop and implement a project-specific guidelines for developing requirement specifications that meets that requirements set forth in the PPPL ENG-006 "Review and Approval of Specifications & Statements of Work".  For the NCSX Project, functional or “design to” specifications provide the design constraints to meet performance requirements flowed down from higher-level specifications where as “build to” specifications provide specific assembly and fabrication details and constraints.  The “build to” specifications naturally flow into the procurement process for obtaining goods or services.  A graded approach will be applied where new and complex systems and components will require extensive and detailed specifications whereas catalogue items such a some electronic components will not require as detailed specifications. Several specification types have been identified for NCSX and the purpose and formats are described in greater detail on the NCSX Engineering Web Page via a link to Specifications. A special type of specification is the Statement of Work (SOW).  The NCSX Engineering Web Page also provides a discussion and format for NCSX SOWs via a link to Statements of Work.  The URL for the NCSX Engineering Web Page is:

- http://www.pppl.gov/me/NCSX_Engineering/

- The specification types for NCSX fall into two broad categories.  The first category deals with overall functional performance requirements definition and includes the GRD as the overall NCSX Project specification and the allocation of requirements specifications at the subsystem or major component level (CI).  The second category deals with specific development (“build to”) specifications that detail how a particular product/component shall be produced, how a particular process such as manufacturing techniques shall be achieved, or how a particular material shall be developed.

NCSX is planning to re-use much equipment previously used on other PPPL experiments, including vacuum pumping equipment, neutral beam injection systems, and power supplies.  Performance requirements will be generated that the legacy equipment must satisfy.  Verification that the legacy equipment satisfies the performance requirements will be provided via testing and the results documented as tasks are completed.  Product specifications and detailed component drawings for legacy equipment will not be developed as part of the NCSX Project.  However, specific attention will be paid to defining the interfaces of and interlocks between new NCSX systems to legacy equipment.

## RISK MANAGEMENT

### Overview of Process

Risk management is a process to assure that the system design is feasible and can be built in a timely and cost effective manner.  For purposes of the risk management process, risk is defined as the probability of an undesirable event occurring multiplied by the severity of the event.  Unmitigated risk could have an adverse effect on program cost and schedule.  Responsibility for risk management lies with NCSX line management.  The Risk Management Plan (NCSX-PLAN-RMP) provides an oversight of the risk management and mitigation processes used on the NCSX Project.

### Risk Identification, Mitigation, and Tracking

Risks will be identified and mitigation strategies addressed in weekly discussions between the NCSX Engineering Manager, the NCSX Project Engineers, WBS Managers and cognizant engineers.  These risk mitigation strategies will then be reflected in the WAFs. The design engineers, with the appropriate management oversight, establish the specific approaches to addressing the individual risk elements.  The early phases of the NCSX project design process is structured to identify risks.  These risks are addressed through design improvements, manufacturing studies, prototypes, schedule contingency and cost contingency.

The Systems Integration Team (SIT) will facilitate identifying areas of critical and near term risk, coordinating the development of risk mitigation plans for these items, and monitoring performance against these plans.  To assist in this process, the SIT has developed a Critical Risk Issues list that is addressed during weekly SIT meetings. This Critical Items list provides a concise and succinct summary of critical and near term risks, an assessment of the potential impact of the risk, the risk mitigation approach, and the current status in mitigating/eliminating the risk.  Table 3-1 below provides a risk consequences assessment matrix that provides a relative ranking of risks and their impacts..

Table 3-1 Consequences Assessment Matrix

| Risk Area\Consequence | Marginal (M) | Significant (S) | Critical (C) |
| --- | --- | --- | --- |
| Cost: Worst Likely Impact | ≤ $25K | ≤ $200K | >$200K |
| Schedule: Worst Likely Impact | < 1 week delay of critical path or DOE milestone | > 1 week, but < 1 month delay of critical path or DOE milestone | > 1 month delay of critical path or DOE milestone |
| Technical: Worst Likely Impact on Scope or Performance | Negligible, if any, degradation of scope or performance | Significant scope or performance degradation which has potential to impact achievement of baseline | Baseline scope and performance will not be achieved |

Minimization and mitigation of risk on the NCSX Project will be provided through early management oversight allowing the application of additional resources, development of alternative technologies, and appropriate contingency allowances.    It should be noted that the NCSX Project has already implemented a proactive approach to risk management.  Early in the conceptual design phase appropriate contingency levels were assigned based on the state of the design and perceived risks and a series of manufacturing studies were conducted to mitigate manufacturing risk in the critical path components, including the modular coils and vacuum vessel. Most recently, a dedicated Value Engineering Task Force not only identified possibly lower-cost alternatives, but also addressed means to mitigate risks by adopting more standardized designs in specific areas.

## System Build, Test, and Demonstration PROCESS

### System Build

The system build process begins with design definition and continues until the system is constructed and is ready for integrated systems testing.  As part of the systems engineering process, the build of the system is an extension of the requirements analysis and design tasks for all subsystems and components.

The stellarator core and interfacing components will be defined in 3D CAD models generated in Pro/Engineer to facilitate the building of a unified assembly.  The Stellarator Core Systems Project Engineer is responsible for the development of the integrated model of the stellarator core.  A Pro/Engineer model of the facility shall also be generated to define space envelopes for locating ancillary equipment and routing of cables and piping.  All 3D models and 2D drawings shall reside in a common database.  The Design Integration Manager is responsible for developing a model of the NCSX facility, which includes the integrated model of the stellarator core.

NCSX will be constructed at PPPL using existing procedures and practices that are familiar to PPPL technicians.  Hazard controls include: work planning; installation, test, and operating procedures; design reviews; job hazard analyses; pre- and post-job briefings; protective equipment; and worker training. The Field Period Assembly (WBS 18) Manager is responsible for coordinating all fabrication and assembly activities in the TFTR Test Cell.  The Machine Assembly Project Engineer is responsible for coordinating all assembly activities in the NCSX Test Cell and Basement.  Coordination of assembly activities outside the TFTR Test Cell and NCSX Test Cell and Basement are the responsibility of the Cognizant WBS Manager.

### System Test

System verification is accomplished through a combination of inspection, demonstration, test, and analysis activities.  The Engineering Manager will establish a cost effective approach to verifying system performance.  Emphasis will be placed on the reduction of overall verification costs and timelines. A verification compliance matrix will be developed and maintained that identifies the verification method and status of each system requirement in order to ensure that system performance requirements, as documented in the GRD, are verified and maintenance and operations procedures are validated.

As some system requirements will require verification via test methods, an integrated test planning approach will be utilized.  System level tests will include activities to verify that subsystems interface properly and individual performance requirements are met, as well as verifying full system operation.  A Test and Evaluation Plan (TEP) will be developed and maintained by Project Engineering to establish how the integrated system testing will be performed and managed. The TEP will include an overview and schedule of the integrated system test program and the purpose, scope, and objective of each system test; test configurations; and test responsibilities.  WBS Managers are responsible for developing plans for subsystem testing.

Early development of test plans is essential because it may drive when certain capabilities and interfaces are required to be operational.    The TEP will be developed during Preliminary Design to provide the WBS Managers knowledge as to what their system test responsibilities are and within what time frame they occur.  This will enable the WBS Managers to do the planning necessary to support system testing.  Initial subsystem test plans will also be developed during Preliminary Design. In support of testing activities, Project Engineering will conduct Test Readiness Reviews (TRRs), track test activities, and resolve test issues.

### Demonstrations

Demonstration or prototyping of critical technologies and development hardware is a cost effective method of reducing risk and will be monitored and controlled through the Risk Management process described in Section 3.3.  Demonstrations provide assurance that the system under development is feasible.  Prototypes will be developed and evaluated to ensure that the critical components of the system can be manufactured to meet performance requirements.

## Configuration Management PROCESS

The CM program is described in the NCSX Configuration Management Plan (NCSX-PLAN-CMP).  The physical and functional description of the components, systems, and software/firmware comprise the “configuration” of the NCSX Project.  The NCSX project (and details of its design configuration) is progressively described in greater detail as it proceeds through the design process.  At the end of the fabrication project, as the NCSX enters its operational phase, the actual physical and functional configuration is documented.  It is not deemed necessary for all drawings to be updated to reflect the as-built condition.  In lieu of as-built drawings, it is considered acceptable to call out on affected drawings the approved NCR that documents each nonconformance.  Configuration Management (CM) is an integrated program that ensures that the configuration is identified and properly document and that changes to the configuration are controlled during this life cycle.  An effective CM program must allow for design evolution without compromising cost and schedule objectives.

The Engineering Manager is responsible for implementing an effective CM program.  The Systems Engineering Support Manager will assist in developing the CM program and will be responsible for its administration.

Figure 3-5 illustrates the process for managing the development and changing of project baselines.  The technical baseline is defined by the General Requirements Document (GRD), the system concept defined by the Pro/Engineer model of the stellarator core, and supporting technical documentation.  During Preliminary Design and Final Design, subsystem and configuration item designs will evolve as changes are made and more detail is added.  This process is natural and must be encouraged.  However, there are two risks that the project needs to manage:

- Proposed changes may compromise cost and schedule objectives

- Proposed changes may compromise the ability of interfacing systems to meet their technical, cost, and schedule objectives.

WBS Managers have the responsibility to identify changes and the impact of the proposed change on cost, schedule, or interfacing systems.  For significant changes, the WBS Managers are obligated to initiate Engineering Change Proposals (ECPs) for updating the project cost, schedule, and technical baselines prior to proceeding with the design.  The project will also require WBS Managers to periodically reconcile the cost and schedule baselines with proposed design changes that have occurred since the project baselines were last changed.  These periodic updates will typically be coordinated with the semi-annual DOE cost and schedule reviews and formal design reviews (such as the Preliminary Design Review and Final Design Review).  “Omnibus” ECPs will be required for these periodic updates to formally update the project baselines and proceed with the design.  The ECPs for these periodic updates will also reflect the actual cost and schedule performance.  An electronic system for preparing and processing ECPs is available via a link from the NCSX Engineering Web page:  http://www.pppl.gov/me/NCSX_Engineering/ .

Figure 3-5Updating Project Baselines

The normal adjudicating body for each ECP is the Change Control Board (CCB).  The CCB is comprised of senior members of the NCSX management team and is chaired by the Project Manager.  Change classifications and approval thresholds for change control are defined in the NCSX Project Execution Plan (NCSX-PLAN-PEP) consistent with DOE Order 413.3.  In instances where the approval authority is in DOE, the Project Manager shall forward the ECP to DOE with a recommendation to approve.

In some instances (e.g., when a pending critical procurement needs to reflect the proposed change, if field activities may be delayed by the normal ECP process involving full reviews and the CCB, or if the proposed change is primarily editorial or minor in scope), a process for “expedited” ECPs may be appropriate.  The NCSX Engineering Manager, in consultation with the NCSX Project Manager, may determine to implement an “expedited” ECP process in which the NCSX Engineering Manager may review and approve the ECP with only an abbreviated review.  However, any “expedited” ECPs will be reviewed “after-the-fact” by the full CCB to ensure that major errors and/or omissions were not made.

## Data Management Process

Data management is provided through defined procedures and the document and drawing control systems. Two NCSX plans describe the data management process utilized for the NCSX Project.

The NCSX The Data Management Plan (NCSX-PLAN-DMP) describes the processes to be used for document and drawing control.  The DMP will be reviewed and approved at the start of preliminary design.

The majority of project documents will be accessible electronically. Electronic Data will be stored in seven sites and physical data not readily convertible to electronic format will be stored in hardcopy format in the PPPL Operations Center.  The purpose and general content contained in each storage site is summarized below:

- Electronic Sites

  - Project Web – contains general project information, external design review data, physics meeting records, PAC meeting records, publications, and the project directory;

  - Procurement Web – contains all documentation required for potential suppliers to develop proposals;

  - Manufacturing Web – contains all project documentation required for suppliers to execute their scope of work;

  - Engineering Web – contains all other project documentation including cost and schedule information, design criteria, internal design review data, engineering and project meeting minutes, memoranda, analysis reports, controlled documents not otherwise posted, and work plans;

  - Pro/INTRALINK Database – contains CAD drawings and models for project use;

  - Project FTP Server – contains large Data Files primarily used in physics analyses; and

  - Supplier FTP Server – contains CAD drawings and models for use by suppliers.

- PPPL Operations Center – contains that information not readily convertible to an electronic format (e.g., hardcopy supplier contract deliverables, hardcopy field activity documentation, etc.). A web site will be created that catalogs the items contained only in hardcopy format in the Operations Center.

A more detailed table listing the seven sites and their customers, custodians, document types, and access restrictions is provided in the NCSX Data Management Plan (NCSX-PLAN-DMP).

The NCSX Document and Records Plan (NCSX-PLAN-DOC) identifies the controlled documents on the NCSX Project.  The DOC will be reviewed and approved at the start of preliminary design and defines the following:

- Identifiers of all project documents, including controlled documents and memoranda

- Approval authority for controlled documents

- Location for storage and retrieval

- Records retention requirements

## INTERFACE CONTROL PROCESS

Interface Control is that part of system design integration that generates and administers technical agreements between two or more activities, when the products must assemble and/or function together. An interface may define a written agreement between WBS systems or define a physical boundary, mating surface geometry or attachment details that exist between two adjoining WBS components.  There are two types of interfaces. A primary interface exists between two separately deliverable items (referred to as Configuration Items/CIs in systems engineering terms) when the mutual boundary area is not controlled by a single developmental or “design to” specification, when the interface is with systems outside the project (external interfaces identified in the General Requirements Document/GRD), or when, at the discretion of the cognizant Project Engineer, the interface is determined to be critical to the performance of the NCSX program.  Secondary interfaces represent technical agreements entirely within a single WBS element or between two WBS elements, but with the same WBS Manager.  Only primary interfaces will come under the configuration control program described in Section 3.5.

Project Engineering is responsible for establishing the processes and procedures for effecting interface control.  The Interface Control Management Plan (NCSX-PLAN-ICMP) will describe the processes to be used in managing interfaces.  The ICMP will be reviewed and approved at the start of preliminary design.  The Systems Engineering Support Manager will administer the interface control management program.  WBS Managers will jointly develop scope sheet agreements at the start of Preliminary Design that identify what interfaces exist and document work plans to finalize the interface definitions.  Working groups will be established to support the development, modification, and maintenance of selected interfaces as required.  Interface control documents (ICDs) will be established to document both functional and physical interface characteristics.  ICDs should be in place by the time of the Preliminary Design Review (the earliest PDR among the affected WBS elements) in order to facilitate completion of Final Design.

## design REVIEW PROCESS

On NCSX, both external and internal design reviews are planned.  External design reviews are determined by DOE and conducted to support DOE Critical Decisions.  Internal design reviews are conducted to assess the technical adequacy of the configuration baseline as it is developed, consistent with ENG-033 Design Verification and P-010 Design Reviews. A NCSX-specific procedure, NCSX-PROC-004 (NCSX Work Planning), has been developed that augments the requirements of ENG-033 and P-010.  These reviews verify the proper development, establishment, and control of the configuration baseline.  They are used to verify conformance with requirements at the system, subsystem, and configuration item (CI) levels.  They also serve as an appropriate point to update project technical, cost, and schedule baselines.

The review process is continual throughout design, fabrication, and assembly.  The Conceptual Design review was conducted in May 2002.  There will be a series of specification validations and design reviews during Preliminary and Final Design as the design evolves from the system level to the CI level.  Test readiness reviews will be conducted during the Fabrication, Assembly, Installation, and Test (FAIT) phase.  The final review, which follows completion of integrated systems testing, will be the Operations Readiness Assessment (ORA).

Design reviews will be conducted at the appropriate time for all systems and components.  The planning, preparation, and conduct of each design review are the responsibility of the cognizant WBS Manager for the system element(s) under review and by the responsible Project Engineer for system-level reviews.

The schedule for design reviews for major systems or critical components will be determined by the Engineering Manager (or Systems Engineering Support Manager) in consultation with the responsible Project Engineer and WBS Managers.  Responsibility for scheduling design reviews for other systems and components will be delegated to the responsible Project Engineer.   Before a design review is scheduled, the responsible official (Project Engineer/Systems Engineering Support Manager) or responsible Project Engineer shall confirm that the required documentation specified in the NCSX WP is completed (e.g., drawings promoted to the appropriate level, specifications approved, analyses completed and checked, etc.).

Successful completion of a design review requires that the design has matured to a level appropriate for the review and that all data necessary to properly evaluate that design is complete, including successful resolution of the design review CHITs.  To facilitate this goal, a NCSX Work Planning Form (NCSX WP) approach will be implemented for the design phases of the project.  The NCSX WP will identify entry requirements that indicate readiness for a review and exit requirements that define review closeout. Success criteria are then established to provide a means to assess satisfaction of the entry and exit requirements.  These data items establish project requirements for readiness for a design review.  The NCSX WP will be documented during each phase of the design by the cognizant WBS Manager in conjunction with the cognizant Project Engineer and Engineering Manager (or Systems Engineering Support Manager) so that the required supporting activities can be properly planned.

# RELATED ENGINEERING PROCESSES

## RELIABILITY, AVAILABILITY, MAINTAINABILITY (RAM)

The RAM program to be implemented on NCSX is defined in the NCSX RAM Plan (NCSX-PLAN-RAM).  A draft RAM Plan will be provided for review at the Preliminary Design Review  (PDR).  The RAM Plan will be reviewed and approved as part of the Final Design Review (FDR).  The RAM program will utilize a graded approach that is based on consideration of risk.  WBS Managers are responsible for optimizing designs for reliability and maintainability through systematic evaluation of design options, and for performing failure modes, effects and criticality analysis (FMECAs) for RAM design improvement and verification.

## VALUE ENGINEERING

Value Engineering (VE) is the systematic application of recognized techniques by a multi-disciplinary team to identify the function of a product or service, establish a worth for that function, generate alternatives through the use of creative thinking, and provide the needed functions to accomplish the original purpose of the project at the lowest life-cycle cost without sacrificing safety, necessary quality, and or environmental attributes of the project.  The NCSX Project will apply VE methodologies following a graded approach to the formal elements of VE.

On NCSX, value engineering methods have already been applied during Conceptual Design.  Specific examples include:

- Coil topology studies conducted by a multi-disciplinary team of physicists and engineers that led to the selection of modular coils for providing helical fields

- Manufacturing studies of the vacuum vessel and modular coils conducted by manufacturing engineers in industry (and supported by laboratory design engineers) that identified and evaluated a variety of fabrication options

Project Engineering and the individual WBS Managers will review each subsystem during Preliminary Design and determine what design areas would likely benefit from additional value engineering.  These value engineering studies would be completed prior to the subsystem PDR.

## QUALITY ASSURANCE (QA)

The NCSX QA program provides a framework that defines quality in terms of goals and expectations and establishes processes to fully integrate the quality function into all phases of the program by providing continual, independent, and disciplined reviews/audits of all processes, products, and services.  The Quality Assurance Plan (NCSX-PLAN-QAP) establishes the requirements for controlling work and for providing management and independent self-assessments to find, report, and solve problems.  The plan identifies implementing policies, plans, and procedures for the NCSX QA program.  The QAP has been reviewed and approved.

While performing their assigned duties and responsibilities, workers, line management, and immediate supervisors are assigned immediate responsibility for the quality of the project's efforts.  Personnel independent of the activities being performed are assigned the responsibility of verifying and validating that the project's efforts are commensurate with project standards.  All personnel have a responsibility to identify quality problems and to recommend solutions.

## PARTS, MATERIALS AND PROCESS STANDARDIZATION AND CONTROL

The purpose of the NCSX parts standardization program is to reduce the number of part types, improve system maintainability, and optimize logistics support by standardizing part types and selecting parts with two or more reliable sources wherever practical.  Project Engineering will maintain a Master Parts List of NCSX parts and materials.

In addition to the Master Parts List, the NCSX Project will develop a Vacuum Materials List.  A Vacuum Materials Review Committee will be established.  This committee will establish the suitability of all parts and materials to be used in the plasma vacuum.

These lists will be developed for review by the time of the PDR and be finalized by the FDR.

## Manufacturability

A Manufacturing, Inspection, and Test Plan (MITP) shall be produced for each configuration item.  This plan will be the controlling document by which the manufacturability of each configuration item will be evaluated.  The plan shall include a process flow diagram showing each of the major manufacturing operations.  The plan will identify any special process procedures required to produce the configuration item to be fabricated.  Inspection and test plans shall also be described.  A draft MITP will be provided for review at the Preliminary Design Review  (PDR).  The MITP will be reviewed and approved as part of the Final Design Review (FDR).  Cognizant WBS managers are responsible for the development of MITPs for each of their configuration items.  The MITPs along with product specifications provide the technical basis for the procurement of configuration items.

## CONSTRUCTability

The Machine Assembly Project Engineer is responsible for coordinating all assembly activities in the NCSX Test Cell and Basement.  The Machine Assembly Project Engineer  will be a member of the Systems Integration Team (SIT), provide input for risk management, and participate in all design reviews for issues of constructability. The Machine Assembly Project Engineer will have discussions with designers and review designs for constructability, covering the following topics:

- Space allocations for ease of construction and maintenance

- Access for assembly

- Required assembly sequence

- Early identification and mitigation of constructability risk issues

- Design features to reduce construction costs

## TRAINING

Training for the NCSX Project will lie within two primary areas.  Lab wide training in safety and other discipline-specific skills and NCSX Project specific training (e.g., operations and maintenance, plans and procedures, etc.).

### Lab Wide Training

Safety training is an important aspect of the Project's program.  The Project's training program for personnel at the PPPL site will follow the PPPL policy stated in P-008 (“Staff Training”), P-028 (“Subcontractor Training Requirements for the PPPL Site”), and P-029 (“Testing for Training Courses”).  Safety training will be coordinated by the PPPL Certification and Training Division and the PPPL ES&H Division.

Additionally, each discipline at PPPL and ORNL has discipline-specific training (e.g., Pro/E CAD training, AutoCad training, etc.) that is required for each person assigned.

### NCSX Project Specific Training

Cognizant WBS Managers shall be responsible for providing initial training and training materials for the operation and maintenance of the subsystems they provide.  They shall create a plan to provide training on the operation and maintenance of their system.  This plan shall include details of the training to be provided including documentation materials and a schedule for the training of experimenters as well as the end user operators.  This plan shall be included either as part of the Final Design Review Data Package or shortly thereafter, and shall be reviewed and approved by the NCSX Project and PPPL Management.

Training will also be conducted on the various NCSX plans and procedures for each person assigned to the NCSX Project.

## TECHNICAL PUBLICATIONS (O&M MANUALS, ETC.)

Project Engineering will be responsible for the storage and retrieval of all technical publications/documents created by support organizations.  This database shall contain all documentation required for the operation and maintenance of the NCSX system including plans, procedures, and training materials.

The Operations Project Engineer (OPE) will be responsible for coordinating of the writing and implementation of the NCSX operating and maintenance procedures.  The OPE shall: review procedures for applicability; identify areas where these procedures are deficient; and assist in the correction/upgrades of these procedures. In addition, the OPE shall identify those areas where no procedures are in existence and coordinate the development of the missing procedures.  Creation and maintenance of the O&M Manuals including operation and maintenance plans and procedures will be the responsibility of cognizant WBS Managers.

## ES&H

NCSX will fully subscribe to the PPPL policy on Integrated Safety Management (ISM) as indicated in the Project Execution Plan (NCSX-PLAN-PEP).  PPPL will furthermore ensure that the design, development, procurement, manufacture, fabrication, construction, installation, testing, operation, maintenance, modification, and eventual decommissioning of the NCSX is accomplished in accordance with the Environment, Safety and Health (ES&H) provisions of:  applicable DOE Orders and other requirements the PPPL Environmental, Safety, and Health Directives (ESHDs); environmental regulations and guidelines of the U. S. Environmental Protection Agency (EPA); and, state and local requirements.

NCSX Project Management is responsible for the safe execution of the NCSX Project.  The PPPL Environment, Safety, and Health Division (ES&HD) provides support to the Project and will monitor all aspects of the project to assure that potential hazards are minimized.  Potential hazards will be identified and evaluated, techniques for elimination and/or control of such hazards will be studied, alternatives will be proposed, and risks will be assessed.  The goals of the ES&H function will be the accomplishment of NCSX program objectives, within reasonable and acceptable risk, and with the least practicable number of undesirable results (i.e., occurrences, incidents, accidents).

The ES&H review and approval process for NCSX will begin with review under the National Environmental Policy Act (NEPA) as prescribed by 10 CFR 1021, DOE Order 451.1B, and PPPL Procedure ESH-014.  An Environmental Assessment (EA) will be prepared by PPPL and submitted to DOE-PAO and DOE-CH (including review by the New Jersey Department of Environmental Protection), and a Finding of No Significant Impact (FONSI) sought from DOE-CH.  The NCSX NEPA process should be completed within about 12 months.

ES&H review of systems designs, drawings and procedures will be conducted by the NCSX ES&H professionals throughout the course of the design and installation stages.  Electrical safety, industrial hygiene, and construction safety staff will support the Project installation activities by performing inspections, in accordance with the installation procedures. The NCSX Project Manager will make a determination as to the hazard level of upcoming NCSX operations, in accordance with PPPL ES&H Directive 5008, Section 11, Chapter 1.  If this determination is for "High Hazard", the PPPL ES&H Executive Board will appoint an Activity Certification Committee (ACC) to perform an independent ES&H review of the NCSX Project's readiness for operation.  A Safety Assessment Document (SAD) will be prepared to provide an overview of the operation; descriptions of structures, systems and components relevant to the operation, with emphasis on environment, safety and health (ES&H) features; identification of hazards associated with the operation and methods employed for their mitigation; and a description of how operations will be conducted with emphasis on ES&H features.  The SAD will be reviewed and approved by the PPPL Safety Review Committee and the ACC.  Based on its review of the SAD and operating plans and procedures, and physical walkdowns of the facility, the ACC will recommend to the PPPL ES&H Executive Board whether to issue a Safety Certificate to commence NCSX operations, including any limiting conditions (see ES&H Directive 5008, Section 11, Chapter 2).

Table A-4-2 provides a correlation between the existing NCSX-specific procedures and PPPL procedures.  In NCSX-specific procedures are intended to augment and/or supercede the existing PPPL procedures as indicated.

Table A-4-2 Correlation Between NCSX & PPPL Procedures and Guidelines

| NCSX-Specific Procedure and Guidelines | Corresponding PPPL Procedure | Modification |
| --- | --- | --- |
| NCSX-PROC-001, “Glossary” | ENG-029, “Technical Definitions and Acronyms” | Augments ENG-029 to include NCSX specific terms and acronyms |
| NCSX-PROC-002, “Configuration Control” |  |  |
| NCSX-PROC-003, “Interface Control” |  |  |
| NCSX-PROC-004, “NCSX Work Planning Form” | ENG-033, “Design Verification” ENG-032, “Work Planning Procedure” | Augments Attachment 4, “Objectives of and Documentation for Design Reviews, ” of ENG-033 Supercedes ENG-032 in its entirety |
| NCSX-PROC-005, “Electronic Signatures” |  |  |
| NCSX-PROC-006, “Supplier Site Postings” |  |  |
| NCSX Engineering Web Page, “Specifications”, http://www.pppl.gov/me/NCSX_Engineering/ | ENG-006, “Review and Approval of Specifications and Statements of Work” | Supercede Attachments 1& 2 of ENG-006 which provide specific specification and SOW formats. NCSX formats slightly modified. |

Martin, J.M., Systems Engineering Guidebook, CRC Press, 1996, pg. 3