Applicability

This procedure covers changes to the following controlled documents that define the functional or technical requirements, the design configuration of NCSX, or cost and schedule baselines associated with the technical baseline:

- The General Requirements Document (GRD);

- The NCSX “Design to” and “Build to” Specifications as defined in the Systems Engineering Management Plan (SEMP);

- Statements of Work (SOW) that provides the framework of contracts with suppliers;

- Controlled NCSX drawings and models that physically depict the NCSX configuration;

- Technical installation and assembly procedures;

- The NCSX cost and schedule baselines; and

- Relevant lower level NCSX design documents, e.g., calculations and analyses, ICDs, etc.

Introduction

This procedure describes how the changes to the NCSX Project baselines (technical, cost, and schedule) are processed and controlled.  A change request can be initiated by anyone associated with the Project.

As described in the NCSX Configuration Management Plan (NCSX-PLAN-CMP), the physical and functional description of the components, systems, and software/firmware comprise the “configuration” of the NCSX MIE Project.  The NCSX project and details of its design configuration is progressively described in greater detail and is placed under configuration control as it proceeds through the design process, fabrication, assembly, and installation.  The goal of the NCSX Configuration Management Program is to ensure that the configuration design evolution is controlled and that the documentation of the configuration design shown in electronic drawings and models accurately reflects what is installed in the field to the extent practicable.

All changes to project baselines will be accomplished by the electronic Engineering Change Proposal (ECP).  Evolutionary changes to baselines (technical, cost, and schedule), in which the design (and the associated cost and schedule impacts) advances in a level of detail, moving beyond but not necessarily changing that which is already under formal change control or adjustments due to actual cost and schedule performance against established baselines, will be handled by periodically updating the reference design to incorporate these developments.  These “omnibus” ECPs will be processed to capture multiple small changes.  Discrete and significant changes in which a change of thinking or understanding causes the project to change something that is already under formal configuration change control will be handled by stand-alone ECPs.

There are two main categories of ECPs.  The first type is the “standard” ECP that requires a full review and approval cycle via the NCSX Change Control Board (CCB).  The second type is the “expedited” ECP that may be approved only an abbreviated review.  Expedited ECPs are reserved for special instances where:

- If a pending critical procurement needs to reflect the proposed change;

- If field activities may be delayed by the normal ECP process involving full reviews and the CCB; or

- If the proposed change is primarily editorial or minor in nature (e.g., clarifications on drawings for dimensions, tolerances, etc.).

If an expedited ECP is deemed appropriate, the NCSX Engineering Manager, after consultation with the NCSX Project Manager, will be the  approving authority after an abbreviated review cycle defined by the Engineering Manager.  Nonetheless, following approval of an expedited ECP, the full CCB will review the ECP “after-the-fact” to ensure that major errors and/or omissions were not made.

The electronic version of the ECP form can be downloaded from an interactive Configuration Management Web Page that is a subordinate web page to the NCSX Engineering Web Page.   The ECP form has three sections:

- Cover Page providing ECP numbering and title, suggested reviewers, and the approval signature blocks.

- Part I to be filled in by the originator and submitted to the Systems Engineering Support Manager for processing.  Amplifying information to the ECP such as design memoranda that provide a rationale/need for the proposed change, sketches, Engineering Change Notices (ECN), and cost and schedule impacts are prepared and attached electronically.  Existing drawings or models or Interface Control Documents (ICDs) need only be referenced.  These attachments/referenced drawings/models or ICDs are prepared in accordance with the following plans and procedures:

  - Specifications – PPPL Engineering Procedure ENG-006, “Review and Approval of Specifications and Statements of Work”

  - Drawings and Models – Pro/INTRALINK Users Guide

  - Sketches and ECNs – PPPL Engineering Procedure ENG-010, “Control of Drawings, Software, and Firmware”

  - Cost and Schedule impacts – prepared using the Primavera Project Planner (P3) software.

- Part II to be completed by each reviewer.

Referenced Documents

| NCSX-PLAN-PEP | NCSX Project Execution Plan |
| --- | --- |
| NCTX-PLAN-CMP | NCSX Configuration Management Plan |
| NCSX-PLAN-DMP | NCSX Data Management Plan |
| NCSX-PLAN-DOC | NCSX Document and Records Plan |
| NCSX-PROC-001 | NCSX Procedure, Glossary of Acronyms and Definitions |
| PPPL- ENG-006 | PPPL Procedure on the Review and Approval of Specifications and Statements of Work |
| PPPL-ENG-010 | PPPL Procedure on Control of Drawings, Software, and Firmware |
| PPPL-ENG-033 | PPPL Procedure on Design Verification |
| NCSX-GUIDE-001 | NCSX Pro/INTRALINK Users Guide |

Procedure

Note:	NCSX documents do not all come under configuration control at the same time.  Rather, as appropriate for the stage of design, the documents and drawings and models will come under configuration in a phased manner, with the higher-level specifications and drawings coming under configuration control prior to lower-level specification and detailed drawings and models.

- Processing an ECP

| Responsibility | Action |
| --- | --- |
| Initiator (Anyone on the Project) | Identifies need for change to the NCSX technical, cost, or schedule baselines. Completes the electronic version of the NCSX ECP form, Part 1. Provides as much detail as necessary to adequately describe the proposed change. Electronic versions of the form may be found on the NCSX Configuration Management web page - accessible via the NCSX Engineering Web page at: http://www.pppl.gov/me/NCSX_Engineering/ . Guidelines for completing Part I of the ECP form is contained in Attachment 1 of this procedure. Continuation sheets may be used as necessary. Sends completed electronic Part I and any electronic attachments and continuation sheets to the Systems Engineering Support Manger for further processing. |
| Systems Engineering Support Manager | Reviews proposed change and, if required, requests additional amplifying information to complete the ECP package. |
| Initiator (as necessary) | Provides additional information requested. |
| Systems Engineering Support Manager | Based on information provided in Part I, determines whether this ECP should be processed as an “expedited” or “standard” ECP, the Change Level of this proposed change and the final approving official. Completes top portion of the electronic ECP Cover page. Guidelines are contained in Attachment 1 to this procedure. Once the change package (electronic Part I) is complete, fills out the top portion of the electronic ECP Cover Page. Guidelines are contained in Attachment 1 of this ECP. Posts the proposed ECP on the Configuration Management Web Page. If the ECP warrants an expedited review, immediately forward the ECP to the NCSX Engineering Manager and proceed to Step # 18. If not an “Expedited” ECP, proceeds to Step #11. Notifies all required reviewers via e-mail that the electronic version of the ECP is now posted on the Configuration Management web page. |
| Reviewer(s) | Completes electronic (Word) version of Part II of the ECP Form. Guidelines for the reviewers is contained in Attachment 1 this procedure. If corrections are needed, returns Part II to the Systems Engineering Support Manager, clearly identifying corrections needed (e.g., additional reviewers, correction to impact statements, etc.). Proceed to Step #15 If no corrections needed, indicate whether or not ECP is acceptable or rejected. If rejected, provide specific reasons why ejected. When review completed, electronically return completed Part II to the Systems Engineering Support Manager. Proceeds to Step #17. |
| Systems Engineering Support Manager | If reviewer indicates that corrections are needed, notifies other reviewers of pending corrections and then reviews recommended corrections and resolves them with the originator. When corrections made and/or resolved, returns ECP to the reviewers to continue the review process. If no corrections needed, receives reviewer comments/input and re-reviews ECP for completeness. Once complete, schedules a Change Control Board (CCB) meeting if deemed necessary. Acts as secretary for the CCB meeting. Enters ECP information into the ECP Tracking Log (Attachment 2) – annotates status on the ECP Tracking Log. If an expedited ECP, proceed to Step #19, otherwise proceed to Step #21 If an expedited ECP, sends ECP directly to the NCSX Engineering Manager for disposition. |
| Engineering Manager | Using information contained on the ECP and discussions with the initiator, either approves the change/recommends approval if DOE approval required or denies the change. Once a decision is made, completes the form and forwards the signed original to the Systems Engineering Support Manager for disposition (i.e., implementation notification, denial notification, or forwarding to DOE. Proceeds to Step #24 |
| CCB Chairman | Determines best method to complete the CCB review. Options include distributing form to committee members with specified response dates or formal committee meetings. Note: If the ECP is a Class 4 ECP, the CCB Chairperson (normally the NCSX Project Manager) is the approving official. If the ECP is a Class 3 or higher level ECP, DOE approval is required. Using information from the CCB members, either approves the change/recommends approval if DOE approval required or denies the change. The review process may include discussing concerns about the change with the ECP initiator. Once a decision is made, completes the form and forwards the signed original to the Systems Engineering Support Manager for disposition (i.e., implementation notification, denial notification, or forwarding to DOE. If a Class 4 ECP that can be approved by the CCB Chairman, disposition the ECP and proceed to Step #26. If DOE approval required, proceed to Step #25. |
| Systems Engineering Support Manager | If the ECP can be dispositioned by the NCSX Engineering Manager, updates the ECP Tracking Log and proceed to Step #26. If the ECP is a Class 3 or higher level ECP, requiring DOE approval, prepare the transmittal letter for NCSX Project Manager signature. Once the ECP is dispositioned by DOE, proceed to Step #26. Updates ECP Tracking Log (Attachment 2). Prepares and transmits notification of approval and implementation authorization or notification of denial to Project. Updates ECP Tracking Log (Attachment 2) indicating final disposition and prepares ECP Implementation Log (Attachment 3) for tracking detailed ECP implementation status. Post approved ECP on the Configuration Management web page. Monthly identify the implementation status of each ECP as part of the monthly status meetings to ensure visibility of the implementation of the ECP. |
|  | Notes: (1) PPPL Procedure ENG-010, Control of Drawings, Software, and Firmware, addresses the use of Engineering Change Notices (ECNs) for implementing changes to drawings and models released for fabrication. The ECN shall be provided as an attachment to the ECP to ensure that all impacted documents are listed on one ECP. (2) PPPL ENG-032, Work Planning Procedure, while not specifically applicable to design work, does have good check list of items to consider when proposing a change. The ECP form that is found on the Configuration Management Web Page, captures the applicable items from the Working Planning (WP) form. (3) The goal of the NCSX Configuration Management Program is to have the documentation accurately reflect the “as-built” condition in the field. However, cost and schedule considerations may preclude complete “as-built” verification. Rather on a case-by-case basis, the NCSX Engineering Manager may determine that “as-built” verification is required. |

## Attachments

Attachment 1:	Guidelines for Completing a NCSX ECP Form

Attachment 2:	ECP Tracking Log

Attachment 3:	ECP Implementation Log

Initiator of the ECP

The initiator of the ECP should complete Part I of the ECP and include the following information:

    - Originator:  Name of Person Initiating the ECP

    - Date:  Date ECP Prepared

    - Type of ECP:  Indicate whether this ECP should be “Expedited” or follow the standard ECP process.

    - Type of Change:  Check all blocks that are applicable => Technical, Cost, Schedule, or Editorial

    - Reason for Change:  Perovide a brief explanation on why the change is necessary.  If this is deemed to require an “expedited” approval, provide the rationale for recommending that this ECP be processed as an “expedited” ECP.

    - Impacted WBS Elements:  Identify impacted WBS element numbers (at least at the two digit WBS level)

    - Impact of Change:  Indicate the areas impacted by the proposed change.  A sample listing of the possible impacted areas is contained below.  A brief (1-2 sentences) should be used to describe the impact in each area.

        - Design (Including Interfaces)

        - Performance

        - Requirements

        - Vendor Contract Requirements

        - Cost

        - Schedule

        - Maintenance

        - ES&H

        - RAM

    - Assessment of Other Options:  Provide brief discussion of other options considered and why this option selected

    - Detailed Description of Change:  Using the continuation page if needed, provide a reasonably detailed explanation of the change, including:

  - List of Attachments

  - List of Impacted Documents

  - List of Analyses (be specific) – examples might include:

- Seismic Analysis

- Thermal Analysis

- Eddy Current Force Analysis

- Mechanical Analysis

- FMECA (ENG-008)

- Radiation/neutron Analysis

- Other calculations (specify)

  - List of Safety-Related Documents – examples might include:

      - NEPA (ESH-014)

      - Hazard Controls (e.g. USQD, SAD) (ESHD 5008, sec 11)

      - Job Hazard Analysis

  - List Interface Control Documents (list each one separately)

    - Requests for Additional Information:  If requested, provide additional information.

Systems Engineering Support Manager

Upon receipt of the final electronic version of Part I of the  ECP form from the originator, the Systems Engineering Support Manager should complete the ECP cover page.  The information that should provided on the ECP cover page includes:

- The identity of the  initiator of the ECP and Date ECP was prepared

- The ECP Number in accordance with the scheme outlined in the CMP

- The ECP Title that is descriptive of the proposed change

- Any amplifying comments to assist in the review and disposition of the proposed change

- Identifying required reviewers. If the ECP is deemed to warrant “expedited” ECP processing, the ECP should be forwarded immediately to the NCSX Engineering Manager for his review and disposition.  If not, the ECP should be processed in accordance with Steps

- Provides any amplifying comments to assist in the review and disposition of the proposed change

Upon receipt of the reviewer comments, the Systems Engineering Support Manager should:

Reviewer(s)

Upon receipt of the final electronic version of the Cover Page and Part I of the ECP form from the Systems Engineering Support Manager, each reviewer should download Part II of the ECP form from the NCSX Configuration Management Web page that is accessible via the NCSX Engineering Web page located at:  http://www.pppl.gov/me/NCSX_Engineering/ .  The reviewer should complete the Part II form to include the following information:

- ECP Number and Title:  Fill out ECP Number and Title.

- Reviewer Name:  Fills in reviewer name.

- Corrections Needed?:  Check block indicating whether or not corrections needed.

  - If corrections needed (e.g., additional reviewers, correction to impact statements, etc. and the specific corrections needed), electronically returns Part II to Systems Engineering Manager for recycling ECP to obtain corrections needed.

  - If no corrections needed, check block on whether or not the reviewer concurs in the ECP.  Provide reason for the rejection recommendation.

- Other Recommendations?:  Identify if there are other recommendations (e.g., modified ECP to include other impacted documents, etc. and specifically identify those recommendations.

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) Implementation Log Status Date: |
| --- |
| ECP No: | ECP Title: |
| Document | Revised? | Date Revised | Revision Number |
| Requirements Documents GRD Specifications (List Each) Spec Spec Procurement Documents | ( Yes ( No ( Yes ( No ( Yes ( No ( Yes ( No |  |  |
| Drawings/Model ECN #=> Dwg # ECN #=> Dwg # | ( Yes ( No ( Yes ( No |  |  |
| Environmental Documents EA SAD | ( Yes ( No ( Yes ( No |  |  |
| Cost Baseline | ( Yes ( No |  |  |
| Schedule Baseline | ( Yes ( No |  |  |