Applicability

This procedure is applicable to the entire NCSX Project.

Introduction

The NCSX Systems Engineering Management Plan (SEMP) provides the project’s approach to design reviews.  On NCSX, both external and internal design reviews are planned.  External design reviews are determined by DOE and conducted to support DOE Critical Decisions.  Internal design reviews are conducted to assess the technical adequacy of the configuration baseline as it is developed, consistent with ENG-033 Design Verification and P-010 Design Reviews.  These reviews verify the proper development, establishment, and control of the configuration baseline.  They are used to verify conformance with requirements for each configuration item (CI).  They also serve as an appropriate point to update project technical, cost, and schedule baselines.

The key work planning document during Preliminary and Final Design is the Systems Engineering Master Logic (SEML).  The SEML defines the logic for design development. The SEML documents this logic in the form of a checklist of activities and deliverables that need to be completed during the Preliminary and Final Design phases of subsystem and component design. The SEML will address:

- Design review objectives and inputs identified in PPPL Design Verification Procedure ENG-033 (tailored to the subsystem or component being designed);

- Elements in the ENG-032 Work Planning Procedure ENG-032 that are appropriate for design activities;

- Guidance provided by NCSX Project Management

The activities and deliverables in the SEML are addressed by WBS Managers in the development of the detailed WAF schedules and completed prior to the next major design review (PDR or FDR). There will be one SEML developed for each major design review.  PPPL Work Planning Forms (WPs) will be used (not SEMLs) for planning all field work (including on-site R&D activities during Preliminary and Final Design) and during the Fabrication, Installation, and Test phase following Final Design, as required by ENG-032 Work Planning.

This procedure basically consists of two subprocedures.  The first subprocedure is to identify the configuration items (subsystems and major components) in the design development and to align the specifications, design reviews, and acquisition plans with the configuration items. The second subprocedure establishes the procedure for development, review, and approval of SEMLs. The attachments to this procedure provide generic guidance for the elements that should be included in SEMLs prepared for Preliminary and Final Design.

Referenced Documents

NCSX Systems Engineering Management Plan (NCSX-PLAN-SEMP)

PPPL Policy 010, “Design Reviews”

PPPL Procedure ENG-032, “Work Planning”

PPPL Procedure ENG-033, “Design Verification”

ES&HD Section 11 Chapter 1 “Operations Hazard Criteria”

Procedure for Configuration Item (CI) Identification

This procedure for CI identification is as follows.  This procedure is done once, before development of the first SEML.

| Responsibility | Action |
| --- | --- |
| WBS Manager | 1. Determines how the subsystem design will be accomplished. Configuration items are defined. Specifications, formal design reviews, and acquisition plans are aligned with the CI identification. |
| Cognizant Project Engineer | Reviews proposed CI identification and upon reconciling issues, concurs and forwards the SEML to the Engineering Manager. |
| Engineering Manager | Approves proposed CI identification. Establishes responsible official (cognizant Project Engineer or Engineering Manager) for approving specifications and coordinating design reviews for each CI. |
| Systems Engineering Support Manager | Updates spec tree and schedule of design reviews on Engineering Web. |
| Project Control Manager | Updates detailed schedule to include major design reviews and acquisitions consistent with approved CI identification. |

## Procedure for SEML Development, Review, and Approval

The procedure for SEML development, review, and approval is as follows.

| Responsibility | Action |
| --- | --- |
| WBS Manager | Develops a detailed SEML appropriate for each design phase and configuration item (one per design review) using the templates provided in the attachments to this procedure. The SEML should contain a detailed list of required accomplishments and associated documentation to be provided before the design review is scheduled. |
|  | Forwards SEML to the cognizant Project Engineer for review, comment, and concurrence. |
| Cognizant Project Engineer | Reviews proposed SEML and upon reconciling issues, concurs, and forwards the SEML to the Systems Engineering Support Manager. |
| Systems Engineering Support Manager | Reviews proposed SEML and upon reconciling issues, concurs and forwards the SEML to the Engineering Manager. |
| Engineering Manager | Reviews proposed SEML and upon reconciling issues, approves and forwards the SEML to the Systems Engineering Support Manager for posting. (Skip this step if the cognizant Project Engineer is the responsible official for this CI.) |
| Systems Engineering Support Manager | Posts the approved SEML on the Engineering Web. |
| WBS Manager | Utilizes the approved SEML as a basis for generating WAFs and preparing for major design reviews. |

## Attachments

  - Generic SEML for Preliminary Design

  - Generic SEML for Final Design

| Item | Requirement | Success Criteria |
| --- | --- | --- |
| Configuration Identification | Identify configuration items (CIs). Include software, support equipment, and tooling. Align specifications, design reviews, and acquisition plans with CI identification. Acquisition plans should address build v. buy issues. | Spec tree, design review schedule, and acquisition plans updated and posted on Web. Project detailed schedule updated by PC Mgr. |
| Specifications | Performance requirements are finalized and documented in approved development ("design-to") specifications , which are under change control. No TBDs allowed. | Approved by responsible official |
| Design vs. Requirements | Document design approach. Demonstrate how the design concept satisfies requirements and design constraints in the relevant development specifications. | Documented in Design Basis Document prior to PDR. Approved by cognizant Project Engineer. |
| Resolution of Design Recommendations | Document resolution of chits from prior design reviews. | Resolution of chits from prior design reviews documented on Web. Action items completed. |
| Interface Identification | Signed scope sheets for all primary interfaces. No TBDs allowed. | Approved by Systems Engineering Support Manager |
|  | Signed ICDs for all primary interfaces. TBDs allowed with closure plans. | Approved by Systems Engineering Support Manager |
| Models and Drawings | Sufficient drawings to support developmental design and analytical evaluation of the inherent ability of the design to attain the required performance. The drawings shall be sufficient to develop manufacturing approaches and cost estimates. All models and drawings promoted to Preliminary Design Release. Drawings shall be provided which define where the equipment will be located in the facility. Preliminary Design Release models and drawings should form a self-consistent package and provide the basis for cost and schedule estimates. | Models and drawings approved for promotion by the cognizant Project Engineer |
|  | Develop a drawing tree with at least enough detail to identify all components necessary to support final design and production planning. | Approved by the cognizant Project Engineer |

| Item | Requirement | Success Criteria |
| --- | --- | --- |
| Analysis | Design criteria to establish limits for acceptability are in place. Sufficient analysis shall be provided to establish that the proposed design is feasible and meets established design criteria. Analyses must be documented in an auditable way – in analysis reports, not viewgraph presentations. The following analyses shall be accomplished as appropriate: structural, thermal, seismic, eddy current, radiation, and circuit analyses. Other analyses shall be included as appropriate. | Design criteria documented. Material properties characterized and documented. Analysis reports reviewed by cognizant Project Engineer, summarized in Design Basis Document. |
| Manufacturability | Provide evidence (if necessary) from R&D activities that the design is manufacturable and has been optimized for manufacturability. | Manufacturing studies conducted as appropriate and results documented in Design Basis Document. |
| Qualification and Acceptance Testing | Qualification and acceptance test plans consistent with verification requirements in the development specifications. Identify when these tests would be performed. These plans provide the basis for subsequently developing test procedures. | Qualification and acceptance test plans documented. |
| Constructability | Document plans for assembly, installation, and test. Provide evidence that risk-related issues have been satisfactorily addressed. These plans provide the basis for subsequently developing assembly, installation, and test procedures. | Assembly, installation, and test plans documented. |
| Value Engineering | Determine what design areas would likely benefit from additional value engineering at the beginning of Preliminary Design. Conduct and document results of value engineering studies (if any). | Results of value engineering studies (if any) documented in Design Basis Document. |
| RAM | Provide FMECA per ENG-008 identifying potential failure modes and recovery provisions. Explain how design has been optimized for reliability, maintainability, and safety through systematic evaluation of design options and application of proven design approaches. | FMECA documented. Summary of findings and design recommendations provided in Design Basis Document. |

| Item | Requirement | Success Criteria |
| --- | --- | --- |
| ES&H | Provide a hazard analysis that address the following: 1. Descriptions of the environment, safety and health (ES&H) features of structures, systems and components, as applicable. 2. Identification of hazards associated with anticipated operation of the structure, system or component and methods employed for their mitigation. 3. Some description of the ES&H aspects of operations, e.g., access controls, setting of hardwired interlocks, operator actions, etc. The depth of the discussions of these topics should be commensurate with the potential severity of the specific hazards, and with the maturity of the designs. The hazard analysis report should address ES&H issues identified in the FMECA. Review existing NEPA documentation. Submit new NEPA Planning Form if new hazards are identified. | Report documenting hazard analysis. Approved by NCSX ES&H Manager. |
| COTS and Legacy Equipment | Identify use of COTS commercial, off-the-shelf (COTS) or legacy equipment. Describe plan for testing the performance of legacy equipment. | Documented in Design Basis Document. |
| Human Engineering | Demonstrate that sound human engineering principles have been followed in the design. | Documented in Design Basis Document. |
| Standardization Considerations | Identify how design has been optimized for standardization, including a list of standardized components | Documented in Design Basis Document. |
| Software and Firmware | Identify and describe all planned software and firmware, including the functional requirements allocated to them. | Documented in Design Basis Document. |
| Preliminary Weight and Size Data | Demonstrate that weight and sizes are compatible with structural supports and size constraints | Documented in Design Basis Document. |
| Risk Management | Identify areas of significant risk and mitigation plans | Documented in Design Basis Document. |
| Baseline Maintenance | Update cost and schedule estimates in P3 database consistent with proposed technical baseline as defined by Preliminary Design Release Level models and drawings and other documentation. Cost and schedule updates should generally be of a higher quality than the prior estimate with increased input from industry. | Approved by the cognizant Project Engineer. Coordinated with Engineering Manager. Incorporated in P3 database by Project Control Manager. |
|  | Provide input to omnibus ECP to reflect proposed changes to the technical, cost, and schedule baselines. ECP will be processed after chits that have significant design, cost, or schedule impacts have been addressed. New baselines will be established upon approval of ECP and implementation of approved changes. | Approved by the cognizant Project Engineer. Coordinated with the Engineering Manager. |

| Item | Requirement | Success Criteria |
| --- | --- | --- |
| Configuration Identification | Confirm that all relevant configuration items (CIs) have been identified, relevant specifications aligned, supporting design reviews performed, and necessary acquisition plans prepared. | Spec tree, design review schedule, and acquisition plans updated and posted on Web. Project detailed schedule updated by PC Mgr. |
| Specifications | Performance requirements are finalized and documented in approved product ("build-to") specifications , which are under change control. No TBDs allowed. | Approved by responsible official |
| Design vs. Requirements | Document design approach. Demonstrate how the design concept satisfies requirements and design constraints in the relevant development specifications. | Documented in Design Basis Document prior to FDR. Approved by cognizant Project Engineer. |
| Resolution of Design Recommendations | Document resolution of chits from prior design reviews. | Resolution of chits from prior design reviews documented on Web. Action items completed. |
| Interface Identification | Signed scope sheets for all primary interfaces and all closure plans completed. No TBDs allowed. | Approved by Systems Engineering Support Manager |
| Models and Drawings | Sufficient drawings to support developmental design and analytical evaluation of the inherent ability of the design to attain the required performance. The drawings shall be sufficient to develop manufacturing approaches and cost estimates. All models and drawings promoted to Final Design Release. Drawings shall be provided which define where the equipment will be located in the facility. Final Design Release models and drawings should form a self-consistent package and provide the basis for cost and schedule estimates. | Models and drawings approved for promotion by the cognizant Project Engineer |
|  | Confirm that all necessary drawings outlined on the drawing tree necessary to support final design and production planning are completed.. | Approved by the cognizant Project Engineer |

| Item | Requirement | Success Criteria |
| --- | --- | --- |
| Analysis | All required analysis shall be provided and checked to establish that the proposed design is feasible and meets established design criteria. Analyses must be documented in an auditable way – in analysis reports, not viewgraph presentations. | Design criteria documented. Material properties characterized and documented. Analysis reports reviewed by cognizant Project Engineer, summarized in Design Basis Document. |
| Manufacturability | Provide evidence (if necessary) from R&D activities that the design is manufacturable and has been optimized for manufacturability. | Manufacturing studies conducted as appropriate and results documented in Design Basis Document. |
| Qualification and Acceptance Testing | Qualification and acceptance test plans consistent with verification requirements are documented in the product specifications. Identify when these tests would be performed. These plans provide the basis for subsequently developing test procedures. | Qualification and acceptance test plans documented by the FDR. |
| Constructability | Document plans for assembly, installation, and test. Provide evidence that risk-related issues have been satisfactorily addressed. These plans provide the basis for subsequently developing assembly, installation, and test procedures. | Assembly, installation, and test plans documented and scheduled by the FDR.. |
| Value Engineering | Determine what design areas would likely benefit from additional value engineering at the beginning of Final Design. Conduct and document results of value engineering studies (if any). | Results of value engineering studies (if any) documented in Design Basis Document. |
| RAM | Provide any updates to the FMECA prepared for Preliminary Design. Explain how design has been optimized for reliability, maintainability, and safety through systematic evaluation of design options and application of proven design approaches. | FMECA documented. Summary of findings and design recommendations provided in Design Basis Document. |

| Item | Requirement | Success Criteria |
| --- | --- | --- |
| ES&H | Update any hazard analyses prepared for Preliminary Design and any new hazard analyses that address the following: 1. Descriptions of the environment, safety and health (ES&H) features of structures, systems and components, as applicable. 2. Identification of hazards associated with anticipated operation of the structure, system or component and methods employed for their mitigation. 3. Some description of the ES&H aspects of operations, e.g., access controls, setting of hardwired interlocks, operator actions, etc. The depth of the discussions of these topics should be commensurate with the potential severity of the specific hazards, and with the maturity of the designs. Submit new NEPA Planning Form if new hazards are identified. | Report documenting hazard analysis. Approved by NCSX ES&H Manager. |
| COTS and Legacy Equipment | Identify use of COTS commercial, off-the-shelf (COTS) or legacy equipment. Document the testing performed to verify the adequacy of the performance of legacy equipment. | Documented in Design Basis Document. |
| Human Engineering | Demonstrate that sound human engineering principles have been followed in the design. | Documented in Design Basis Document. |
| Standardization Considerations | Identify how design has been optimized for standardization, including a list of standardized components | Documented in Design Basis Document. |
| Software and Firmware | Identify and describe all planned software and firmware, including the functional requirements allocated to them. | Documented in Design Basis Document. |
| Preliminary Weight and Size Data | Demonstrate that weight and sizes are compatible with structural supports and size constraints | Documented in Design Basis Document. |
| Risk Management | Identify areas of significant risk and mitigation plans. | Documented in Design Basis Document. |
| Baseline Maintenance | Update cost and schedule estimates in P3 database consistent with proposed technical baseline as defined by Preliminary Design Release Level models and drawings and other documentation. Cost and schedule updates should generally be of a higher quality than the prior estimate with increased input from industry. | Approved by the cognizant Project Engineer. Coordinated with Engineering Manager. Incorporated in P3 database by Project Control Manager. |
|  | Provide input to omnibus ECP to reflect proposed changes to the technical, cost, and schedule baselines. ECP will be processed after chits that have significant design, cost, or schedule impacts have been addressed. New baselines will be established upon approval of ECP and implementation of approved changes. | Approved by the cognizant Project Engineer. Coordinated with the Engineering Manager. |