Applicability

This procedure is applicable to the entire NCSX Project.

Introduction

This procedure provides the NCSX Project requirements for design verification and work planning.  This procedure is intended to supplement PPPL Procedures ENG-032, Work Planning and ENG-033, Design Verification.

ENG-033, Design Verification, identifies design review objectives and input documentation for formal design reviews, i.e. a Conceptual Design Review (CDR), Preliminary Design Review (PDR) and Final Design Review (FDR).  ENG-032, Work Planning, establishes criteria by which work planning will proceed, integrates safety into all work planning, organizes the avenues by which changes will be planned, prepared, reviewed, implemented, and documented into a systematic whole, and provides key cross references to other lab procedures to expedite the planning process.  ENG-032 applies to all activities at PPPL involving physical changes to engineering, facilities, control computing, and technical infrastructure and equipment or involving collaborations for others. It is not directly applicable to work performed during the conceptual, preliminary, or final design phases.

The purpose of this procedure is to establish project-specific objectives and input documentation requirements for formal design reviews, using ENG-033 as a guide, and to integrate the important considerations for work planning, identified in ENG-032, into design activities.  ENG-032 will be used directly for all activities to which it applies.

To achieve this purpose, the NCSX Project will use a Systems Engineering Master Logic (SEML).  The SEML documents the accomplishment criteria for all critical tasks and milestones.  The detailed tasks required to satisfy the criteria in the SEML should to be identified in the Work Authorizations Forms (WAFs) that are initiated and approved to authorize the work.  The content of the SEML will be defined by the Engineering Manager, Systems Engineering Support Manager, Project Engineers, and WBS Managers.

Systems Engineering will define the objectives and input documentation required for formal design reviews.   These will be documented in generic SEMLs for Preliminary Design and Final Design.  The generic SEMLs will identify (in the checklist fashion of ENG-032) important considerations in work planning such as:

- Interfaces, both internal and external to the Project

- Design documentation (e.g. specifications, drawings, and bills of materials)

- Required analyses and calculation checking

- Safety considerations, analyses, and documentation

- Required procedures, tests, support, and training

The generic SEMLs will be used as a basis for generating detailed SEMLs for each configuration item and each design phase.  The detailed SEMLs should be in place near the start of each design activity in time for the necessary work to be planned and authorized.  Formal design reviews will be scheduled when the accomplishment criteria are satisfied or can confidently be projected to be satisfied.  The procedure for conducting formal design reviews (and peer reviews) is defined in ENG-033.  Project-specific objectives and input documentation for formal design reviews are defined in Attachment 1.  Generic SEMLs for Preliminary and Final Design are provided in Attachment 2.  The procedure for preparing a SEML is defined in the following section.

Procedure

This procedure for SEML preparation is as follows:

| Responsibility | Action |
| --- | --- |
| WBS Manager | 1. Determines how the subsystem design will be accomplished. Configuration items are defined. Specifications and formal design reviews and specifications are aligned with the configuration item identification. |
|  | Develops a detailed SEML appropriate for each design phase and configuration item (one per design review) using the templates provided in Attachment 1. Provides detailed list of required accomplishments and associated documentation to be provided for the design review. |
|  | Forwards SEML to the cognizant Project Engineer for review, comment, and concurrence. |
| Cognizant Project Engineer | Reviews proposed SEML and upon reconciling issues, concurs and forwards the SEML to the Systems Engineering Support Manager. |
| Systems Engineering Support Manager | Reviews proposed SEML and upon reconciling issues, concurs and forwards the SEML to the Engineering Manager. |
| Engineering Manager | Reviews proposed SEML and upon reconciling issues, approves and forwards the SEML to the Systems Engineering Support Manager for posting. |
| Systems Engineering Support Manager | Posts the approved SEML on the Engineering Web Page. |
| WBS Manager | Utilizes the approved SEML as a basis for work planning and authorization. |

|  |  | Entry Data (Exit Data) |  | Page 1 of 5 |
| --- | --- | --- | --- | --- |
| Item | Point of Contact | Requirement | Success Criteria | Job # |
| Specifications | WBS Manager | All relevant development ("design-to") specifications are approved and under change control. No TBDs allowed. | Approved by the Cognizant Project Engineer and the Engineering Manager |  |
|  |  | A road map is provided which shows when other equipment specifications will be developed and other design reviews will be held. | Approved by the Cognizant Project Engineer. Coordinated with the Engineering Manager. |  |
|  |  | Applicable chits closed | Approved by PDR chair |  |
| Configuration Identification | WBS Manager | Develop an equipment/spec tree identifying all known/anticipated equipment. Identify whether a specification is anticipated, what type of specification, and the responsible individual. Include software and support equipment as well as hardware. | Approved by the Cognizant Project Engineer. Coordinated with the Engineering Manager. |  |
|  |  | Applicable chits closed | Approved by PDR chair |  |
| Design vs. Requirements | WBS Manager | Demonstrate how the design concept satisfies each requirement and design constraint in the relevant development specifications. | Approved by the Cognizant Project Engineer |  |
|  |  | Applicable chits closed | Approved by PDR chair |  |
| Interface Identification | WBS Manager | Signed scope sheets for all primary interfaces. No TBDs allowed. | Approved by Systems Engineering Support Manager |  |
|  |  | Signed ICDs for all primary interfaces. TBDs allowed with closure plans. | Approved by Systems Engineering Support Manager |  |
|  |  | Applicable chits closed | Approved by PDR chair |  |

|  |  | Entry Data (Exit Data) |  | Page 2 of 5 |
| --- | --- | --- | --- | --- |
| Item | Point of Contact | Requirement | Success Criteria | Job # |
| Models and drawings | WBS Manager | Develop a drawing tree with at least enough detail to identify all components necessary to support final design and production planning. The drawing tree should have a numbering system which correlates to the equipment/spec tree. | Approved by the Cognizant Project Engineer |  |
|  |  | Sufficient drawings to support developmental design and analytical evaluation of the inherent ability of the design to attain the required performance. The drawings shall be suffcient to develop manufacturing approaches and cost estimates. All models and drawings promoted to Preliminary Design Release. Drawings shall be provided which define where the equipment will be located in the facility. Preliminary Design Release models and drawings should form a self-consistent package and provide the basis for cost and schedule estimates. | Models and drawings approved for promotion by the Cognizant Project Engineer |  |
|  |  | Develop a drawing tree with at least enough detail to identify all components necessary to support final design and production planning. | Approved by the Cognizant Project Engineer |  |
|  |  | Applicable chits closed | Approved by PDR chair |  |
| Design Basis | WBS Manager | Design criteria to establish limits for acceptability are in place. Sufficient analysis shall be provided to establish that the proposed design is feasible and meets established design criteria. Analyses must be documented in an auditable way - not a viewgraph presentation. The following analyses shall be accomplished (or reasons given for not performing): Seismic Analyses Thermal Analyses Eddy Current Force Analyses Radiation/Neutron Calculations Other Calculations (specifiy) | Approved by the Cognizant Project Engineer |  |
|  |  | Applicable chits closed | Approved by PDR chair |  |

|  |  | Entry Data (Exit Data) |  | Page 3 of 5 |
| --- | --- | --- | --- | --- |
| Item | Point of Contact | Requirement | Success Criteria | Job # |
| Qualification and Acceptance Testing | WBS Manager | Qualification and acceptance test plans consistent with verification requirements in the development specifications. Identify when these tests would be performed. These plans provide the basis for subsequently developing test procedures. | Approved by the Cognizant Project Engineer |  |
|  |  | Applicable chits closed | Approved by PDR chair |  |
| Manufacturability | WBS Manager | Provide evidence (if necessary) from R&D activities that the design is manufacturable and has been optimized for manufacturability. | Approved by the Cognizant Project Engineer |  |
|  |  | Applicable chits closed | Approved by PDR chair |  |
| Constructability | WBS Manager | Document plans for assembly, installation, and test. Provide evidence that risk-related issues have been satisfactorily addressed. These plans provide the basis for subsequently developing assembly, installation, and test procedures. | Approved by Cognizant Project Engineer(s) |  |
|  |  | Applicable chits closed | Approved by PDR chair |  |
| Transportability | WBS Manager | Determine feasibility of transportability. Identify any environmental factors such as shock, temperature, moisture, dust, etc. during transport that require mitigating provisions. | Approved by the Cognizant Project Engineer |  |
|  |  | Applicable chits closed | Approved by PDR chair |  |
| Value Engineering | WBS Manager | Determine what design areas would likely benefit from additional value engineering at the beginning of Preliminary Design. Conduct and document results of value engineering studies (if any). | Approved by the Cognizant Project Engineer |  |
|  |  | Applicable chits closed | Approved by PDR chair |  |
| RAM | WBS Manager | Provide FMECA per ENG-008 identifying potential failure modes and recovery provisions. Explain how design has been optimized for reliability, maintainability, and safety through systematic evaluation of design options and application of proven design approaches. | Approved by the Cognizant Project Engineer |  |
|  |  | Applicable chits closed | Approved by PDR chair |  |

|  |  | Entry Data (Exit Data) |  | Page 4 of 5 |
| --- | --- | --- | --- | --- |
| Item | Point of Contact | Requirement | Success Criteria | Job # |
| ES&H | WBS Manager | Identify hazards and mitigating features, including any special hazards controls needed or comtemplated | Approved by the the Cognizant Project Engineer and NCSX ES&H Manager |  |
|  |  | Complete NEPA Planning Form per ESH-014 | Approved by the the Cognizant Project Engineer and NCSX ES&H Manager |  |
|  |  | Complete Job Hazards Analysis (JHA) Form per ESH-004 | Approved by the the Cognizant Project Engineer and NCSX ES&H Manager |  |
|  |  | Applicable chits closed | Approved by PDR chair |  |
| Human Engineering | WBS Manager | Demonstrate that sound human engineering principles have been followed in the design of the modular coils | Approved by the Cognizant Project Engineer |  |
|  |  | Applicable chits closed | Approved by PDR chair |  |
| COTS and Legacy Equipment | WBS Manager | Identify use of COTS commercial, off-the-shelf (COTS) or legacy equipment. Describe plan for testing the performance of legacy equipment. | Approved by the Cognizant Project Engineer |  |
|  |  | Applicable chits closed | Approved by PDR chair |  |
| Standardization Considerations | WBS Manager | Identify how design has been optimized for standardization, including a list of standardized components | Approved by the Cognizant Project Engineer |  |
|  |  | Applicable chits closed | Approved by PDR chair |  |
| Software and Firmware | WBS Manager | Identify and describe all planned software and firmware, including the functional requirements allocated to them. | Approved by the Cognizant Project Engineer |  |
|  |  | Applicable chits closed | Approved by PDR chair |  |
| Preliminary Weight and Size Data | WBS Manager | Demonstrate that weight and sizes are compatible with structural supports and size constraints | Approved by the Cognizant Project Engineer |  |
|  |  | Applicable chits closed | Approved by PDR chair |  |
| Risk Management | WBS Manager | Identify areas of significant risk and mitigation plans | Approved by the Cognizant Project Engineer |  |
|  |  | Applicable chits closed | Approved by PDR chair |  |

|  |  | Entry Data (Exit Data) |  | Page 5 of 5 |
| --- | --- | --- | --- | --- |
| Item | Point of Contact | Requirement | Success Criteria | Job # |
| Baseline Maintenance | WBS Manager | Update cost and schedule estimates in P3 database consistent with proposed technical baseline as defined by Preliminary Design Release Level models and drawings and other documentation. Cost and schedule updates should generally be of a higher quality than the prior estimate with increased input from industry. | Approved by the Cognizant Project Engineer. Coordinated with Engineering Manager. Incorporated in P3 database by Project Control Manager. |  |
|  | WBS Manager | Provide input to omnibus ECP to reflect proposed changes to the technical, cost, and schedule baselines. ECP will be processed after chits which have significant design, cost, or schedule impacts have been addressed. New baselines will be established upon approval of ECP and implementation of approved changes. | Approved by the Cognizant Project Engineer. Coordinated with the Engineering Manager. |  |
|  |  | Applicable chits closed | Approved by PDR chair |  |
|  | Systems Engineering Support Manager | Process ECP to establish new baselines and implement approved changes | Approved by CCB |  |
| Supporting Events |  |  |  |  |

| Level of Review | Objectives | Inputs for Design Review |
| --- | --- | --- |
| Peer and Prototype Review | The objectives for any peer review might include a subset of the following: Communicate a proposed change to a requesting or performing group. Assure that the proper requirements are identified. Requirements should include functional, ES&H, regulatory, quality, reliability, interfaces, project specific, test, cost, and schedule. Assures that the documentation (drawings and specifications) that will provide the technical basis of the procurement contract is consistent with the established design and accurately reflects the desired design concept. Identify hazards associated with the work or its impact on operations and appropriate mitigation, including NEPA or Job Hazards Analysis documentation needed. Alert impacted organizations or systems and others (e.g. ES&H, QA, ER/WM) of a the change in order to clarify group responsibilities within the change. Discuss resources, schedule, and cost. | Updated Work Planning form, if applicable. Documented requirements, if required by WP. Otherwise, requirements presented as part of review presentation. Identified hazards and appropriate mitigation techniques, including completed NEPA Review and Job Hazards Analysis forms, if required. Set of drawings and specifications proposed to be included in the procurement package. Formal drawings, to level required to proceed with procurement/ fabrication/ assembly as applicable. Examples are P&IDs and schematics. Drawings should be checked but need not be signed pending outcome of review and chit resolution. Updated resources, schedule and costs |

| Level of Review | Objectives | Inputs for Design Review |
| --- | --- | --- |
| Conceptual (CDR) | Assure that the proper requirements are identified and can be satisfied within acceptable envelops. Requirements should include functional, ES&H, regulatory, quality, reliability, interfaces, project specific, and test Review development and design plans and schedules. Review cost and schedule estimates, including contingencies. Review configurations or designs that are novel to PPPL. Obtain input when competing design approaches exist. Identify hazards associated with the work or its impact on operations and appropriate mitigation Review and discuss key ES&H considerations Review and assure that appropriate design and development plans and schedules have been developed. Discuss resources, schedule, and cost. | Updated Work Planning form, if applicable. Draft Project Execution Plan, if applicable Requirements. Design and development plan consistent with the requirements. Resource, schedule, and cost estimates consistent with the requirements. Resolution of chits from prior reviews, if any. Completed NEPA Review Form and Job Hazards Analysis forms, if applicable Present the results of key design analyses/calculations to verify the proposed design concept. These analyses and calculations should include a subset of the following: Seismic Analysis Thermal Analysis Eddy Current Force Analysis Mechanical Analysis Radiological/Neutron Analysis Other Calculations (specify) |

| Level of Review | Objectives | Inputs for Design Review |
| --- | --- | --- |
| Preliminary (PDR) | Verify that all requirements are being addressed. Identify requirements or design conflicts and potential "show-stoppers".. Review the results of analyses, calculations, and tests conducted to obtain additional information for the design. Review the ability to implement the proposed design taking into consideration capabilities, tolerances, costs, quality, reliability, and ES&H. Review procurement issues, e.g. build vs. buy. Review test requirements and plans. Review updated design and development plans and schedules. Assure the appropriate incorporation of recommendations from previous design reviews. Review manufacturability. Review updated resource requirements and cost and schedule estimates. | Updated Work Planning form, if applicable. Resolution of CDR Chits, if any Requirement changes since CDR, if held. Otherwise, requirements. Documentation defining proposed design approach. Design and development information. Results of calculations upon which design is based. These analyses and calculations should include a subset of the following: Seismic Analysis Thermal Analysis Eddy Current Force Analysis Mechanical Analysis Radiological/Neutron Analyses Other calculations (specify) Design plans. Updated cost & schedule estimates. Drawings, as appropriate. List of identified procurements and build vs. buy decision. Completed NEPA Review Form and Job Hazards Analysis forms, if applicable Completed Environmental Assessment (EA) or Environmental Impact Statement (EIS), as required. |

| Level of Review | Objectives | Inputs for Design Review |
| --- | --- | --- |
| Final (FDR) | Verify that the final design satisfies the requirements and is ready for implementation. Assure that detailed analyses, calculations, and tests to validate the design are complete and documented. Verify, as appropriate, that the final product can be manufactured, inspected, assembled, stored, delivered, and installed reliably, safely, and cost effectively. Verify that procurement issues have been identified and resolved. Verify that appropriate documentation is available for producing the final product (e.g. drawings, installation procedures). Verify that appropriate test plans for the final product have been established. Assure the appropriate incorporation of recommendations from previous design reviews. Review manufacturability. Review updated resource requirements and cost and schedule estimates. | Updated Work Planning form, if applicable. Resolution of PDR Chits, if any Requirement changes since PDR, if held. Otherwise, requirements. Documentation defining final design approach. Documented and checked calculations upon which design is based. These analyses and calculations should include a subset of the following: Seismic Analysis Thermal Analysis Eddy Current Force Analysis Mechanical Analysis Radiological/Neutron Analyses Other calculations (specify) Formal drawings, to level required to proceed with procurement/ fabrication/ assembly as applicable. Examples are P&IDs and schematics. Drawings should be checked but need not be signed pending outcome of review and chit resolution. Revised cost and schedule estimates. Documentation of tests to be performed. Completed Safety Assessment Document (SAD), as required. |