| Item | Requirement | Success Criteria |
| --- | --- | --- |
| Specifications and drawings | Documentation (specifications and drawings) required for product acquisition (to build or buy) is complete. Product ("build-to") specifications are approved and under change control. No TBDs allowed. The NCSX Systems Engineering Management Plan (SEMP) and the NCSX Engineering Web page (specifications provides guidance on content and format of these specs. All models and drawings should be checked (reviewed for consistency, completeness, and adherence to drawing standards) and promoted to Final Design Release level. Drawings need not be signed (promoted to Fabrication Release Level) pending outcome of the review and chit resolution. The NCSX Pro/INTALINK Users Guide provides information on handling models and drawings. | Documentation package for product acquisition is complete. |
| Design vs. Requirements | Document significant design changes since the PDR. Demonstrate how the final design concept satisfies requirements and design constraints in the relevant development specifications. Update Design Basis Document with regard to considerations previously addressed at the PDR, including: manufacturability; COTS and legacy equipment; human engineering; standardization; software and firmware; weight and size data; and risk management. | Update Design Basis Document for FDR. Design Basis Document approved by responsible Project Engineer. |
| Resolution of Design Recommendations | Document resolution of chits from prior design reviews. | Resolution of chits from prior design reviews documented on Web. Action items completed. |

| Item | Requirement | Success Criteria |
| --- | --- | --- |
| Interface Identification | Signed ICDs for all primary interfaces. No TBDs allowed. The NCSX Interface Control Management Plan (ICMP) and NCSX Procedure 003 provide details of content and format expected. | Approved by Systems Engineering Support Manager |
| Analysis | All required analysis shall be perfromed and checked to establish that the proposed design is feasible and meets established design criteria. Analyses must be documented in an auditable way – in analysis reports, not viewgraph presentations. | Design criteria documented. Material properties characterized and documented. Analysis reports and calculation checks reviewed by responsible Project Engineer, summarized in updated Design Basis Document. |
| Qualification and Acceptance Testing | Document plans and procedures for product qualification and acceptance. | Qualification and acceptance test plans documented and approved. Required procedures in place. |
| Constructability | Document plans and procedures for assembly, installation, and test. | Assembly, installation, and test plans documented and approved. Required procedures in place. |
| RAM | Update the FMECA prepared during Preliminary Design based on the additional design information available. | FMECA documented. Summary of findings and design recommendations provided in updated Design Basis Document. |
| ES&H | Update hazard analysis performed during Preliminary Design, including the following: 1. Descriptions of the environment, safety and health (ES&H) features of structures, systems and components, as applicable. 2. Identification of hazards associated with anticipated operation of the structure, system or component and methods employed for their mitigation. 3. Some description of the ES&H aspects of operations, e.g., access controls, setting of hardwired interlocks, operator actions, etc. The depth of the discussions of these topics should be commensurate with the potential severity of the specific hazards, and with the maturity of the designs. Submit new NEPA Planning Form if new hazards are identified. | Updated hazard analysis documentation. Approved by NCSX ES&H Manager. |

| Item | Requirement | Success Criteria |
| --- | --- | --- |
| Baseline Maintenance | Update cost and schedule estimates in Primavera Project Planner (P3) database consistent with proposed technical baseline as defined by Final Design Release Level models and drawings and other documentation. Cost and schedule updates should generally be of a higher quality than the prior estimate with increased input from industry. | Approved by the responsible Project Engineer. Coordinated with Engineering Manager. Incorporated in P3 database by Project Control Manager. |
|  | Provide input to ECP to reflect proposed changes to the technical, cost, and schedule baselines. ECP will be processed after chits that have significant design, cost, or schedule impacts have been addressed. New baselines will be established upon approval of ECP and implementation of approved changes. The NCSX Configuration Management Plan (CMP) and NCSX Procedure 002 provide guidance on developing and processing an ECP. | Approved by the responsible Project Engineer. Coordinated with the Engineering Manager. |