Applicability

This procedure is applicable to the entire NCSX Project.

Introduction

It is essential for the configuration control of information provided to NCSX suppliers that the contract information and the technical information posted on the two supplier sites (i.e., the Manufacturing Web and the Supplier FTP Site) are entirely self-consistent.  This procedure describes how revised information for vendor subcontracts for the NCSX Project are processed and the appropriate supplier site revised.

The starting point for any revision to a supplier contract and technical information is a directed change that impacts the contract.  The processing and approval of this change is controlled by the NCSX Configuration Management Program.  This procedure outlines the processes by which the NCSX Project ensures that the supplier contract and technical information remains self-consistent.

Referenced Documents

| NCSX-PLAN-PEP | NCSX Project Execution Plan |
| --- | --- |
| NCSX-PLAN-SEMP | NCSX Systems Engineering Plan |
| NCTX-PLAN-CMP | NCSX Configuration Management Plan |
| NCSX-PLAN-DMP | NCSX Data Management Plan |
| NCSX-PLAN-DOC | NCSX Document and Records Plan |
| NCSX-PROC-001 | NCSX Procedure, Glossary of Acronyms and Definitions |
| NCSX-PROC-002 | NCSX Configuration Control |
| PPPL Engineering Procedure 006 | ENG-006 - Review and Approval of Specifications and Statement of Work |

Procedure

- Processing Changes to Supplier Contracts and Technical Information

| Responsibility | Action |
| --- | --- |
| Systems Engineering Support Manager | 1. Notifies the responsible Procurement Representative (PR), Procurement Technical Representative (PTR), Procurement Quality Assurance (PQA), and Design Integration Manager (DI) that a change as been approved that has the potential and/or will impact an existing or pending supplier contract. |
| Procurement Technical Representative | - In consultation with the Design Integration Manager, evaluates impact of directed change (if not already done in the evaluation of the ECP) on the contract and technical supporting information for impact. - If directed change impacts contract or existing supporting technical information, proceed to Step #3 or - If directed change has no impact on the contract or supporting technical information, notify Systems Engineering Support Manager, Procurement Representative, and Procurement Quality Assurance Manager by e-mail. |
| Procurement Technical Representative, Design Integration Manager, and Procurement Representative | - Revises documents as necessary: - PTR modifies Statement of Work (SOW) and Specification as necessary. Guidelines for NCSX SOWs and Specifications are posted on the NCSX Engineering Web page http://www.pppl.gov/me/NCSX_Engineering/ - DI modifies necessary models and drawing in accordance with the guidelines contained in the NCSX Pro/INTRALINK Users Guide (NCSX-GUID-ProE_INTRALINK) also accessible from the NCSX Engineering Web page. - PR modifies contract as appropriate, using the latest versions of SOW, Specification, and drawings and model information provided by PTR and DI. |
| Procurement Quality Assurance | - Reviews proposed revisions to contract documents (e.g., contract, SOW, Specification, and models and drawings for self-consistency. Identifies inconsistencies. |
| Procurement Technical Representative, Design Integration Manager, and Procurement Representative | - Revises contract documents to resolve inconsistencies identified. |
| Procurement Representative | - Negotiates proposed changes with supplier. |
|  | - Notifies PTR, DI, and PQA of any necessary modifications due to negotiations. |
| Procurement Technical Representative, Design Integration Manager, and Procurement Representative | - Revises contract documents to reflect results of supplier negotiations and processes for final approval. |
| Procurement Technical Representative and Design Integration Manager | - Post updated information on the supplier sites: - DI posts updated models and drawings on the Supplier FTP sites, removing any out-of-date information. - PTR posts SOW and Specification and any appropriate clarifying information on the Manufacturing Web site for that contract. Removes any out-of-date information. - DI and PTR notify PQA and Systems Engineering Support Manager that sites updated. |
| PQA and Systems Engineering Support Manager | - Checks posting for accuracy and consistency. If not correct, notify PTR and DI to correct immediately. If postings are correct, notify Procurement Representative that postings are self-consistent and contract modification may be executed. |
| Procurement Representative | - Executes contract modification and notifies PTR. |