Applicability

This procedure is applicable to the entire NCSX Project.

Introduction

It is essential for the configuration control of information provided to NCSX suppliers that the contract information and the technical information posted on the two supplier sites (i.e., the Manufacturing Web and the Supplier FTP Site) are entirely self-consistent.  This procedure describes how revised information for vendor subcontracts for the NCSX Project are processed and the appropriate supplier site revised.

The starting point for any revision to a supplier contract and technical information is a directed change that impacts the contract.  The NCSX Configuration Management Program controls the processing and approval of this change.  This procedure outlines the processes by which the NCSX Project ensures that the supplier contract and technical information remains self-consistent.

Referenced Documents

| NCSX-PLAN-PEP | NCSX Project Execution Plan |
| --- | --- |
| NCSX-PLAN-SEMP | NCSX Systems Engineering Plan |
| NCTX-PLAN-CMP | NCSX Configuration Management Plan |
| NCSX-PLAN-DMP | NCSX Data Management Plan |
| NCSX-PLAN-DOC | NCSX Document and Records Plan |
| NCSX-PROC-001 | NCSX Procedure, Glossary of Acronyms and Definitions |
| NCSX-PROC-002 | NCSX Configuration Control |
| PPPL Engineering Procedure 006 | ENG-006 - Review and Approval of Specifications and Statement of Work |

Procedure

- Processing Changes to Supplier Contracts and Technical Information

| Responsibility | Action |
| --- | --- |
| Systems Engineering Support Manager | 1. Notifies the responsible Procurement Technical Representative (PTR),and Design Integration Manager (DI) that a change as been approved that has the potential to impact an existing or pending supplier contract. |
| Procurement Technical Representative | - In consultation with the Design Integration Manager, evaluates impact of directed change (if not already done in the evaluation of the ECP) on the contract and technical supporting information for impact. - If directed change impacts the contract or existing supporting technical information, notifies the Procurement Representative and Procurement Quality Assurance and proceeds to Step #3 or - If directed change has no impact on the contract or supporting technical information, notifies the Design Integration Manager and the Systems Engineering Support Manager by e-mail. |
| Procurement Technical Representative, and Design Integration Manager | - Revises documents as necessary: - PTR revises Statement of Work (SOW) and Specification as necessary. Guidelines for NCSX SOWs and Specifications are posted on the NCSX Engineering Web page http://www.pppl.gov/me/NCSX_Engineering/. Sends revision for review, with reviewers consistent with those for the original SOW or Specification. - DI modifies necessary models and drawings in accordance with the guidelines contained in the NCSX Pro/INTRALINK Users Guide (NCSX-GUID-PRO) also accessible from the NCSX Engineering Web page. |
| Procurement Technical Representative | - Evaluates reviewer comments on SOW and Specification and incorporates as appropriate. Reviews proposed revisions to models and drawings for self-consistency. Resolves inconsistencies with DI as appropriate. Once proposed revisions deemed appropriate and self-consistent, notifies Procurement Representative of proposed changes and requests that contract be modified to incorporate these changes. |
| Procurement Representative | - Modifies contract as appropriate, using the latest versions of SOW, Specification, and drawings and model information provided by PTR and DI. Reviews changes with PTR. |
|  | - Negotiates proposed changes with supplier. |
|  | - Notifies PTR, DI, and PQA of any necessary modifications due to negotiations. |
| Procurement Representative, Procurement Technical Representative, and Design Integration Manager | - Revises contract documents (e.g., SOW, specifications, drawings and models, and contract) to reflect results of supplier negotiations and processes for final approval. |
| Procurement Representative | - Executes contract modification and notifies PTR |
| Procurement Technical Representative and Design Integration Manager | - Post updated information on the supplier sites: - DI posts updated models and drawings on the Supplier FTP sites, removing any out-of-date information. - PTR posts SOW and Specification and any appropriate clarifying information on the Manufacturing Web site for that contract. Removes any out-of-date information. |
| Procurement Technical Representative | - Checks postings for accuracy and consistency. If not, notify the Procurement Representative of the inconsistencies and correct them immediately. |
|  | - Notifies Procurement Representative and Systems Engineering Support Manager that contract and postings are now self-consistent. |