Applicability

This procedure is applicable to the entire NCSX Project.

Introduction

It is essential for the configuration control of information provided to NCSX suppliers that the contract information and the technical information provided to potential suppliers for Requests for Quote (RFQ) and suppliers awarded contracts is correctly dispositioned and approved from a procurement and technical basis.  The NCSX cognizant engineer/technical representative is responsible for developing and assuring that the necessary administrative (e.g., approved specification and/or statement of work, requisition, etc.) and technical (e.g., signed specifications and signed drawings) documentation is available for procurement to facilitate their procurement actons.  PPPL Procurement is then responsible for gathering this information into an approved procurement package for transmittal to potential suppliers or suppliers awarded contracts.

For the NCSX Project, wide use of electronic documentation will be the norm.  This electronic information is posted on the two supplier sites (i.e., the Manufacturing Web and the Supplier FTP Site) are entirely self-consistent.  This procedure describes how the initial information is developed, verified, and then approved before posting on the appropriate supplier site and delivery to PPPL Procurement and how revised information for supplier subcontracts for the NCSX Project are processed and the appropriate supplier site revised.  In all instances, it is expected that the necessary initial or revised information will not be posted on these ftp sites until authorized by both the technical authority and PPPL procurement.

The initial effort will be to develop the documentation package necessary for either RFQs or recently awarded contracts.  Part A of this procedure describes the process for initially approving procurement-related documentation for either RFQ or Release for Fabrication.

Once the contract is awarded, it may become necessary to update that documentation.  The starting point for any revision to a supplier contract and technical information is a directed change that impacts the contract.  The NCSX Configuration Management Program controls the processing and approval of this change.  This procedure outlines the processes by which the NCSX Project ensures that the supplier contract and technical information remains self-consistent. Part B of this procedure describes this process.

Referenced Documents

| NCSX-PLAN-PEP | NCSX Project Execution Plan |
| --- | --- |
| NCSX-PLAN-SEMP | NCSX Systems Engineering Plan |
| NCTX-PLAN-CMP | NCSX Configuration Management Plan |
| NCSX-PLAN-DMP | NCSX Data Management Plan |
| NCSX-PLAN-DOC | NCSX Document and Records Plan |
| NCSX-PROC-001 | NCSX Procedure, Glossary of Acronyms and Definitions |
| NCSX_GUID-PRO | NCSX Pro/INTRALINK Users Guide |
| NCSX-PROC-002 | NCSX Configuration Control |
| NCSX-PROC-004 | NCSX Work Planning During Design |
| PPPL Engineering Procedure 006 | ENG-006 - Review and Approval of Specifications and Statement of Work |
| PPPL Engineering Procedure 032 | ENG-032 – Work Planning |
| PPPL Engineering Procedure 033 | ENG-033 – Design Verification |

Procedure

- Initial Development of Procurement-Related Documentation

| Responsibility | Action |
| --- | --- |
| Cognizant Engineer or Procurement Technical Representative (PTR) | - Identifies need for a procurement action once the design has progressed sufficiently. Notifies PPPL Procurement Representative (PR) of pending procurement action. |
|  | - Prepares the necessary administrative and technical documentation necessary for the procurement action: - Administrative documentation required: - Statement of Work (SOW) prepared per ENG-006 and NCSX format requirements and approved - Requisition prepared and approved. - Technical documentation required: - Specification (Product Spec/CSPEC) prepared per ENG-006 and NCSX format requirements and approved. - Drawing(s) developed, checked, and approved per the PPPL Drawing Standards and the NCSX Pro/INTRALINK Users Guide at the appropriate level for RFQ or Release for Fabrication. |
|  | - Prior to submitting information to PPPL Procurement, ensures that the proper level of design review (e.g., Final Design Review or other agreed-upon proper design review completed and procurement-related (i.e., that needed for RFQ or Release for Fabrication) CHITs are satisfactorily resolved. DO NOT SUBMIT PROCUREMENT PACKAGE UNTIL SUCH TIME THAT CHITs ARE RESOLVED. If desired, utilize checklist contained in Attachment 1 to ensure that all the necessary pre-requisites are completed. |
|  | - Prepares memorandum to both PPPL Procurement, Design Integration (DI) Manager, and Systems Engineering Support Manager that all pre-requisites for procurement action are satisfied. |
|  | - Assembles completed procurement package and forwards the necessary administrative documentation and technical documentation other than drawing(s) to PPPL Procurement for processing. Notifies Design Integration (DI) Manager that drawings ready for RFQ or Release for Fabrication Status. |
| Design Integration Manager | - Ensures that the drawings are properly approved and annotated with appropriate RFQ or Release for Fabrication status clearly annotated on drawing(s). |
| Procurement Representative | - Prepares appropriate procurement package (RFQ or supplier contract). |
|  | - Notifies Cognizant Engineer/PTR and DI Manager that drawing(s) and SOW and Specification may be posted on the supplier web sites. |
| Procurement Technical Representative and Design Integration Manager | - Post updated information on the supplier sites: - DI posts updated models and drawings on the Supplier FTP sites, removing any out-of-date information. - PTR posts SOW and Specification and any appropriate clarifying information on the Manufacturing Web site for that contract. Removes any out-of-date information. - Ensures appropriate disclaimer statements posted on both the Supplier FTP Site and the Manufacturing Web Site (see Attachment 2). |
| Procurement Technical Representative and Design Integration Manager | - Notifies PPPL Procurement that the appropriate supplier sites have been updated to reflect this information. |
| Procurement Representative | - Confirms to potential suppliers/suppliers that the necessary technical documentation is posted on the supplier ftp sites and is available. |
| Procurement Technical Representative | - Checks postings for accuracy and consistency. If not, notify the Procurement Representative of the inconsistencies and correct them immediately. |
|  | - Notifies PR, PQA, DI, and Systems Engineering Support Manager that postings have been updated and that contract and postings are now self-consistent. |

- Processing Changes to Supplier Contracts and Technical Information

| Responsibility | Action |
| --- | --- |
| Systems Engineering Support Manager | 1. Notifies the responsible Procurement Technical Representative (PTR) and Design Integration Manager (DI) that a change as been approved as part of the configuration management system that has the potential to impact an existing or pending supplier contract. |
| Procurement Technical Representative | - In consultation with the Design Integration Manager, evaluates impact of directed change (if not already done in the evaluation of the ECP) on the contract and technical supporting information for impact. - If directed change impacts an existing NCSX contract, a pending NCSX contract, or supporting technical information distributed for proposals, notifies the Procurement Representative and Procurement Quality Assurance and proceeds to Step #3 or - If directed change has no impact on the contract or supporting technical information, notifies the Design Integration Manager and the Systems Engineering Support Manager by e-mail. |
| Procurement Technical Representative, and Design Integration Manager | - Revises documents as necessary: - PTR revises Statement of Work (SOW) and Specification as necessary. Guidelines for NCSX SOWs and Specifications are posted on the NCSX Engineering Web page http://www.pppl.gov/me/NCSX_Engineering/. Sends revision for review, with reviewers consistent with those for the original SOW or Specification. - DI directs the necessary modifications to existing models and drawings in accordance with the guidelines contained in the NCSX Pro/INTRALINK Users Guide (NCSX-GUID-PRO) also accessible from the NCSX Engineering Web page. |
| Procurement Technical Representative | - Evaluates reviewer comments on SOW and Specification and incorporates as appropriate. Reviews proposed revisions to models and drawings for self-consistency. Resolves inconsistencies with DI as appropriate. Once proposed revisions deemed appropriate and self-consistent, prepares ECP in accordance with NCSX-PROC-002 and coordinates approval of the impacted documents. |
|  | - When ECP approved, notifies Procurement Representative of proposed changes and requests that contract be modified to incorporate these changes. |
| Procurement Representative | - Modifies contract as appropriate, using the latest versions of SOW, Specification, and drawings and model information provided by PTR and DI. Reviews changes with PTR. |
|  | - Negotiates proposed changes with supplier. |
|  | - Notifies PTR, DI, and PQA of any necessary modifications due to negotiations. |
| Procurement Representative, Procurement Technical Representative, and Design Integration Manager | - Revises contract documents (e.g., SOW, specifications, drawings and models, and contract) to reflect results of supplier negotiations and processes for final approval. ENSURES THAT ENGINEERING CHANGE NOTICE (ECN) IS PROCESSED PER PPPL DRAWING STANDARDS. |
| Procurement Representative | - Executes contract modification and notifies PTR |
| Procurement Technical Representative and Design Integration Manager | - Post updated information on the supplier sites: - DI posts updated models and drawings on the Supplier FTP sites, removing any out-of-date information. - PTR posts SOW and Specification and any appropriate clarifying information on the Manufacturing Web site for that contract. Removes any out-of-date information. - Ensures appropriate disclaimer statements posted on both the Supplier FTP Site and the Manufacturing Web Site (see Attachment 2). |
| Procurement Technical Representative | - Checks postings for accuracy and consistency. If not, notify the Procurement Representative of the inconsistencies and correct them immediately. |
|  | - Notifies PR, PQA, DI, and Systems Engineering Support Manager that postings have been updated and that contract and postings are now self-consistent. |

Attachment 1 – Procurement Package Check List

Attachment 2 – Disclaimer Statements

The following checklist can be utilized to ensure that the necessary pre-requisite administrative and technical procurement documentation is completed.  This checklist may be attached to the certification memorandum specified in Part A of this procedure.

| Pre-Requisite Documentation | Completed? (Yes or No) | Comments |
| --- | --- | --- |
| FDR Report finalized and ALL procurement-related CHITs resolved? |  |  |
| Approved SOW available and ready to be posted? |  |  |
| Approved Specification available and ready to be posted? |  |  |
| Approved and properly annotated drawing package available and ready to be posted? |  |  |
| Pre-requisite supplier deliverables received and approved? |  |  |
| Funded and approved requisition (including any JCNP or other supporting documentation) available? |  |  |
| Other? |  |  |

FTP SERVER VERSION:

DISCLAIMER

Unless specifically incorporated by reference in a subcontract or purchase order issued by the Procurement Division of Princeton Plasma Physics Laboratory (PPPL), the files available on this ftp server are provided for information purposes only, and shall not be used for fabrication or otherwise employed in subcontract performance.

NCSX MANUFACTURING WEB PAGE VERSION:

DISCLAIMER

Unless specifically incorporated by reference in a subcontract or purchase order issued by the Procurement Division of Princeton Plasma Physics Laboratory (PPPL), the files available on this site are provided for information purposes only, and shall not be used for fabrication or otherwise employed in subcontract performance.