Applicability

This procedure is applicable to the entire NCSX Project.

Introduction

It is essential for the configuration control of information provided to NCSX suppliers that the subcontract or purchase order information and the technical information provided to potential suppliers for Requests for Quote (RFQ) and Requests for Proposals (RFPs), and to suppliers awarded subcontract or purchase orders is correctly dispositioned and approved from a procurement and technical perspective.  The NCSX cognizant engineer/technical representative is responsible for developing and assuring that the necessary administrative (e.g., approved statement of work, requisition, etc.) and technical (e.g., signed technical specifications and signed drawings) documentation is available for Procurement to facilitate the solicitation and award process.  PPPL Procurement is then responsible for gathering this information into an approved procurement package for transmittal to potential suppliers or suppliers awarded subcontract or purchase orders.

For the NCSX Project, wide use of electronic documentation will be the norm.  This electronic information is posted on the three supplier sites (i.e., the Procurement Web, the Manufacturing Web, and the Supplier FTP Site) and should be entirely self-consistent.  As described in the NCSX Data Management Plan (NCSX_PLAN_DMP), the three related webs have slightly different but related purposes:

- The Procurement Web contains all documentation with the exception of electronic drawings and/or large data files required for potential suppliers to develop proposals;

- The Manufacturing Web contains all project documentation  for  subcontract  with awarded subcontracts or purchase orders except electronic drawing and/or large data files of suppliers; and

- The Supplier FTP Web Site contains all electronic drawings and large date files, whether for proposal or subcontract or purchase order execution use.

This procedure describes how the initial information is developed, verified, and then approved before posting on the appropriate supplier site and delivery to PPPL Procurement and how revised information for supplier subcontracts or purchase orders for the NCSX Project is processed and the appropriate supplier site(s) revised. It also outlines the processes by which the NCSX Project ensures that the supplier subcontract or purchase order and technical information remains self-consistent.  In all instances, the necessary initial or revised information will not be posted on these ftp sites until authorized by both the technical authority (cognizant Engineer/PTR) and PPPL Procurement.

The initial effort will be to develop the documentation package necessary for either RFQs/RFPs or recently awarded subcontract or purchase orders.  Part A of this procedure describes the process for initially approving and posting procurement-related documentation for either RFQ/RFP, design basis for start of subcontract or purchase order work, or Release for Fabrication.

Once the subcontract or purchase order is awarded, it may become necessary to update the documentation.  The starting point for any revision to supplier subcontract or purchase order and technical information is a directed change that impacts the subcontract or purchase order.  The NCSX Configuration Management Program controls the processing and approval of this change. Part B of this procedure describes this process.

Referenced Documents

| NCSX-PLAN-PEP | NCSX Project Execution Plan |
| --- | --- |
| NCSX-PLAN-SEMP | NCSX Systems Engineering Plan |
| NCTX-PLAN-CMP | NCSX Configuration Management Plan |
| NCSX-PLAN-DMP | NCSX Data Management Plan |
| NCSX-PLAN-DOC | NCSX Document and Records Plan |
| NCSX-PROC-001 | NCSX Procedure, Glossary of Acronyms and Definitions |
| NCSX_GUID-PRO | NCSX Pro/INTRALINK Users Guide |
| NCSX-PROC-002 | NCSX Configuration Control |
| NCSX-PROC-004 | NCSX Work Planning |
| NCSX Engineering Web Page – Specifications | Specification Format < |
| PPPL Engineering Procedure 006 | Review and Approval of Specifications and Statement of Work |
| PPPL Engineering Procedure 010 | Control of Drawings, Software, and Firmware |
| PPPL Engineering Procedure 032 | Work Planning |
| PPPL Engineering Procedure 033 | Design Verification |

Procedure

- Initial Development of Procurement-Related Documentation

| Responsibility | Action |
| --- | --- |
| Cognizant Engineer/ Procurement Technical Representative (PTR) | Identifies need for a procurement action once the design has progressed sufficiently. Notifies PPPL Procurement Representative (PR) of pending procurement action. |
|  | - Prepares the necessary administrative and technical documentation for the procurement action: - Administrative documentation required: - Statement of Work (SOW) prepared per ENG-006 and NCSX format requirements and approved. (Note: for simple fabrication contracts, the Cognizant Engineer/PTR, in consultation with the PPPL Procurement Representative, may decide that a requisition and drawing is sufficient.) - Requisition prepared and approved. - Technical documentation required: - Specification (Product Spec/CSPEC) prepared per ENG-006 and NCSX format requirements. Guidelines for NCSX SOWs and Specifications are posted on the NCSX Engineering Web page: http://www.pppl.gov/me/NCSX_Engineering/. Specifications must be approved. (Note: for simple fabrication contracts, the Cognizant Engineer/PTR, in consultation with the PPPL Procurement Representative, may decide that a requisition and drawing is sufficient.) - Drawing(s) developed, checked, and approved per the PPPL Drawing Standards and the NCSX Pro/INTRALINK Users Guide at the appropriate level for RFQ (proposal stage) or Release for Fabrication (authorization to start fabrication). |
|  | - Prior to submitting information to PPPL Procurement, ensures that the proper level of design review (e.g., Final Design Review or designated per NCSX Engineering Manager) is completed and procurement-related (i.e., that needed for RFQ or Release for Fabrication) CHITs are satisfactorily resolved. DO NOT SUBMIT PROCUREMENT PACKAGE UNTIL SUCH TIME THAT CHITs ARE RESOLVED. If desired, utilize checklist contained in Attachment 1 to ensure that all the necessary prerequisites are completed. |
|  | - Notifies Design Integration (DI) Manager and Systems Engineering Support Manager that all prerequisites for procurement action are satisfied. This step certifies that the Cognizant Engineer/PTR believes that all prerequisites are satisfied and that the procurement action can proceed. |
|  | - Assembles completed procurement package and forwards the necessary administrative documentation and technical documentation other than drawing(s) to PPPL Procurement for processing. Notifies Design Integration (DI) Manager that the drawings are ready for RFQ or Release for Fabrication Status. |
| Design Integration Manager | - Ensures that the drawings are properly approved and annotated with appropriate RFQ or Release for Fabrication status clearly annotated on drawing(s). If the drawings are not yet ready for RFQ or Release for Fabrication: - Immediately notifies the Cognizant Engineer/PTR and PPPL Procurement Administrative Representative that the procurement action should be placed on HOLD until such time that the drawings are satisfactory. - Works with the Cognizant Engineer/PTR to resolve open issues remaining on the drawings prior to promoting to RFQ or Release for Fabrication status. - When drawings satisfactory, promotes drawing to RFQ or Release for Fabrication status and obains proper stamp per the NCSX Pro/INTRALINK Guidelines. |
| Procurement Representative | - Receives completed procurement package of the administrative documentation, other technical documentation (e.g., specifications, etc.), and drawings. - After briefly reviewing the package for completeness (i.e., is everything needed provided?), prepares appropriate procurement package (RFQ or supplier subcontract or purchase order). - Post necessary information on the Procurement Web page and notifies Cognizant Engineer/PTR and DI Manager that drawing(s) and SOW and Specification may be posted on the supplier web sites. |
| Cognizant Engineer/PTR and/or Design Integration Manager | - Post updated information on the supplier sites: - DI posts updated models and drawings on the Supplier FTP sites, removing any out-of-date information. - PTR posts SOW and Specification and any appropriate clarifying information on the Manufacturing Web site for that subcontract or purchase order. Removes any out-of-date information. - Ensures appropriate disclaimer statements posted on both the Supplier FTP Site and the Manufacturing Web Site (see Attachment 2). - Checks postings for accuracy and consistency. If not, notify the Procurement Representative of the inconsistencies and correct them immediately. - Once sites are properly updated, notifies PPPL Procurement , Procurement QA, DI, and Systems Engineering Support Manager that the appropriate supplier sites have been updated to reflect this information and are self-consistent. |
| Procurement Representative | - Confirms to potential suppliers and/or suppliers already awarded subcontract or purchase orders that the appropriate Procurement, Supplier FTP, and Manufacturing web pages have been updated and that the information posted may be used. If requested by a potential or awarded supplier, hard copies can be provided. |

- Processing Changes to Supplier Subcontract or Purchase Order Administrative and/or Technical Information

| Responsibility | Action |
| --- | --- |
| Systems Engineering Support Manager | - Notifies the responsible Cognizant Engineer/PTR and Design Integration Manager (DI) that a change as been approved as part of the configuration management system that has the potential to impact an existing or pending supplier subcontract or purchase order. |
| Cognizant Engineer/PTR | - In consultation with the Design Integration Manager, evaluates impact of directed change (if not already done in the evaluation of the ECP) on the subcontract or purchase order and technical supporting information for impact. - If directed change impacts an existing or pending NCSX subcontract or purchase order, or supporting technical information distributed for proposals, notifies the Procurement Representative and Procurement Quality Assurance and proceeds to Step #3 or: - If directed change has no impact on the subcontract or purchase order, or supporting technical information, notifies the Design Integration Manager and the Systems Engineering Support Manager by e-mail. |
| Cognizant Engineer/PTR and Design Integration Manager | - Revises documents as necessary: - Cognizant Engineer/PTR revises Statement of Work (SOW) and Specification as necessary. Guidelines for NCSX SOWs and Specifications are posted on the NCSX Engineering Web page http://www.pppl.gov/me/NCSX_Engineering/. Sends revision for review, with reviewers consistent with those for the original SOW or Specification. - DI directs the necessary modifications to existing models and drawings in accordance with the guidelines contained in the NCSX Pro/INTRALINK Users Guide (NCSX-GUID-PRO) also accessible from the NCSX Engineering Web page. |
| Cognizant Engineer/PTR | - Evaluates reviewer comments on SOW and Specification and incorporates as appropriate. Reviews proposed revisions to models and drawings for self-consistency. Resolves inconsistencies with DI as appropriate. Once proposed revisions deemed appropriate and self-consistent, prepares ECP in accordance with NCSX-PROC-002 and coordinates approval of the impacted documents. |
|  | - When ECP approved, notifies Procurement Representative of proposed changes and requests that subcontract or purchase order be modified to incorporate these changes. |
| Procurement Representative | - Modifies subcontract or purchase order as appropriate, using the latest approved versions of SOW, Specification, and drawings and model information provided by PTR and DI. Reviews changes with PTR. |
|  | - Negotiates proposed changes with supplier. |
|  | - Notifies PTR, DI, and PQA of any necessary modifications due to negotiations. |
| Procurement Representative, Procurement Technical Representative, and Design Integration Manager | - Revises subcontract or purchase order documents (e.g., SOW, specifications, drawings and models, and subcontract or purchase order) to reflect results of supplier negotiations and processes for final approval. ENSURES THAT ENGINEERING CHANGE NOTICE (ECN) IS PROCESSED PER PPPL DRAWING STANDARDS. |
| Procurement Representative | - Executes subcontract or purchase order modification and notifies PTR |
| Procurement Technical Representative and Design Integration Manager | - Post updated information on the supplier sites: - DI posts updated models and drawings on the Supplier FTP sites, removing any out-of-date information. - PTR posts SOW and Specification and any appropriate clarifying information on the Manufacturing Web site for that contract. Removes any out-of-date information. - Ensures appropriate disclaimer statements posted on both the Supplier FTP Site and the Manufacturing Web Site (see Attachment 2). |
| Procurement Technical Representative | - Checks postings for accuracy and consistency. If not, notify the Procurement Representative of the inconsistencies and correct them immediately. |
|  | - Notifies PR, PQA, DI, and Systems Engineering Support Manager that postings have been updated and that subcontract or purchase order and postings are now self-consistent. |

Attachment 1 – Procurement Package Check List

Attachment 2 – Disclaimer Statements

The following checklist can be utilized to ensure that the necessary pre-requisite administrative and technical procurement documentation is completed.  This checklist may be attached to the certification memorandum specified in Part A of this procedure.

| Pre-Requisite Documentation | Completed? (Yes or No) | Comments |
| --- | --- | --- |
| FDR Report finalized and ALL procurement-related CHITs resolved? |  |  |
| Approved SOW available and ready to be posted? |  |  |
| Approved Specification available and ready to be posted? |  |  |
| Approved and properly annotated drawing package available and ready to be posted? |  |  |
| Pre-requisite supplier deliverables received and approved? |  |  |
| Funded and approved requisition (including any JCNP or other supporting documentation) available? |  |  |
| Other? |  |  |

FTP SERVER VERSION:

DISCLAIMER

Unless specifically incorporated by reference in a subcontract or purchase order issued by the Procurement Division of Princeton Plasma Physics Laboratory (PPPL), the files available on this ftp server are provided for information purposes only, and shall not be used for fabrication or otherwise employed in subcontract performance.

NCSX MANUFACTURING WEB PAGE VERSION:

DISCLAIMER

Unless specifically incorporated by reference in a subcontract or purchase order issued by the Procurement Division of Princeton Plasma Physics Laboratory (PPPL), the files available on this site are provided for information purposes only, and shall not be used for fabrication or otherwise employed in subcontract performance.