Record of Revisions

| Revision | Date | Description of Changes |
| --- | --- | --- |
| 0-dC | 1/13/2005 | Initial Issue (Draft C) |

Applicability

This procedure covers the process for preparing and processing Requests for Deviation (RFDs) on the NCSX Project.

Introduction

Prior to performing a specified step in a manufacturing or fabrication process, either the Project or a supplier may identify  an alternative design/method/material to the requirements that could result in technical, cost, or schedule savings.  The documentation to formally define this proposed departure from the established performance or design requirements is called a Request for Deviation (RFD).  The RFD is a specific written request to depart from a particular requirement(s) of the item’s current approved technical documentation.  A RFD shall be processed and adjudicated under the Engineering Change Process (ECP) process defined in the NCSX Configuration Management Plan (NCSX-PLAN-CMP) and its accompanying NCSX Configuration Control Procedure (NCSX-PROC-002).  Until the ECP associated with the RFD is approved, the item or process may not deviate from the technical requirements. The RFD may be either a letter or tabular format and shall contain the specific required information as defined in this procedure.

A deviation is distinguished from non-conformance reports (NCRs) in that NCRs address the departure after the manufacturing step that incorporates the requirement (design/method/material) has begun.  The processing of NCRs is addressed in PPPL Quality Assurance Procedure QA-005, “Control of Nonconformances.”

Referenced Documents

| NCSX-PLAN-CMP | NCSX Configuration Management Plan |
| --- | --- |
| NCSX-PROC-002 | NCSX Configuration Control |
| NCSX-PROC-008 | NCSX Procurement Contract Fast Response Process |
| QA-005 | Control of Non-conformances |

*Note:   RLM may decide to do nothing relative to revising design documentation once a RFD is approved.  This is usually reserved for prototypes or items that will not be installed on the experiment.

Attachment:

1 – Necessary Information Needed on a RFD

ATTACHMENT 1

The RFD may be provided in any format (i.e., letter, tabular, or supplier format), but must contain at a minimum the following information in sufficient detail to permit NCSX Project assessment of the RFD:

- Initiator Name and Organization

- Date RFD was initiated

- RFD Title – short description of the deviation requested

- List of impacted documents (e.g., specification and sections, each model and drawing, SOW sections – if the SOW has been used to convey technical information).  Be as specific as possible.

- Impact on cost, schedule, and interfaces with other items – if none so state.  If there are impacts be as specific as possible.

- Full description of the deviation requested, including specific item/part impacted by this RFD and the rationale on why this deviation is needed. Include amplifying information that may assist in the NCSX Project’s assessment of this RFD.

The RFD number is assigned by the NCSX Systems Engineering Support Manager.

A Sample Form

| NCSX RFD | Number: | RFD Description: |
| --- | --- | --- |
| Initiator: | Organization: |
| List of Impacted Documents: |
| Cost Impact: (If none, so state) |
| Schedule Impact: (If none, so state) |
| Impact on Interfaces with Other WBS Elements/Items: (If none, so state) |
| Full Description of the Deviation Requested: (Use continuation pages as needed and include amplifying information as appropriate) |

# Text boxes

From Page 2

To  Page 3

RFD Complete?

PPPL Procurement Technical Representative obtains WBS Manager, Project Engineer, and RLM verbal Concurrence

Do Nothing*

Systems Engineering Support Manager processes an ECP for the RFD in accordance with the appropriate NCSX configuration control procedure (NCSX-PROC-002 or NCSX-PROC-008).

Note:  If the RFD is initiated by a supplier, the PPPL Procurement Technical Representative and PPPL Subcontract Administrator will be invited to participate in the CCB.

If supplier initiated, PPPL Subcontract Administrator:

- Notifies the supplier that they are NOT authorized to proceed with the proposed departure until such time that the RFD is approved;

- Ensures that the PPPL Technical Representative has a copy of the RFD and that proper project concurrences have been received; and

- Forwards the RFD to the Systems Engineering Support Manager.

Project Initiated

Supplier Initiated

Job Manager prepares the RFD containing at a minimum the information specified in Attachment 1 to this procedure.  Obtains WBS Manager, Project Engineer, and RLM  verbal concurrence.

Supplier notifies the PPPL Procurement Technical Representative and the respective PPPL Subcontract Administrator of the issue and submits a Request for Deviation (RFD) containing at a minimum the information specified in Attachment 1 to this procedure.

Initiator (Anyone on the Project or a Supplier) proposes an alternative design, approach, material, etc. than currently specified.

RLM determines how the RFD will be incorporated into the design documentation

Comment: The subcontract administrator already had the RFD as indicated above.

From Page 4

Job Manager revises impacted design documentation to incorporate the RFD

Annotate

Revise

END

Job Manager annotates design documentation by adding a stamp on drawing or other means (notes on a specification, SOW , MIT/QA Plan, etc.) that clearly identifies the RFD.

To Page 4

CCB Chair (or NCSX Engineering Manager if an expedited ECP) approves or disapproves the RFD and associated ECP, notifies the initiator directly if project initiated RFD or PPPL Procurement Technical Representative and PPPL Subcontract Administrator if the RFD is supplier initiated.

Initiator

Systems Engineering Support Manager reviews the RFD to ensure that it contains all the necessary information.

Concurrences Received?

RFD Rejected

If supplier initiated, PPPL Procurement Technical Representative notifies supplier and PPPL Subcontract Administrator that RFD is rejected.

Concurrences Received

END

More information needed

RFD Complete

Systems Engineering Support Manager iterates until complete with:

- The initiator directly if a project initiated RFD;  or

- The PPPL Technical Representative and Procurement Technical Representative if the RFD is supplier initiated.

From Page 3

ECP Approved?

No

Yes

Systems Engineering Support Manager notifies:

- Job Manager if project initiated RFD; or

- PPPL Procurement Technical Representative and PPPL Subcontract Administrator if supplier initiated.

PPPL Procurement Technical Representative and PPPL Subcontract Administrator notify supplier

END

Systems Engineering Support Manager

- Notifies Job Manager if RFD was project initiated or PPPL Procurement Technical Representative and PPPL Subcontract Administrator if RFD was supplier initiated.

- Posts the dispositioned RFD and ECP on the NCSX Engineering Web page

- Provides unique RFD number per Attachment 1 to this procedure. using the format 
NCSX-RFD-WBS-###-XX where:

  - WBS is the three digit WBS number (e.g., 121, 142, etc.)

  - ### is sequential number of the deviation

  - XX is the revision number of the RFD

PPPL Procurement Technical Representative and PPPL Subcontract Administrator notify supplier

To Page 5

Comment: I had the make the box bigger so that all the text inside would show. There is no easy way for the reader to see that text is not visible. As an example, there is more below here but you can’t see it. We must be careful here.