Record of Revisions

| Revision | Date | Description of Changes |
| --- | --- | --- |
| 0-dA | 1/21/2005 | Initial Issue |
| 0-dB | 4/13/2005 | Removed all references to Audit Findings – QA-002 addresses these and the QA Data Base is the source file for status of audit findings. |

Applicability

- This procedure is applicable to the entire NCSX Project. PPPL Engineering Procedure ENG-033, Design Verification, describe the processes and procedures by which design verification activities shall be conducted.  TheNCSX Project is committed to following all the processes and procedures of ENG-033 completely, except that the Project will maintain its design review records in an electronic format (e.g., design review reports, CHITs, and tracking logs) , in keeping with its adoption of an electronic data record system.

Introduction

The NCSX Systems Engineering Management Plan (NCSX-PLAN-SEMP) provides the project’s approach to the conduct of design reviews.  Sections B (Peer Reviews) and C (Design Reviews) of  PPPL Engineering Procedure ENG-033 address the conduct and requirements for conducting design reviews. The NCSX Project will continue to utilize the CHIT form provided in ENG-033, however, at the completion of the review, this data will be electronically transcribed to an Excel Spreadsheet to facilitate electronic posting of the design review report and CHITs.  Additionally, in accordance with this procedure, each CHIT will be tracked and statused on a routine basis to ensure timely closure of each CHIT.

Referenced Documents

NCSX Systems Engineering Management Plan (NCSX-PLAN-SEMP)

PPPL Policy 010, “Design Reviews”

PPPL Procedure ENG-033, “Design Verification”

ES&HD 5008, “PPPL ES&H Manual”

Procedure

## NCSX Design Review Process

The NCSX Project will fully implement the requirements and processes for conducting and documenting design reviews with the exception that all design review records will be stored electronically on the NCSX Engineering Web site and not as hard copies in the PPPL Operations Center.

## Attachments

  - Generic Design Checklist for Preliminary Design

  - Generic Design Checklist for Final Design

  - Sample NCSX Project CHIT Tracking Log

| Item | Requirement | Success Criteria |
| --- | --- | --- |
| Configuration Identification | Configuration Items (CI’s) represent the lowest level of control under configuration management and may be a single physical or functional item or collection of items that will satisfy a final end product or deliverable. A CI may be a subsystem, a component, assembly, or subassembly. The WBS Manager will determine the appropriate level of the CI. The process of identifying and agreeing to the interfaces between CIs is key to fully understanding requirements and design constraints.. Acquisition plans should address build v. buy issues. | Spec tree, design review schedule, and acquisition plans updated and posted on Web. Project detailed schedule updated by PC Mgr. |
| Specifications | Performance requirements are finalized and documented in approved development ("design-to") specifications , which are under change control. No TBDs are allowed. The NCSX Systems Engineering Management Plan (SEMP) and the NCSX Engineering Web page (specifications provides guidance on content and format of these specs. | Approved specification(s). |
| Design vs. Requirements | Document design approach. Demonstrate how the design concept satisfies requirements and design constraints in the relevant development specifications. | Documented in Design Basis Document prior to PDR. Approved by responsible Project Engineer. |
| Resolution of Design Recommendations | Document resolution of chits from prior design reviews. PPPL Procedure ENG-033 provides guidance. | Resolution of chits from prior design reviews documented on Web. Action items completed. |
| Interface Identification | Signed scope sheets for all primary interfaces. No TBDs allowed. The NCSX Interface Control Management Plan (ICMP) and NCSX Procedure 003 provide details of content and format expected. | Approved by Systems Engineering Support Manager |
|  | Signed ICDs for all primary interfaces. TBDs allowed with closure plans. The NCSX Interface Control Management Plan (ICMP) and NCSX Procedure 003 provide details of content and format expected. | Approved by Systems Engineering Support Manager |

| Item | Requirement | Success Criteria |
| --- | --- | --- |
| Models and Drawings | Sufficient drawings to support developmental design and analytical evaluation of the inherent ability of the design to attain the required performance. The drawings shall be sufficient to develop manufacturing approaches and cost estimates. All models and drawings promoted to Preliminary Design Release. Drawings shall be provided which define where the equipment will be located in the facility. Preliminary Design Release models and drawings should form a self-consistent package and provide the basis for cost and schedule estimates. The NCSX Pro/INTALINK Users Guide provides information on handling models and drawings. | Models and drawings approved for promotion by the responsible Project Engineer |
|  | Develop a drawing tree with at least enough detail to identify all components necessary to support final design and production planning. | Approved by the cognizant Project Engineer |
| Analysis | Design criteria to establish limits for acceptability are in place. Sufficient analysis shall be provided to establish that the proposed design is feasible and meets established design criteria. Analyses must be documented in an auditable way – in analysis reports, not viewgraph presentations. The following analyses shall be accomplished as appropriate: structural, thermal, seismic, eddy current, radiation, and circuit analyses. Other analyses shall be included as appropriate. | Design criteria documented. Material properties characterized and documented. Analysis reports reviewed by responsible Project Engineer, summarized in Design Basis Document. |
| Manufacturability | Provide evidence (if necessary) from R&D activities that the design is manufacturable and has been optimized for manufacturability. | Manufacturing studies conducted as appropriate and results documented in Design Basis Document. |
| Qualification and Acceptance Testing | Qualification and acceptance test plans consistent with verification requirements in the development specifications. Identify when these tests would be performed. These plans provide the basis for subsequently developing test procedures. PPPL Procedure ENG-030 provides guidance. | Qualification and acceptance test plans documented and approved. |
| Constructability | Document plans for assembly, installation, and test. Provide evidence that risk-related issues have been satisfactorily addressed. These plans provide the basis for subsequently developing assembly, installation, and test procedures. PPPL Procedure ENG-030 provides guidance. | Assembly, installation, and test plans documented and approved. |

| Item | Requirement | Success Criteria |
| --- | --- | --- |
| Value Engineering | Determine what design areas would likely benefit from additional value engineering/management assessments at the beginning of Preliminary Design. Conduct and document results of value engineering studies (if any). NCSX Project Execution Plan (PEP) provides approach and the Value Engineering Report provides examples. | Results of value engineering studies (if any) documented in Design Basis Document. |
| RAM | Provide FMECA per PPPL Procedure ENG-008 identifying potential failure modes and recovery provisions. Explain how design has been optimized for reliability, maintainability, and safety through systematic evaluation of design options and application of proven design approaches. | FMECA documented. Summary of findings and design recommendations provided in Design Basis Document. |
| ES&H | Provide a hazard analysis per PPPL Procedure ESH-004 that address the following: 1. Descriptions of the environment, safety and health (ES&H) features of structures, systems and components, as applicable. 2. Identification of hazards associated with anticipated operation of the structure, system or component and methods employed for their mitigation. 3. Some description of the ES&H aspects of operations, e.g., access controls, setting of hardwired interlocks, operator actions, etc. The depth of the discussions of these topics should be commensurate with the potential severity of the specific hazards, and with the maturity of the designs. The hazard analysis report should address ES&H issues identified in the FMECA. Review existing NEPA documentation per PPPL Procedure ESH-014. Submit new NEPA Planning Form if new hazards are identified. | Report documenting hazard analysis. Approved by NCSX ES&H Manager. |
| COTS and Legacy Equipment | Identify use of commercial, off-the-shelf (COTS) as appropriate or legacy equipment. Describe plan for testing the performance of legacy equipment. | Documented in Design Basis Document. |
| Human Engineering | Demonstrate that sound human engineering principles have been followed in the design. | Documented in Design Basis Document. |
| Standardization Considerations | Identify how design has been optimized for standardization, including a list of standardized components | Documented in Design Basis Document. |
| Software and Firmware | Identify and describe all planned software and firmware, including the functional requirements allocated to them, how they will be validated and verified. This may be part of a Manufacturing, Inspection, and Test Plan (MITP). | Documented in Design Basis Document. |

| Item | Requirement | Success Criteria |
| --- | --- | --- |
| Preliminary Weight and Size Data | Demonstrate that weight and sizes are compatible with structural supports and size constraints | Documented in Design Basis Document. |
| Risk Management | Identify areas of significant risk and mitigation plans. The NCSX Project Execution Plan (PEP) describes the approach and the NCSX Risk Management Plan (RMP) provides specific risk mitigation strategies. | Documented in Design Basis Document. |
| Baseline Maintenance | Update cost and schedule estimates in Primavera Project Planner (P3) database consistent with proposed technical baseline as defined by Preliminary Design Release Level models and drawings and other documentation. Cost and schedule updates should generally be of a higher quality than the prior estimate with increased input from industry. | Approved by the cognizant Project Engineer. Coordinated with Engineering Manager. Incorporated in P3 database by Project Control Manager. |
|  | Provide input to ECP to reflect proposed changes to the technical, cost, and schedule baselines. ECP will be processed after chits that have significant design, cost, or schedule impacts have been addressed. New baselines will be established upon approval of ECP and implementation of approved changes. The NCSX Configuration Management Plan (CMP) and NCSX Procedure 002 provide guidance on developing and processing an ECP. | Approved by the responsible Project Engineer. Coordinated with the Engineering Manager. |

| Item | Requirement | Success Criteria |
| --- | --- | --- |
| Specifications and drawings | Documentation (specifications and drawings) required for product acquisition (to build or buy) is complete. Product ("build-to") specifications are approved and under change control. No TBDs allowed. The NCSX Systems Engineering Management Plan (SEMP) and the NCSX Engineering Web page (specifications provides guidance on content and format of these specs. All models and drawings should be checked (reviewed for consistency, completeness, and adherence to drawing standards) and promoted to Final Design Release level. Drawings need not be signed (promoted to Fabrication Release Level) pending outcome of the review and chit resolution. The NCSX Pro/INTALINK Users Guide provides information on handling models and drawings. | Documentation package for product acquisition is complete. |
| Design vs. Requirements | Document significant design changes since the PDR. Demonstrate how the final design concept satisfies requirements and design constraints in the relevant development specifications. Update Design Basis Document with regard to considerations previously addressed at the PDR, including: manufacturability; COTS and legacy equipment; human engineering; standardization; software and firmware; weight and size data; and risk management. | Update Design Basis Document for FDR. Design Basis Document approved by responsible Project Engineer. |
| Resolution of Design Recommendations | Document resolution of chits from prior design reviews. PPPL Procedure ENG-033 provides guidance. | Resolution of chits from prior design reviews documented on Web. Action items completed. |

| Item | Requirement | Success Criteria |
| --- | --- | --- |
| Interface Identification | Signed ICDs for all primary interfaces. No TBDs allowed. The NCSX Interface Control Management Plan (ICMP) and NCSX Procedure 003 provide details of content and format expected. | Approved by Systems Engineering Support Manager |
| Analysis | All required analysis shall be performed and checked to establish that the proposed design is feasible and meets established design criteria. Analyses must be documented in an auditable way – in analysis reports, not viewgraph presentations. | Design criteria documented. Material properties characterized and documented. Analysis reports and calculation checks reviewed by responsible Project Engineer, summarized in updated Design Basis Document. |
| Qualification and Acceptance Testing | Document plans and procedures for product qualification and acceptance. PPPL Procedure ENG-030 provides guidance. | Qualification and acceptance test plans documented and approved. Required procedures in place. |
| Constructability | Document plans and procedures for assembly, installation, and test. PPPL Procedure ENG-030 provides guidance. | Assembly, installation, and test plans documented and approved. Required procedures in place. |
| RAM | Update the FMECA prepared per PPPL Procedure ENG-008 during Preliminary Design based on the additional design information available. | FMECA documented. Summary of findings and design recommendations provided in updated Design Basis Document. |
| ES&H | Update hazard analysis performed per PPPL Procedure ESH-004 during Preliminary Design, including the following: Descriptions of the environment, safety, and health (ES&H) features of structures, systems and components, as applicable. Identification of hazards associated with anticipated operation of the structure, system or component and methods employed for their mitigation. Some description of the ES&H aspects of operations, e.g., access controls, setting of hardwired interlocks, operator actions, etc. The depth of the discussions of these topics should be commensurate with the potential severity of the specific hazards, and with the maturity of the designs. Submit new NEPA Planning Form if new hazards are identified. | Updated hazard analysis documentation. Approved by NCSX ES&H Manager. |

| Item | Requirement | Success Criteria |
| --- | --- | --- |
| Baseline Maintenance | Update cost and schedule estimates in Primavera Project Planner (P3) database consistent with proposed technical baseline as defined by Final Design Release Level models and drawings and other documentation. Cost and schedule updates should generally be of a higher quality than the prior estimate with increased input from industry. | Approved by the responsible Project Engineer. Coordinated with Engineering Manager. Incorporated in P3 database by Project Control Manager. |
|  | Provide input to ECP to reflect proposed changes to the technical, cost, and schedule baselines. ECP will be processed after chits that have significant design, cost, or schedule impacts have been addressed. New baselines will be established upon approval of ECP and implementation of approved changes. The NCSX Configuration Management Plan (CMP) and NCSX Procedure 002 provide guidance on developing and processing an ECP. | Approved by the responsible Project Engineer. Coordinated with the Engineering Manager. |

# Text boxes

1

1

Cognizant Engineer/WBS Manager develops design review documentation package using the guidelines and requirements contained in ENG-033 and Attachments 1 and 2 of this procedure and forwards this documentation (or identifies where it is located on the NCSX Engineering Web) to the assigned Design Review Board members.

Cognizant Engineer/WBS Manager conducts design review, discussing:

- Presentation;

- Specification(s);

- Models and drawings; and

- Any other amplifying information that will assist the Design Review Board in assessing the design.

At the completion of the review, forward Design Review material to the NCSX Engineering Administrator for posting on the NCSX Engineering Web.

Design Review Board assesses design and prepare CHITs and recommendations. Discuss with the Cognizant Engineer/WBS Manager.

Review Board Chair prepares Report and forwards Report and CHIT to NCSX Engineering Administrator for posting on the NCSX Engineering Web.

NCSX Engineering Administrator posts design review documentation (e.g., design review presentation and other documentation, Design Review Report, and CHITS) on the NCSX Engineering Web.

2

2

Review Board Chair confirms that CHITs and Design Review Report were properly recorded.  Iterate posting with the NCSX Engineering Administrator until satisfied that CHITs and Design Review Report properly recorded on the NCSX Engineering Web.

NCSX Engineering Administrator records CHITs into a NCSX Project CHIT Tracking Log (Attachment 3) and notifies the Cognizant Engineer /WBS Manager and others having responsibility for developing responses to CHITs.

Cognizant Engineer/WBS Manager/Individuals   assigned responsibilities on CHITS generate Project response to CHITS and submit to the RLM.

RLM review proposed Project response and approve or iterate with the response author until satisfied and then approve.  Provides updated copy of the CHIT to

the NCSX Engineering Administrator or posting.

NCSX Engineering Administrator updates NCSX Project CHIT Tracking Log and posts.

END

Cognizant Engineer/WBS Manager implements Project response and notifies the NCSX Project Administrator when the CHITs are closed to enable updating of the NCSX Project CHIT Tracking Log and CHITs.