## Sheet1
Chit# | Chit Content [Originator] | Review Board Comments and Recommendations | Project Disposition | Responsibility | Status | Due Date
1 | Location of the inconel-to-stainless transition joint and requirements for diagnostic flexibility need to be captured somewhere. Is it an interface or flowed down from the GRD? [H. Neilson] | The location of the transition joint is a design feature, not a requirement. However, the need for a joint to accommodate alternate port extensions is an interface requirement and should be captured in the SRD. | Will add as an interface requirement. |  |  | 2005-04-27
2 | What sets the VV insulation thickness? Is there a reference in the interface section or do you state that the insulation is 1" thick. [T. Brown] | Concur | ??? |  |  | 2005-04-27
3 | Section 3.2.1.2.1.2 or section 3.2.1.3.2 needs to recognize the GRD requirement to operate with the 250ºC liner (for lithium OP), presumably by operating with the vessel at 250ºC [M. Zarnstorff] | Concur | Agreed. |  |  | 2005-04-27
4 | Need a metrology requirement requiring that design features be incorporated to enable accurate measurement of the vessel position during assembly and in the assembled state during operation. [M. Zarnstoff] | Concur | Agreed. |  |  | 2005-04-27
5 | Need to look at consequences of loss of site power, loss of heating/cooling , etc., see any requirements derived from this? [W. Reiersen] | Concur | Will be addressed in the FMECA. |  |  | 2005-04-27
6 | Resolve issue of "what is possible" i.e. horizontal and vertical design loads. [W.Reiersen] | Concur | VV is being designed to accommodate loads from a 320kA instantaneous plasma disruption which has no net radial or vertical loads |  | Complete
7 | Organize 3.13 as a stand-alone section, not along WBS lines. [W. Reiersen] | Concur | Done |  | Complete
8 | Section 3.3.1.4: NCSX structural & cryogenic design criteria is a draft & almost 2 yrs. old. Valid reference? [J. Malsbury] | Concur | The design criteria document is under revision control and properly referenced in the SRD. |  | Complete
9 | Section 3.3.1.2 b) standards for degreases & cleaning. [J. Malsbury] | Concur | Will investigate applicable PPPL standards. |  |  | 2005-04-27
10 | ( paragraph 2) add all docs ref'd in body of spec. [J.Malsbury] | Concur | Agreed. |  |  | 2005-04-27
11 | Revise GRD to clarify pre-pulse temp. 20-60 ºC following pulse. Uniformities of temp required on VV? [B. Simmons] | Concur | GRD modified appropriately. SRD is consistent with GRD. |  | Complete