Purpose and Time Needed for this Module:

This module is intended to how the NCSX Project does business – specifically, how the NCSX Project conducts and documents design reviews.  The instructor and student(s) will need access to the NCSX Project Web via a computer to see the specific web pages referenced.  It is anticipated that this topic will take require approximately one 45 minute session to complete.

Content:

The NCSX Project Home page should be the first point of contact for the vast majority of project information:  This site is directly accessible from the PPPL Employee Services page http://www-local.pppl.gov/  or via the following URL: http://ncsx.pppl.gov/.  The Project Web was the subject of Module 1.

The Engineering Web is accessible from the NCSX Project Web by clicking on the link labeled Engineering, which takes the user to the Engineering Home page.  The Engineering Home page is the gateway to the technical information used by project participants.  Exceptions are the electronic models and drawings in the ProE/INTRALINK System and those hard copies of run procedures and supplier submittals stored in the PPPL Operations Center.  Access to the Engineering Web is restricted to people logging in from the pppl.gov, ornl.gov, and doe.gov domains.  User name and password access is required outside those domains.

Since this is a protected site, you must use the NCX search engine => other search engines such as Google will not be able to access items on the Engineering Web.

Design Reviews:

Overall Process

PPPL design review processes are defined in PPPL Engineering Procedure ENG-033, Design Verification.  The NCSX Project is committed to following the procedures and processes of ENG-033, including the preparation of design review reports and use of CHITs.  The major difference on NCSX is that all design review documentation will be stored in an electronic format vs. in hard copy in the PPPL Operations Center. NCSX Procedure PROC-010 supplements ENG-033.

A process for electronically documenting design reviews has been implemented and is documented at:

http://ncsx.pppl.gov/NCSX_Engineering/Design_Review_Prep/DesignReviewMechanics/DesignReviews.ppt

Design reviews facilitate orderly design and implementation and are a key element in the overall project risk mitigation strategy.  They are the primary means of verifying that a project element is ready to proceed to the next phase:

- Preliminary design;

- Final design;

- Installation;

- Test; and

- Operation

NCSX Job Managers are expected to be pro-active in including design reviews as part of their plans and for providing visibility of them in the Master Schedule (long range view) and in near term jobs.  Activities and deliverables required to support the design review should be explicitly identified in jobs. Responsible Line Managers (RLMs) should call for design reviews in the WPs (see Training Module #4 and PROC-004) and should review jobs to ensure that the reviews and supporting activities have been identified.

When is a Design Review Needed?

Although the RLM is ultimately responsible for setting the need for a design review, several key guidelines can be provided:

- If you are designing something, conduct a Preliminary Design Review (PDR) to confirm that the requirements are well defined and that the design meets those requirements.

- If you are building something or having something built to print, conduct a Final Design Review (FDR) to confirm that the design and design documentation package are ready to go ahead with the fabrication or procurement.

- If you are buying a major off-the-shelf item (e.g. , a metrology system, etc.), conduct a FDR to confirm that the requirements are well defined and that the item optimally meets those requirements.

- If you are installing, testing, or operating something for the first time, conduct a design review to assure that the equipment is ready, that hazards have been adequately assessed and mitigated, and appropriate installation/test/operating procedures are in place.

Guidelines for Planning Design Reviews

Both ENG-033 and PROC-010 contain design review objectives and design review input documentation.  The input documentation should be completed and provided to the Design Review Board prior to the review.  Until all prerequisite design review documentation is completed, the review will not be scheduled or held.

Design review objectives and input documentation can be found in ENG-033.  Generic checklists for planning work for preliminary and final design reviews are provided in PROC-010 (Wayne – we need to update the Dsn Review Guidelines on web to reflect PROC-010 vs. PROC-004).  Together, these provide clear guidelines for planning design activities and conducting design reviews.  ENG-033 can be found at:  http://www.pppl.gov/eshis/procedures/eng033.pdf  and PROC-010 can be found at:

http://ncsx.pppl.gov/SystemsEngineering/Plans_Procedures/NCSX_Procedures.htm

For example, requirements for a PDR include:

- Requirements have been finalized (e.g., in signed Developmental “design to” specs);

- The design has been shown to meet the requirements;

- Design basis analyses and R&D have been documented;

- Interfaces have been defined (prefer as early as possible); and

- Drawings and models have been promoted to a PD release level.

For a FDR, the requirements include:

- Technical documentation package required for fabrication or procurement is complete (e.g., signed Product “build to” specs;

- Drawings and models have been promoted to a FD release level;

- Design basis analyses have been checked; and

- All interfaces have been defined and documented (if not already done for a PDR).

Keys to a Successful Design Review

The key to having a good design review is to define the requirements for a successful design in the charge to the Design Review Committee.  The charge should clearly identify:

- The purpose of the review; and

- Everything that is required for the review to be deemed successful (only include what is needed – don’t embellish!)– the charge is the key to making the review add value  without adding excessive burden.

  - Establish the charge using a graded approach in applying the guidelines provided in NCSX and PPPL procedures – recognize that the requirements for a piece of tooling should be more modest than the requirements one might expect for a multi-million, mission critical component.

The RLM should be the person drafting the charge in consultation with the NCSX Job and NCSX WBS Manager.

Until the charge elements have been addressed or completion is imminent, do not schedule the review!

The Design Review Process

Results of Design Reviews

Can be found at:  http://ncsx.pppl.gov/NCSX_Admin/Design_Reviews/index_DsgnRvws.htm

Close Out of CHITs

The Cognizant Individual (NCSX Job Manager) is responsible for tracking the close out of CHITs and other action items following a design review.  To facilitate this, a NCSX CHIT/Audit Tracking Log has been developed and is maintained by the NCSX Administrator.  The NCSX Administrator will track completion of past due CHITs and Audit findings on a monthly basis.  This log can be found at:  ??????????????????????????????????? Wayne – we need to get Marianne to post this!

Peer Reviews

Peer reviews, while useful as a means for soliciting expert input for the Job Manager, are not to be used as substitutes for PDRs or FDRs.  The title of the review should clearly identify the purpose of the peer review.

Other Modules

- Module 1 – Overview of the NCSX Web

- Module 2A - Overview of the Engineering Web (Part I)

- Module 2B – Overview of the Engineering Web (Part II)

- Module 3 – Specifications, Design Criteria, and Statements of Work

- Module 4 – Work Authorization Processes

- Module 6 – Electronic Models and Drawings

- Module 7 – Configuration Control Processes

- Module 8 – Interface Control Processes

- Module 9 – WBS Dictionaries and Management Plans

- Module 10 – ESH & QA

- Module 11 – Supplier FTP Site and Postings

- Module 12 – Administrative Processes (Electronic Signatures, Style and Document Preparation Guidelines & File Naming Conventions)